## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | Railway Station Sint-Joost | 1 |  |  | 2011-01-26 08:00 | 2011-10-10 17:00 | 135d |  |  | 0 |  |  | 59830.7575
1 | inrichten werf | 1.1 |  | FS2;FS3;FS4 | 2011-01-26 08:00 | 2011-02-04 17:00 | 7d | werkkracht[0.83 #1];kraan[0.25 #1] | 3045.3616 | 0 | 0 | 0 | 3045.3616
2 | verwijdering pui n en afval | 1.2 | 1FS | FS5;FS10;FS11;FS13 | 2011-03-04 08:00 | 2011-03-07 17:00 | 2d | werkkracht;kraan[0.25 #1] | 1020.16 | 0 | 0 | 0 | 1020.16
3 | opbraak blauwe hardsteen | 1.3 | 1FS | FS5;FS7;FS8;FS10;FS11;FS13 | 2011-02-24 08:00 | 2011-03-03 17:00 | 6d | werkkracht[0.50 #1];kraan[0.75 #1] | 2430.24 | 0 | 0 | 0 | 2430.24
4 | opbraak metselwerk | 1.4 | 1FS | FS5;FS10;FS11;FS13 | 2011-03-08 08:00 | 2011-03-15 17:00 | 6d | werkkracht[0.83 #1];kraan[0.50 #1] | 2961.3984 | 0 | 0 | 0 | 2961.3984
5 | structuur gewapend beton | 1.5 | 2FS;3FS;4FS | FS6;FS9 | 2011-03-16 08:00 | 2011-04-13 17:00 | 20d | werkkracht[0.83 #1];kraan[0.50 #1] | 9871.328 | 0 | 0 | 0 | 9871.328
6 | baksteen metselwerk | 1.6 | 5FS | FS12 | 2011-04-14 08:00 | 2011-08-30 17:00 | 66d | werkkracht[0.50 #1];kraan[0.25 #1] | 18812.64 | 0 | 0 | 0 | 18812.64
7 | levering blauwe hardsteen | 1.7 | 3FS | FS9 | 2011-05-04 08:00 | 2011-05-06 17:00 | 3d | werkkracht[0.50 #1] | 675.12 | 0 | 0 | 0 | 675.12
8 | restauratie blauwe hardteen | 1.8 | 3FS | FS9 | 2011-05-09 08:00 | 2011-05-12 17:00 | 4d | werkkracht[0.33 #1] | 599.8666 | 0 | 0 | 0 | 599.8666
9 | plaatsen blauwe hardteen | 1.9 | 5FS;7FS;8FS | FS12 | 2011-05-13 08:00 | 2011-06-17 17:00 | 24d | werkkracht[0.50 #1];kraan[0.75 #1] | 9720.96 | 0 | 0 | 0 | 9720.96
10 | decoratieve elementen | 1.10 | 2FS;3FS;4FS | FS15 | 2011-04-14 08:00 | 2011-04-15 17:00 | 2d | werkkracht[0.50 #1] | 450.08 | 0 | 0 | 0 | 450.08
11 | buitenschrijnwerk aluminium | 1.11 | 2FS;3FS;4FS | FS15 | 2011-04-26 08:00 | 2011-05-03 17:00 | 5d | werkkracht[0.50 #1] | 1125.2 | 0 | 0 | 0 | 1125.2
12 | zandstralen trappen en steunmuren | 1.12 | 6FS;9FS | FS14;FS16 | 2011-09-02 08:00 | 2011-09-07 17:00 | 4d | werkkracht[0.50 #1] | 900.16 | 0 | 0 | 0 | 900.16
13 | zandstralen kopmuur | 1.13 | 2FS;3FS;4FS | FS18 | 2011-08-31 08:00 | 2011-09-01 17:00 | 2d | werkkracht[0.83 #1] | 747.1328 | 0 | 0 | 0 | 747.1328
14 | herstelling gereinigde elementen natuursteen | 1.14 | 12FS | FS15 | 2011-09-09 08:00 | 2011-09-14 17:00 | 4d | werkkracht[0.50 #1] | 900.16 | 0 | 0 | 0 | 900.16
15 | anti-graffiti behandeling | 1.15 | 10FS;11FS;14FS;17FS | FS18 | 2011-09-23 08:00 | 2011-09-30 17:00 | 6d | werkkracht[0.50 #1] | 1350.24 | 0 | 0 | 0 | 1350.24
16 | herstelling metselwerk | 1.16 | 12FS | FS17 | 2011-09-09 08:00 | 2011-09-14 17:00 | 4d | werkkracht[0.50 #1] | 900.16 | 0 | 0 | 0 | 900.16
17 | heropvoeging metselwerk | 1.17 | 16FS | FS15 | 2011-09-15 08:00 | 2011-09-22 17:00 | 6d | werkkracht[0.33 #1] | 900.07 | 0 | 0 | 0 | 900.07
18 | opkuis werf | 1.18 | 13FS;15FS |  | 2011-10-03 08:00 | 2011-10-10 17:00 | 6d | werkkracht;kraan[0.50 #1] | 3420.48 | 0 | 0 | 0 | 3420.48

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | werkkracht | Renewable | 1 | 0 | 56.26 | 1[0.83 werkkracht];2;3[0.50 werkkracht];4[0.83 werkkracht];5[0.83 werkkracht];6[0.50 werkkracht];7[0.50 werkkracht];8[0.33 werkkracht];9[0.50 werkkracht];10[0.50 werkkracht];11[0.50 werkkracht];12[0.50 werkkracht];13[0.83 werkkracht];14[0.50 werkkracht];15[0.50 werkkracht];16[0.50 werkkracht];17[0.33 werkkracht];18; | 46090.7539
2 | kraan | Renewable | 1 | 0 | 30 | 1[0.25 kraan];2[0.25 kraan];3[0.75 kraan];4[0.50 kraan];5[0.50 kraan];6[0.25 kraan];9[0.75 kraan];18[0.50 kraan]; | 13740

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | Railway Station Sint-Joost | 1080h
1 | inrichten werf | 56h | standard - symmetric | 80 | 100 | 120
2 | verwijdering pui n en afval | 16h | standard - symmetric | 80 | 100 | 120
3 | opbraak blauwe hardsteen | 48h | standard - symmetric | 80 | 100 | 120
4 | opbraak metselwerk | 48h | standard - symmetric | 80 | 100 | 120
5 | structuur gewapend beton | 160h | standard - symmetric | 80 | 100 | 120
6 | baksteen metselwerk | 528h | standard - symmetric | 80 | 100 | 120
7 | levering blauwe hardsteen | 24h | standard - symmetric | 80 | 100 | 120
8 | restauratie blauwe hardteen | 32h | standard - symmetric | 80 | 100 | 120
9 | plaatsen blauwe hardteen | 192h | standard - symmetric | 80 | 100 | 120
10 | decoratieve elementen | 16h | standard - symmetric | 80 | 100 | 120
11 | buitenschrijnwerk aluminium | 40h | standard - symmetric | 80 | 100 | 120
12 | zandstralen trappen en steunmuren | 32h | standard - symmetric | 80 | 100 | 120
13 | zandstralen kopmuur | 16h | standard - symmetric | 80 | 100 | 120
14 | herstelling gereinigde elementen natuursteen | 32h | standard - symmetric | 80 | 100 | 120
15 | anti-graffiti behandeling | 48h | standard - symmetric | 80 | 100 | 120
16 | herstelling metselwerk | 32h | standard - symmetric | 80 | 100 | 120
17 | heropvoeging metselwerk | 48h | standard - symmetric | 80 | 100 | 120
18 | opkuis werf | 48h | standard - symmetric | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes | 2011-04-18
1:00 - 2:00 | No | Tuesday | Yes | 2011-04-19
2:00 - 3:00 | No | Wednesday | Yes | 2011-04-20
3:00 - 4:00 | No | Thursday | Yes | 2011-04-21
4:00 - 5:00 | No | Friday | Yes | 2011-04-22
5:00 - 6:00 | No | Saturday | No | 2011-04-23
6:00 - 7:00 | No | Sunday | No | 2011-04-24
7:00 - 8:00 | No |  |  | 2011-04-25
8:00 - 9:00 | Yes |  |  | 2011-05-02
9:00 - 10:00 | Yes |  |  | 2011-07-11
10:00 - 11:00 | Yes |  |  | 2011-07-12
11:00 - 12:00 | Yes |  |  | 2011-07-13
12:00 - 13:00 | No |  |  | 2011-07-14
13:00 - 14:00 | Yes |  |  | 2011-07-15
14:00 - 15:00 | Yes |  |  | 2011-07-16
15:00 - 16:00 | Yes |  |  | 2011-07-17
16:00 - 17:00 | Yes |  |  | 2011-07-18
17:00 - 18:00 | No |  |  | 2011-07-19
18:00 - 19:00 | No |  |  | 2011-07-20
19:00 - 20:00 | No |  |  | 2011-07-21
20:00 - 21:00 | No |  |  | 2011-07-22
21:00 - 22:00 | No |  |  | 2011-07-23
22:00 - 23:00 | No |  |  | 2011-07-24
23:00 - 0:00 | No |  |  | 2011-07-25
2011-07-26
2011-07-27
Generated by PMConverter v1.1.3 |  |  |  | 2011-07-28
2011-07-29
2011-07-30
2011-07-31
2011-08-01
2011-08-15
2011-08-23
2011-05-16
2011-09-24
2011-02-07
2011-02-08
2011-02-09
2011-02-10
2011-02-11
2011-02-14
2011-02-15
2011-02-16
2011-02-17
2011-02-18
2011-02-21
2011-02-22
2011-02-23
2012-01-31
2012-05-31
2012-06-20
2012-06-22
2012-08-03
2012-08-08
2012-08-22
2012-08-23
2011-01-31
2011-03-31
2011-05-31
2011-06-20
2011-06-22
2011-08-03
2011-08-08
2011-08-22
2011-08-26
2011-09-08

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t))