## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | Sports Center Tielt | 1 |  |  | 2011-01-21 08:00 | 2011-05-05 17:00 | 75d |  |  | 200464.1299 |  |  | 254564.1299
1 | Voorbereidende Werken | 1.1 |  | FS2 | 2011-01-21 08:00 | 2011-02-03 17:00 | 10d | #People[10.00 #10] | 10000 | 7610 | 0 | 0 | 17610
2 | Grondverzet | 1.2 | 1FS | FS3;FS4 | 2011-02-04 08:00 | 2011-02-22 17:00 | 13d | #People[6.00 #10] | 7800 | 15732.5 | 0 | 0 | 23532.5
3 | Geschikt maken zate ophoging/baanbed uitgraving | 1.3 | 2FS | FS5 | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | #People | 100 | 200 | 0 | 0 | 300
4 | Bescherming van de onderfundering | 1.4 | 2FS | FS5 | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | #People[2.00 #10] | 200 | 600 | 0 | 0 | 800
5 | Fundering | 1.5 | 3FS;4FS | FS6 | 2011-02-24 08:00 | 2011-03-02 17:00 | 5d | #People[7.00 #10] | 3500 | 18656 | 0 | 0 | 22156
6 | Cementbetonverhardingen | 1.6 | 5FS | FS7;FS8 | 2011-03-03 08:00 | 2011-03-04 17:00 | 2d | #People[4.00 #10] | 800 | 49798 | 0 | 0 | 50598
7 | Bestratingen | 1.7 | 6FS | FS9 | 2011-03-07 08:00 | 2011-03-08 17:00 | 2d | #People[5.00 #10] | 1000 | 13180 | 0 | 0 | 14180
8 | Andere verhardingen | 1.8 | 6FS | FS9 | 2011-03-07 08:00 | 2011-03-07 17:00 | 1d | #People[3.00 #10] | 300 | 2612.5 | 0 | 0 | 2912.5
9 | Riolering en afvoer van water aangelegd in een sleuf | 1.9 | 7FS;8FS | FS10 | 2011-03-09 08:00 | 2011-03-11 17:00 | 3d | #People[5.00 #10] | 1500 | 3120 | 0 | 0 | 4620
10 | Verbindings-, las-, blinde-, of verzonken put | 1.10 | 9FS | FS11;FS12 | 2011-03-14 08:00 | 2011-03-14 17:00 | 1d | #People[2.00 #10] | 200 | 2300 | 0 | 0 | 2500
11 | Bovenbouw van inspectieputten | 1.11 | 10FS | FS13 | 2011-03-15 08:00 | 2011-03-18 17:00 | 4d | #People[7.00 #10] | 2800 | 600 | 0 | 0 | 3400
12 | Regenwaterput | 1.12 | 10FS | FS13 | 2011-03-21 08:00 | 2011-03-23 17:00 | 3d | #People[5.00 #10] | 1500 | 6000 | 0 | 0 | 7500
13 | Aansluitingen op de riolering | 1.13 | 11FS;12FS | FS14 | 2011-03-24 08:00 | 2011-03-31 17:00 | 6d | #People[8.00 #10] | 4800 | 3330 | 0 | 0 | 8130
14 | Draineringen | 1.14 | 13FS | FS15 | 2011-04-01 08:00 | 2011-04-04 17:00 | 2d | #People[6.00 #10] | 1200 | 3135 | 0 | 0 | 4335
15 | Trottoirbanden (borduren), trottoirbanden-watergreppels en schampkanten + Watergreppels van polyesterbeton | 1.15 | 14FS | FS24 | 2011-04-05 08:00 | 2011-04-08 17:00 | 4d | #People[6.00 #10] | 2400 | 21065 | 0 | 0 | 23465
16 | Doorsteken voor nutsleidingen | 1.16 |  | FS17;FS18;FS19;FS20;FS21;FS23 | 2011-02-04 08:00 | 2011-02-07 17:00 | 2d | #People[3.00 #10] | 600 | 1900 | 0 | 0 | 2500
17 | Herplaatsen van fietsenstalling | 1.17 | 16FS | FS22 | 2011-02-08 08:00 | 2011-02-08 17:00 | 1d | #People[2.00 #10] | 200 | 1750 | 0 | 0 | 1950
18 | Inrichten petanqueveldje | 1.18 | 16FS | FS26 | 2011-02-09 08:00 | 2011-02-10 17:00 | 2d | #People[3.00 #10] | 600 | 1000 | 0 | 0 | 1600
19 | Poorten en afsluitingen | 1.19 | 16FS | FS26 | 2011-02-08 08:00 | 2011-02-08 17:00 | 1d | #People[2.00 #10] | 200 | 900 | 0 | 0 | 1100
20 | Metalen borstwering | 1.20 | 16FS | FS26 | 2011-02-23 08:00 | 2011-02-23 17:00 | 1d | #People[5.00 #10] | 500 | 2695 | 0 | 0 | 3195
21 | Betonnen trappen + Houten traptredes | 1.21 | 16FS | FS26 | 2011-02-24 08:00 | 2011-02-28 17:00 | 3d | #People[3.00 #10] | 900 | 8000 | 0 | 0 | 8900
22 | Schilderwerken | 1.22 | 17FS | FS26 | 2011-02-14 08:00 | 2011-02-23 17:00 | 8d | #People[2.00 #10] | 1600 | 2250 | 0 | 0 | 3850
23 | Besproeiingspomp voor voetbalvelden | 1.23 | 16FS | FS26 | 2011-02-11 08:00 | 2011-02-11 17:00 | 1d | #People[3.00 #10] | 300 | 7750 | 0 | 0 | 8050
24 | Keerwand | 1.24 | 15FS | FS25 | 2011-04-11 08:00 | 2011-04-18 17:00 | 6d | #People[8.00 #10] | 4800 | 11937.5 | 0 | 0 | 16737.5
25 | Markeringen | 1.25 | 24FS | FS26 | 2011-04-19 08:00 | 2011-04-19 17:00 | 1d | #People[3.00 #10] | 300 | 1025 | 0 | 0 | 1325
26 | Groenaanleg | 1.26 | 18FS;19FS;20FS;21FS;22FS;23FS;25FS |  | 2011-04-20 08:00 | 2011-05-05 17:00 | 12d | #People[5.00 #10] | 6000 | 13317.6299 | 0 | 0 | 19317.6299

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | #People | Renewable | 10 #10 | 0 | 12.5 | 1[10.00 #People];2[6.00 #People];3;4[2.00 #People];5[7.00 #People];6[4.00 #People];7[5.00 #People];8[3.00 #People];9[5.00 #People];10[2.00 #People];11[7.00 #People];12[5.00 #People];13[8.00 #People];14[6.00 #People];15[6.00 #People];16[3.00 #People];17[2.00 #People];18[3.00 #People];19[2.00 #People];20[5.00 #People];21[3.00 #People];22[2.00 #People];23[3.00 #People];24[8.00 #People];25[3.00 #People];26[5.00 #People]; | 54100

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | Sports Center Tielt | 600h
1 | Voorbereidende Werken | 80h | standard - symmetric | 80 | 100 | 120
2 | Grondverzet | 104h | standard - symmetric | 80 | 100 | 120
3 | Geschikt maken zate ophoging/baanbed uitgraving | 8h | standard - symmetric | 80 | 100 | 120
4 | Bescherming van de onderfundering | 8h | standard - symmetric | 80 | 100 | 120
5 | Fundering | 40h | standard - symmetric | 80 | 100 | 120
6 | Cementbetonverhardingen | 16h | standard - symmetric | 80 | 100 | 120
7 | Bestratingen | 16h | standard - symmetric | 80 | 100 | 120
8 | Andere verhardingen | 8h | standard - symmetric | 80 | 100 | 120
9 | Riolering en afvoer van water aangelegd in een sleuf | 24h | standard - symmetric | 80 | 100 | 120
10 | Verbindings-, las-, blinde-, of verzonken put | 8h | standard - symmetric | 80 | 100 | 120
11 | Bovenbouw van inspectieputten | 32h | standard - symmetric | 80 | 100 | 120
12 | Regenwaterput | 24h | standard - symmetric | 80 | 100 | 120
13 | Aansluitingen op de riolering | 48h | standard - symmetric | 80 | 100 | 120
14 | Draineringen | 16h | standard - symmetric | 80 | 100 | 120
15 | Trottoirbanden (borduren), trottoirbanden-watergreppels en schampkanten + Watergreppels van polyesterbeton | 32h | standard - symmetric | 80 | 100 | 120
16 | Doorsteken voor nutsleidingen | 16h | standard - symmetric | 80 | 100 | 120
17 | Herplaatsen van fietsenstalling | 8h | standard - symmetric | 80 | 100 | 120
18 | Inrichten petanqueveldje | 16h | standard - symmetric | 80 | 100 | 120
19 | Poorten en afsluitingen | 8h | standard - symmetric | 80 | 100 | 120
20 | Metalen borstwering | 8h | standard - symmetric | 80 | 100 | 120
21 | Betonnen trappen + Houten traptredes | 24h | standard - symmetric | 80 | 100 | 120
22 | Schilderwerken | 64h | standard - symmetric | 80 | 100 | 120
23 | Besproeiingspomp voor voetbalvelden | 8h | standard - symmetric | 80 | 100 | 120
24 | Keerwand | 48h | standard - symmetric | 80 | 100 | 120
25 | Markeringen | 8h | standard - symmetric | 80 | 100 | 120
26 | Groenaanleg | 96h | standard - symmetric | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t))