## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | Nut Mixing Station | 1 |  |  | 2010-02-25 08:00 | 2010-03-29 12:00 | 22d 4h |  |  | 894581 |  |  | 1056501
5 | Constructie gebouw | 1.1 |  |  | 2010-02-25 08:00 | 2010-03-29 12:00 | 22d 4h |  |  | 395934 |  |  | 523934
6 | Herassen + vergaderkeet | 1.1.1 |  |  | 2010-03-23 16:00 | 2010-03-24 16:00 | 1d | Vergaderkeet;Herassen[50.00 #100] | 0 | 2500 | 0 | 0 | 2500
7 | Grondwerk | 1.1.2 |  |  | 2010-03-09 09:00 | 2010-03-26 09:00 | 13d |  |  | 17360 |  |  | 45000
8 | Uitgraven + concassé + dichten gracht | 1.1.2.1 |  | FS9 | 2010-03-09 09:00 | 2010-03-12 09:00 | 3d | Graafkraan + bestuurder;Vrachtwagen;Arbeider | 8160 | 1840 | 0 | 0 | 10000
9 | Palen | 1.1.2.2 | 8FS | FS10 | 2010-03-12 09:00 | 2010-03-16 09:00 | 2d | Paalboorinstallatie + bestuurder;Arbeider[2.00 #20] | 6880 | 5120 | 0 | 0 | 12000
10 | Delven paalkoppen + sleuven + riolering + zuivering | 1.1.2.3 | 9FS | FS11 | 2010-03-16 09:00 | 2010-03-18 09:00 | 2d | Graafkraan + bestuurder;Arbeider[3.00 #20] | 4320 | 3700 | 0 | 0 | 8020
11 | Staking | 1.1.2.4 | 10FS | FS12 | 2010-03-18 09:00 | 2010-03-19 09:00 | 1d |  | 0 | 0 | 0 | 0 | 0
12 | Paalkoppen ALHB | 1.1.2.5 | 11FS |  | 2010-03-19 09:00 | 2010-03-26 09:00 | 5d | Pneumatische drilhamer;Arbeider[4.00 #20] | 7000 | 6000 | 0 | 0 | 13000
13 | aansluiten in bestaande put | 1.1.2.6 |  |  | 2010-03-23 08:00 | 2010-03-24 17:00 | 2d | Arbeider[2.00 #20] | 1280 | 700 | 0 | 0 | 1980
14 | Montage | 1.1.3 |  |  | 2010-02-25 08:00 | 2010-03-25 15:00 | 20d 6h |  |  | 64000 |  |  | 100000
15 | Montage (kraan binnen bij as 4) | 1.1.3.1 |  | FS16;FS36 | 2010-02-25 08:00 | 2010-03-01 17:00 | 3d | Montagekraan + bestuurder;Arbeider[3.00 #20];Hoogtewerker[2.00 #12] | 10800 | 21200 | 0 | 0 | 32000
16 | Montage (kraan binnen bij as 1) | 1.1.3.2 | 15FS | FS17;FS22 | 2010-03-02 08:00 | 2010-03-05 17:00 | 4d | Montagekraan + bestuurder;Arbeider[3.00 #20];Hoogtewerker[2.00 #12] | 14400 | 25600 | 0 | 0 | 40000
17 | Montage (kraan buiten) | 1.1.3.3 | 16FS |  | 2010-03-22 15:00 | 2010-03-25 15:00 | 3d | Montagekraan + bestuurder;Arbeider[3.00 #20];Hoogtewerker[2.00 #12] | 10800 | 17200 | 0 | 0 | 28000
18 | Vloeren | 1.1.4 |  |  | 2010-03-08 08:00 | 2010-03-26 14:00 | 14d 5h |  |  | 37840 |  |  | 55000
19 | Druklaag (klaarleggen + gieten) | 1.1.4.1 | 36FS | FS20;FS25+1w 1d | 2010-03-15 09:00 | 2010-03-17 09:00 | 2d | Arbeider[2.00 #20];Betonpomp + bediener;Vlindertoestel | 2640 | 2360 | 0 | 0 | 5000
20 | Ondervloer goot gieten | 1.1.4.2 | 19FS | FS21 | 2010-03-23 14:00 | 2010-03-24 14:00 | 1d | Arbeider[2.00 #20] | 640 | 860 | 0 | 0 | 1500
21 | Borduren zetten | 1.1.4.3 | 20FS |  | 2010-03-24 14:00 | 2010-03-25 14:00 | 1d | Verreiker + bestuurder;Arbeider | 1520 | 2030 | 0 | 0 | 3550
22 | Nivelleren binnen | 1.1.4.4 | 16FS | FS23 | 2010-03-08 08:00 | 2010-03-08 17:00 | 1d | Graafkraan + bestuurder;Arbeider | 1520 | 480 | 0 | 0 | 2000
23 | Wapening | 1.1.4.5 | 22FS | FS24 | 2010-03-09 08:00 | 2010-03-09 17:00 | 1d | Arbeider[4.00 #20] | 1280 | 13720 | 0 | 0 | 15000
24 | Vloeren binnen en buiten | 1.1.4.6 | 23FS | FS26+2d;FS27+4d;FS28+1w 1d | 2010-03-10 08:00 | 2010-03-10 17:00 | 1d | Betonpomp + bediener;Arbeider[4.00 #20];Vlindertoestel[2.00 #2] | 2040 | 16480 | 0 | 0 | 18520
25 | Plintjes boven | 1.1.4.7 | 19FS+1w 1d |  | 2010-03-25 09:00 | 2010-03-26 09:00 | 1d | Arbeider[2.00 #20] | 640 | 350 | 0 | 0 | 990
26 | Metsen muur | 1.1.4.8 | 24FS+2d |  | 2010-03-23 10:00 | 2010-03-26 10:00 | 3d | Arbeider;Metser | 1920 | 1060 | 0 | 0 | 2980
27 | Plaatsen rijplaten | 1.1.4.9 | 24FS+4d | FS40;FS42;FS43;FS44;FS51 | 2010-03-17 08:00 | 2010-03-17 17:00 | 1d | Verreiker + bestuurder;Arbeider[2.00 #20] | 1840 | 150 | 0 | 0 | 1990
28 | Plintjes zetten beneden | 1.1.4.10 | 24FS+1w 1d |  | 2010-03-24 14:00 | 2010-03-26 14:00 | 2d | Arbeider[2.00 #20] | 1280 | 350 | 0 | 0 | 1630
29 | Verwijderen rijplaten | 1.1.4.11 |  | FS46 | 2010-03-23 08:00 | 2010-03-23 17:00 | 1d | Verreiker + bestuurder;Arbeider[2.00 #20] | 1840 | 0 | 0 | 0 | 1840
30 | Dak | 1.1.5 |  |  | 2010-03-15 14:00 | 2010-03-25 14:00 | 8d |  |  | 17440 |  |  | 24000
31 | Plaatsen opstanden voor koepels | 1.1.5.1 |  | FS32 | 2010-03-15 14:00 | 2010-03-17 14:00 | 2d | Arbeider[2.00 #20] | 1280 | 1220 | 0 | 0 | 2500
32 | Dakwerken (onderlaag) | 1.1.5.2 | 31FS | FS33 | 2010-03-17 14:00 | 2010-03-19 14:00 | 2d | Dakwerkers[3.00 #3] | 1920 | 8080 | 0 | 0 | 10000
33 | Dakwerken (afwerking) | 1.1.5.3 | 32FS | FS34 | 2010-03-19 14:00 | 2010-03-24 14:00 | 3d | Dakwerkers[3.00 #3] | 2880 | 5620 | 0 | 0 | 8500
34 | Levenslijn | 1.1.5.4 | 33FS |  | 2010-03-24 14:00 | 2010-03-25 14:00 | 1d | Veiligheidsinstallateur | 480 | 2520 | 0 | 0 | 3000
35 | Staalstructuur | 1.1.6 |  |  | 2010-03-12 09:00 | 2010-03-29 12:00 | 11d 3h |  |  | 75080 |  |  | 95000
36 | Plaatsen railing rond verdiep | 1.1.6.1 | 15FS | FS19;FS37 | 2010-03-12 09:00 | 2010-03-15 09:00 | 1d | Staalmonteur[2.00 #4] | 640 | 4360 | 0 | 0 | 5000
37 | Plaatsen RACK | 1.1.6.2 | 36FS | FS38;SS59 | 2010-03-18 15:00 | 2010-03-22 15:00 | 2d | Staalmonteur[4.00 #4];Hoogtewerker[2.00 #12];Montagekraan + bestuurder | 7840 | 17160 | 0 | 0 | 25000
38 | Plaatsen kolommen en liggers | 1.1.6.3 | 37FS | FS39 | 2010-03-22 15:00 | 2010-03-24 15:00 | 2d | Verreiker + bestuurder;Staalmonteur[2.00 #4];Hoogtewerker[2.00 #12] | 4960 | 15040 | 0 | 0 | 20000
39 | Plaatsen zwenkarm | 1.1.6.4 | 38FS |  | 2010-03-26 13:00 | 2010-03-29 12:00 | 1d | Verreiker + bestuurder;Hoogtewerker;Staalmonteur[2.00 #4] | 2160 | 12840 | 0 | 0 | 15000
40 | Montage wandelbrug, poort, trap | 1.1.6.5 | 27FS |  | 2010-03-24 13:00 | 2010-03-26 12:00 | 2d | Verreiker + bestuurder;Hoogtewerker;Staalmonteur[2.00 #4] | 4320 | 25680 | 0 | 0 | 30000
41 | Technische voorzieningen | 1.1.7 |  |  | 2010-03-18 16:00 | 2010-03-26 12:00 | 5d 5h |  |  | 129954 |  |  | 140834
42 | Elektriciteit + verlichting | 1.1.7.1 | 27FS | FF60+1d;SS61 | 2010-03-18 16:00 | 2010-03-25 16:00 | 5d | Elektricien[3.00 #3];Hoogtewerker | 6400 | 29600 | 0 | 0 | 36000
43 | Leidingen | 1.1.7.2 | 27FS |  | 2010-03-24 13:00 | 2010-03-26 12:00 | 2d | Hoogtewerker;Loodgieter[3.00 #5] | 2560 | 65718 | 0 | 0 | 68278
44 | Perslucht | 1.1.7.3 | 27FS |  | 2010-03-24 13:00 | 2010-03-26 12:00 | 2d | Loodgieter[2.00 #5];Hoogtewerker | 1920 | 34636 | 0 | 0 | 36556
45 | Plaatsing wegneembare wand | 1.1.8 |  |  | 2010-03-25 14:00 | 2010-03-26 14:00 | 1d |  |  | 25340 |  |  | 27500
46 | Plaatsen isolatiepanelen | 1.1.8.1 | 29FS |  | 2010-03-25 14:00 | 2010-03-26 14:00 | 1d | Verreiker + bestuurder;Hoogtewerker;Arbeider[2.00 #20] | 2160 | 25340 | 0 | 0 | 27500
47 | Afwerking | 1.1.9 |  |  | 2010-03-17 11:00 | 2010-03-25 11:00 | 6d |  |  | 26420 |  |  | 34100
48 | Inrichting verstiaire | 1.1.9.1 |  | FS49 | 2010-03-17 11:00 | 2010-03-22 11:00 | 3d | Stukadoor;Schilder;Arbeider[2.00 #20] | 3840 | 2510 | 0 | 0 | 6350
49 | Epoxy deklaag | 1.1.9.2 | 48FS |  | 2010-03-22 11:00 | 2010-03-25 11:00 | 3d | Arbeider[4.00 #20] | 3840 | 23910 | 0 | 0 | 27750
50 | Nut mixing station | 1.2 |  |  | 2010-03-18 08:00 | 2010-03-29 12:00 | 7d 4h |  |  | 498647 |  |  | 532567
51 | Plaatsen tanks | 1.2.1 | 27FS | FS52;FS53;FS54;FS55 | 2010-03-18 08:00 | 2010-03-18 17:00 | 1d | Arbeider[3.00 #20];Verreiker + bestuurder;Paalboorinstallatie + bestuurder | 4960 | 192520 | 0 | 0 | 197480
52 | Plaatsen leidingen | 1.2.2 | 51FS | FS56;FS57;FS58 | 2010-03-19 08:00 | 2010-03-23 17:00 | 3d | Verreiker + bestuurder;Techniekers Nut Mixing Station[3.00 #9];Hoogtewerker[2.00 #12] | 8400 | 91600 | 0 | 0 | 100000
53 | Weegsysteem | 1.2.3 | 51FS |  | 2010-03-25 13:00 | 2010-03-26 12:00 | 1d | Verreiker + bestuurder;Techniekers Nut Mixing Station[3.00 #9] | 2160 | 13840 | 0 | 0 | 16000
54 | Plaatsten filter | 1.2.4 | 51FS |  | 2010-03-26 13:00 | 2010-03-29 12:00 | 1d | Hoogtewerker;Techniekers Nut Mixing Station[2.00 #9] | 960 | 16040 | 0 | 0 | 17000
55 | Plaatsen pompen | 1.2.5 | 51FS |  | 2010-03-24 14:00 | 2010-03-26 14:00 | 2d | Verreiker + bestuurder;Techniekers Nut Mixing Station[2.00 #9] | 3680 | 35320 | 0 | 0 | 39000
56 | Pigged pipe | 1.2.6 | 52FS |  | 2010-03-24 16:00 | 2010-03-26 16:00 | 2d | Techniekers Nut Mixing Station[2.00 #9];Hoogtewerker | 1920 | 28080 | 0 | 0 | 30000
57 | Verwarming | 1.2.7 | 52FS |  | 2010-03-24 08:00 | 2010-03-26 17:00 | 3d | Chauffagist[2.00 #2];Hoogtewerker | 2880 | 52120 | 0 | 0 | 55000
58 | Pièce magnétique | 1.2.8 | 52FS |  | 2010-03-24 16:00 | 2010-03-26 16:00 | 2d | Techniekers Nut Mixing Station[2.00 #9];Hoogtewerker | 1920 | 9580 | 0 | 0 | 11500
59 | Boren van openingen | 1.2.9 | 37SS |  | 2010-03-24 10:00 | 2010-03-25 10:00 | 1d | Hoogtewerker;Arbeider[2.00 #20] | 960 | 3040 | 0 | 0 | 4000
60 | Automatisering | 1.2.10 | 42FF+1d |  | 2010-03-19 16:00 | 2010-03-26 16:00 | 5d | Technieker Automatisering;Hoogtewerker | 3200 | 45200 | 0 | 0 | 48400
61 | Brandbeveiliging en sensoren | 1.2.11 | 42SS |  | 2010-03-23 14:00 | 2010-03-26 14:00 | 3d | Hoogtewerker;Brandtechnicus[2.00 #2] | 2880 | 11307 | 0 | 0 | 14187

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Herassen | Renewable | 100 | 0 | 0 | 6[50.00 Herassen]; | 0
2 | Vergaderkeet | Renewable | 1 | 0 | 0 | 6; | 0
3 | Graafkraan + bestuurder | Renewable | 1 | 0 | 150 | 8;10;22; | 7200
4 | Vrachtwagen | Renewable | 1 | 0 | 150 | 8; | 3600
5 | Paalboorinstallatie + bestuurder | Renewable | 1 | 0 | 350 | 9;51; | 8400
6 | Arbeider | Renewable | 20 | 0 | 40 | 8;9[2.00 Arbeider];10[3.00 Arbeider];12[4.00 Arbeider];13[2.00 Arbeider];15[3.00 Arbeider];16[3.00 Arbeider];17[3.00 Arbeider];19[2.00 Arbeider];20[2.00 Arbeider];21;22;23[4.00 Arbeider];24[4.00 Arbeider];25[2.00 Arbeider];26;27[2.00 Arbeider];28[2.00 Arbeider];29[2.00 Arbeider];31[2.00 Arbeider];46[2.00 Arbeider];48[2.00 Arbeider];49[4.00 Arbeider];51[3.00 Arbeider];59[2.00 Arbeider]; | 40000
7 | Montagekraan + bestuurder | Renewable | 1 | 0 | 250 | 15;16;17;37; | 24000
8 | Betonpomp + bediener | Renewable | 1 | 0 | 75 | 19;24; | 1800
9 | Vlindertoestel | Renewable | 2 | 0 | 10 | 19;24[2.00 Vlindertoestel]; | 320
10 | Metser | Renewable | 1 | 0 | 40 | 26; | 960
11 | Hoogtewerker | Renewable | 12 | 0 | 40 | 15[2.00 Hoogtewerker];16[2.00 Hoogtewerker];17[2.00 Hoogtewerker];37[2.00 Hoogtewerker];38[2.00 Hoogtewerker];39;40;42;43;44;46;52[2.00 Hoogtewerker];54;56;57;58;59;60;61; | 20480
12 | Verreiker + bestuurder | Renewable | 4 | 0 | 150 | 21;27;29;38;39;40;46;51;52;53;55; | 19200
13 | Dakwerkers | Renewable | 3 | 0 | 40 | 32[3.00 Dakwerkers];33[3.00 Dakwerkers]; | 4800
14 | Veiligheidsinstallateur | Renewable | 1 | 0 | 60 | 34; | 480
15 | Staalmonteur | Renewable | 4 | 0 | 40 | 36[2.00 Staalmonteur];37[4.00 Staalmonteur];38[2.00 Staalmonteur];39[2.00 Staalmonteur];40[2.00 Staalmonteur]; | 6400
16 | Elektricien | Renewable | 3 | 0 | 40 | 42[3.00 Elektricien]; | 4800
17 | Stukadoor | Renewable | 1 | 0 | 40 | 48; | 960
18 | Schilder | Renewable | 1 | 0 | 40 | 48; | 960
19 | Loodgieter | Renewable | 5 | 0 | 40 | 43[3.00 Loodgieter];44[2.00 Loodgieter]; | 3200
20 | Techniekers Nut Mixing Station | Renewable | 9 | 0 | 40 | 52[3.00 Techniekers Nut Mixing Station];53[3.00 Techniekers Nut Mixing Station];54[2.00 Techniekers Nut Mixing Station];55[2.00 Techniekers Nut Mixing Station];56[2.00 Techniekers Nut Mixing Station];58[2.00 Techniekers Nut Mixing Station]; | 8320
21 | Technieker Automatisering | Renewable | 2 | 0 | 40 | 60; | 1600
22 | Brandtechnicus | Renewable | 2 | 0 | 40 | 61[2.00 Brandtechnicus]; | 1920
23 | Pneumatische drilhamer | Renewable | 2 | 0 | 15 | 12; | 600
24 | Chauffagist | Renewable | 2 | 0 | 40 | 57[2.00 Chauffagist]; | 1920

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | Nut Mixing Station | 180h
5 | Constructie gebouw | 180h
6 | Herassen + vergaderkeet | 8h | standard - symmetric | 80 | 100 | 120
7 | Grondwerk | 104h
8 | Uitgraven + concassé + dichten gracht | 24h | standard - symmetric | 80 | 100 | 120
9 | Palen | 16h | standard - symmetric | 80 | 100 | 120
10 | Delven paalkoppen + sleuven + riolering + zuivering | 16h | standard - symmetric | 80 | 100 | 120
11 | Staking | 8h | standard - symmetric | 80 | 100 | 120
12 | Paalkoppen ALHB | 40h | standard - symmetric | 80 | 100 | 120
13 | aansluiten in bestaande put | 16h | standard - symmetric | 80 | 100 | 120
14 | Montage | 166h
15 | Montage (kraan binnen bij as 4) | 24h | standard - symmetric | 80 | 100 | 120
16 | Montage (kraan binnen bij as 1) | 32h | standard - symmetric | 80 | 100 | 120
17 | Montage (kraan buiten) | 24h | standard - symmetric | 80 | 100 | 120
18 | Vloeren | 117h
19 | Druklaag (klaarleggen + gieten) | 16h | standard - symmetric | 80 | 100 | 120
20 | Ondervloer goot gieten | 8h | standard - symmetric | 80 | 100 | 120
21 | Borduren zetten | 8h | standard - symmetric | 80 | 100 | 120
22 | Nivelleren binnen | 8h | standard - symmetric | 80 | 100 | 120
23 | Wapening | 8h | standard - symmetric | 80 | 100 | 120
24 | Vloeren binnen en buiten | 8h | standard - symmetric | 80 | 100 | 120
25 | Plintjes boven | 8h | standard - symmetric | 80 | 100 | 120
26 | Metsen muur | 24h | standard - symmetric | 80 | 100 | 120
27 | Plaatsen rijplaten | 8h | standard - symmetric | 80 | 100 | 120
28 | Plintjes zetten beneden | 16h | standard - symmetric | 80 | 100 | 120
29 | Verwijderen rijplaten | 8h | standard - symmetric | 80 | 100 | 120
30 | Dak | 64h
31 | Plaatsen opstanden voor koepels | 16h | standard - symmetric | 80 | 100 | 120
32 | Dakwerken (onderlaag) | 16h | standard - symmetric | 80 | 100 | 120
33 | Dakwerken (afwerking) | 24h | standard - symmetric | 80 | 100 | 120
34 | Levenslijn | 8h | standard - symmetric | 80 | 100 | 120
35 | Staalstructuur | 91h
36 | Plaatsen railing rond verdiep | 8h | standard - symmetric | 80 | 100 | 120
37 | Plaatsen RACK | 16h | standard - symmetric | 80 | 100 | 120
38 | Plaatsen kolommen en liggers | 16h | standard - symmetric | 80 | 100 | 120
39 | Plaatsen zwenkarm | 8h | standard - symmetric | 80 | 100 | 120
40 | Montage wandelbrug, poort, trap | 16h | standard - symmetric | 80 | 100 | 120
41 | Technische voorzieningen | 45h
42 | Elektriciteit + verlichting | 40h | standard - symmetric | 80 | 100 | 120
43 | Leidingen | 16h | standard - symmetric | 80 | 100 | 120
44 | Perslucht | 16h | standard - symmetric | 80 | 100 | 120
45 | Plaatsing wegneembare wand | 8h
46 | Plaatsen isolatiepanelen | 8h | standard - symmetric | 80 | 100 | 120
47 | Afwerking | 48h
48 | Inrichting verstiaire | 24h | standard - symmetric | 80 | 100 | 120
49 | Epoxy deklaag | 24h | standard - symmetric | 80 | 100 | 120
50 | Nut mixing station | 60h
51 | Plaatsen tanks | 8h | standard - symmetric | 80 | 100 | 120
52 | Plaatsen leidingen | 24h | standard - symmetric | 80 | 100 | 120
53 | Weegsysteem | 8h | standard - symmetric | 80 | 100 | 120
54 | Plaatsten filter | 8h | standard - symmetric | 80 | 100 | 120
55 | Plaatsen pompen | 16h | standard - symmetric | 80 | 100 | 120
56 | Pigged pipe | 16h | standard - symmetric | 80 | 100 | 120
57 | Verwarming | 24h | standard - symmetric | 80 | 100 | 120
58 | Pièce magnétique | 16h | standard - symmetric | 80 | 100 | 120
59 | Boren van openingen | 8h | standard - symmetric | 80 | 100 | 120
60 | Automatisering | 40h | standard - symmetric | 80 | 100 | 120
61 | Brandbeveiliging en sensoren | 24h | standard - symmetric | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t))