## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | Asti-Cuneo Highway | 1 |  |  | 2012-04-12 07:00 | 2013-05-14 17:00 | 284d |  |  | 0 |  |  | 6230961
10 | Installation of fixed yard | 1.1 |  |  | 2012-04-12 07:00 | 2012-04-27 17:00 | 12d |  |  | 0 |  |  | 151200
1 | Pegging and fence | 1.1.1 |  | FS2 | 2012-04-12 07:00 | 2012-04-12 17:00 | 1d | Labourers[2.00 #10];Truck IVECO Trakker;Materials[10000.00F #-1] | 11710 | 0 | 0 | 0 | 11710
2 | Clearing site | 1.1.2 | 1FS | FS3 | 2012-04-13 07:00 | 2012-04-16 17:00 | 2d | Labourers[4.00 #10];Truck IVECO Trakker[3.00 #6];Wheel Loader | 9180 | 0 | 0 | 0 | 9180
3 | Levelling ground | 1.1.3 | 2FS | FS4 | 2012-04-17 07:00 | 2012-04-17 17:00 | 1d | Labourers[3.00 #10];Bulldozer D8T;Wheel Loader;Truck IVECO Trakker | 3465 | 0 | 0 | 0 | 3465
4 | Containers placement | 1.1.4 | 3FS | FS5 | 2012-04-18 07:00 | 2012-04-18 17:00 | 1d | Labourers[2.00 #10];Truck IVECO Trakker;Crane | 2655 | 0 | 0 | 0 | 2655
5 | Connection to network service | 1.1.5 | 4FS | FS6 | 2012-04-19 07:00 | 2012-04-20 17:00 | 2d | Labourers[3.00 #10];Truck IVECO Trakker | 4500 | 0 | 0 | 0 | 4500
6 | Pegging road | 1.1.6 | 5FS | FS7 | 2012-04-23 07:00 | 2012-04-23 17:00 | 1d | Labourers[2.00 #10];Truck IVECO Trakker;Materials[30000.00F #-1] | 31710 | 0 | 0 | 0 | 31710
7 | Alternative road system | 1.1.7 | 6FS | FS8;FS9 | 2012-04-24 07:00 | 2012-04-27 17:00 | 4d | Labourers[7.00 #10];Truck IVECO Trakker[5.00 #6];Wheel Loader[2.00 #2];Sheepfoot rolles;Concrete Mixer Truck;Materials[50000.00F #-1] | 87980 | 0 | 0 | 0 | 87980
16 | Zone B working | 1.2 |  |  | 2012-04-30 07:00 | 2012-06-20 17:00 | 38d |  |  | 0 |  |  | 430524
8 | Demolition | 1.2.1 | 7FS | FS24;FS41 | 2012-04-30 07:00 | 2012-04-30 17:00 | 1d | Labourers[4.00 #10];Truck IVECO Trakker[2.00 #6];Crawler Excavator;Paler | 4887 | 0 | 0 | 0 | 4887
9 | Clearing subbase and topsoil removal | 1.2.2 | 7FS | FS14;FS11 | 2012-04-30 07:00 | 2012-05-03 17:00 | 4d | Labourers[3.00 #10];Truck IVECO Trakker;Bulldozer D8T;Wheel Loader | 13860 | 0 | 0 | 0 | 13860
15 | Minor works | 1.2.3 |  |  | 2012-05-04 07:00 | 2012-06-01 17:00 | 21d |  |  | 0 |  |  | 13785
14 | Manhole covers | 1.2.3.1 | 9FS | FS24;FS41 | 2012-06-01 07:00 | 2012-06-01 17:00 | 1d | Labourers[3.00 #10];Truck IVECO Trakker;Crane;Materials[3000.00F #-1] | 6195 | 0 | 0 | 0 | 6195
13 | Culverts box | 1.2.3.2 |  |  | 2012-05-04 07:00 | 2012-05-18 17:00 | 11d |  |  | 0 |  |  | 7590
11 | Placement formworks and concrete casting | 1.2.3.2.1 | 9FS | FS12;FS19 | 2012-05-04 07:00 | 2012-05-04 17:00 | 1d | Labourers[4.00 #10];Truck IVECO Trakker;Concrete Mixer Truck;Crane;Materials[3000.00F #-1] | 7590 | 0 | 0 | 0 | 7590
12 | Culverts concrete aging | 1.2.3.2.2 | 11FS | FS24;FS41 | 2012-05-07 07:00 | 2012-05-18 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0
97 | Ground movement | 1.2.4 |  |  | 2012-05-07 07:00 | 2012-06-13 17:00 | 28d |  |  | 0 |  |  | 373407
19 | Road embankments | 1.2.4.1 | 11FS | FS20;FS17 | 2012-05-07 07:00 | 2012-05-29 17:00 | 17d | Labourers[10.00 #10];Truck IVECO Trakker[6.00 #6];Wheel Loader[2.00 #2];Sheepfoot rolles;Concrete Mixer Truck;Materials[55000.00F #-1] | 254665 | 0 | 0 | 0 | 254665
20 | Sound barriers | 1.2.4.2 | 19FS | FS24;FS41 | 2012-05-30 07:00 | 2012-05-31 17:00 | 2d | Labourers[4.00 #10];Truck IVECO Trakker;Crane;Materials[23000.00F #-1] | 30470 | 0 | 0 | 0 | 30470
18 | Trench | 1.2.4.3 |  |  | 2012-06-04 07:00 | 2012-06-13 17:00 | 8d |  |  | 0 |  |  | 88272
17 | Digging | 1.2.4.3.1 | 19FS | FS22 | 2012-06-04 07:00 | 2012-06-13 17:00 | 8d | Labourers[9.00 #10];Crawler Excavator[2.00 #2];Truck IVECO Trakker[6.00 #6];Sheepfoot rolles | 88272 | 0 | 0 | 0 | 88272
23 | Hydraulic works | 1.2.5 |  |  | 2012-06-14 07:00 | 2012-06-20 17:00 | 5d |  |  | 0 |  |  | 24585
22 | Longitudinal drains (ditches) | 1.2.5.1 | 17FS | FS24;FS41 | 2012-06-14 07:00 | 2012-06-20 17:00 | 5d | Labourers[4.00 #10];Truck IVECO Trakker;Crane;Crawler Excavator;Materials[1500.00F #-1] | 24585 | 0 | 0 | 0 | 24585
37 | Overpass construction | 1.3 |  |  | 2012-06-21 07:00 | 2012-12-10 17:00 | 123d |  |  | 0 |  |  | 604317
24 | Plinths excavation | 1.3.1 | 8FS;12FS;14FS;20FS;22FS | FS25 | 2012-06-21 07:00 | 2012-06-21 17:00 | 1d | Labourers[4.00 #10];Truck IVECO Trakker[3.00 #6];Crawler Excavator;Materials[0.00F #-1] | 4932 | 0 | 0 | 0 | 4932
25 | Pouring piles frameworks and drilling | 1.3.2 | 24FS | FS26 | 2012-06-25 07:00 | 2012-06-28 17:00 | 4d | Labourers[6.00 #10];Truck IVECO Trakker;Drilling Rid;Crane;Wheel Loader;Concrete Mixer Truck;Materials[190000.00F #-1] | 217540 | 0 | 0 | 0 | 217540
26 | Piles concrete aging | 1.3.3 | 25FS | FS27 | 2012-06-29 07:00 | 2012-07-12 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0
27 | Making of plinths (pouring frameworks and concrete casting) | 1.3.4 | 26FS | FS28 | 2012-08-03 07:00 | 2012-08-06 17:00 | 2d | Labourers[4.00 #10];Truck IVECO Trakker;Concrete Mixer Truck;Crane;Materials[100000.00F #-1] | 109180 | 0 | 0 | 0 | 109180
28 | Plinths concrete aging | 1.3.5 | 27FS | FS29 | 2012-08-07 07:00 | 2012-08-20 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0
29 | Making of pylons (pouring frameworks and concrete casting) | 1.3.6 | 28FS | FS30 | 2012-08-21 07:00 | 2012-08-21 17:00 | 1d | Labourers[4.00 #10];Truck IVECO Trakker;Concrete Mixer Truck;Crane;Materials[11000.00F #-1] | 15590 | 0 | 0 | 0 | 15590
30 | Pylons concrete aging | 1.3.7 | 29FS | FS31 | 2012-08-22 07:00 | 2012-09-04 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0
31 | Making of shoulders (pouring frameworks and concrete casting) | 1.3.8 | 30FS | FS32 | 2012-09-05 07:00 | 2012-09-05 17:00 | 1d | Labourers[4.00 #10];Truck IVECO Trakker;Concrete Mixer Truck;Crane;Materials[81000.00F #-1] | 85590 | 0 | 0 | 0 | 85590
32 | Shoulders concrete aging | 1.3.9 | 31FS | FS33 | 2012-09-06 07:00 | 2012-09-19 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0
33 | Pouring prefabricated beam | 1.3.10 | 32FS | FS34 | 2012-09-20 07:00 | 2012-09-20 17:00 | 1d | Labourers[4.00 #10];Truck IVECO Trakker;Crane;Materials[52000.00F #-1] | 55735 | 0 | 0 | 0 | 55735
34 | Making of slab (pouring frameworks and concrete casting) | 1.3.11 | 33FS | FS35 | 2012-09-21 07:00 | 2012-09-21 17:00 | 1d | Labourers[5.00 #10];Truck IVECO Trakker;Concrete Mixer Truck;Crane;Materials[23500.00F #-1] | 28630 | 0 | 0 | 0 | 28630
35 | Slab's concrete aging | 1.3.12 | 34FS | FS36 | 2012-09-24 07:00 | 2012-10-05 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0
36 | Making of embankments | 1.3.13 | 35FS | FS58;FS85 | 2012-11-23 07:00 | 2012-12-10 17:00 | 12d | Labourers[5.00 #10];Truck IVECO Trakker[3.00 #6];Wheel Loader;Sheepfoot rolles;Materials[18000.00F #-1] | 87120 | 0 | 0 | 0 | 87120
96 | Zone A working | 1.4 |  |  | 2012-06-21 07:00 | 2012-08-01 17:00 | 30d |  |  | 0 |  |  | 373496
41 | Demolitions | 1.4.1 | 8FS;12FS;14FS;20FS;22FS | FS42;FS63 | 2012-06-21 07:00 | 2012-06-21 17:00 | 1d | Labourers[3.00 #10];Truck IVECO Trakker[2.00 #6];Cold Milling Machine | 4950 | 0 | 0 | 0 | 4950
42 | Topsoil removal and clearing subbase | 1.4.2 | 41FS | FS38 | 2012-06-22 07:00 | 2012-06-28 17:00 | 5d | Labourers[3.00 #10];Truck IVECO Trakker;Wheel Loader;Bulldozer D8T | 17325 | 0 | 0 | 0 | 17325
40 | Ground movement | 1.4.3 |  |  | 2012-06-29 07:00 | 2012-07-27 17:00 | 21d |  |  | 0 |  |  | 311825
38 | Embankments | 1.4.3.1 | 42FS | FS39 | 2012-06-29 07:00 | 2012-07-25 17:00 | 19d | Labourers[10.00 #10];Truck IVECO Trakker[6.00 #6];Wheel Loader[2.00 #2];Sheepfoot rolles;Concrete Mixer Truck;Materials[68600.00F #-1] | 291755 | 0 | 0 | 0 | 291755
39 | Sound barriers | 1.4.3.2 | 38FS | FS62 | 2012-07-26 07:00 | 2012-07-27 17:00 | 2d | Labourers[4.00 #10];Truck IVECO Trakker;Crane;Materials[12600.00F #-1] | 20070 | 0 | 0 | 0 | 20070
65 | Minor works | 1.4.4 |  |  | 2012-06-22 07:00 | 2012-06-22 17:00 | 1d |  |  | 0 |  |  | 8655
63 | Manhole covers | 1.4.4.1 | 41FS | FS66 | 2012-06-22 07:00 | 2012-06-22 17:00 | 1d | Labourers[2.00 #10];Truck IVECO Trakker;Crane;Materials[6000.00F #-1] | 8655 | 0 | 0 | 0 | 8655
64 | Hydraulic works | 1.4.5 |  |  | 2012-07-30 07:00 | 2012-08-01 17:00 | 3d |  |  | 0 |  |  | 30741
62 | Catch water drains | 1.4.5.1 | 39FS | FS66 | 2012-07-30 07:00 | 2012-08-01 17:00 | 3d | Labourers[4.00 #10];Truck IVECO Trakker[2.00 #6];Crawler Excavator;Crane;Materials[15000.00F #-1] | 30741 | 0 | 0 | 0 | 30741
71 | Subway construction | 1.5 |  |  | 2012-08-02 07:00 | 2012-09-03 17:00 | 23d |  |  | 0 |  |  | 159140
66 | Retaining walls (frameworks and concrete casting) | 1.5.1 | 62FS;63FS | FS67 | 2012-08-02 07:00 | 2012-08-02 17:00 | 1d | Labourers[5.00 #10];Crane;Truck IVECO Trakker;Concrete Mixer Truck;Materials[88000.00F #-1] | 93130 | 0 | 0 | 0 | 93130
67 | Retaining walls concrete aging | 1.5.2 | 66FS | FS68 | 2012-08-03 07:00 | 2012-08-16 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0
68 | Pouring prefabricated beams | 1.5.3 | 67FS | FS69 | 2012-08-17 07:00 | 2012-08-17 17:00 | 1d | Labourers[4.00 #10];Truck IVECO Trakker;Crane;Materials[50000.00F #-1] | 53735 | 0 | 0 | 0 | 53735
69 | Making of slabs (frameworks pouring and concrete casting) | 1.5.4 | 68FS | FS70 | 2012-08-20 07:00 | 2012-08-20 17:00 | 1d | Labourers[5.00 #10];Truck IVECO Trakker;Crane;Materials[8000.00F #-1] | 12275 | 0 | 0 | 0 | 12275
70 | Slabs concrete aging | 1.5.5 | 69FS | FS82 | 2012-08-21 07:00 | 2012-09-03 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0
84 | Zone D working | 1.6 |  |  | 2012-09-04 07:00 | 2012-11-28 17:00 | 62d |  |  | 0 |  |  | 755051
82 | Demolitions | 1.6.1 | 70FS | FS83 | 2012-09-04 07:00 | 2012-09-04 17:00 | 1d | Labourers[3.00 #10];Truck IVECO Trakker[2.00 #6];Cold Milling Machine | 4950 | 0 | 0 | 0 | 4950
83 | Topsoil removal and subbase clearing | 1.6.2 | 82FS | FS75;FS80 | 2012-09-05 07:00 | 2012-09-20 17:00 | 12d | Labourers[4.00 #10];Truck IVECO Trakker[2.00 #6];Bulldozer D8T;Wheel Loader | 55620 | 0 | 0 | 0 | 55620
76 | Ground movement | 1.6.3 |  |  | 2012-09-24 07:00 | 2012-11-22 17:00 | 44d |  |  | 0 |  |  | 644090
75 | Embankments | 1.6.3.1 | 83FS | FS73;FS78;FS77 | 2012-09-24 07:00 | 2012-11-20 17:00 | 42d | Labourers[10.00 #10];Truck IVECO Trakker[6.00 #6];Wheel Loader[2.00 #2];Sheepfoot rolles;Tank Truck;Materials[140000.00F #-1] | 626864 | 0 | 0 | 0 | 626864
74 | Hillside (mezzacosta) works | 1.6.3.2 |  |  | 2012-11-21 07:00 | 2012-11-22 17:00 | 2d |  |  | 0 |  |  | 17226
73 | Terracing | 1.6.3.2.1 | 75FS | FS72 | 2012-11-21 07:00 | 2012-11-21 17:00 | 1d | Labourers[3.00 #10];Crawler Excavator;Sheepfoot rolles;Tank Truck;Materials[1800.00F #-1] | 5634 | 0 | 0 | 0 | 5634
72 | Carrying remaining soil | 1.6.3.2.2 | 73FS | FS48 | 2012-11-22 07:00 | 2012-11-22 17:00 | 1d | Labourers[10.00 #10];Truck IVECO Trakker[6.00 #6];Wheel Loader[2.00 #2];Sheepfoot rolles;Tank Truck | 11592 | 0 | 0 | 0 | 11592
81 | Minor works | 1.6.4 |  |  | 2012-11-27 07:00 | 2012-11-28 17:00 | 2d |  |  | 0 |  |  | 13390
80 | Culverts | 1.6.4.1 | 83FS | FS48 | 2012-11-27 07:00 | 2012-11-28 17:00 | 2d | Labourers[3.00 #10];Crane;Truck IVECO Trakker;Materials[7000.00F #-1] | 13390 | 0 | 0 | 0 | 13390
79 | Hydraulic works | 1.6.5 |  |  | 2012-11-21 07:00 | 2012-11-26 17:00 | 4d |  |  | 0 |  |  | 37001
78 | Catch water drains | 1.6.5.1 | 75FS | FS48 | 2012-11-21 07:00 | 2012-11-21 17:00 | 1d | Labourers[4.00 #10];Truck IVECO Trakker[2.00 #6];Crawler Excavator;Crane;Materials[20000.00F #-1] | 25247 | 0 | 0 | 0 | 25247
77 | Draining trenches | 1.6.5.2 | 75FS | FS48 | 2012-11-23 07:00 | 2012-11-26 17:00 | 2d | Labourers[3.00 #10];Truck IVECO Trakker;Crawler Excavator;Crane;Materials[3600.00F #-1] | 11754 | 0 | 0 | 0 | 11754
50 | Zone E working | 1.7 |  |  | 2012-11-29 07:00 | 2012-12-25 17:00 | 19d |  |  | 0 |  |  | 178512
48 | Demolitions | 1.7.1 | 72FS;77FS;78FS;80FS | FS49 | 2012-11-29 07:00 | 2012-11-29 17:00 | 1d | Labourers[3.00 #10];Truck IVECO Trakker[2.00 #6];Cold Milling Machine | 4950 | 0 | 0 | 0 | 4950
49 | Topsoil removal and clearing subbase | 1.7.2 | 48FS | FS46 | 2012-11-30 07:00 | 2012-12-04 17:00 | 3d | Labourers[3.00 #10];Truck IVECO Trakker;Wheel Loader;Bulldozer D8T | 10395 | 0 | 0 | 0 | 10395
47 | Ground movement | 1.7.3 |  |  | 2012-12-11 07:00 | 2012-12-24 17:00 | 10d |  |  | 0 |  |  | 147920
46 | Embankments | 1.7.3.1 | 49FS | FS44 | 2012-12-11 07:00 | 2012-12-24 17:00 | 10d | Labourers[10.00 #10];Truck IVECO Trakker[6.00 #6];Wheel Loader[2.00 #2];Sheepfoot rolles;Tank Truck;Materials[32000.00F #-1] | 147920 | 0 | 0 | 0 | 147920
45 | Hydraulic works | 1.7.4 |  |  | 2012-12-25 07:00 | 2012-12-25 17:00 | 1d |  |  | 0 |  |  | 15247
44 | Catch water drains | 1.7.4.1 | 46FS | FS58 | 2012-12-25 07:00 | 2012-12-25 17:00 | 1d | Labourers[4.00 #10];Truck IVECO Trakker[2.00 #6];Crawler Excavator;Crane;Materials[10000.00F #-1] | 15247 | 0 | 0 | 0 | 15247
60 | Zone C working | 1.8 |  |  | 2012-12-26 07:00 | 2013-02-14 17:00 | 37d |  |  | 0 |  |  | 261942
58 | Demolitions | 1.8.1 | 36FS;44FS | FS59 | 2012-12-26 07:00 | 2012-12-26 17:00 | 1d | Labourers[3.00 #10];Truck IVECO Trakker[2.00 #6];Cold Milling Machine | 4950 | 0 | 0 | 0 | 4950
59 | Topsoil removal and clearing subbase | 1.8.2 | 58FS | FS52 | 2012-12-27 07:00 | 2013-01-08 17:00 | 9d | Labourers[4.00 #10];Bulldozer D8T;Truck IVECO Trakker[2.00 #6];Wheel Loader | 41715 | 0 | 0 | 0 | 41715
54 | Ground movement | 1.8.3 |  |  | 2013-01-09 07:00 | 2013-01-28 17:00 | 14d |  |  | 0 |  |  | 116916
53 | Hillside (mezzacosta) works | 1.8.3.1 |  |  | 2013-01-09 07:00 | 2013-01-28 17:00 | 14d |  |  | 0 |  |  | 116916
52 | Terracing | 1.8.3.1.1 | 59FS | FS51 | 2013-01-09 07:00 | 2013-01-16 17:00 | 6d | Labourers[3.00 #10];Crawler Excavator;Sheepfoot rolles;Tank Truck;Materials[15000.00F #-1] | 38004 | 0 | 0 | 0 | 38004
51 | Carrying remaining soil | 1.8.3.1.2 | 52FS | FS55 | 2013-01-17 07:00 | 2013-01-28 17:00 | 8d | Labourers[8.00 #10];Truck IVECO Trakker[6.00 #6];Crawler Excavator[2.00 #2] | 78912 | 0 | 0 | 0 | 78912
57 | Hydraulic works | 1.8.4 |  |  | 2013-01-29 07:00 | 2013-02-14 17:00 | 13d |  |  | 0 |  |  | 98361
55 | Draining trenches | 1.8.4.1 | 51FS | FS56 | 2013-01-29 07:00 | 2013-02-04 17:00 | 5d | Labourers[3.00 #10];Crawler Excavator;Truck IVECO Trakker;Crane;Materials[26000.00F #-1] | 46385 | 0 | 0 | 0 | 46385
56 | Catch water drains | 1.8.4.2 | 55FS | FS85 | 2013-02-05 07:00 | 2013-02-14 17:00 | 8d | Labourers[4.00 #10];Truck IVECO Trakker[2.00 #6];Crawler Excavator;Crane;Materials[10000.00F #-1] | 51976 | 0 | 0 | 0 | 51976
85 | Paving | 1.9 | 56FS;36FS | FS86;FS87;FS89 | 2013-02-15 07:00 | 2013-03-28 17:00 | 30d | Labourers[7.00 #10];Truck IVECO Trakker[5.00 #6];Paler;Smooth Roller;Paving Material[2500000.00F #-1] | 2741650 | 0 | 0 | 0 | 2741650
90 | Completation works | 1.10 |  |  | 2013-03-29 07:00 | 2013-05-06 17:00 | 27d |  |  | 0 |  |  | 560054
86 | Guardrails pouring | 1.10.1 | 85FS | FS91;FS92 | 2013-03-29 07:00 | 2013-05-06 17:00 | 27d | Labourers[4.00 #10];Truck IVECO Trakker;Pile Driver;Materials[300000.00F #-1] | 386994 | 0 | 0 | 0 | 386994
87 | Coverage and shaping slopes | 1.10.2 | 85FS | FS88 | 2013-03-29 07:00 | 2013-04-10 17:00 | 9d | Labourers[5.00 #10];Truck IVECO Trakker[2.00 #6];Wheel Loader[2.00 #2];Pruning Machine;Materials[15000.00F #-1] | 63600 | 0 | 0 | 0 | 63600
88 | Cascades pouring | 1.10.3 | 87FS | FS91;FS92 | 2013-04-11 07:00 | 2013-04-16 17:00 | 4d | Labourers[3.00 #10];Truck IVECO Trakker;Materials[16500.00F #-1] | 25500 | 0 | 0 | 0 | 25500
89 | Road signals pouring | 1.10.4 | 85FS | FS91;FS92 | 2013-04-11 07:00 | 2013-04-12 17:00 | 2d | Labourers[2.00 #10];Truck IVECO Trakker;Line Striper Machine;Materials[80000.00F #-1] | 83960 | 0 | 0 | 0 | 83960
95 | Fixed yard removal | 1.11 |  |  | 2013-05-07 07:00 | 2013-05-14 17:00 | 6d |  |  | 0 |  |  | 15075
91 | Network connections removal | 1.11.1 | 86FS;88FS;89FS |  | 2013-05-07 07:00 | 2013-05-07 17:00 | 1d | Labourers[2.00 #10];Truck IVECO Trakker | 1710 | 0 | 0 | 0 | 1710
92 | Containers removal | 1.11.2 | 86FS;88FS;89FS | FS93 | 2013-05-07 07:00 | 2013-05-07 17:00 | 1d | Labourers[2.00 #10];Truck IVECO Trakker;Crane | 2655 | 0 | 0 | 0 | 2655
93 | Rubbles removal | 1.11.3 | 92FS | FS94 | 2013-05-08 07:00 | 2013-05-13 17:00 | 4d | Labourers[2.00 #10];Truck IVECO Trakker;Wheel Loader | 9000 | 0 | 0 | 0 | 9000
94 | Fences removal | 1.11.4 | 93FS |  | 2013-05-14 07:00 | 2013-05-14 17:00 | 1d | Labourers[2.00 #10];Truck IVECO Trakker | 1710 | 0 | 0 | 0 | 1710

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Labourers | Renewable | 10 men | 0 | 60 | 1[2.00 Labourers];2[4.00 Labourers];3[3.00 Labourers];4[2.00 Labourers];5[3.00 Labourers];6[2.00 Labourers];7[7.00 Labourers];8[4.00 Labourers];9[3.00 Labourers];14[3.00 Labourers];11[4.00 Labourers];19[10.00 Labourers];20[4.00 Labourers];17[9.00 Labourers];22[4.00 Labourers];24[4.00 Labourers];25[6.00 Labourers];27[4.00 Labourers];29[4.00 Labourers];31[4.00 Labourers];33[4.00 Labourers];34[5.00 Labourers];36[5.00 Labourers];41[3.00 Labourers];42[3.00 Labourers];38[10.00 Labourers];39[4.00 Labourers];63[2.00 Labourers];62[4.00 Labourers];66[5.00 Labourers];68[4.00 Labourers];69[5.00 Labourers];82[3.00 Labourers];83[4.00 Labourers];75[10.00 Labourers];73[3.00 Labourers];72[10.00 Labourers];80[3.00 Labourers];78[4.00 Labourers];77[3.00 Labourers];48[3.00 Labourers];49[3.00 Labourers];46[10.00 Labourers];44[4.00 Labourers];58[3.00 Labourers];59[4.00 Labourers];52[3.00 Labourers];51[8.00 Labourers];55[3.00 Labourers];56[4.00 Labourers];85[7.00 Labourers];86[4.00 Labourers];87[5.00 Labourers];88[3.00 Labourers];89[2.00 Labourers];91[2.00 Labourers];92[2.00 Labourers];93[2.00 Labourers];94[2.00 Labourers]; | 1014120
2 | Truck IVECO Trakker | Renewable | 6 mach | 0 | 70 | 1;2[3.00 Truck IVECO Trakker];3;4;5;6;7[5.00 Truck IVECO Trakker];8[2.00 Truck IVECO Trakker];9;14;11;19[6.00 Truck IVECO Trakker];20;17[6.00 Truck IVECO Trakker];22;24[3.00 Truck IVECO Trakker];25;27;29;31;33;34;36[3.00 Truck IVECO Trakker];41[2.00 Truck IVECO Trakker];42;38[6.00 Truck IVECO Trakker];39;63;62[2.00 Truck IVECO Trakker];66;68;69;82[2.00 Truck IVECO Trakker];83[2.00 Truck IVECO Trakker];75[6.00 Truck IVECO Trakker];72[6.00 Truck IVECO Trakker];80;78[2.00 Truck IVECO Trakker];77;48[2.00 Truck IVECO Trakker];49;46[6.00 Truck IVECO Trakker];44[2.00 Truck IVECO Trakker];58[2.00 Truck IVECO Trakker];59[2.00 Truck IVECO Trakker];51[6.00 Truck IVECO Trakker];55;56[2.00 Truck IVECO Trakker];85[5.00 Truck IVECO Trakker];86;87[2.00 Truck IVECO Trakker];88;89;91;92;93;94; | 650790
3 | Bulldozer D8T | Renewable | 1 mach | 0 | 75 | 3;9;42;83;49;59; | 22950
4 | Wheel Loader | Renewable | 2 mach | 0 | 60 | 2;3;7[2.00 Wheel Loader];9;19[2.00 Wheel Loader];25;36;42;38[2.00 Wheel Loader];83;75[2.00 Wheel Loader];72[2.00 Wheel Loader];49;46[2.00 Wheel Loader];59;87[2.00 Wheel Loader];93; | 140400
5 | Sheepfoot rolles | Renewable | 2 mach | 0 | 70 | 7;19;17;36;38;75;73;72;46;52; | 75600
6 | Smooth Roller | Renewable | 2 mach | 0 | 60 | 85; | 16200
7 | Crawler Excavator | Renewable | 2 mach | 0 | 98 | 8;17[2.00 Crawler Excavator];22;24;62;73;78;77;44;52;51[2.00 Crawler Excavator];55;56; | 58212
8 | Drilling Rid | Renewable | 1 mach | 0 | 75 | 25; | 2700
9 | Concrete Mixer Truck | Renewable | 1 mach | 0 | 95 | 7;11;19;25;27;29;31;34;38;66; | 43605
10 | Crane | Renewable | 1 mach | 0 | 105 | 4;14;11;20;22;25;27;29;31;33;34;39;63;62;66;68;69;80;78;77;44;55;56;92; | 46305
11 | Paler | Renewable | 1 mach | 0 | 65 | 8;85; | 18135
12 | Cold Milling Machine | Renewable | 1 mach | 0 | 230 | 41;82;48;58; | 8280
13 | Pile Driver | Renewable | 1 mach | 0 | 48 | 86; | 11664
14 | Pruning Machine | Renewable | 1 mach | 0 | 40 | 87; | 3240
15 | Tank Truck | Renewable | 1 mach | 0 | 78 | 75;73;72;46;52; | 42120
16 | Line Striper Machine | Renewable | 1 mach | 0 | 30 | 89; | 540
17 | Materials | Consumable | -1 € | 0 | 1 | 1[10000.00F Materials];6[30000.00F Materials];7[50000.00F Materials];14[3000.00F Materials];11[3000.00F Materials];19[55000.00F Materials];20[23000.00F Materials];22[1500.00F Materials];24[0.00F Materials];25[190000.00F Materials];27[100000.00F Materials];29[11000.00F Materials];31[81000.00F Materials];33[52000.00F Materials];34[23500.00F Materials];36[18000.00F Materials];38[68600.00F Materials];39[12600.00F Materials];63[6000.00F Materials];62[15000.00F Materials];66[88000.00F Materials];68[50000.00F Materials];69[8000.00F Materials];75[140000.00F Materials];73[1800.00F Materials];80[7000.00F Materials];78[20000.00F Materials];77[3600.00F Materials];46[32000.00F Materials];44[10000.00F Materials];52[15000.00F Materials];55[26000.00F Materials];56[10000.00F Materials];86[300000.00F Materials];87[15000.00F Materials];88[16500.00F Materials];89[80000.00F Materials]; | 1576100
18 | Paving Material | Consumable | -1 € | 0 | 1 | 85[2500000.00F Paving Material]; | 2500000

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | Asti-Cuneo Highway | 2556h
10 | Installation of fixed yard | 108h
1 | Pegging and fence | 9h | standard - symmetric | 80 | 100 | 120
2 | Clearing site | 18h | standard - symmetric | 80 | 100 | 120
3 | Levelling ground | 9h | standard - symmetric | 80 | 100 | 120
4 | Containers placement | 9h | standard - symmetric | 80 | 100 | 120
5 | Connection to network service | 18h | standard - symmetric | 80 | 100 | 120
6 | Pegging road | 9h | standard - symmetric | 80 | 100 | 120
7 | Alternative road system | 36h | standard - symmetric | 80 | 100 | 120
16 | Zone B working | 342h
8 | Demolition | 9h | standard - symmetric | 80 | 100 | 120
9 | Clearing subbase and topsoil removal | 36h | standard - symmetric | 80 | 100 | 120
15 | Minor works | 189h
14 | Manhole covers | 9h | standard - symmetric | 80 | 100 | 120
13 | Culverts box | 99h
11 | Placement formworks and concrete casting | 9h | standard - symmetric | 80 | 100 | 120
12 | Culverts concrete aging | 90h | standard - symmetric | 80 | 100 | 120
97 | Ground movement | 252h
19 | Road embankments | 153h | standard - symmetric | 80 | 100 | 120
20 | Sound barriers | 18h | standard - symmetric | 80 | 100 | 120
18 | Trench | 72h
17 | Digging | 72h | standard - symmetric | 80 | 100 | 120
23 | Hydraulic works | 45h
22 | Longitudinal drains (ditches) | 45h | standard - symmetric | 80 | 100 | 120
37 | Overpass construction | 1107h
24 | Plinths excavation | 9h | standard - symmetric | 80 | 100 | 120
25 | Pouring piles frameworks and drilling | 36h | standard - symmetric | 80 | 100 | 120
26 | Piles concrete aging | 90h | standard - symmetric | 80 | 100 | 120
27 | Making of plinths (pouring frameworks and concrete casting) | 18h | standard - symmetric | 80 | 100 | 120
28 | Plinths concrete aging | 90h | standard - symmetric | 80 | 100 | 120
29 | Making of pylons (pouring frameworks and concrete casting) | 9h | standard - symmetric | 80 | 100 | 120
30 | Pylons concrete aging | 90h | standard - symmetric | 80 | 100 | 120
31 | Making of shoulders (pouring frameworks and concrete casting) | 9h | standard - symmetric | 80 | 100 | 120
32 | Shoulders concrete aging | 90h | standard - symmetric | 80 | 100 | 120
33 | Pouring prefabricated beam | 9h | standard - symmetric | 80 | 100 | 120
34 | Making of slab (pouring frameworks and concrete casting) | 9h | standard - symmetric | 80 | 100 | 120
35 | Slab's concrete aging | 90h | standard - symmetric | 80 | 100 | 120
36 | Making of embankments | 108h | standard - symmetric | 80 | 100 | 120
96 | Zone A working | 270h
41 | Demolitions | 9h | standard - symmetric | 80 | 100 | 120
42 | Topsoil removal and clearing subbase | 45h | standard - symmetric | 80 | 100 | 120
40 | Ground movement | 189h
38 | Embankments | 171h | standard - symmetric | 80 | 100 | 120
39 | Sound barriers | 18h | standard - symmetric | 80 | 100 | 120
65 | Minor works | 9h
63 | Manhole covers | 9h | standard - symmetric | 80 | 100 | 120
64 | Hydraulic works | 27h
62 | Catch water drains | 27h | standard - symmetric | 80 | 100 | 120
71 | Subway construction | 207h
66 | Retaining walls (frameworks and concrete casting) | 9h | standard - symmetric | 80 | 100 | 120
67 | Retaining walls concrete aging | 90h | standard - symmetric | 80 | 100 | 120
68 | Pouring prefabricated beams | 9h | standard - symmetric | 80 | 100 | 120
69 | Making of slabs (frameworks pouring and concrete casting) | 9h | standard - symmetric | 80 | 100 | 120
70 | Slabs concrete aging | 90h | standard - symmetric | 80 | 100 | 120
84 | Zone D working | 558h
82 | Demolitions | 9h | standard - symmetric | 80 | 100 | 120
83 | Topsoil removal and subbase clearing | 108h | standard - symmetric | 80 | 100 | 120
76 | Ground movement | 396h
75 | Embankments | 378h | standard - symmetric | 80 | 100 | 120
74 | Hillside (mezzacosta) works | 18h
73 | Terracing | 9h | standard - symmetric | 80 | 100 | 120
72 | Carrying remaining soil | 9h | standard - symmetric | 80 | 100 | 120
81 | Minor works | 18h
80 | Culverts | 18h | standard - symmetric | 80 | 100 | 120
79 | Hydraulic works | 36h
78 | Catch water drains | 9h | standard - symmetric | 80 | 100 | 120
77 | Draining trenches | 18h | standard - symmetric | 80 | 100 | 120
50 | Zone E working | 171h
48 | Demolitions | 9h | standard - symmetric | 80 | 100 | 120
49 | Topsoil removal and clearing subbase | 27h | standard - symmetric | 80 | 100 | 120
47 | Ground movement | 90h
46 | Embankments | 90h | standard - symmetric | 80 | 100 | 120
45 | Hydraulic works | 9h
44 | Catch water drains | 9h | standard - symmetric | 80 | 100 | 120
60 | Zone C working | 333h
58 | Demolitions | 9h | standard - symmetric | 80 | 100 | 120
59 | Topsoil removal and clearing subbase | 81h | standard - symmetric | 80 | 100 | 120
54 | Ground movement | 126h
53 | Hillside (mezzacosta) works | 126h
52 | Terracing | 54h | standard - symmetric | 80 | 100 | 120
51 | Carrying remaining soil | 72h | standard - symmetric | 80 | 100 | 120
57 | Hydraulic works | 117h
55 | Draining trenches | 45h | standard - symmetric | 80 | 100 | 120
56 | Catch water drains | 72h | standard - symmetric | 80 | 100 | 120
85 | Paving | 270h | standard - symmetric | 80 | 100 | 120
90 | Completation works | 243h
86 | Guardrails pouring | 243h | standard - symmetric | 80 | 100 | 120
87 | Coverage and shaping slopes | 81h | standard - symmetric | 80 | 100 | 120
88 | Cascades pouring | 36h | standard - symmetric | 80 | 100 | 120
89 | Road signals pouring | 18h | standard - symmetric | 80 | 100 | 120
95 | Fixed yard removal | 54h
91 | Network connections removal | 9h | standard - symmetric | 80 | 100 | 120
92 | Containers removal | 9h | standard - symmetric | 80 | 100 | 120
93 | Rubbles removal | 36h | standard - symmetric | 80 | 100 | 120
94 | Fences removal | 9h | standard - symmetric | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | Yes
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t))