## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | Tappan Zee Bridge | 1 |  |  | 2013-01-01 07:00 | 2017-12-08 18:00 | 1289d |  |  | 4260000000 |  |  | 4999958000
1 | Preparation, Mobilization, Temporary Roadworks | 1.1 |  | FS2;FS3 | 2013-01-01 07:00 | 2013-06-24 18:00 | 125d | Compressors[4.00 #20];Generators[16.00 #25] | 27800000 | 500000000 | 0 | 0 | 527800000
2 | Consruction of Support Facilities | 1.2 | 1FS | FS4;FS9 | 2013-06-25 07:00 | 2013-10-07 18:00 | 75d | Generators[5.00 #25];Dump Scows | 5482500 | 100000000 | 0 | 0 | 105482500
3 | Construction of Temporary Trestle Platforms | 1.3 | 1FS | FS4;FS9 | 2013-06-25 07:00 | 2013-09-16 18:00 | 60d | Barge Mounted 100 ton Crane[2.00 #8];Compressors[10.00 #20];Generators[15.00 #25];Rock Socket Drilling Rig[2.00 #4];Tug Boats[2.00 #18];Hopper Scows[12.00 #40];Dump Scows;Concrete Pumping Barges[4.00 #6] | 58506000 | 100000000 | 0 | 0 | 158506000
4 | Dredging I | 1.4 | 2FS;3FS | FS5 | 2014-08-04 07:00 | 2014-10-17 18:00 | 55d | Tug Boats[4.00 #18];Dredges[2.00 #2];Dump Scows[4.00 #6] | 14822500 | 20000000 | 0 | 0 | 34822500
5 | Dredging II | 1.5 | 4FS | FS6;FS7 | 2015-08-03 07:00 | 2015-10-16 18:00 | 55d | Tug Boats[4.00 #18];Dredges[2.00 #2];Dump Scows[4.00 #6] | 14822500 | 20000000 | 0 | 0 | 34822500
6 | Dredging III | 1.6 | 5FS | FS14;FS17;FS19 | 2016-08-01 07:00 | 2016-10-14 18:00 | 55d | Tug Boats[4.00 #18];Dredges[2.00 #2];Dump Scows[4.00 #6] | 14822500 | 20000000 | 0 | 0 | 34822500
7 | Pile Driving for Main | 1.7 | 5FS | FS8 | 2015-10-19 07:00 | 2015-12-11 18:00 | 40d | Tug Boats[8.00 #18];Hopper Scows[12.00 #40];Pile Delivery Barges[6.00 #8] | 27104000 | 100000000 | 0 | 0 | 127104000
8 | Building Main Span | 1.8 | 7FS | FS14;FS17 | 2015-12-14 07:00 | 2016-06-03 18:00 | 125d | Barge Mounted 500 ton Crane;Barge Mounted 100 ton Crane[3.00 #8];Pile Vibratory Hammer[4.00 #4];Generators[10.00 #25];Tug Boats[2.00 #18];Hopper Scows[20.00 #40];Jacking T Cranes (pylons)[2.00 #10];Temporary Cable Stayed Pylon[6.00 #8] | 142812500 | 800000000 | 0 | 0 | 942812500
9 | Preparation for Approach Building South | 1.9 | 2FS;3FS | FS10;FS12 | 2013-10-08 07:00 | 2013-12-02 18:00 | 40d | Sheetpile Vibratory Hammer[2.00 #3];Compressors[15.00 #20];Generators[15.00 #25];Water Pumps[20.00 #25];Rock Socket Drilling Rig[2.00 #4];Tug Boats[4.00 #18];Hopper Scows[8.00 #40];Dump Scows;Concrete Pumping Barges[5.00 #6] | 52368000 | 100000000 | 0 | 0 | 152368000
10 | Preparation for Approach Building North | 1.10 | 9FS | FS11 | 2013-12-03 07:00 | 2014-01-27 18:00 | 40d | Sheetpile Vibratory Hammer[2.00 #3];Compressors[15.00 #20];Generators[15.00 #25];Water Pumps[20.00 #25];Rock Socket Drilling Rig[2.00 #4];Tug Boats[4.00 #18];Hopper Scows[8.00 #40];Dump Scows;Concrete Pumping Barges[5.00 #6] | 52368000 | 100000000 | 0 | 0 | 152368000
11 | Approach Building North | 1.11 | 10FS;12FS | FS13 | 2014-02-25 07:00 | 2014-05-19 18:00 | 60d | Barge Mounted 100 ton Crane[2.00 #8];Pile Vibratory Hammer[2.00 #4];Generators[10.00 #25];Water Pumps[5.00 #25];Tug Boats[4.00 #18];Hopper Scows[12.00 #40];Dump Scows;Pile Delivery Barges[2.00 #8];Truss Delivery Barges[2.00 #2];Truss Lifting Winches;Jacking T Cranes (pylons);Temporary Cable Stayed Pylon[2.00 #8] | 58731000 | 300000000 | 0 | 0 | 358731000
12 | Approach Building South | 1.12 | 9FS | FS11;FS16 | 2013-12-03 07:00 | 2014-02-24 18:00 | 60d | Barge Mounted 100 ton Crane[2.00 #8];Pile Vibratory Hammer[2.00 #4];Generators[10.00 #25];Water Pumps[5.00 #25];Tug Boats[4.00 #18];Hopper Scows[12.00 #40];Dump Scows;Pile Delivery Barges[2.00 #8];Truss Delivery Barges[2.00 #2];Truss Lifting Winches;Jacking T Cranes (pylons);Temporary Cable Stayed Pylon[2.00 #8] | 58731000 | 300000000 | 0 | 0 | 358731000
13 | Construction of Temporary Finger Piers North | 1.13 | 11FS | FS14 | 2014-05-20 07:00 | 2014-09-01 18:00 | 75d | Sheetpile Vibratory Hammer;Barge Mounted 100 ton Crane;Compressors[15.00 #20];Generators[15.00 #25];Water Pumps[15.00 #25];Tug Boats[2.00 #18];Hopper Scows[10.00 #40];Dump Scows[2.00 #6];Concrete Pumping Barges[2.00 #6] | 82950000 | 100000000 | 0 | 0 | 182950000
14 | Staged Demolition of Parts North | 1.14 | 6FS;8FS;13FS | FS15;FS17 | 2016-10-17 07:00 | 2016-12-23 18:00 | 50d | Compressors[5.00 #20];Generators[10.00 #25];Dump Scows[2.00 #6] | 11210000 | 200000000 | 0 | 0 | 211210000
15 | Construction of Abutment North | 1.15 | 14FS | FS18;FS19 | 2016-12-26 07:00 | 2017-05-12 18:00 | 100d | Generators[5.00 #25];Water Pumps[5.00 #25] | 12500000 | 100000000 | 0 | 0 | 112500000
16 | Construction of Temporary Finger Piers South | 1.16 | 12FS | FS17 | 2014-09-02 07:00 | 2014-12-15 18:00 | 75d | Sheetpile Vibratory Hammer;Barge Mounted 100 ton Crane;Compressors[15.00 #20];Generators[15.00 #25];Water Pumps[15.00 #25];Tug Boats[2.00 #18];Hopper Scows[10.00 #40];Dump Scows;Concrete Pumping Barges[2.00 #6] | 81217500 | 100000000 | 0 | 0 | 181217500
17 | Staged Demoltion of Parts South | 1.17 | 6FS;8FS;16FS;14FS | FS18 | 2016-12-26 07:00 | 2017-03-03 18:00 | 50d | Compressors[5.00 #20];Generators[10.00 #25];Dump Scows[2.00 #6] | 11210000 | 200000000 | 0 | 0 | 211210000
18 | Construction of Abutment South | 1.18 | 15FS;17FS | FS19 | 2017-05-15 07:00 | 2017-09-29 18:00 | 100d | Generators[5.00 #25];Water Pumps[5.00 #25] | 12500000 | 100000000 | 0 | 0 | 112500000
19 | Demolition of Excisting TBZ Bridge | 1.19 | 6FS;15FS;18FS |  | 2017-10-02 07:00 | 2017-12-08 18:00 | 50d |  | 0 | 1000000000 | 0 | 0 | 1000000000

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Sheetpile Vibratory Hammer | Renewable | 3 | 0 | 2000 | 9[2.00 Sheetpile Vibratory Hammer];10[2.00 Sheetpile Vibratory Hammer];13;16; | 6200000
2 | Barge Mounted 500 ton Crane | Renewable | 1 | 0 | 3500 | 8; | 4375000
3 | Barge Mounted 100 ton Crane | Renewable | 8 | 0 | 1500 | 3[2.00 Barge Mounted 100 ton Crane];8[3.00 Barge Mounted 100 ton Crane];11[2.00 Barge Mounted 100 ton Crane];12[2.00 Barge Mounted 100 ton Crane];13;16; | 13275000
4 | Pile Vibratory Hammer | Renewable | 4 | 0 | 2695 | 8[4.00 Pile Vibratory Hammer];11[2.00 Pile Vibratory Hammer];12[2.00 Pile Vibratory Hammer]; | 19943000
5 | Compressors | Renewable | 20 | 0 | 1560 | 1[4.00 Compressors];3[10.00 Compressors];9[15.00 Compressors];10[15.00 Compressors];13[15.00 Compressors];14[5.00 Compressors];16[15.00 Compressors];17[5.00 Compressors]; | 78780000
6 | Generators | Renewable | 25 | 0 | 1000 | 1[16.00 Generators];2[5.00 Generators];3[15.00 Generators];8[10.00 Generators];9[15.00 Generators];10[15.00 Generators];11[10.00 Generators];12[10.00 Generators];13[15.00 Generators];14[10.00 Generators];15[5.00 Generators];16[15.00 Generators];17[10.00 Generators];18[5.00 Generators]; | 111750000
7 | Water Pumps | Renewable | 25 | 0 | 1500 | 9[20.00 Water Pumps];10[20.00 Water Pumps];11[5.00 Water Pumps];12[5.00 Water Pumps];13[15.00 Water Pumps];15[5.00 Water Pumps];16[15.00 Water Pumps];18[5.00 Water Pumps]; | 81750000
8 | Rock Socket Drilling Rig | Renewable | 4 | 0 | 3080 | 3[2.00 Rock Socket Drilling Rig];9[2.00 Rock Socket Drilling Rig];10[2.00 Rock Socket Drilling Rig]; | 8624000
9 | Tug Boats | Renewable | 18 | 0 | 1540 | 3[2.00 Tug Boats];4[4.00 Tug Boats];5[4.00 Tug Boats];6[4.00 Tug Boats];7[8.00 Tug Boats];8[2.00 Tug Boats];9[4.00 Tug Boats];10[4.00 Tug Boats];11[4.00 Tug Boats];12[4.00 Tug Boats];13[2.00 Tug Boats];16[2.00 Tug Boats]; | 37730000
10 | Dredges | Renewable | 2 | 0 | 5775 | 4[2.00 Dredges];5[2.00 Dredges];6[2.00 Dredges]; | 19057500
11 | Hopper Scows | Renewable | 40 | 0 | 3080 | 3[12.00 Hopper Scows];7[12.00 Hopper Scows];8[20.00 Hopper Scows];9[8.00 Hopper Scows];10[8.00 Hopper Scows];11[12.00 Hopper Scows];12[12.00 Hopper Scows];13[10.00 Hopper Scows];16[10.00 Hopper Scows]; | 224224000
12 | Dump Scows | Renewable | 6 | 0 | 2310 | 2;3;4[4.00 Dump Scows];5[4.00 Dump Scows];6[4.00 Dump Scows];9;10;11;12;13[2.00 Dump Scows];14[2.00 Dump Scows];16;17[2.00 Dump Scows]; | 32802000
13 | Flat Deck Barges | Renewable | 20 | 0 | 0 |  | 0
14 | Concrete Delivery Barges | Renewable | 20 | 0 | 3080 |  | 0
15 | Concrete Pumping Barges | Renewable | 6 | 0 | 3850 | 3[4.00 Concrete Pumping Barges];9[5.00 Concrete Pumping Barges];10[5.00 Concrete Pumping Barges];13[2.00 Concrete Pumping Barges];16[2.00 Concrete Pumping Barges]; | 36190000
16 | Pile Delivery Barges | Renewable | 8 | 0 | 3080 | 7[6.00 Pile Delivery Barges];11[2.00 Pile Delivery Barges];12[2.00 Pile Delivery Barges]; | 14784000
17 | Truss Delivery Barges | Renewable | 2 | 0 | 4620 | 11[2.00 Truss Delivery Barges];12[2.00 Truss Delivery Barges]; | 11088000
18 | Truss Lifting Winches | Renewable | 3 | 0 | 2695 | 11;12; | 3234000
19 | Jacking T Cranes (pylons) | Renewable | 10 | 0 | 4620 | 8[2.00 Jacking T Cranes (pylons)];11;12; | 17094000
20 | Temporary Cable Stayed Pylon | Renewable | 8 | 0 | 1925 | 8[6.00 Temporary Cable Stayed Pylon];11[2.00 Temporary Cable Stayed Pylon];12[2.00 Temporary Cable Stayed Pylon]; | 19057500

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | Tappan Zee Bridge | 12890h
1 | Preparation, Mobilization, Temporary Roadworks | 1250h | standard - symmetric | 80 | 100 | 120
2 | Consruction of Support Facilities | 750h | standard - symmetric | 80 | 100 | 120
3 | Construction of Temporary Trestle Platforms | 600h | standard - symmetric | 80 | 100 | 120
4 | Dredging I | 550h | standard - symmetric | 80 | 100 | 120
5 | Dredging II | 550h | standard - symmetric | 80 | 100 | 120
6 | Dredging III | 550h | standard - symmetric | 80 | 100 | 120
7 | Pile Driving for Main | 400h | standard - symmetric | 80 | 100 | 120
8 | Building Main Span | 1250h | standard - symmetric | 80 | 100 | 120
9 | Preparation for Approach Building South | 400h | standard - symmetric | 80 | 100 | 120
10 | Preparation for Approach Building North | 400h | standard - symmetric | 80 | 100 | 120
11 | Approach Building North | 600h | standard - symmetric | 80 | 100 | 120
12 | Approach Building South | 600h | standard - symmetric | 80 | 100 | 120
13 | Construction of Temporary Finger Piers North | 750h | standard - symmetric | 80 | 100 | 120
14 | Staged Demolition of Parts North | 500h | standard - symmetric | 80 | 100 | 120
15 | Construction of Abutment North | 1000h | standard - symmetric | 80 | 100 | 120
16 | Construction of Temporary Finger Piers South | 750h | standard - symmetric | 80 | 100 | 120
17 | Staged Demoltion of Parts South | 500h | standard - symmetric | 80 | 100 | 120
18 | Construction of Abutment South | 1000h | standard - symmetric | 80 | 100 | 120
19 | Demolition of Excisting TBZ Bridge | 500h | standard - symmetric | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | Yes
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | Yes
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t))