## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | Metal Extraction | 1 |  |  | 2008-02-25 08:00 | 2008-06-25 17:00 | 88d |  |  | 0 |  |  | 0
1 | Foundation UG | 1.1 | 33FS | FS3 | 2008-04-23 08:00 | 2008-04-29 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0
2 | Additional part foundation for aspiration filters | 1.2 | 85FS | FS4 | 2008-03-17 08:00 | 2008-03-20 17:00 | 4d |  | 0 | 0 | 0 | 0 | 0
3 | Drying foundation UG | 1.3 | 1FS | FS54 | 2008-04-30 08:00 | 2008-05-05 17:00 | 4d |  | 0 | 0 | 0 | 0 | 0
4 | Drying foundation for aspiration filters | 1.4 | 2FS | FS6;FS78;FS79 | 2008-03-21 08:00 | 2008-03-26 17:00 | 4d |  | 0 | 0 | 0 | 0 | 0
5 | Wall whole for conveyor 1.060 | 1.5 | 85FS | FS36;FS38 | 2008-03-27 08:00 | 2008-03-27 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0
6 | Wall wholes for explosion-flapps filters | 1.6 | 4FS | FS80 | 2008-03-27 08:00 | 2008-03-27 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0
7 | Closing wall wholes | 1.7 | 80FS | FS81 | 2008-05-01 08:00 | 2008-05-01 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0
8 | Roof whole for Aspiration 1 | 1.8 | 78FS | FS81 | 2008-04-22 08:00 | 2008-04-22 17:00 | 1d | 4 Telescope lifting platform[0.50 #1] | 0 | 0 | 0 | 0 | 0
9 | Roof whole for Aspiration 2 | 1.9 | 79FS | FS81 | 2008-04-24 08:00 | 2008-04-24 17:00 | 1d | 4 Telescope lifting platform[0.50 #1] | 0 | 0 | 0 | 0 | 0
10 | Closing roof wholes | 1.10 | 81FS | FS83 | 2008-05-12 08:00 | 2008-05-12 17:00 | 1d | 4 Telescope lifting platform | 0 | 0 | 0 | 0 | 0
11 | Electric cable for central cabinet | 1.11 | 85FS | FS82 | 2008-02-29 08:00 | 2008-03-03 17:00 | 2d | Construction[2.00 #8] | 0 | 0 | 0 | 0 | 0
12 | Electric cable for aspiration | 1.12 | 79FS;80FS | FS17 | 2008-05-01 08:00 | 2008-05-02 17:00 | 2d | Construction[2.00 #8] | 0 | 0 | 0 | 0 | 0
13 | Electric cable for windsifter | 1.13 | 49FS;50FS | FS16 | 2008-05-06 08:00 | 2008-05-07 17:00 | 2d | Construction[2.00 #8] | 0 | 0 | 0 | 0 | 0
14 | Electric cable for UC | 1.14 | 22FS;72FS | FS82 | 2008-04-28 08:00 | 2008-04-29 17:00 | 2d | Construction[2.00 #8] | 0 | 0 | 0 | 0 | 0
15 | Electric cable for UG's | 1.15 | 75FS;76FS;77FS | FS82 | 2008-05-29 08:00 | 2008-05-30 17:00 | 2d | Construction[2.00 #8] | 0 | 0 | 0 | 0 | 0
16 | Air pressure for service works | 1.16 | 13FS | FS70 | 2008-05-08 08:00 | 2008-05-12 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0
17 | Air pressure for filter cleaning | 1.17 | 12FS | FS81 | 2008-05-05 08:00 | 2008-05-06 17:00 | 2d |  | 0 | 0 | 0 | 0 | 0
18 | Boxes for particular product | 1.18 | 82FS | FS19 | 2008-06-12 08:00 | 2008-06-12 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0
19 | Drying boxes for particular product | 1.19 | 18FS | FS84 | 2008-06-13 08:00 | 2008-06-18 17:00 | 4d |  | 0 | 0 | 0 | 0 | 0
20 | Tranformer | 1.20 | 86FS | FS21 | 2008-03-06 08:00 | 2008-03-10 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0
21 | Low-Voltage Distribution System (NSHV) | 1.21 | 20FS | FS82 | 2008-03-11 08:00 | 2008-03-13 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0
22 | UC 150, M-875 | 1.22 | 71FS | FS14 | 2008-04-23 08:00 | 2008-04-25 17:00 | 3d | Construction[4.00 #8];1 Manitu 6t;3 Fork lift 6t[0.50 #1];4 Telescope lifting platform[0.25 #1] | 0 | 0 | 0 | 0 | 0
23 | UG 208 MSL, M-766 | 1.23 | 52FS;55FS | FS24 | 2008-05-13 08:00 | 2008-05-14 17:00 | 2d | Construction[4.00 #8];1 Manitu 6t;4 Telescope lifting platform[0.50 #1] | 0 | 0 | 0 | 0 | 0
24 | UG 208 MSL, M-832 | 1.24 | 23FS | FS25 | 2008-05-15 08:00 | 2008-05-20 17:00 | 4d | Construction[4.00 #8];1 Manitu 6t;4 Telescope lifting platform[0.50 #1] | 0 | 0 | 0 | 0 | 0
25 | UG 208 MSL, M-872 | 1.25 | 24FS | FS75;FS76;FS77 | 2008-05-21 08:00 | 2008-05-23 17:00 | 3d | Construction[4.00 #8];1 Manitu 6t;4 Telescope lifting platform[0.50 #1] | 0 | 0 | 0 | 0 | 0
26 | Steel constructions for ascending conveyor UC | 1.26 | 85FS | FS35 | 2008-03-27 08:00 | 2008-03-28 17:00 | 2d | Construction[3.00 #8];1 Manitu 6t[0.50 #2];2 Hand lift truck;3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.25 #1];5 Scherenhubbuhne[0.50 #1] | 0 | 0 | 0 | 0 | 0
27 | Steel constructions for lifting electric overband magnet | 1.27 | 85FS | FS62 | 2008-03-05 08:00 | 2008-03-06 17:00 | 2d | Construction[3.00 #8];1 Manitu 6t[0.50 #2];2 Hand lift truck;3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.25 #1];5 Scherenhubbuhne[0.50 #1] | 0 | 0 | 0 | 0 | 0
28 | Steel constructions for lifting overband magnet | 1.28 |  | FS43;FS44;FS45 | 2008-03-11 08:00 | 2008-03-12 17:00 | 2d | Construction[3.00 #8];1 Manitu 6t[0.50 #2];2 Hand lift truck;3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.25 #1];5 Scherenhubbuhne[0.50 #1] | 0 | 0 | 0 | 0 | 0
29 | Steel constructions for fine screen | 1.29 | 85FS | FS47 | 2008-03-26 08:00 | 2008-03-28 17:00 | 3d | Construction[3.00 #8];1 Manitu 6t[0.50 #2];2 Hand lift truck;3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.25 #1];5 Scherenhubbuhne[0.50 #1] | 0 | 0 | 0 | 0 | 0
30 | Steel constructions for windsifter | 1.30 | 85FS | FS68 | 2008-02-29 08:00 | 2008-03-04 17:00 | 3d | Construction[3.00 #8];1 Manitu 6t[0.50 #2];2 Hand lift truck;3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.25 #1];5 Scherenhubbuhne[0.50 #1] | 0 | 0 | 0 | 0 | 0
31 | Steel constructions for lifting overband magnet | 1.31 | 85FS | FS58;FS65 | 2008-03-20 08:00 | 2008-03-21 17:00 | 2d | Construction[3.00 #8];1 Manitu 6t[0.50 #2];2 Hand lift truck;3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.25 #1];5 Scherenhubbuhne[0.50 #1] | 0 | 0 | 0 | 0 | 0
32 | Steel constructions for eddy current separator | 1.32 | 85FS | FS58;FS66;FS67 | 2008-03-31 08:00 | 2008-04-02 17:00 | 3d | Construction[3.00 #8];1 Manitu 6t[0.50 #2];2 Hand lift truck;3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.25 #1];5 Scherenhubbuhne[0.50 #1] | 0 | 0 | 0 | 0 | 0
33 | Railings around Ugs | 1.33 | 85FS | FS1 | 2008-04-02 08:00 | 2008-04-04 17:00 | 3d | Construction[2.00 #8];4 Telescope lifting platform[0.25 #1] | 0 | 0 | 0 | 0 | 0
34 | Steel construction for output conveyors from Ugs | 1.34 | 85FS | FS55 | 2008-03-17 08:00 | 2008-03-20 17:00 | 4d | Construction[3.00 #8];1 Manitu 6t[0.50 #2];2 Hand lift truck;3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.25 #1];5 Scherenhubbuhne[0.50 #1] | 0 | 0 | 0 | 0 | 0
35 | Ascending conveyor (UC) | 1.35 | 26FS | FS71;FS72 | 2008-03-31 08:00 | 2008-04-01 17:00 | 2d | Construction[2.00 #8];1 Manitu 6t[0.50 #2];3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.25 #1] | 0 | 0 | 0 | 0 | 0
36 | Ascending conveyor for electric overband magnet | 1.36 | 5FS;62FS | FS37 | 2008-05-01 08:00 | 2008-05-02 17:00 | 2d | Construction[2.00 #8];1 Manitu 6t[0.50 #2];3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.50 #1] | 0 | 0 | 0 | 0 | 0
37 | Depletion conveyor for electric overband magnet | 1.37 | 36FS;38FS | FS82 | 2008-05-05 08:00 | 2008-05-05 17:00 | 1d | Construction[2.00 #8];1 Manitu 6t[0.50 #2];3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.50 #1] | 0 | 0 | 0 | 0 | 0
38 | Ascending conveyor for drum screen | 1.38 | 5FS;62FS | FS37 | 2008-04-30 08:00 | 2008-05-01 17:00 | 2d | Construction[3.00 #8];1 Manitu 6t;3 Fork lift 6t[0.50 #1];4 Telescope lifting platform[0.50 #1] | 0 | 0 | 0 | 0 | 0
39 | Drum screen | 1.39 | 40FS | FS41;FS42;FS43 | 2008-03-04 08:00 | 2008-03-06 17:00 | 3d | Construction[3.00 #8];1 Manitu 6t;3 Fork lift 6t[0.50 #1];5 Scherenhubbuhne[0.50 #1] | 0 | 0 | 0 | 0 | 0
40 | Steel construction for drum screen | 1.40 | 85FS | FS39 | 2008-02-29 08:00 | 2008-03-03 17:00 | 2d | Construction[2.00 #8];1 Manitu 6t;2 Hand lift truck;3 Fork lift 6t[0.50 #1];5 Scherenhubbuhne[0.50 #1] | 0 | 0 | 0 | 0 | 0
41 | Depletion conveyor under drum screen | 1.41 | 39FS | FS49 | 2008-03-07 08:00 | 2008-03-10 17:00 | 2d | Construction[2.00 #8];1 Manitu 6t[0.50 #2];3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.50 #1] | 0 | 0 | 0 | 0 | 0
42 | Depletion conveyor under drum screen | 1.42 | 39FS | FS49 | 2008-03-07 08:00 | 2008-03-10 17:00 | 2d | Construction[2.00 #8];1 Manitu 6t[0.50 #2];3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.50 #1] | 0 | 0 | 0 | 0 | 0
43 | Ascending conveyor from drum screen to magnet-fine screen | 1.43 | 39FS;28FS | FS63 | 2008-03-13 08:00 | 2008-03-14 17:00 | 2d | Construction[2.00 #8];1 Manitu 6t[0.50 #2];3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.50 #1] | 0 | 0 | 0 | 0 | 0
44 | Depletion conveyor for overband magnet | 1.44 | 28FS | FS82 | 2008-03-19 08:00 | 2008-03-20 17:00 | 2d | Construction[2.00 #8];1 Manitu 6t[0.50 #2];3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.50 #1] | 0 | 0 | 0 | 0 | 0
45 | Ascending conveyor to fine screen | 1.45 | 28FS;64FS | FS63 | 2008-04-10 08:00 | 2008-04-11 17:00 | 2d | Construction[2.00 #8];1 Manitu 6t[0.50 #2];3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.50 #1] | 0 | 0 | 0 | 0 | 0
46 | Depletion conveyor fraction 10-30 mm | 1.46 | 48FS | FS64 | 2008-04-03 08:00 | 2008-04-04 17:00 | 2d | Construction[2.00 #8];1 Manitu 6t[0.50 #2];3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.25 #1] | 0 | 0 | 0 | 0 | 0
47 | Depletion conveyor fraction 0-10 mm | 1.47 | 29FS | FS48 | 2008-03-31 08:00 | 2008-04-01 17:00 | 2d | Construction[2.00 #8];1 Manitu 6t[0.50 #2];3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.25 #1] | 0 | 0 | 0 | 0 | 0
48 | Depletion conveyor under fine screen towards 10-30 mm | 1.48 | 47FS | FS46 | 2008-04-02 08:00 | 2008-04-02 17:00 | 1d | Construction[2.00 #8];1 Manitu 6t[0.50 #2];3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.25 #1] | 0 | 0 | 0 | 0 | 0
49 | Ascending conveyor towards windsifeter | 1.49 | 41FS;42FS;68FS | FS13 | 2008-03-14 08:00 | 2008-03-18 17:00 | 3d | Construction[3.00 #8];1 Manitu 6t;3 Fork lift 6t[0.50 #1];4 Telescope lifting platform[0.50 #1] | 0 | 0 | 0 | 0 | 0
50 | Depletion conveyor under windsifter - heavy fraction | 1.50 | 51FS | FS13 | 2008-05-02 08:00 | 2008-05-05 17:00 | 2d | Construction[2.00 #8];1 Manitu 6t[0.50 #2];3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.25 #1] | 0 | 0 | 0 | 0 | 0
51 | Ascending conveyor with light fraction under windsifter | 1.51 | 69FS | FS50 | 2008-04-25 08:00 | 2008-04-29 17:00 | 3d | Construction[2.00 #8];1 Manitu 6t[0.50 #2];3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.50 #1] | 0 | 0 | 0 | 0 | 0
52 | Ascending conveyor onto changing (direction) conveyor 1.170 | 1.52 | 53FS | FS23 | 2008-05-08 08:00 | 2008-05-08 17:00 | 1d | Construction[3.00 #8];1 Manitu 6t[0.50 #2];3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.50 #1] | 0 | 0 | 0 | 0 | 0
53 | Changing direction conveyor over UG M-872 | 1.53 | 54FS | FS52 | 2008-05-07 08:00 | 2008-05-07 17:00 | 1d | Construction[2.00 #8];1 Manitu 6t;3 Fork lift 6t[0.50 #1];4 Telescope lifting platform[0.50 #1] | 0 | 0 | 0 | 0 | 0
54 | Changing direction conveyor over UG M-766/M-832 | 1.54 | 3FS | FS53 | 2008-05-06 08:00 | 2008-05-06 17:00 | 1d | Construction[3.00 #8];1 Manitu 6t;3 Fork lift 6t[0.50 #1];4 Telescope lifting platform[0.50 #1] | 0 | 0 | 0 | 0 | 0
55 | Giving through conveyor with cleaner onto conveyor 1.230 | 1.55 | 34FS | FS23 | 2008-04-23 08:00 | 2008-04-25 17:00 | 3d | Construction[2.00 #8];1 Manitu 6t[0.50 #2];3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.25 #1] | 0 | 0 | 0 | 0 | 0
56 | Ascending conveyor towards magnets 1.240 | 1.56 | 65FS | FS82 | 2008-04-04 08:00 | 2008-04-07 17:00 | 2d | Construction[2.00 #8];1 Manitu 6t[0.50 #2];3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.25 #1] | 0 | 0 | 0 | 0 | 0
57 | Depletion conveyor iron | 1.57 | 65FS | FS82 | 2008-03-27 08:00 | 2008-03-28 17:00 | 2d | Construction[2.00 #8];1 Manitu 6t[0.50 #2];3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.25 #1] | 0 | 0 | 0 | 0 | 0
58 | Ascending conveyor towards eddy current separator | 1.58 | 31FS;32FS | FS82 | 2008-04-03 08:00 | 2008-04-07 17:00 | 3d | Construction[2.00 #8];1 Manitu 6t[0.50 #2];3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.25 #1] | 0 | 0 | 0 | 0 | 0
59 | Depletion conveyor non-iron | 1.59 | 66FS;67FS | FS60;FS61 | 2008-04-11 08:00 | 2008-04-14 17:00 | 2d | Construction[2.00 #8];1 Manitu 6t[0.50 #2];3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.25 #1] | 0 | 0 | 0 | 0 | 0
60 | Depletion conveyor SRF | 1.60 | 59FS | FS73;FS74 | 2008-04-15 08:00 | 2008-04-15 17:00 | 1d | Construction[2.00 #8];1 Manitu 6t[0.50 #2];3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.25 #1] | 0 | 0 | 0 | 0 | 0
61 | Depletion conveyor SRF | 1.61 | 59FS | FS73;FS74 | 2008-04-15 08:00 | 2008-04-15 17:00 | 1d | Construction[2.00 #8];1 Manitu 6t[0.50 #2];3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.25 #1] | 0 | 0 | 0 | 0 | 0
62 | Electric overband magnet | 1.62 | 27FS | FS36;FS38 | 2008-03-21 08:00 | 2008-03-25 17:00 | 3d | Construction[3.00 #8];1 Manitu 6t;4 Telescope lifting platform[0.50 #1] | 0 | 0 | 0 | 0 | 0
63 | Overband magnet | 1.63 | 43FS;45FS | FS82 | 2008-04-14 08:00 | 2008-04-16 17:00 | 3d | Construction[3.00 #8];1 Manitu 6t;4 Telescope lifting platform[0.50 #1] | 0 | 0 | 0 | 0 | 0
64 | Trisomat-fine screen | 1.64 | 46FS | FS45 | 2008-04-07 08:00 | 2008-04-09 17:00 | 3d | Construction[3.00 #8];1 Manitu 6t;3 Fork lift 6t[0.50 #1];4 Telescope lifting platform[0.50 #1];5 Scherenhubbuhne[0.50 #1] | 0 | 0 | 0 | 0 | 0
65 | Overband magnet | 1.65 | 31FS | FS56;FS57 | 2008-03-24 08:00 | 2008-03-26 17:00 | 3d | Construction[2.00 #8];1 Manitu 6t;4 Telescope lifting platform[0.50 #1] | 0 | 0 | 0 | 0 | 0
66 | Eddy current separator | 1.66 | 32FS | FS59 | 2008-04-08 08:00 | 2008-04-10 17:00 | 3d | Construction;1 Manitu 6t;4 Telescope lifting platform[0.50 #1] | 0 | 0 | 0 | 0 | 0
67 | Loading viration channel for eddy current | 1.67 | 32FS | FS59 | 2008-04-03 08:00 | 2008-04-03 17:00 | 1d | 1 Manitu 6t[0.50 #2];3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.25 #1] | 0 | 0 | 0 | 0 | 0
68 | Windsifter | 1.68 | 30FS | FS49;FS69 | 2008-03-11 08:00 | 2008-03-13 17:00 | 3d | 1 Manitu 6t;3 Fork lift 6t[0.50 #1];4 Telescope lifting platform[0.50 #1];5 Scherenhubbuhne[0.50 #1] | 0 | 0 | 0 | 0 | 0
69 | Ascending conveyor - windsifter | 1.69 | 68FS | FS51 | 2008-03-17 08:00 | 2008-03-18 17:00 | 2d | 1 Manitu 6t[0.50 #2];3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.25 #1] | 0 | 0 | 0 | 0 | 0
70 | Connection windsifter part | 1.70 | 16FS | FS82 | 2008-05-13 08:00 | 2008-05-14 17:00 | 2d |  | 0 | 0 | 0 | 0 | 0
71 | Steel construction for UC | 1.71 | 35FS | FS22 | 2008-04-17 08:00 | 2008-04-18 17:00 | 2d | 1 Manitu 6t;2 Hand lift truck;3 Fork lift 6t[0.50 #1];4 Telescope lifting platform[0.25 #1];5 Scherenhubbuhne[0.50 #1] | 0 | 0 | 0 | 0 | 0
72 | Hopper for UC | 1.72 | 35FS | FS14 | 2008-04-02 08:00 | 2008-04-02 17:00 | 1d | 1 Manitu 6t[0.50 #2] | 0 | 0 | 0 | 0 | 0
73 | FE-chutes | 1.73 | 60FS;61FS | FS82 | 2008-04-16 08:00 | 2008-04-16 17:00 | 1d | 1 Manitu 6t[0.50 #2];3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.25 #1] | 0 | 0 | 0 | 0 | 0
74 | NE-chutes | 1.74 | 60FS;61FS | FS82 | 2008-04-16 08:00 | 2008-04-16 17:00 | 1d | 1 Manitu 6t[0.50 #2];3 Fork lift 6t[0.25 #1];4 Telescope lifting platform[0.25 #1] | 0 | 0 | 0 | 0 | 0
75 | Connection UG 2008 MSL M= 872 | 1.75 | 25FS | FS15 | 2008-05-26 08:00 | 2008-05-28 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0
76 | a | 1.76 | 25FS | FS15 | 2008-05-26 08:00 | 2008-05-28 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0
77 | Connection UG 2008 MSL M= 766 | 1.77 | 25FS | FS15 | 2008-05-26 08:00 | 2008-05-28 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0
78 | Aspiration UG | 1.78 | 4FS | FS8 | 2008-04-17 08:00 | 2008-04-21 17:00 | 3d | 4 Telescope lifting platform[0.50 #1];5 Scherenhubbuhne[0.50 #1] | 0 | 0 | 0 | 0 | 0
79 | Aspiration rest | 1.79 | 4FS | FS9;FS12 | 2008-04-21 08:00 | 2008-04-23 17:00 | 3d | 4 Telescope lifting platform[0.50 #1];5 Scherenhubbuhne[0.50 #1] | 0 | 0 | 0 | 0 | 0
80 | Filter ECO-VAR | 1.80 | 6FS | FS7;FS12 | 2008-04-28 08:00 | 2008-04-30 17:00 | 3d | 4 Telescope lifting platform[0.50 #1];5 Scherenhubbuhne[0.50 #1] | 0 | 0 | 0 | 0 | 0
81 | Connection aspiration system | 1.81 | 17FS;8FS;9FS;7FS | FS10 | 2008-05-07 08:00 | 2008-05-09 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0
82 | Electrical installation | 1.82 | 14FS;15FS;37FS;44FS;56FS;57FS;58FS;63FS;70FS;73FS;74FS;11FS;21FS | FS18;FS83 | 2008-06-02 08:00 | 2008-06-06 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0
83 | Test installation cold | 1.83 | 82FS;10FS | FS84 | 2008-06-12 08:00 | 2008-06-18 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0
84 | Test installation with material | 1.84 | 83FS;19FS |  | 2008-06-19 08:00 | 2008-06-25 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0
85 | Installation of central cabinet | 1.85 |  | FS26;FS27;FS5;FS2;FS86;FS29;FS40;FS30;FS34;FS33;FS31;FS32;FS11 | 2008-02-25 08:00 | 2008-02-28 17:00 | 4d |  | 0 | 0 | 0 | 0 | 0
86 | Electrical cables for Trafo and NSHV from power grid | 1.86 | 85FS | FS20 | 2008-02-29 08:00 | 2008-03-05 17:00 | 4d |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Construction | Renewable | 8 | 0 | 0 | 11[2.00 Construction];12[2.00 Construction];13[2.00 Construction];14[2.00 Construction];15[2.00 Construction];22[4.00 Construction];23[4.00 Construction];24[4.00 Construction];25[4.00 Construction];26[3.00 Construction];27[3.00 Construction];28[3.00 Construction];29[3.00 Construction];30[3.00 Construction];31[3.00 Construction];32[3.00 Construction];33[2.00 Construction];34[3.00 Construction];35[2.00 Construction];36[2.00 Construction];37[2.00 Construction];38[3.00 Construction];39[3.00 Construction];40[2.00 Construction];41[2.00 Construction];42[2.00 Construction];43[2.00 Construction];44[2.00 Construction];45[2.00 Construction];46[2.00 Construction];47[2.00 Construction];48[2.00 Construction];49[3.00 Construction];50[2.00 Construction];51[2.00 Construction];52[3.00 Construction];53[2.00 Construction];54[3.00 Construction];55[2.00 Construction];56[2.00 Construction];57[2.00 Construction];58[2.00 Construction];59[2.00 Construction];60[2.00 Construction];61[2.00 Construction];62[3.00 Construction];63[3.00 Construction];64[3.00 Construction];65[2.00 Construction];66; | 0
2 | 1 Manitu 6t | Renewable | 2 | 0 | 0 | 22;23;24;25;26[0.50 1 Manitu 6t];27[0.50 1 Manitu 6t];28[0.50 1 Manitu 6t];29[0.50 1 Manitu 6t];30[0.50 1 Manitu 6t];31[0.50 1 Manitu 6t];32[0.50 1 Manitu 6t];34[0.50 1 Manitu 6t];35[0.50 1 Manitu 6t];36[0.50 1 Manitu 6t];37[0.50 1 Manitu 6t];38;39;40;41[0.50 1 Manitu 6t];42[0.50 1 Manitu 6t];43[0.50 1 Manitu 6t];44[0.50 1 Manitu 6t];45[0.50 1 Manitu 6t];46[0.50 1 Manitu 6t];47[0.50 1 Manitu 6t];48[0.50 1 Manitu 6t];49;50[0.50 1 Manitu 6t];51[0.50 1 Manitu 6t];52[0.50 1 Manitu 6t];53;54;55[0.50 1 Manitu 6t];56[0.50 1 Manitu 6t];57[0.50 1 Manitu 6t];58[0.50 1 Manitu 6t];59[0.50 1 Manitu 6t];60[0.50 1 Manitu 6t];61[0.50 1 Manitu 6t];62;63;64;65;66;67[0.50 1 Manitu 6t];68;69[0.50 1 Manitu 6t];71;72[0.50 1 Manitu 6t];73[0.50 1 Manitu 6t];74[0.50 1 Manitu 6t]; | 0
3 | 2 Hand lift truck | Renewable | 2 | 0 | 0 | 26;27;28;29;30;31;32;34;40;71; | 0
4 | 3 Fork lift 6t | Renewable | 1 | 0 | 0 | 22[0.50 3 Fork lift 6t];26[0.25 3 Fork lift 6t];27[0.25 3 Fork lift 6t];28[0.25 3 Fork lift 6t];29[0.25 3 Fork lift 6t];30[0.25 3 Fork lift 6t];31[0.25 3 Fork lift 6t];32[0.25 3 Fork lift 6t];34[0.25 3 Fork lift 6t];35[0.25 3 Fork lift 6t];36[0.25 3 Fork lift 6t];37[0.25 3 Fork lift 6t];38[0.50 3 Fork lift 6t];39[0.50 3 Fork lift 6t];40[0.50 3 Fork lift 6t];41[0.25 3 Fork lift 6t];42[0.25 3 Fork lift 6t];43[0.25 3 Fork lift 6t];44[0.25 3 Fork lift 6t];45[0.25 3 Fork lift 6t];46[0.25 3 Fork lift 6t];47[0.25 3 Fork lift 6t];48[0.25 3 Fork lift 6t];49[0.50 3 Fork lift 6t];50[0.25 3 Fork lift 6t];51[0.25 3 Fork lift 6t];52[0.25 3 Fork lift 6t];53[0.50 3 Fork lift 6t];54[0.50 3 Fork lift 6t];55[0.25 3 Fork lift 6t];56[0.25 3 Fork lift 6t];57[0.25 3 Fork lift 6t];58[0.25 3 Fork lift 6t];59[0.25 3 Fork lift 6t];60[0.25 3 Fork lift 6t];61[0.25 3 Fork lift 6t];64[0.50 3 Fork lift 6t];67[0.25 3 Fork lift 6t];68[0.50 3 Fork lift 6t];69[0.25 3 Fork lift 6t];71[0.50 3 Fork lift 6t];73[0.25 3 Fork lift 6t];74[0.25 3 Fork lift 6t]; | 0
5 | 4 Telescope lifting platform | Renewable | 1 | 0 | 0 | 8[0.50 4 Telescope lifting platform];9[0.50 4 Telescope lifting platform];10;22[0.25 4 Telescope lifting platform];23[0.50 4 Telescope lifting platform];24[0.50 4 Telescope lifting platform];25[0.50 4 Telescope lifting platform];26[0.25 4 Telescope lifting platform];27[0.25 4 Telescope lifting platform];28[0.25 4 Telescope lifting platform];29[0.25 4 Telescope lifting platform];30[0.25 4 Telescope lifting platform];31[0.25 4 Telescope lifting platform];32[0.25 4 Telescope lifting platform];33[0.25 4 Telescope lifting platform];34[0.25 4 Telescope lifting platform];35[0.25 4 Telescope lifting platform];36[0.50 4 Telescope lifting platform];37[0.50 4 Telescope lifting platform];38[0.50 4 Telescope lifting platform];41[0.50 4 Telescope lifting platform];42[0.50 4 Telescope lifting platform];43[0.50 4 Telescope lifting platform];44[0.50 4 Telescope lifting platform];45[0.50 4 Telescope lifting platform];46[0.25 4 Telescope lifting platform];47[0.25 4 Telescope lifting platform];48[0.25 4 Telescope lifting platform];49[0.50 4 Telescope lifting platform];50[0.25 4 Telescope lifting platform];51[0.50 4 Telescope lifting platform];52[0.50 4 Telescope lifting platform];53[0.50 4 Telescope lifting platform];54[0.50 4 Telescope lifting platform];55[0.25 4 Telescope lifting platform];56[0.25 4 Telescope lifting platform];57[0.25 4 Telescope lifting platform];58[0.25 4 Telescope lifting platform];59[0.25 4 Telescope lifting platform];60[0.25 4 Telescope lifting platform];61[0.25 4 Telescope lifting platform];62[0.50 4 Telescope lifting platform];63[0.50 4 Telescope lifting platform];64[0.50 4 Telescope lifting platform];65[0.50 4 Telescope lifting platform];66[0.50 4 Telescope lifting platform];67[0.25 4 Telescope lifting platform];68[0.50 4 Telescope lifting platform];69[0.25 4 Telescope lifting platform];71[0.25 4 Telescope lifting platform];73[0.25 4 Telescope lifting platform];74[0.25 4 Telescope lifting platform];78[0.50 4 Telescope lifting platform];79[0.50 4 Telescope lifting platform];80[0.50 4 Telescope lifting platform]; | 0
6 | 5 Scherenhubbuhne | Renewable | 1 | 0 | 0 | 26[0.50 5 Scherenhubbuhne];27[0.50 5 Scherenhubbuhne];28[0.50 5 Scherenhubbuhne];29[0.50 5 Scherenhubbuhne];30[0.50 5 Scherenhubbuhne];31[0.50 5 Scherenhubbuhne];32[0.50 5 Scherenhubbuhne];34[0.50 5 Scherenhubbuhne];39[0.50 5 Scherenhubbuhne];40[0.50 5 Scherenhubbuhne];64[0.50 5 Scherenhubbuhne];68[0.50 5 Scherenhubbuhne];71[0.50 5 Scherenhubbuhne];78[0.50 5 Scherenhubbuhne];79[0.50 5 Scherenhubbuhne];80[0.50 5 Scherenhubbuhne]; | 0
7 | 6 Mobil crane for special weight | Renewable | 2 | 0 | 0 |  | 0
8 | Shanks | Renewable | 2 | 0 | 0 |  | 0
9 | Subconstructor - Transformer + NSHV | Renewable | 1 | 0 | 0 |  | 0
10 | Subconsructor - air preasure | Renewable | 1 | 0 | 0 |  | 0

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | Metal Extraction | 704h
1 | Foundation UG | 40h | standard - symmetric | 80 | 100 | 120
2 | Additional part foundation for aspiration filters | 32h | standard - symmetric | 80 | 100 | 120
3 | Drying foundation UG | 32h | standard - symmetric | 80 | 100 | 120
4 | Drying foundation for aspiration filters | 32h | standard - symmetric | 80 | 100 | 120
5 | Wall whole for conveyor 1.060 | 8h | standard - symmetric | 80 | 100 | 120
6 | Wall wholes for explosion-flapps filters | 8h | standard - symmetric | 80 | 100 | 120
7 | Closing wall wholes | 8h | standard - symmetric | 80 | 100 | 120
8 | Roof whole for Aspiration 1 | 8h | standard - symmetric | 80 | 100 | 120
9 | Roof whole for Aspiration 2 | 8h | standard - symmetric | 80 | 100 | 120
10 | Closing roof wholes | 8h | standard - symmetric | 80 | 100 | 120
11 | Electric cable for central cabinet | 16h | standard - symmetric | 80 | 100 | 120
12 | Electric cable for aspiration | 16h | standard - symmetric | 80 | 100 | 120
13 | Electric cable for windsifter | 16h | standard - symmetric | 80 | 100 | 120
14 | Electric cable for UC | 16h | standard - symmetric | 80 | 100 | 120
15 | Electric cable for UG's | 16h | standard - symmetric | 80 | 100 | 120
16 | Air pressure for service works | 24h | standard - symmetric | 80 | 100 | 120
17 | Air pressure for filter cleaning | 16h | standard - symmetric | 80 | 100 | 120
18 | Boxes for particular product | 8h | standard - symmetric | 80 | 100 | 120
19 | Drying boxes for particular product | 32h | standard - symmetric | 80 | 100 | 120
20 | Tranformer | 24h | standard - symmetric | 80 | 100 | 120
21 | Low-Voltage Distribution System (NSHV) | 24h | standard - symmetric | 80 | 100 | 120
22 | UC 150, M-875 | 24h | standard - symmetric | 80 | 100 | 120
23 | UG 208 MSL, M-766 | 16h | standard - symmetric | 80 | 100 | 120
24 | UG 208 MSL, M-832 | 32h | standard - symmetric | 80 | 100 | 120
25 | UG 208 MSL, M-872 | 24h | standard - symmetric | 80 | 100 | 120
26 | Steel constructions for ascending conveyor UC | 16h | standard - symmetric | 80 | 100 | 120
27 | Steel constructions for lifting electric overband magnet | 16h | standard - symmetric | 80 | 100 | 120
28 | Steel constructions for lifting overband magnet | 16h | standard - symmetric | 80 | 100 | 120
29 | Steel constructions for fine screen | 24h | standard - symmetric | 80 | 100 | 120
30 | Steel constructions for windsifter | 24h | standard - symmetric | 80 | 100 | 120
31 | Steel constructions for lifting overband magnet | 16h | standard - symmetric | 80 | 100 | 120
32 | Steel constructions for eddy current separator | 24h | standard - symmetric | 80 | 100 | 120
33 | Railings around Ugs | 24h | standard - symmetric | 80 | 100 | 120
34 | Steel construction for output conveyors from Ugs | 32h | standard - symmetric | 80 | 100 | 120
35 | Ascending conveyor (UC) | 16h | standard - symmetric | 80 | 100 | 120
36 | Ascending conveyor for electric overband magnet | 16h | standard - symmetric | 80 | 100 | 120
37 | Depletion conveyor for electric overband magnet | 8h | standard - symmetric | 80 | 100 | 120
38 | Ascending conveyor for drum screen | 16h | standard - symmetric | 80 | 100 | 120
39 | Drum screen | 24h | standard - symmetric | 80 | 100 | 120
40 | Steel construction for drum screen | 16h | standard - symmetric | 80 | 100 | 120
41 | Depletion conveyor under drum screen | 16h | standard - symmetric | 80 | 100 | 120
42 | Depletion conveyor under drum screen | 16h | standard - symmetric | 80 | 100 | 120
43 | Ascending conveyor from drum screen to magnet-fine screen | 16h | standard - symmetric | 80 | 100 | 120
44 | Depletion conveyor for overband magnet | 16h | standard - symmetric | 80 | 100 | 120
45 | Ascending conveyor to fine screen | 16h | standard - symmetric | 80 | 100 | 120
46 | Depletion conveyor fraction 10-30 mm | 16h | standard - symmetric | 80 | 100 | 120
47 | Depletion conveyor fraction 0-10 mm | 16h | standard - symmetric | 80 | 100 | 120
48 | Depletion conveyor under fine screen towards 10-30 mm | 8h | standard - symmetric | 80 | 100 | 120
49 | Ascending conveyor towards windsifeter | 24h | standard - symmetric | 80 | 100 | 120
50 | Depletion conveyor under windsifter - heavy fraction | 16h | standard - symmetric | 80 | 100 | 120
51 | Ascending conveyor with light fraction under windsifter | 24h | standard - symmetric | 80 | 100 | 120
52 | Ascending conveyor onto changing (direction) conveyor 1.170 | 8h | standard - symmetric | 80 | 100 | 120
53 | Changing direction conveyor over UG M-872 | 8h | standard - symmetric | 80 | 100 | 120
54 | Changing direction conveyor over UG M-766/M-832 | 8h | standard - symmetric | 80 | 100 | 120
55 | Giving through conveyor with cleaner onto conveyor 1.230 | 24h | standard - symmetric | 80 | 100 | 120
56 | Ascending conveyor towards magnets 1.240 | 16h | standard - symmetric | 80 | 100 | 120
57 | Depletion conveyor iron | 16h | standard - symmetric | 80 | 100 | 120
58 | Ascending conveyor towards eddy current separator | 24h | standard - symmetric | 80 | 100 | 120
59 | Depletion conveyor non-iron | 16h | standard - symmetric | 80 | 100 | 120
60 | Depletion conveyor SRF | 8h | standard - symmetric | 80 | 100 | 120
61 | Depletion conveyor SRF | 8h | standard - symmetric | 80 | 100 | 120
62 | Electric overband magnet | 24h | standard - symmetric | 80 | 100 | 120
63 | Overband magnet | 24h | standard - symmetric | 80 | 100 | 120
64 | Trisomat-fine screen | 24h | standard - symmetric | 80 | 100 | 120
65 | Overband magnet | 24h | standard - symmetric | 80 | 100 | 120
66 | Eddy current separator | 24h | standard - symmetric | 80 | 100 | 120
67 | Loading viration channel for eddy current | 8h | standard - symmetric | 80 | 100 | 120
68 | Windsifter | 24h | standard - symmetric | 80 | 100 | 120
69 | Ascending conveyor - windsifter | 16h | standard - symmetric | 80 | 100 | 120
70 | Connection windsifter part | 16h | standard - symmetric | 80 | 100 | 120
71 | Steel construction for UC | 16h | standard - symmetric | 80 | 100 | 120
72 | Hopper for UC | 8h | standard - symmetric | 80 | 100 | 120
73 | FE-chutes | 8h | standard - symmetric | 80 | 100 | 120
74 | NE-chutes | 8h | standard - symmetric | 80 | 100 | 120
75 | Connection UG 2008 MSL M= 872 | 24h | standard - symmetric | 80 | 100 | 120
76 | a | 24h | standard - symmetric | 80 | 100 | 120
77 | Connection UG 2008 MSL M= 766 | 24h | standard - symmetric | 80 | 100 | 120
78 | Aspiration UG | 24h | standard - symmetric | 80 | 100 | 120
79 | Aspiration rest | 24h | standard - symmetric | 80 | 100 | 120
80 | Filter ECO-VAR | 24h | standard - symmetric | 80 | 100 | 120
81 | Connection aspiration system | 24h | standard - symmetric | 80 | 100 | 120
82 | Electrical installation | 40h | standard - symmetric | 80 | 100 | 120
83 | Test installation cold | 40h | standard - symmetric | 80 | 100 | 120
84 | Test installation with material | 40h | standard - symmetric | 80 | 100 | 120
85 | Installation of central cabinet | 32h | standard - symmetric | 80 | 100 | 120
86 | Electrical cables for Trafo and NSHV from power grid | 32h | standard - symmetric | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t))