## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Staff Authorization System | 1 |  |  | 2014-02-24 08:00 | 2014-05-09 17:00 | 55d |  |  | 0 |  |  | 14400 | 74.375
14 | supporting tasks | 1.1 |  |  | 2014-02-26 08:00 | 2014-04-16 15:00 | 35d 6h |  |  | 0 |  |  | 3525 | 49.2917
1 | project management | 1.1.1 |  | FS2;FS3 | 2014-02-26 08:00 | 2014-02-28 12:00 | 2d 4h | Employee A | 1800 | 0 | 0 | 0 | 1800 | 2.1667
2 | validation and support | 1.1.2 | 1FS |  | 2014-04-14 08:00 | 2014-04-14 09:00 | 1h | Employee B | 75 | 0 | 0 | 0 | 75 | 0.041667
3 | validation and support | 1.1.3 | 1FS |  | 2014-04-14 08:00 | 2014-04-16 15:00 | 2d 6h | Employee C | 1650 | 0 | 0 | 0 | 1650 | 2.2917
15 | requirements | 1.2 |  |  | 2014-02-24 08:00 | 2014-02-28 17:00 | 5d |  |  | 0 |  |  | 1275 | 4.375
4 | requirements | 1.2.1 |  | FS5 | 2014-02-24 08:00 | 2014-02-26 09:00 | 2d 1h | Employee D | 1275 | 0 | 0 | 0 | 1275 | 2.0417
5 | requirements validated | 1.2.2 | 4FS | FS13 | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
16 | analysis | 1.3 |  |  | 2014-02-25 08:00 | 2014-03-19 17:00 | 17d |  |  | 0 |  |  | 4500 | 22.375
6 | analysis - business analysis | 1.3.1 |  | FS7 | 2014-02-25 08:00 | 2014-03-05 10:00 | 6d 2h | Employee A | 4500 | 0 | 0 | 0 | 4500 | 8.0833
7 | analysis validated | 1.3.2 | 6FS | FS13 | 2014-03-19 17:00 | 2014-03-19 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
17 | development | 1.4 |  |  | 2014-03-03 08:00 | 2014-03-31 17:00 | 21d |  |  | 0 |  |  | 5100 | 28.375
8 | development - coding | 1.4.1 |  | FS10;FS9 | 2014-03-03 08:00 | 2014-03-06 15:00 | 3d 6h | Employee D | 2250 | 0 | 0 | 0 | 2250 | 3.2917
9 | development - bugfixing and support | 1.4.2 | 8FS | FS10 | 2014-03-17 08:00 | 2014-03-21 15:00 | 4d 6h | Employee D | 2850 | 0 | 0 | 0 | 2850 | 4.2917
10 | development completed | 1.4.3 | 8FS;9FS | FS13 | 2014-03-31 17:00 | 2014-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
18 | implementation | 1.5 |  |  | 2014-03-21 17:00 | 2014-05-09 17:00 | 35d |  |  | 0 |  |  | 0 | 49
11 | release handover | 1.5.1 |  | FS13 | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
12 | code freeze | 1.5.2 |  | FS13 | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
13 | go live | 1.5.3 | 5FS;7FS;10FS;12FS;11FS |  | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Employee A | Renewable | 1 | 0 | 90 | 1;6; | 6300
2 | Employee B | Renewable | 1 | 0 | 75 | 2; | 75
3 | Employee C | Renewable | 1 | 0 | 75 | 3; | 1650
4 | Employee D | Renewable | 1 | 0 | 75 | 4;8;9; | 6375
5 | Employee E | Renewable | 1 | 0 | 75 |  | 0

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Staff Authorization System | 440h |  |  |  |  | 99 | 100 | 101
14 | supporting tasks | 286h |  |  |  |  | 99 | 100 | 101
1 | project management | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | validation and support | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | validation and support | 22h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | requirements | 40h |  |  |  |  | 99 | 100 | 101
4 | requirements | 17h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | requirements validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | analysis | 136h |  |  |  |  | 99 | 100 | 101
6 | analysis - business analysis | 50h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | analysis validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | development | 168h |  |  |  |  | 99 | 100 | 101
8 | development - coding | 30h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | development - bugfixing and support | 38h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | development completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | implementation | 280h |  |  |  |  | 99 | 100 | 101
11 | release handover | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | code freeze | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | go live | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2014-03-17 22:00 |  | TP Name | Tracking 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Staff Authorization System | 2014-02-24 08:00 | 2014-05-09 17:00 | 55d |  |  | 0 |  |  | 14400 |  | 16d | [5 empty] | 3960 |  | 41.73% |  | 6009 | 10425
14 | supporting tasks | 2014-02-26 08:00 | 2014-04-16 15:00 | 35d 6h |  |  | 0 |  |  | 3525 |  | 16d | [5 empty] | 720 |  | 19.4% |  | 684 | 1800
1 | project management | 2014-02-26 08:00 | 2014-02-28 12:00 | 2d 4h | Employee A | 1800 | 0 | 0 | 0 | 1800 | 2014-02-24 08:00 | 1d | 720 | 270 | 3h | 0 | 0 | 720 | 270 | 38% | Started | 684 | 1800 | 100 | 40 | 38 | 100 | 40 | 38
2 | validation and support | 2014-04-14 08:00 | 2014-04-14 09:00 | 1h | Employee B | 75 | 0 | 0 | 0 | 75 |  | 0 | 0 | 75 | 1h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | validation and support | 2014-04-14 08:00 | 2014-04-16 15:00 | 2d 6h | Employee C | 1650 | 0 | 0 | 0 | 1650 |  | 0 | 0 | 1650 | 2d 6h | 0 | 0 | 0 | 1650 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | requirements | 2014-02-24 08:00 | 2014-02-28 17:00 | 5d |  |  | 0 |  |  | 1275 |  | 4d 7h | [5 empty] | 1275 |  | 100% |  | 1275 | 1275
4 | requirements | 2014-02-24 08:00 | 2014-02-26 09:00 | 2d 1h | Employee D | 1275 | 0 | 0 | 0 | 1275 | 2014-02-24 08:00 | 2d 1h | 1275 | 0 | 0 | 0 | 0 | 1275 | 0 | 100% | Finished | 1275 | 1275 | 100 | 100 | 100 | 100 | 100 | 100
5 | requirements validated | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-28 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
16 | analysis | 2014-02-25 08:00 | 2014-03-19 17:00 | 17d |  |  | 0 |  |  | 4500 |  | 16d | [5 empty] | 1890 |  | 40% |  | 1800 | 4500
6 | analysis - business analysis | 2014-02-25 08:00 | 2014-03-05 10:00 | 6d 2h | Employee A | 4500 | 0 | 0 | 0 | 4500 | 2014-02-24 08:00 | 2d 5h | 1890 | 90 | 1h | 0 | 0 | 1890 | 90 | 40% | Started | 1800 | 4500 | 100 | 42 | 40 | 100 | 42 | 40
7 | analysis validated | 2014-03-19 17:00 | 2014-03-19 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | development | 2014-03-03 08:00 | 2014-03-31 17:00 | 21d |  |  | 0 |  |  | 5100 |  | 11d | [5 empty] | 75 |  | 44.12% |  | 2250 | 2850
8 | development - coding | 2014-03-03 08:00 | 2014-03-06 15:00 | 3d 6h | Employee D | 2250 | 0 | 0 | 0 | 2250 | 2014-03-03 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 2250 | 2250 | 100 | 3.3333 | 100 | 100 | 3.3333 | 100
9 | development - bugfixing and support | 2014-03-17 08:00 | 2014-03-21 15:00 | 4d 6h | Employee D | 2850 | 0 | 0 | 0 | 2850 |  | 0 | 0 | 2850 | 4d 6h | 0 | 0 | 0 | 2850 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
10 | development completed | 2014-03-31 17:00 | 2014-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | implementation | 2014-03-21 17:00 | 2014-05-09 17:00 | 35d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
11 | release handover | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2014-04-14 22:00 |  | TP Name | Tracking 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Staff Authorization System | 2014-02-24 08:00 | 2014-05-09 17:00 | 55d |  |  | 0 |  |  | 14400 |  | 36d | [5 empty] | 7935 |  | 92.44% |  | 13311 | 13350
14 | supporting tasks | 2014-02-26 08:00 | 2014-04-16 15:00 | 35d 6h |  |  | 0 |  |  | 3525 |  | 36d | [5 empty] | 1680 |  | 93.36% |  | 3291 | 2475
1 | project management | 2014-02-26 08:00 | 2014-02-28 12:00 | 2d 4h | Employee A | 1800 | 0 | 0 | 0 | 1800 | 2014-02-24 08:00 | 2d 1h | 1530 | 90 | 1h | 0 | 0 | 1530 | 90 | 87% | Started | 1566 | 1800 | 100 | 85 | 87 | 100 | 85 | 87
2 | validation and support | 2014-04-14 08:00 | 2014-04-14 09:00 | 1h | Employee B | 75 | 0 | 0 | 0 | 75 | 2014-04-14 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
3 | validation and support | 2014-04-14 08:00 | 2014-04-16 15:00 | 2d 6h | Employee C | 1650 | 0 | 0 | 0 | 1650 | 2014-04-14 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1650 | 600 | 100 | 4.5455 | 100 | 100 | 4.5455 | 100
15 | requirements | 2014-02-24 08:00 | 2014-02-28 17:00 | 5d |  |  | 0 |  |  | 1275 |  | 4d 7h | [5 empty] | 1275 |  | 100% |  | 1275 | 1275
4 | requirements | 2014-02-24 08:00 | 2014-02-26 09:00 | 2d 1h | Employee D | 1275 | 0 | 0 | 0 | 1275 | 2014-02-24 08:00 | 2d 1h | 1275 | 0 | 0 | 0 | 0 | 1275 | 0 | 100% | Finished | 1275 | 1275 | 100 | 100 | 100 | 100 | 100 | 100
5 | requirements validated | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-28 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
16 | analysis | 2014-02-25 08:00 | 2014-03-19 17:00 | 17d |  |  | 0 |  |  | 4500 |  | 36d | [5 empty] | 3780 |  | 81% |  | 3645 | 4500
6 | analysis - business analysis | 2014-02-25 08:00 | 2014-03-05 10:00 | 6d 2h | Employee A | 4500 | 0 | 0 | 0 | 4500 | 2014-02-24 08:00 | 5d 2h | 3780 | 90 | 1h | 0 | 0 | 3780 | 90 | 81% | Started | 3645 | 4500 | 100 | 84 | 81 | 100 | 84 | 81
7 | analysis validated | 2014-03-19 17:00 | 2014-03-19 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | development | 2014-03-03 08:00 | 2014-03-31 17:00 | 21d |  |  | 0 |  |  | 5100 |  | 26d 7h | [5 empty] | 1200 |  | 100% |  | 5100 | 5100
8 | development - coding | 2014-03-03 08:00 | 2014-03-06 15:00 | 3d 6h | Employee D | 2250 | 0 | 0 | 0 | 2250 | 2014-03-03 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 2250 | 2250 | 100 | 3.3333 | 100 | 100 | 3.3333 | 100
9 | development - bugfixing and support | 2014-03-17 08:00 | 2014-03-21 15:00 | 4d 6h | Employee D | 2850 | 0 | 0 | 0 | 2850 | 2014-03-31 08:00 | 1d 7h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 100% | Finished | 2850 | 2850 | 100 | 39.4737 | 100 | 100 | 39.4737 | 100
10 | development completed | 2014-03-31 17:00 | 2014-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-08 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
18 | implementation | 2014-03-21 17:00 | 2014-05-09 17:00 | 35d |  |  | 0 |  |  | 0 |  | 16d 1h | [5 empty] | 0 |  | 0% |  | 0 | 0
11 | release handover | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
12 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2014-05-12 08:00 |  | TP Name | Closure
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Staff Authorization System | 2014-02-24 08:00 | 2014-05-09 17:00 | 55d |  |  | 0 |  |  | 14400 |  | 54d 7h | [5 empty] | 9105 |  | 100% |  | 14400 | 14400
14 | supporting tasks | 2014-02-26 08:00 | 2014-04-16 15:00 | 35d 6h |  |  | 0 |  |  | 3525 |  | 35d 1h | [5 empty] | 1950 |  | 100% |  | 3525 | 3525
1 | project management | 2014-02-26 08:00 | 2014-02-28 12:00 | 2d 4h | Employee A | 1800 | 0 | 0 | 0 | 1800 | 2014-02-24 08:00 | 2d 4h | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 100% | Finished | 1800 | 1800 | 100 | 100 | 100 | 100 | 100 | 100
2 | validation and support | 2014-04-14 08:00 | 2014-04-14 09:00 | 1h | Employee B | 75 | 0 | 0 | 0 | 75 | 2014-04-14 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
3 | validation and support | 2014-04-14 08:00 | 2014-04-16 15:00 | 2d 6h | Employee C | 1650 | 0 | 0 | 0 | 1650 | 2014-04-14 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1650 | 1650 | 100 | 4.5455 | 100 | 100 | 4.5455 | 100
15 | requirements | 2014-02-24 08:00 | 2014-02-28 17:00 | 5d |  |  | 0 |  |  | 1275 |  | 4d 7h | [5 empty] | 1275 |  | 100% |  | 1275 | 1275
4 | requirements | 2014-02-24 08:00 | 2014-02-26 09:00 | 2d 1h | Employee D | 1275 | 0 | 0 | 0 | 1275 | 2014-02-24 08:00 | 2d 1h | 1275 | 0 | 0 | 0 | 0 | 1275 | 0 | 100% | Finished | 1275 | 1275 | 100 | 100 | 100 | 100 | 100 | 100
5 | requirements validated | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-28 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
16 | analysis | 2014-02-25 08:00 | 2014-03-19 17:00 | 17d |  |  | 0 |  |  | 4500 |  | 41d 7h | [5 empty] | 4680 |  | 100% |  | 4500 | 4500
6 | analysis - business analysis | 2014-02-25 08:00 | 2014-03-05 10:00 | 6d 2h | Employee A | 4500 | 0 | 0 | 0 | 4500 | 2014-02-24 08:00 | 6d 4h | 4680 | 0 | 0 | 0 | 0 | 4680 | 0 | 100% | Finished | 4500 | 4500 | 100 | 104 | 100 | 100 | 104 | 100
7 | analysis validated | 2014-03-19 17:00 | 2014-03-19 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-22 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
17 | development | 2014-03-03 08:00 | 2014-03-31 17:00 | 21d |  |  | 0 |  |  | 5100 |  | 26d 7h | [5 empty] | 1200 |  | 100% |  | 5100 | 5100
8 | development - coding | 2014-03-03 08:00 | 2014-03-06 15:00 | 3d 6h | Employee D | 2250 | 0 | 0 | 0 | 2250 | 2014-03-03 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 2250 | 2250 | 100 | 3.3333 | 100 | 100 | 3.3333 | 100
9 | development - bugfixing and support | 2014-03-17 08:00 | 2014-03-21 15:00 | 4d 6h | Employee D | 2850 | 0 | 0 | 0 | 2850 | 2014-03-31 08:00 | 1d 7h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 100% | Finished | 2850 | 2850 | 100 | 39.4737 | 100 | 100 | 39.4737 | 100
10 | development completed | 2014-03-31 17:00 | 2014-03-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-08 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
18 | implementation | 2014-03-21 17:00 | 2014-05-09 17:00 | 35d |  |  | 0 |  |  | 0 |  | 35d | [5 empty] | 0 |  | 0% |  | 0 | 0
11 | release handover | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
12 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-25 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
13 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-09 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking 1 | 2014-02-24 08:00 | 2014-03-17 22:00 | 10425 | 6009 | 3960 | 2014-02-28 17:00 | -4416 | 57.64% | 2049 | 151.7% | -11d | 31.25% | 63.12% | 2014-06-03 16:00 | 2014-07-07 11:00 | 2014-05-21 16:00 | 2014-05-20 15:00 | 2014-07-07 11:00 | 2014-05-29 11:00 | 2014-05-26 17:00 | 2014-10-27 17:00 | 2014-08-12 12:00 | 12351 | 9489.7653 | 18517.5261 | 30811.1999 | 13553.5769 | 21655.249 | 10272.7249 | 10533.7551 | 0.3125 | 1.5174 | 0.5764 | 0.63123 | -11 | 1.5174 | 1 | 0.3125 | 1
Tracking 2 | 2014-03-17 22:00 | 2014-04-14 22:00 | 13350 | 13311 | 7935 | 2014-04-14 16:00 | -39 | 99.71% | 5376 | 167.8% | -1h | 99.65% | 91.8% | 2014-05-12 09:00 | 2014-05-12 09:00 | 2014-04-09 16:00 | 2014-05-12 09:00 | 2014-05-12 09:00 | 2014-04-30 11:00 | 2014-05-12 09:00 | 2014-05-12 10:00 | 2014-04-30 12:00 | 9024 | 8584.1785 | 9027.1906 | 9027.7944 | 8586.0805 | 8586.4404 | 8641.4916 | 8641.5421 | 0.99653 | 1.6775 | 0.99708 | 0.91797 | -0.125 | 1.6775 | 1 | 0.99653 | 1
Closure | 2014-04-14 22:00 | 2014-05-12 08:00 | 14400 | 14400 | 9105 | 2014-05-09 17:00 | 0 | 100% | 5295 | 158.2% | 0 | 100% | 100% | 2014-05-09 17:00 | 2014-05-09 17:00 | 2014-04-11 15:00 | 2014-05-09 17:00 | 2014-05-09 17:00 | 2014-05-09 17:00 | 2014-05-09 17:00 | 2014-05-09 17:00 | 2014-05-09 17:00 | 9105 | 9105 | 9105 | 9105 | 9105 | 9105 | 9105 | 9105 | 1 | 1.5815 | 1 | 1 | 0 | 1.5815 | 1 | 1 | 1