## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Tax Return System (2) | 1 |  |  | 2014-01-02 08:00 | 2014-06-30 17:00 | 128d |  |  | 0 |  |  | 39450 | 179.375
23 | supporting tasks | 1.1 |  |  | 2014-01-03 08:00 | 2014-01-10 09:00 | 5d 1h |  |  | 0 |  |  | 3690 | 7.0417
1 | project management | 1.1.1 |  | FS19 | 2014-01-03 08:00 | 2014-01-10 09:00 | 5d 1h | Employee A | 3690 | 0 | 0 | 0 | 3690 | 7.0417
24 | analyse | 1.2 |  |  | 2014-01-02 08:00 | 2014-03-28 17:00 | 62d |  |  | 0 |  |  | 5010 | 85.375
2 | analyse | 1.2.1 |  | FS5 | 2014-01-02 08:00 | 2014-01-03 15:00 | 1d 6h | Employee A | 1260 | 0 | 0 | 0 | 1260 | 1.2917
4 | analyse AIA | 1.2.2 |  | FS5 | 2014-01-06 08:00 | 2014-01-14 10:00 | 6d 2h | Employee B | 3750 | 0 | 0 | 0 | 3750 | 8.0833
5 | analysis validated | 1.2.3 | 2FS;4FS | FS19 | 2014-03-28 17:00 | 2014-03-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
25 | design | 1.3 |  |  | 2014-01-29 08:00 | 2014-04-11 17:00 | 53d |  |  | 0 |  |  | 6750 | 72.375
6 | design HP | 1.3.1 |  | FS9 | 2014-01-29 08:00 | 2014-02-10 15:00 | 8d 6h | Employee C | 5250 | 0 | 0 | 0 | 5250 | 12.2917
7 | design HP | 1.3.2 |  | FS9 | 2014-01-29 08:00 | 2014-01-30 11:00 | 1d 3h | Employee D | 825 | 0 | 0 | 0 | 825 | 1.125
8 | design AIA | 1.3.3 |  | FS9 | 2014-02-12 08:00 | 2014-02-13 09:00 | 1d 1h | Employee B | 675 | 0 | 0 | 0 | 675 | 1.0417
9 | design validated | 1.3.4 | 6FS;7FS;8FS | FS19 | 2014-04-11 17:00 | 2014-04-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
26 | development | 1.4 |  |  | 2014-01-28 08:00 | 2014-05-23 17:00 | 84d |  |  | 0 |  |  | 15675 | 115.375
10 | build HP | 1.4.1 |  | FS13 | 2014-01-28 08:00 | 2014-02-07 17:00 | 9d | Employee E | 5400 | 0 | 0 | 0 | 5400 | 10.375
11 | build MF | 1.4.2 |  | FS13 | 2014-01-30 08:00 | 2014-02-07 15:00 | 6d 6h | Employee F | 4050 | 0 | 0 | 0 | 4050 | 8.2917
12 | build AIA | 1.4.3 |  | FS13 | 2014-04-16 08:00 | 2014-04-30 11:00 | 10d 3h | Employee B | 6225 | 0 | 0 | 0 | 6225 | 14.125
13 | development MF completed | 1.4.4 | 10FS;11FS;12FS | FS19 | 2014-05-23 17:00 | 2014-05-23 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
27 | test ict & uat | 1.5 |  |  | 2014-03-24 08:00 | 2014-06-13 17:00 | 60d |  |  | 0 |  |  | 6000 | 81.375
14 | testing HP | 1.5.1 |  | FS18 | 2014-05-05 08:00 | 2014-05-06 16:00 | 1d 7h | Employee C | 1125 | 0 | 0 | 0 | 1125 | 1.3333
15 | testing HP | 1.5.2 |  | FS18 | 2014-05-05 08:00 | 2014-05-07 16:00 | 2d 7h | Employee D | 1725 | 0 | 0 | 0 | 1725 | 2.3333
16 | testing MF | 1.5.3 |  | FS18 | 2014-03-24 08:00 | 2014-03-24 12:00 | 4h | Employee F | 300 | 0 | 0 | 0 | 300 | 0.16667
17 | testing AIA | 1.5.4 |  | FS18 | 2014-05-26 08:00 | 2014-05-30 15:00 | 4d 6h | Employee B | 2850 | 0 | 0 | 0 | 2850 | 4.2917
18 | testing MF completed | 1.5.5 | 14FS;15FS;16FS;17FS | FS19 | 2014-06-13 17:00 | 2014-06-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
28 | implementation | 1.6 |  |  | 2014-06-16 17:00 | 2014-06-16 17:00 | 0 |  |  | 0 |  |  | 0
19 | go live MF | 1.6.1 | 5FS;1FS;9FS;13FS;18FS |  | 2014-06-16 17:00 | 2014-06-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
29 | post implementation | 1.7 |  |  | 2014-06-16 08:00 | 2014-06-30 17:00 | 11d |  |  | 0 |  |  | 2325 | 14.375
20 | post implementation - post go live support | 1.7.1 |  | FS22 | 2014-06-16 08:00 | 2014-06-16 17:00 | 1d | Employee F | 600 | 0 | 0 | 0 | 600 | 0.375
21 | post implementation - post go live support | 1.7.2 |  | FS22 | 2014-06-16 08:00 | 2014-06-18 16:00 | 2d 7h | Employee B | 1725 | 0 | 0 | 0 | 1725 | 2.3333
22 | closure project | 1.7.3 | 20FS;21FS |  | 2014-06-30 17:00 | 2014-06-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Employee A | Renewable | 1 | 0 | 90 | 1;2; | 4950
2 | Employee B | Renewable | 1 | 0 | 75 | 4;8;12;17;21; | 15225
3 | Employee C | Renewable | 1 | 0 | 75 | 6;14; | 6375
4 | Employee D | Renewable | 1 | 0 | 75 | 7;15; | 2550
5 | Employee E | Renewable | 1 | 0 | 75 | 10; | 5400
6 | Employee F | Renewable | 1 | 0 | 75 | 11;16;20; | 4950

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Tax Return System (2) | 1024h |  |  |  |  | 99 | 100 | 101
23 | supporting tasks | 41h |  |  |  |  | 99 | 100 | 101
1 | project management | 41h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | analyse | 496h |  |  |  |  | 99 | 100 | 101
2 | analyse | 14h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | analyse AIA | 50h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | analysis validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | design | 424h |  |  |  |  | 99 | 100 | 101
6 | design HP | 70h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | design HP | 11h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | design AIA | 9h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | design validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | development | 672h |  |  |  |  | 99 | 100 | 101
10 | build HP | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | build MF | 54h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | build AIA | 83h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | development MF completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | test ict & uat | 480h |  |  |  |  | 99 | 100 | 101
14 | testing HP | 15h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | testing HP | 23h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | testing MF | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | testing AIA | 38h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | testing MF completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | implementation | 0 |  |  |  |  | 99 | 100 | 101
19 | go live MF | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | post implementation | 88h |  |  |  |  | 99 | 100 | 101
20 | post implementation - post go live support | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | post implementation - post go live support | 23h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | closure project | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2014-02-03 22:00 |  | TP Name | Tracking 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Tax Return System (2) | 2014-01-02 08:00 | 2014-06-30 17:00 | 128d |  |  | 0 |  |  | 39450 |  | 23d | [5 empty] | 5730 |  | 16.71% |  | 6591.1499 | 16725
23 | supporting tasks | 2014-01-03 08:00 | 2014-01-10 09:00 | 5d 1h |  |  | 0 |  |  | 3690 |  | 23d | [5 empty] | 900 |  | 40% |  | 1476 | 3690
1 | project management | 2014-01-03 08:00 | 2014-01-10 09:00 | 5d 1h | Employee A | 3690 | 0 | 0 | 0 | 3690 | 2014-01-02 08:00 | 1d 2h | 900 | 1800 | 2d 4h | 0 | 0 | 900 | 1800 | 40% | Started | 1476 | 3690 | 100 | 24.3902 | 40 | 100 | 24.3902 | 40
24 | analyse | 2014-01-02 08:00 | 2014-03-28 17:00 | 62d |  |  | 0 |  |  | 5010 |  | 23d | [5 empty] | 3930 |  | 79.15% |  | 3965.3999 | 5010
2 | analyse | 2014-01-02 08:00 | 2014-01-03 15:00 | 1d 6h | Employee A | 1260 | 0 | 0 | 0 | 1260 | 2014-01-02 08:00 | 2h | 180 | 1890 | 2d 5h | 0 | 0 | 180 | 1890 | 29% | Started | 365.4 | 1260 | 100 | 14.2857 | 29 | 100 | 14.2857 | 29
4 | analyse AIA | 2014-01-06 08:00 | 2014-01-14 10:00 | 6d 2h | Employee B | 3750 | 0 | 0 | 0 | 3750 | 2014-01-06 08:00 | 6d 2h | 3750 | 75 | 1h | 0 | 0 | 3750 | 75 | 96% | Started | 3599.9999 | 3750 | 100 | 100 | 96 | 100 | 100 | 96
5 | analysis validated | 2014-03-28 17:00 | 2014-03-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | design | 2014-01-29 08:00 | 2014-04-11 17:00 | 53d |  |  | 0 |  |  | 6750 |  | 6d | [5 empty] | 225 |  | 4.033% |  | 272.25 | 3225
6 | design HP | 2014-01-29 08:00 | 2014-02-10 15:00 | 8d 6h | Employee C | 5250 | 0 | 0 | 0 | 5250 |  | 0 | 0 | 5250 | 8d 6h | 0 | 0 | 0 | 5250 | 0% | Not Started | 0 | 2400 | 100 |  | 0 | 100 |  | 0
7 | design HP | 2014-01-29 08:00 | 2014-01-30 11:00 | 1d 3h | Employee D | 825 | 0 | 0 | 0 | 825 | 2014-01-27 08:00 | 3h | 225 | 375 | 5h | 0 | 0 | 225 | 375 | 33% | Started | 272.25 | 825 | 100 | 27.2727 | 33 | 100 | 27.2727 | 33
8 | design AIA | 2014-02-12 08:00 | 2014-02-13 09:00 | 1d 1h | Employee B | 675 | 0 | 0 | 0 | 675 |  | 0 | 0 | 675 | 1d 1h | 0 | 0 | 0 | 675 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | design validated | 2014-04-11 17:00 | 2014-04-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | development | 2014-01-28 08:00 | 2014-05-23 17:00 | 84d |  |  | 0 |  |  | 15675 |  | 6d | [5 empty] | 675 |  | 5.598% |  | 877.5 | 4800
10 | build HP | 2014-01-28 08:00 | 2014-02-07 17:00 | 9d | Employee E | 5400 | 0 | 0 | 0 | 5400 | 2014-01-27 08:00 | 4h | 300 | 4500 | 7d 4h | 0 | 0 | 300 | 4500 | 8% | Started | 432 | 3000 | 100 | 5.5556 | 8 | 100 | 5.5556 | 8
11 | build MF | 2014-01-30 08:00 | 2014-02-07 15:00 | 6d 6h | Employee F | 4050 | 0 | 0 | 0 | 4050 | 2014-01-27 08:00 | 5h | 375 | 3300 | 5d 4h | 0 | 0 | 375 | 3300 | 11% | Started | 445.5 | 1800 | 100 | 9.2593 | 11 | 100 | 9.2593 | 11
12 | build AIA | 2014-04-16 08:00 | 2014-04-30 11:00 | 10d 3h | Employee B | 6225 | 0 | 0 | 0 | 6225 |  | 0 | 0 | 6225 | 10d 3h | 0 | 0 | 0 | 6225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | development MF completed | 2014-05-23 17:00 | 2014-05-23 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | test ict & uat | 2014-03-24 08:00 | 2014-06-13 17:00 | 60d |  |  | 0 |  |  | 6000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
14 | testing HP | 2014-05-05 08:00 | 2014-05-06 16:00 | 1d 7h | Employee C | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | testing HP | 2014-05-05 08:00 | 2014-05-07 16:00 | 2d 7h | Employee D | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | testing MF | 2014-03-24 08:00 | 2014-03-24 12:00 | 4h | Employee F | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | testing AIA | 2014-05-26 08:00 | 2014-05-30 15:00 | 4d 6h | Employee B | 2850 | 0 | 0 | 0 | 2850 |  | 0 | 0 | 2850 | 4d 6h | 0 | 0 | 0 | 2850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | testing MF completed | 2014-06-13 17:00 | 2014-06-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | implementation | 2014-06-16 17:00 | 2014-06-16 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | go live MF | 2014-06-16 17:00 | 2014-06-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | post implementation | 2014-06-16 08:00 | 2014-06-30 17:00 | 11d |  |  | 0 |  |  | 2325 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | post implementation - post go live support | 2014-06-16 08:00 | 2014-06-16 17:00 | 1d | Employee F | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | post implementation - post go live support | 2014-06-16 08:00 | 2014-06-18 16:00 | 2d 7h | Employee B | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | closure project | 2014-06-30 17:00 | 2014-06-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2014-03-17 22:00 |  | TP Name | Tracking 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Tax Return System (2) | 2014-01-02 08:00 | 2014-06-30 17:00 | 128d |  |  | 0 |  |  | 39450 |  | 53d | [5 empty] | 12405 |  | 40.83% |  | 16109.4 | 24900
23 | supporting tasks | 2014-01-03 08:00 | 2014-01-10 09:00 | 5d 1h |  |  | 0 |  |  | 3690 |  | 53d | [5 empty] | 1350 |  | 60% |  | 2214.0001 | 3690
1 | project management | 2014-01-03 08:00 | 2014-01-10 09:00 | 5d 1h | Employee A | 3690 | 0 | 0 | 0 | 3690 | 2014-01-02 08:00 | 1d 7h | 1350 | 1350 | 1d 7h | 0 | 0 | 1350 | 1350 | 60% | Started | 2214.0001 | 3690 | 100 | 36.5854 | 60 | 100 | 36.5854 | 60
24 | analyse | 2014-01-02 08:00 | 2014-03-28 17:00 | 62d |  |  | 0 |  |  | 5010 |  | 53d | [5 empty] | 4005 |  | 82.14% |  | 4115.4 | 5010
2 | analyse | 2014-01-02 08:00 | 2014-01-03 15:00 | 1d 6h | Employee A | 1260 | 0 | 0 | 0 | 1260 | 2014-01-02 08:00 | 2h | 180 | 1890 | 2d 5h | 0 | 0 | 180 | 1890 | 29% | Started | 365.4 | 1260 | 100 | 14.2857 | 29 | 100 | 14.2857 | 29
4 | analyse AIA | 2014-01-06 08:00 | 2014-01-14 10:00 | 6d 2h | Employee B | 3750 | 0 | 0 | 0 | 3750 | 2014-01-06 08:00 | 6d 3h | 3825 | 0 | 0 | 0 | 0 | 3825 | 0 | 100% | Finished | 3750 | 3750 | 100 | 102 | 100 | 100 | 102 | 100
5 | analysis validated | 2014-03-28 17:00 | 2014-03-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | design | 2014-01-29 08:00 | 2014-04-11 17:00 | 53d |  |  | 0 |  |  | 6750 |  | 36d | [5 empty] | 3300 |  | 55.52% |  | 3747.75 | 6750
6 | design HP | 2014-01-29 08:00 | 2014-02-10 15:00 | 8d 6h | Employee C | 5250 | 0 | 0 | 0 | 5250 | 2014-02-24 08:00 | 4d 2h | 2550 | 2550 | 4d 2h | 0 | 0 | 2550 | 2550 | 48% | Started | 2519.9999 | 5250 | 100 | 48.5714 | 48 | 100 | 48.5714 | 48
7 | design HP | 2014-01-29 08:00 | 2014-01-30 11:00 | 1d 3h | Employee D | 825 | 0 | 0 | 0 | 825 | 2014-01-27 08:00 | 6h | 450 | 150 | 2h | 0 | 0 | 450 | 150 | 67% | Started | 552.75 | 825 | 100 | 54.5455 | 67 | 100 | 54.5455 | 67
8 | design AIA | 2014-02-12 08:00 | 2014-02-13 09:00 | 1d 1h | Employee B | 675 | 0 | 0 | 0 | 675 | 2014-02-10 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 675 | 675 | 100 | 44.4444 | 100 | 100 | 44.4444 | 100
9 | design validated | 2014-04-11 17:00 | 2014-04-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | development | 2014-01-28 08:00 | 2014-05-23 17:00 | 84d |  |  | 0 |  |  | 15675 |  | 36d | [5 empty] | 3750 |  | 38.48% |  | 6032.25 | 9450
10 | build HP | 2014-01-28 08:00 | 2014-02-07 17:00 | 9d | Employee E | 5400 | 0 | 0 | 0 | 5400 | 2014-01-27 08:00 | 6h | 450 | 4350 | 7d 2h | 0 | 0 | 450 | 4350 | 12% | Started | 648 | 5400 | 100 | 8.3333 | 12 | 100 | 8.3333 | 12
11 | build MF | 2014-01-30 08:00 | 2014-02-07 15:00 | 6d 6h | Employee F | 4050 | 0 | 0 | 0 | 4050 | 2014-01-27 08:00 | 4d | 2400 | 1275 | 2d 1h | 0 | 0 | 2400 | 1275 | 73% | Started | 2956.5001 | 4050 | 100 | 59.2593 | 73 | 100 | 59.2593 | 73
12 | build AIA | 2014-04-16 08:00 | 2014-04-30 11:00 | 10d 3h | Employee B | 6225 | 0 | 0 | 0 | 6225 | 2014-03-10 08:00 | 1d 4h | 900 | 1950 | 3d 2h | 0 | 0 | 900 | 1950 | 39% | Started | 2427.7499 | 0 | 100 | 14.4578 | 39 | 100 | 14.4578 | 39
13 | development MF completed | 2014-05-23 17:00 | 2014-05-23 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | test ict & uat | 2014-03-24 08:00 | 2014-06-13 17:00 | 60d |  |  | 0 |  |  | 6000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
14 | testing HP | 2014-05-05 08:00 | 2014-05-06 16:00 | 1d 7h | Employee C | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | testing HP | 2014-05-05 08:00 | 2014-05-07 16:00 | 2d 7h | Employee D | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | testing MF | 2014-03-24 08:00 | 2014-03-24 12:00 | 4h | Employee F | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | testing AIA | 2014-05-26 08:00 | 2014-05-30 15:00 | 4d 6h | Employee B | 2850 | 0 | 0 | 0 | 2850 |  | 0 | 0 | 2850 | 4d 6h | 0 | 0 | 0 | 2850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | testing MF completed | 2014-06-13 17:00 | 2014-06-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | implementation | 2014-06-16 17:00 | 2014-06-16 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | go live MF | 2014-06-16 17:00 | 2014-06-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | post implementation | 2014-06-16 08:00 | 2014-06-30 17:00 | 11d |  |  | 0 |  |  | 2325 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | post implementation - post go live support | 2014-06-16 08:00 | 2014-06-16 17:00 | 1d | Employee F | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | post implementation - post go live support | 2014-06-16 08:00 | 2014-06-18 16:00 | 2d 7h | Employee B | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | closure project | 2014-06-30 17:00 | 2014-06-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2014-07-01 08:00 |  | TP Name | Closure
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Tax Return System (2) | 2014-01-02 08:00 | 2014-06-30 17:00 | 128d |  |  | 0 |  |  | 39450 |  | 127d 7h | [5 empty] | 25380 |  | 100% |  | 39450 | 39450
23 | supporting tasks | 2014-01-03 08:00 | 2014-01-10 09:00 | 5d 1h |  |  | 0 |  |  | 3690 |  | 3d 1h | [5 empty] | 2250 |  | 100% |  | 3690 | 3690
1 | project management | 2014-01-03 08:00 | 2014-01-10 09:00 | 5d 1h | Employee A | 3690 | 0 | 0 | 0 | 3690 | 2014-01-02 08:00 | 3d 1h | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 3690 | 3690 | 100 | 60.9756 | 100 | 100 | 60.9756 | 100
24 | analyse | 2014-01-02 08:00 | 2014-03-28 17:00 | 62d |  |  | 0 |  |  | 5010 |  | 67d 7h | [5 empty] | 4455 |  | 100% |  | 5010 | 5010
2 | analyse | 2014-01-02 08:00 | 2014-01-03 15:00 | 1d 6h | Employee A | 1260 | 0 | 0 | 0 | 1260 | 2014-01-02 08:00 | 7h | 630 | 0 | 0 | 0 | 0 | 630 | 0 | 100% | Finished | 1260 | 1260 | 100 | 50 | 100 | 100 | 50 | 100
4 | analyse AIA | 2014-01-06 08:00 | 2014-01-14 10:00 | 6d 2h | Employee B | 3750 | 0 | 0 | 0 | 3750 | 2014-01-06 08:00 | 6d 3h | 3825 | 0 | 0 | 0 | 0 | 3825 | 0 | 100% | Finished | 3750 | 3750 | 100 | 102 | 100 | 100 | 102 | 100
5 | analysis validated | 2014-03-28 17:00 | 2014-03-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-07 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
25 | design | 2014-01-29 08:00 | 2014-04-11 17:00 | 53d |  |  | 0 |  |  | 6750 |  | 59d 7h | [5 empty] | 6300 |  | 100% |  | 6750 | 6750
6 | design HP | 2014-01-29 08:00 | 2014-02-10 15:00 | 8d 6h | Employee C | 5250 | 0 | 0 | 0 | 5250 | 2014-02-24 08:00 | 8d 7h | 5325 | 0 | 0 | 0 | 0 | 5325 | 0 | 100% | Finished | 5250 | 5250 | 100 | 101.4286 | 100 | 100 | 101.4286 | 100
7 | design HP | 2014-01-29 08:00 | 2014-01-30 11:00 | 1d 3h | Employee D | 825 | 0 | 0 | 0 | 825 | 2014-01-27 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 100% | Finished | 825 | 825 | 100 | 81.8182 | 100 | 100 | 81.8182 | 100
8 | design AIA | 2014-02-12 08:00 | 2014-02-13 09:00 | 1d 1h | Employee B | 675 | 0 | 0 | 0 | 675 | 2014-02-10 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 675 | 675 | 100 | 44.4444 | 100 | 100 | 44.4444 | 100
9 | design validated | 2014-04-11 17:00 | 2014-04-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-18 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
26 | development | 2014-01-28 08:00 | 2014-05-23 17:00 | 84d |  |  | 0 |  |  | 15675 |  | 84d 7h | [5 empty] | 9450 |  | 100% |  | 15675 | 15675
10 | build HP | 2014-01-28 08:00 | 2014-02-07 17:00 | 9d | Employee E | 5400 | 0 | 0 | 0 | 5400 | 2014-01-27 08:00 | 6d 3h | 3825 | 0 | 0 | 0 | 0 | 3825 | 0 | 100% | Finished | 5400 | 5400 | 100 | 70.8333 | 100 | 100 | 70.8333 | 100
11 | build MF | 2014-01-30 08:00 | 2014-02-07 15:00 | 6d 6h | Employee F | 4050 | 0 | 0 | 0 | 4050 | 2014-01-27 08:00 | 5d 4h | 3300 | 0 | 0 | 0 | 0 | 3300 | 0 | 100% | Finished | 4050 | 4050 | 100 | 81.4815 | 100 | 100 | 81.4815 | 100
12 | build AIA | 2014-04-16 08:00 | 2014-04-30 11:00 | 10d 3h | Employee B | 6225 | 0 | 0 | 0 | 6225 | 2014-03-10 08:00 | 3d 7h | 2325 | 0 | 0 | 0 | 0 | 2325 | 0 | 100% | Finished | 6225 | 6225 | 100 | 37.3494 | 100 | 100 | 37.3494 | 100
13 | development MF completed | 2014-05-23 17:00 | 2014-05-23 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-23 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
27 | test ict & uat | 2014-03-24 08:00 | 2014-06-13 17:00 | 60d |  |  | 0 |  |  | 6000 |  | 39d 7h | [5 empty] | 2250 |  | 100% |  | 6000 | 6000
14 | testing HP | 2014-05-05 08:00 | 2014-05-06 16:00 | 1d 7h | Employee C | 1125 | 0 | 0 | 0 | 1125 | 2014-05-05 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 1125 | 1125 | 100 | 53.3333 | 100 | 100 | 53.3333 | 100
15 | testing HP | 2014-05-05 08:00 | 2014-05-07 16:00 | 2d 7h | Employee D | 1725 | 0 | 0 | 0 | 1725 | 2014-05-05 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 1725 | 1725 | 100 | 34.7826 | 100 | 100 | 34.7826 | 100
16 | testing MF | 2014-03-24 08:00 | 2014-03-24 12:00 | 4h | Employee F | 300 | 0 | 0 | 0 | 300 | 2014-04-21 08:00 | 1d 5h | 975 | 0 | 0 | 0 | 0 | 975 | 0 | 100% | Finished | 300 | 300 | 100 | 325 | 100 | 100 | 325 | 100
17 | testing AIA | 2014-05-26 08:00 | 2014-05-30 15:00 | 4d 6h | Employee B | 2850 | 0 | 0 | 0 | 2850 | 2014-05-26 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 2850 | 2850 | 100 | 2.6316 | 100 | 100 | 2.6316 | 100
18 | testing MF completed | 2014-06-13 17:00 | 2014-06-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-06-13 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
28 | implementation | 2014-06-16 17:00 | 2014-06-16 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | go live MF | 2014-06-16 17:00 | 2014-06-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-06-16 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
29 | post implementation | 2014-06-16 08:00 | 2014-06-30 17:00 | 11d |  |  | 0 |  |  | 2325 |  | 10d 7h | [5 empty] | 675 |  | 100% |  | 2325 | 2325
20 | post implementation - post go live support | 2014-06-16 08:00 | 2014-06-16 17:00 | 1d | Employee F | 600 | 0 | 0 | 0 | 600 | 2014-06-16 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 600 | 600 | 100 | 100 | 100 | 100 | 100 | 100
21 | post implementation - post go live support | 2014-06-16 08:00 | 2014-06-18 16:00 | 2d 7h | Employee B | 1725 | 0 | 0 | 0 | 1725 | 2014-06-16 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1725 | 1725 | 100 | 4.3478 | 100 | 100 | 4.3478 | 100
22 | closure project | 2014-06-30 17:00 | 2014-06-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-06-30 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking 1 | 2014-01-02 08:00 | 2014-02-03 22:00 | 16725 | 6591.1499 | 5730 | 2014-01-09 11:00 | -10133.8501 | 39.41% | 861.1499 | 115% | -17d 5h | 23.37% | 60.08% | 2014-08-14 16:00 | 2015-04-01 15:00 | 2015-02-02 11:00 | 2014-07-18 16:00 | 2015-04-01 15:00 | 2015-02-05 11:00 | 2014-07-24 14:00 | 2016-02-08 15:00 | 2015-11-04 09:00 | 38588.8501 | 34295.7606 | 89109.118 | 146335.3119 | 78215.4314 | 127964.8825 | 38620.1519 | 39711.2688 | 0.2337 | 1.1503 | 0.39409 | 0.60084 | -17.625 | 1.1503 | 1 | 0.2337 | 1
Tracking 2 | 2014-02-03 22:00 | 2014-03-17 22:00 | 24900 | 16109.4 | 12405 | 2014-02-03 14:00 | -8790.6 | 64.7% | 3704.4 | 129.9% | -30d 3h | 42.69% | 70.28% | 2014-08-08 12:00 | 2014-10-06 16:00 | 2014-08-04 11:00 | 2014-07-25 15:00 | 2014-10-06 16:00 | 2014-08-20 12:00 | 2014-08-12 11:00 | 2015-02-25 16:00 | 2014-12-09 09:00 | 35745.6 | 30378.366 | 48482.1313 | 67081.3226 | 40186.0976 | 54508.3547 | 32383.4302 | 33165.5868 | 0.42689 | 1.2986 | 0.64696 | 0.70281 | -30.375 | 1.2986 | 1 | 0.42689 | 1
Closure | 2014-03-17 22:00 | 2014-07-01 08:00 | 39450 | 39450 | 25380 | 2014-06-30 17:00 | 0 | 100% | 14070 | 155.4% | 0 | 100% | 100% | 2014-06-30 17:00 | 2014-06-30 17:00 | 2014-04-28 11:00 | 2014-06-30 17:00 | 2014-06-30 17:00 | 2014-06-30 17:00 | 2014-06-30 17:00 | 2014-06-30 17:00 | 2014-06-30 17:00 | 25380 | 25380 | 25380 | 25380 | 25380 | 25380 | 25380 | 25380 | 1 | 1.5544 | 1 | 1 | 0 | 1.5544 | 1 | 1 | 1