## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Railway Station Antwerp | 1 |  |  | 2014-01-27 08:00 | 2014-04-30 17:00 | 68d |  |  | 0 |  |  | 22703.5193 | 93.375
3 | zaal Andries | 1.1 |  |  | 2014-01-27 08:00 | 2014-03-19 17:00 | 38d |  |  | 0 |  |  | 4958.2398 | 51.375
1 | schilderen traphal zaal Andries | 1.1.1 |  | FS2 | 2014-01-27 08:00 | 2014-02-13 17:00 | 14d | Employee B;Employee C;Employee A | 0 | 0 | 32.62 | 3653.4399 | 3653.4399 | 17.375
2 | trapje naar beneden schilderen | 1.1.2 | 1FS;13FS |  | 2014-03-13 08:00 | 2014-03-19 17:00 | 5d | Employee B | 0 | 0 | 32.62 | 1304.8 | 1304.8 | 6.375
10 | aanpassing magazijn B-MO niv. +0 | 1.2 |  |  | 2014-02-03 08:00 | 2014-02-14 17:00 | 10d |  |  | 0 |  |  | 3131.5199 | 11.375
6 | schilderwerken | 1.2.1 |  |  | 2014-02-03 08:00 | 2014-02-14 17:00 | 10d |  |  | 0 |  |  | 2609.5999 | 11.375
4 | schilderwerken - deel 1 | 1.2.1.1 |  | FS5 | 2014-02-03 08:00 | 2014-02-07 17:00 | 5d | Employee D | 0 | 0 | 32.62 | 1304.8 | 1304.8 | 4.375
5 | schilderwerken - deel 2 | 1.2.1.2 | 4FS | FF8;FS11 | 2014-02-10 08:00 | 2014-02-14 17:00 | 5d | Employee D | 0 | 0 | 32.62 | 1304.8 | 1304.8 | 4.375
9 | overige werken | 1.2.2 |  |  | 2014-02-12 08:00 | 2014-02-14 17:00 | 3d |  |  | 0 |  |  | 521.92 | 2.375
7 | plaatsing boiler | 1.2.2.1 |  | FS8 | 2014-02-12 08:00 | 2014-02-12 17:00 | 1d | Employee E;Employee F | 0 | 0 | 32.62 | 260.96 | 260.96 | 0.375
8 | verplaatsen deurstop | 1.2.2.2 | 5FF;7FS |  | 2014-02-14 08:00 | 2014-02-14 17:00 | 1d | Employee G | 0 | 0 | 32.62 | 260.96 | 260.96 | 0.375
12 | travel center | 1.3 |  |  | 2014-02-17 08:00 | 2014-03-03 17:00 | 11d |  |  | 0 |  |  | 2870.5599 | 14.375
11 | travel center - vernieuwen urinoirs | 1.3.1 | 5FS | FS13 | 2014-02-17 08:00 | 2014-03-03 17:00 | 11d | Employee E;Employee F | 0 | 0 | 32.62 | 2870.5599 | 2870.5599 | 14.375
14 | herstellingswerken restaurant | 1.4 |  |  | 2014-03-10 08:00 | 2014-03-12 17:00 | 3d |  |  | 0 |  |  | 782.88 | 2.375
13 | schilderen radiatoren | 1.4.1 | 11FS | FS2;FS19 | 2014-03-10 08:00 | 2014-03-12 17:00 | 3d | Employee B | 0 | 0 | 32.62 | 782.88 | 782.88 | 2.375
16 | portiersloge | 1.5 |  |  | 2014-03-11 08:00 | 2014-03-14 17:00 | 4d |  |  | 0 |  |  | 1043.84 | 3.375
15 | schilderwerken portiersloge | 1.5.1 |  | FS21;FS20 | 2014-03-11 08:00 | 2014-03-14 17:00 | 4d | Employee D | 0 | 0 | 32.62 | 1043.84 | 1043.84 | 3.375
22 | lok. 211 | 1.6 |  |  | 2014-03-17 08:00 | 2014-03-31 17:00 | 11d |  |  | 0 |  |  | 6002.0798 | 14.375
21 | schilderen lok. 211 | 1.6.1 | 15FS |  | 2014-03-17 08:00 | 2014-03-21 17:00 | 5d | Employee D | 0 | 0 | 32.62 | 1304.8 | 1304.8 | 4.375
19 | herstelling schilderwerk | 1.6.2 | 13FS |  | 2014-03-17 08:00 | 2014-03-26 17:00 | 8d | Employee B | 0 | 0 | 32.62 | 2087.6799 | 2087.6799 | 9.375
20 | schilderen automatische deuren | 1.6.3 | 15FS | FS23 | 2014-03-18 08:00 | 2014-03-31 17:00 | 10d | Employee D | 0 | 0 | 32.62 | 2609.5999 | 2609.5999 | 13.375
29 | renovatie toiletten VOO +1 | 1.7 |  |  | 2014-04-14 08:00 | 2014-04-30 17:00 | 13d |  |  | 0 |  |  | 3914.3999 | 16.375
23 | aanpassing verlichting | 1.7.1 | 20FS |  | 2014-04-14 08:00 | 2014-04-14 17:00 | 1d | Employee H | 0 | 0 | 32.62 | 260.96 | 260.96 | 0.375
24 | afbraak bestaande plafonds | 1.7.2 |  | FS26;SS25 | 2014-04-14 08:00 | 2014-04-14 17:00 | 1d | Employee H;Employee I | 0 | 0 | 32.62 | 260.96 | 260.96 | 0.375
25 | demontage elec uit bestaande plafonds | 1.7.3 | 24SS |  | 2014-04-14 08:00 | 2014-04-14 17:00 | 1d | Employee K;Employee J | 0 | 0 | 32.62 | 260.96 | 260.96 | 0.375
26 | opbouw nieuw vals plafond | 1.7.4 | 24FS | FS28 | 2014-04-15 08:00 | 2014-04-17 17:00 | 3d | Employee I;Employee H | 0 | 0 | 32.62 | 782.88 | 782.88 | 2.375
27 | schilderwerken | 1.7.5 | 28FS |  | 2014-04-22 08:00 | 2014-04-30 17:00 | 7d | Employee B | 0 | 0 | 32.62 | 1826.7199 | 1826.7199 | 8.375
28 | herstelling bestaand vals plafond in toiletten | 1.7.6 | 26FS | FS27 | 2014-04-18 08:00 | 2014-04-21 17:00 | 2d | Employee I;Employee H | 0 | 0 | 32.62 | 521.92 | 521.92 | 3.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Employee A | Renewable | 1 | 0 | 0 | 1; | 0
2 | Employee B | Renewable | 1 | 0 | 0 | 1;2;13;19;27; | 0
3 | Employee C | Renewable | 1 | 0 | 0 | 1; | 0
4 | Employee D | Renewable | 1 | 0 | 0 | 4;5;15;21;20; | 0
5 | Employee E | Renewable | 1 | 0 | 0 | 7;11; | 0
6 | Employee F | Renewable | 1 | 0 | 0 | 7;11; | 0
7 | Employee G | Renewable | 1 | 0 | 0 | 8; | 0
8 | Employee H | Renewable | 1 | 0 | 0 | 23;24;26;28; | 0
9 | Employee I | Renewable | 1 | 0 | 0 | 24;26;28; | 0
10 | Employee J | Renewable | 1 | 0 | 0 | 25; | 0
11 | Employee K | Renewable | 1 | 0 | 0 | 25; | 0

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Railway Station Antwerp | 544h |  |  |  |  | 99 | 100 | 101
3 | zaal Andries | 304h |  |  |  |  | 99 | 100 | 101
1 | schilderen traphal zaal Andries | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | trapje naar beneden schilderen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | aanpassing magazijn B-MO niv. +0 | 80h |  |  |  |  | 99 | 100 | 101
6 | schilderwerken | 80h |  |  |  |  | 99 | 100 | 101
4 | schilderwerken - deel 1 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | schilderwerken - deel 2 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | overige werken | 24h |  |  |  |  | 99 | 100 | 101
7 | plaatsing boiler | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | verplaatsen deurstop | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | travel center | 88h |  |  |  |  | 99 | 100 | 101
11 | travel center - vernieuwen urinoirs | 88h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | herstellingswerken restaurant | 24h |  |  |  |  | 99 | 100 | 101
13 | schilderen radiatoren | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | portiersloge | 32h |  |  |  |  | 99 | 100 | 101
15 | schilderwerken portiersloge | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | lok. 211 | 88h |  |  |  |  | 99 | 100 | 101
21 | schilderen lok. 211 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | herstelling schilderwerk | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | schilderen automatische deuren | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | renovatie toiletten VOO +1 | 104h |  |  |  |  | 99 | 100 | 101
23 | aanpassing verlichting | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | afbraak bestaande plafonds | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | demontage elec uit bestaande plafonds | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | opbouw nieuw vals plafond | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | schilderwerken | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | herstelling bestaand vals plafond in toiletten | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2014-02-10 18:00 |  | TP Name | Tracking 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Station Antwerp | 2014-01-27 08:00 | 2014-04-30 17:00 | 68d |  |  | 0 |  |  | 22703.5193 |  | 11d | [5 empty] | 5219.1998 |  | 16.37% |  | 3716.0704 | 4436.3199
3 | zaal Andries | 2014-01-27 08:00 | 2014-03-19 17:00 | 38d |  |  | 0 |  |  | 4958.2398 |  | 11d | [5 empty] | 3392.4799 |  | 48.63% |  | 2411.2704 | 2870.5599
1 | schilderen traphal zaal Andries | 2014-01-27 08:00 | 2014-02-13 17:00 | 14d | Employee B;Employee C;Employee A | 0 | 0 | 32.62 | 3653.4399 | 3653.4399 | 2014-01-27 08:00 | 13d | 3392.4799 | 1043.84 | 4d | 0 | 0 | 3392.4799 | 1043.84 | 66% | Started | 2411.2704 | 2870.5599 | 100 | 92.8571 | 66 | 100 | 92.8571 | 66
2 | trapje naar beneden schilderen | 2014-03-13 08:00 | 2014-03-19 17:00 | 5d | Employee B | 0 | 0 | 32.62 | 1304.8 | 1304.8 |  | 0 | 0 | 1304.8 | 5d | 0 | 0 | 0 | 1304.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | aanpassing magazijn B-MO niv. +0 | 2014-02-03 08:00 | 2014-02-14 17:00 | 10d |  |  | 0 |  |  | 3131.5199 |  | 8d | [5 empty] | 1826.7199 |  | 41.67% |  | 1304.8 | 1565.7599
6 | schilderwerken | 2014-02-03 08:00 | 2014-02-14 17:00 | 10d |  |  | 0 |  |  | 2609.5999 |  | 8d | [5 empty] | 1826.7199 |  | 50% |  | 1304.8 | 1565.7599
4 | schilderwerken - deel 1 | 2014-02-03 08:00 | 2014-02-07 17:00 | 5d | Employee D | 0 | 0 | 32.62 | 1304.8 | 1304.8 | 2014-01-30 08:00 | 7d | 1826.7199 | 0 | 0 | 0 | 0 | 1826.7199 | 0 | 100% | Finished | 1304.8 | 1304.8 | 100 | 140 | 100 | 100 | 140 | 100
5 | schilderwerken - deel 2 | 2014-02-10 08:00 | 2014-02-14 17:00 | 5d | Employee D | 0 | 0 | 32.62 | 1304.8 | 1304.8 |  | 0 | 0 | 1304.8 | 5d | 0 | 0 | 0 | 1304.8 | 0% | Not Started | 0 | 260.96 | 100 |  | 0 | 100 |  | 0
9 | overige werken | 2014-02-12 08:00 | 2014-02-14 17:00 | 3d |  |  | 0 |  |  | 521.92 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | plaatsing boiler | 2014-02-12 08:00 | 2014-02-12 17:00 | 1d | Employee E;Employee F | 0 | 0 | 32.62 | 260.96 | 260.96 |  | 0 | 0 | 260.96 | 1d | 0 | 0 | 0 | 260.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | verplaatsen deurstop | 2014-02-14 08:00 | 2014-02-14 17:00 | 1d | Employee G | 0 | 0 | 32.62 | 260.96 | 260.96 |  | 0 | 0 | 260.96 | 1d | 0 | 0 | 0 | 260.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | travel center | 2014-02-17 08:00 | 2014-03-03 17:00 | 11d |  |  | 0 |  |  | 2870.5599 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
11 | travel center - vernieuwen urinoirs | 2014-02-17 08:00 | 2014-03-03 17:00 | 11d | Employee E;Employee F | 0 | 0 | 32.62 | 2870.5599 | 2870.5599 |  | 0 | 0 | 2870.5599 | 11d | 0 | 0 | 0 | 2870.5599 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | herstellingswerken restaurant | 2014-03-10 08:00 | 2014-03-12 17:00 | 3d |  |  | 0 |  |  | 782.88 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
13 | schilderen radiatoren | 2014-03-10 08:00 | 2014-03-12 17:00 | 3d | Employee B | 0 | 0 | 32.62 | 782.88 | 782.88 |  | 0 | 0 | 782.88 | 3d | 0 | 0 | 0 | 782.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | portiersloge | 2014-03-11 08:00 | 2014-03-14 17:00 | 4d |  |  | 0 |  |  | 1043.84 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
15 | schilderwerken portiersloge | 2014-03-11 08:00 | 2014-03-14 17:00 | 4d | Employee D | 0 | 0 | 32.62 | 1043.84 | 1043.84 |  | 0 | 0 | 1043.84 | 4d | 0 | 0 | 0 | 1043.84 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | lok. 211 | 2014-03-17 08:00 | 2014-03-31 17:00 | 11d |  |  | 0 |  |  | 6002.0798 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | schilderen lok. 211 | 2014-03-17 08:00 | 2014-03-21 17:00 | 5d | Employee D | 0 | 0 | 32.62 | 1304.8 | 1304.8 |  | 0 | 0 | 1304.8 | 5d | 0 | 0 | 0 | 1304.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | herstelling schilderwerk | 2014-03-17 08:00 | 2014-03-26 17:00 | 8d | Employee B | 0 | 0 | 32.62 | 2087.6799 | 2087.6799 |  | 0 | 0 | 2087.6799 | 8d | 0 | 0 | 0 | 2087.6799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | schilderen automatische deuren | 2014-03-18 08:00 | 2014-03-31 17:00 | 10d | Employee D | 0 | 0 | 32.62 | 2609.5999 | 2609.5999 |  | 0 | 0 | 2609.5999 | 10d | 0 | 0 | 0 | 2609.5999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | renovatie toiletten VOO +1 | 2014-04-14 08:00 | 2014-04-30 17:00 | 13d |  |  | 0 |  |  | 3914.3999 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
23 | aanpassing verlichting | 2014-04-14 08:00 | 2014-04-14 17:00 | 1d | Employee H | 0 | 0 | 32.62 | 260.96 | 260.96 |  | 0 | 0 | 260.96 | 1d | 0 | 0 | 0 | 260.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | afbraak bestaande plafonds | 2014-04-14 08:00 | 2014-04-14 17:00 | 1d | Employee H;Employee I | 0 | 0 | 32.62 | 260.96 | 260.96 |  | 0 | 0 | 260.96 | 1d | 0 | 0 | 0 | 260.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | demontage elec uit bestaande plafonds | 2014-04-14 08:00 | 2014-04-14 17:00 | 1d | Employee K;Employee J | 0 | 0 | 32.62 | 260.96 | 260.96 |  | 0 | 0 | 260.96 | 1d | 0 | 0 | 0 | 260.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | opbouw nieuw vals plafond | 2014-04-15 08:00 | 2014-04-17 17:00 | 3d | Employee I;Employee H | 0 | 0 | 32.62 | 782.88 | 782.88 |  | 0 | 0 | 782.88 | 3d | 0 | 0 | 0 | 782.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | schilderwerken | 2014-04-22 08:00 | 2014-04-30 17:00 | 7d | Employee B | 0 | 0 | 32.62 | 1826.7199 | 1826.7199 |  | 0 | 0 | 1826.7199 | 7d | 0 | 0 | 0 | 1826.7199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | herstelling bestaand vals plafond in toiletten | 2014-04-18 08:00 | 2014-04-21 17:00 | 2d | Employee I;Employee H | 0 | 0 | 32.62 | 521.92 | 521.92 |  | 0 | 0 | 521.92 | 2d | 0 | 0 | 0 | 521.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2014-02-24 18:00 |  | TP Name | Tracking 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Station Antwerp | 2014-01-27 08:00 | 2014-04-30 17:00 | 68d |  |  | 0 |  |  | 22703.5193 |  | 21d | [5 empty] | 9655.5197 |  | 26.48% |  | 6011.7451 | 8350.7197
3 | zaal Andries | 2014-01-27 08:00 | 2014-03-19 17:00 | 38d |  |  | 0 |  |  | 4958.2398 |  | 21d | [5 empty] | 6002.0798 |  | 62.77% |  | 3112.1896 | 3653.4399
1 | schilderen traphal zaal Andries | 2014-01-27 08:00 | 2014-02-13 17:00 | 14d | Employee B;Employee C;Employee A | 0 | 0 | 32.62 | 3653.4399 | 3653.4399 | 2014-01-27 08:00 | 23d | 6002.0798 | 1043.84 | 4d | 0 | 0 | 6002.0798 | 1043.84 | 85.19% | Started | 3112.1896 | 3653.4399 | 100 | 164.2857 | 85.1852 | 100 | 164.2857 | 85.1852
2 | trapje naar beneden schilderen | 2014-03-13 08:00 | 2014-03-19 17:00 | 5d | Employee B | 0 | 0 | 32.62 | 1304.8 | 1304.8 |  | 0 | 0 | 1304.8 | 5d | 0 | 0 | 0 | 1304.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | aanpassing magazijn B-MO niv. +0 | 2014-02-03 08:00 | 2014-02-14 17:00 | 10d |  |  | 0 |  |  | 3131.5199 |  | 18d | [5 empty] | 3653.4399 |  | 92.59% |  | 2899.5555 | 3131.5199
6 | schilderwerken | 2014-02-03 08:00 | 2014-02-14 17:00 | 10d |  |  | 0 |  |  | 2609.5999 |  | 13d 4h | [5 empty] | 3131.5199 |  | 100% |  | 2609.5999 | 2609.5999
4 | schilderwerken - deel 1 | 2014-02-03 08:00 | 2014-02-07 17:00 | 5d | Employee D | 0 | 0 | 32.62 | 1304.8 | 1304.8 | 2014-01-30 08:00 | 7d | 1826.7199 | 0 | 0 | 0 | 0 | 1826.7199 | 0 | 100% | Finished | 1304.8 | 1304.8 | 100 | 140 | 100 | 100 | 140 | 100
5 | schilderwerken - deel 2 | 2014-02-10 08:00 | 2014-02-14 17:00 | 5d | Employee D | 0 | 0 | 32.62 | 1304.8 | 1304.8 | 2014-02-11 13:00 | 5d | 1304.8 | 0 | 0 | 0 | 0 | 1304.8 | 0 | 100% | Finished | 1304.8 | 1304.8 | 100 | 100 | 100 | 100 | 100 | 100
9 | overige werken | 2014-02-12 08:00 | 2014-02-14 17:00 | 3d |  |  | 0 |  |  | 521.92 |  | 7d | [5 empty] | 521.92 |  | 55.56% |  | 289.9555 | 521.92
7 | plaatsing boiler | 2014-02-12 08:00 | 2014-02-12 17:00 | 1d | Employee E;Employee F | 0 | 0 | 32.62 | 260.96 | 260.96 | 2014-02-24 08:00 | 1d | 260.96 | 2087.6799 | 8d | 0 | 0 | 260.96 | 2087.6799 | 11.11% | Started | 28.9956 | 260.96 | 100 | 100 | 11.1111 | 100 | 100 | 11.1111
8 | verplaatsen deurstop | 2014-02-14 08:00 | 2014-02-14 17:00 | 1d | Employee G | 0 | 0 | 32.62 | 260.96 | 260.96 | 2014-02-14 08:00 | 1d | 260.96 | 0 | 0 | 0 | 0 | 260.96 | 0 | 100% | Finished | 260.96 | 260.96 | 100 | 100 | 100 | 100 | 100 | 100
12 | travel center | 2014-02-17 08:00 | 2014-03-03 17:00 | 11d |  |  | 0 |  |  | 2870.5599 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1565.7599
11 | travel center - vernieuwen urinoirs | 2014-02-17 08:00 | 2014-03-03 17:00 | 11d | Employee E;Employee F | 0 | 0 | 32.62 | 2870.5599 | 2870.5599 |  | 0 | 0 | 2870.5599 | 11d | 0 | 0 | 0 | 2870.5599 | 0% | Not Started | 0 | 1565.7599 | 100 |  | 0 | 100 |  | 0
14 | herstellingswerken restaurant | 2014-03-10 08:00 | 2014-03-12 17:00 | 3d |  |  | 0 |  |  | 782.88 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
13 | schilderen radiatoren | 2014-03-10 08:00 | 2014-03-12 17:00 | 3d | Employee B | 0 | 0 | 32.62 | 782.88 | 782.88 |  | 0 | 0 | 782.88 | 3d | 0 | 0 | 0 | 782.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | portiersloge | 2014-03-11 08:00 | 2014-03-14 17:00 | 4d |  |  | 0 |  |  | 1043.84 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
15 | schilderwerken portiersloge | 2014-03-11 08:00 | 2014-03-14 17:00 | 4d | Employee D | 0 | 0 | 32.62 | 1043.84 | 1043.84 |  | 0 | 0 | 1043.84 | 4d | 0 | 0 | 0 | 1043.84 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | lok. 211 | 2014-03-17 08:00 | 2014-03-31 17:00 | 11d |  |  | 0 |  |  | 6002.0798 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | schilderen lok. 211 | 2014-03-17 08:00 | 2014-03-21 17:00 | 5d | Employee D | 0 | 0 | 32.62 | 1304.8 | 1304.8 |  | 0 | 0 | 1304.8 | 5d | 0 | 0 | 0 | 1304.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | herstelling schilderwerk | 2014-03-17 08:00 | 2014-03-26 17:00 | 8d | Employee B | 0 | 0 | 32.62 | 2087.6799 | 2087.6799 |  | 0 | 0 | 2087.6799 | 8d | 0 | 0 | 0 | 2087.6799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | schilderen automatische deuren | 2014-03-18 08:00 | 2014-03-31 17:00 | 10d | Employee D | 0 | 0 | 32.62 | 2609.5999 | 2609.5999 |  | 0 | 0 | 2609.5999 | 10d | 0 | 0 | 0 | 2609.5999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | renovatie toiletten VOO +1 | 2014-04-14 08:00 | 2014-04-30 17:00 | 13d |  |  | 0 |  |  | 3914.3999 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
23 | aanpassing verlichting | 2014-04-14 08:00 | 2014-04-14 17:00 | 1d | Employee H | 0 | 0 | 32.62 | 260.96 | 260.96 |  | 0 | 0 | 260.96 | 1d | 0 | 0 | 0 | 260.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | afbraak bestaande plafonds | 2014-04-14 08:00 | 2014-04-14 17:00 | 1d | Employee H;Employee I | 0 | 0 | 32.62 | 260.96 | 260.96 |  | 0 | 0 | 260.96 | 1d | 0 | 0 | 0 | 260.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | demontage elec uit bestaande plafonds | 2014-04-14 08:00 | 2014-04-14 17:00 | 1d | Employee K;Employee J | 0 | 0 | 32.62 | 260.96 | 260.96 |  | 0 | 0 | 260.96 | 1d | 0 | 0 | 0 | 260.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | opbouw nieuw vals plafond | 2014-04-15 08:00 | 2014-04-17 17:00 | 3d | Employee I;Employee H | 0 | 0 | 32.62 | 782.88 | 782.88 |  | 0 | 0 | 782.88 | 3d | 0 | 0 | 0 | 782.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | schilderwerken | 2014-04-22 08:00 | 2014-04-30 17:00 | 7d | Employee B | 0 | 0 | 32.62 | 1826.7199 | 1826.7199 |  | 0 | 0 | 1826.7199 | 7d | 0 | 0 | 0 | 1826.7199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | herstelling bestaand vals plafond in toiletten | 2014-04-18 08:00 | 2014-04-21 17:00 | 2d | Employee I;Employee H | 0 | 0 | 32.62 | 521.92 | 521.92 |  | 0 | 0 | 521.92 | 2d | 0 | 0 | 0 | 521.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2014-03-10 18:00 |  | TP Name | Tracking 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Station Antwerp | 2014-01-27 08:00 | 2014-04-30 17:00 | 68d |  |  | 0 |  |  | 22703.5193 |  | 31d | [5 empty] | 12265.1196 |  | 32.44% |  | 7364.8709 | 9916.4797
3 | zaal Andries | 2014-01-27 08:00 | 2014-03-19 17:00 | 38d |  |  | 0 |  |  | 4958.2398 |  | 31d | [5 empty] | 6002.0798 |  | 73.68% |  | 3653.4399 | 3653.4399
1 | schilderen traphal zaal Andries | 2014-01-27 08:00 | 2014-02-13 17:00 | 14d | Employee B;Employee C;Employee A | 0 | 0 | 32.62 | 3653.4399 | 3653.4399 | 2014-01-27 08:00 | 23d | 6002.0798 | 0 | 0 | 0 | 0 | 6002.0798 | 0 | 100% | Finished | 3653.4399 | 3653.4399 | 100 | 164.2857 | 100 | 100 | 164.2857 | 100
2 | trapje naar beneden schilderen | 2014-03-13 08:00 | 2014-03-19 17:00 | 5d | Employee B | 0 | 0 | 32.62 | 1304.8 | 1304.8 |  | 0 | 0 | 1304.8 | 5d | 0 | 0 | 0 | 1304.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | aanpassing magazijn B-MO niv. +0 | 2014-02-03 08:00 | 2014-02-14 17:00 | 10d |  |  | 0 |  |  | 3131.5199 |  | 26d | [5 empty] | 5741.1198 |  | 100% |  | 3131.5199 | 3131.5199
6 | schilderwerken | 2014-02-03 08:00 | 2014-02-14 17:00 | 10d |  |  | 0 |  |  | 2609.5999 |  | 13d 4h | [5 empty] | 3131.5199 |  | 100% |  | 2609.5999 | 2609.5999
4 | schilderwerken - deel 1 | 2014-02-03 08:00 | 2014-02-07 17:00 | 5d | Employee D | 0 | 0 | 32.62 | 1304.8 | 1304.8 | 2014-01-30 08:00 | 7d | 1826.7199 | 0 | 0 | 0 | 0 | 1826.7199 | 0 | 100% | Finished | 1304.8 | 1304.8 | 100 | 140 | 100 | 100 | 140 | 100
5 | schilderwerken - deel 2 | 2014-02-10 08:00 | 2014-02-14 17:00 | 5d | Employee D | 0 | 0 | 32.62 | 1304.8 | 1304.8 | 2014-02-11 13:00 | 5d | 1304.8 | 0 | 0 | 0 | 0 | 1304.8 | 0 | 100% | Finished | 1304.8 | 1304.8 | 100 | 100 | 100 | 100 | 100 | 100
9 | overige werken | 2014-02-12 08:00 | 2014-02-14 17:00 | 3d |  |  | 0 |  |  | 521.92 |  | 15d | [5 empty] | 2609.5999 |  | 100% |  | 521.92 | 521.92
7 | plaatsing boiler | 2014-02-12 08:00 | 2014-02-12 17:00 | 1d | Employee E;Employee F | 0 | 0 | 32.62 | 260.96 | 260.96 | 2014-02-24 08:00 | 9d | 2348.6399 | 0 | 0 | 0 | 0 | 2348.6399 | 0 | 100% | Finished | 260.96 | 260.96 | 100 | 900 | 100 | 100 | 900 | 100
8 | verplaatsen deurstop | 2014-02-14 08:00 | 2014-02-14 17:00 | 1d | Employee G | 0 | 0 | 32.62 | 260.96 | 260.96 | 2014-02-14 08:00 | 1d | 260.96 | 0 | 0 | 0 | 0 | 260.96 | 0 | 100% | Finished | 260.96 | 260.96 | 100 | 100 | 100 | 100 | 100 | 100
12 | travel center | 2014-02-17 08:00 | 2014-03-03 17:00 | 11d |  |  | 0 |  |  | 2870.5599 |  | 1d | [5 empty] | 260.96 |  | 11.11% |  | 318.9511 | 2870.5599
11 | travel center - vernieuwen urinoirs | 2014-02-17 08:00 | 2014-03-03 17:00 | 11d | Employee E;Employee F | 0 | 0 | 32.62 | 2870.5599 | 2870.5599 | 2014-03-10 08:00 | 1d | 260.96 | 2087.6799 | 8d | 0 | 0 | 260.96 | 2087.6799 | 11.11% | Started | 318.9511 | 2870.5599 | 100 | 9.0909 | 11.1111 | 100 | 9.0909 | 11.1111
14 | herstellingswerken restaurant | 2014-03-10 08:00 | 2014-03-12 17:00 | 3d |  |  | 0 |  |  | 782.88 |  | 1d | [5 empty] | 260.96 |  | 33.33% |  | 260.96 | 260.96
13 | schilderen radiatoren | 2014-03-10 08:00 | 2014-03-12 17:00 | 3d | Employee B | 0 | 0 | 32.62 | 782.88 | 782.88 | 2014-03-10 08:00 | 1d | 260.96 | 521.92 | 2d | 0 | 0 | 260.96 | 521.92 | 33.33% | Started | 260.96 | 260.96 | 100 | 33.3333 | 33.3333 | 100 | 33.3333 | 33.3333
16 | portiersloge | 2014-03-11 08:00 | 2014-03-14 17:00 | 4d |  |  | 0 |  |  | 1043.84 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
15 | schilderwerken portiersloge | 2014-03-11 08:00 | 2014-03-14 17:00 | 4d | Employee D | 0 | 0 | 32.62 | 1043.84 | 1043.84 |  | 0 | 0 | 1043.84 | 4d | 0 | 0 | 0 | 1043.84 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | lok. 211 | 2014-03-17 08:00 | 2014-03-31 17:00 | 11d |  |  | 0 |  |  | 6002.0798 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | schilderen lok. 211 | 2014-03-17 08:00 | 2014-03-21 17:00 | 5d | Employee D | 0 | 0 | 32.62 | 1304.8 | 1304.8 |  | 0 | 0 | 1304.8 | 5d | 0 | 0 | 0 | 1304.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | herstelling schilderwerk | 2014-03-17 08:00 | 2014-03-26 17:00 | 8d | Employee B | 0 | 0 | 32.62 | 2087.6799 | 2087.6799 |  | 0 | 0 | 2087.6799 | 8d | 0 | 0 | 0 | 2087.6799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | schilderen automatische deuren | 2014-03-18 08:00 | 2014-03-31 17:00 | 10d | Employee D | 0 | 0 | 32.62 | 2609.5999 | 2609.5999 |  | 0 | 0 | 2609.5999 | 10d | 0 | 0 | 0 | 2609.5999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | renovatie toiletten VOO +1 | 2014-04-14 08:00 | 2014-04-30 17:00 | 13d |  |  | 0 |  |  | 3914.3999 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
23 | aanpassing verlichting | 2014-04-14 08:00 | 2014-04-14 17:00 | 1d | Employee H | 0 | 0 | 32.62 | 260.96 | 260.96 |  | 0 | 0 | 260.96 | 1d | 0 | 0 | 0 | 260.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | afbraak bestaande plafonds | 2014-04-14 08:00 | 2014-04-14 17:00 | 1d | Employee H;Employee I | 0 | 0 | 32.62 | 260.96 | 260.96 |  | 0 | 0 | 260.96 | 1d | 0 | 0 | 0 | 260.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | demontage elec uit bestaande plafonds | 2014-04-14 08:00 | 2014-04-14 17:00 | 1d | Employee K;Employee J | 0 | 0 | 32.62 | 260.96 | 260.96 |  | 0 | 0 | 260.96 | 1d | 0 | 0 | 0 | 260.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | opbouw nieuw vals plafond | 2014-04-15 08:00 | 2014-04-17 17:00 | 3d | Employee I;Employee H | 0 | 0 | 32.62 | 782.88 | 782.88 |  | 0 | 0 | 782.88 | 3d | 0 | 0 | 0 | 782.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | schilderwerken | 2014-04-22 08:00 | 2014-04-30 17:00 | 7d | Employee B | 0 | 0 | 32.62 | 1826.7199 | 1826.7199 |  | 0 | 0 | 1826.7199 | 7d | 0 | 0 | 0 | 1826.7199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | herstelling bestaand vals plafond in toiletten | 2014-04-18 08:00 | 2014-04-21 17:00 | 2d | Employee I;Employee H | 0 | 0 | 32.62 | 521.92 | 521.92 |  | 0 | 0 | 521.92 | 2d | 0 | 0 | 0 | 521.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2014-03-31 18:00 |  | TP Name | Tracking 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Station Antwerp | 2014-01-27 08:00 | 2014-04-30 17:00 | 68d |  |  | 0 |  |  | 22703.5193 |  | 46d | [5 empty] | 21920.6393 |  | 82.76% |  | 18789.1194 | 18789.1194
3 | zaal Andries | 2014-01-27 08:00 | 2014-03-19 17:00 | 38d |  |  | 0 |  |  | 4958.2398 |  | 34d | [5 empty] | 6263.0398 |  | 100% |  | 4958.2398 | 4958.2398
1 | schilderen traphal zaal Andries | 2014-01-27 08:00 | 2014-02-13 17:00 | 14d | Employee B;Employee C;Employee A | 0 | 0 | 32.62 | 3653.4399 | 3653.4399 | 2014-01-27 08:00 | 23d | 6002.0798 | 0 | 0 | 0 | 0 | 6002.0798 | 0 | 100% | Finished | 3653.4399 | 3653.4399 | 100 | 164.2857 | 100 | 100 | 164.2857 | 100
2 | trapje naar beneden schilderen | 2014-03-13 08:00 | 2014-03-19 17:00 | 5d | Employee B | 0 | 0 | 32.62 | 1304.8 | 1304.8 | 2014-03-13 08:00 | 1d | 260.96 | 0 | 0 | 0 | 0 | 260.96 | 0 | 100% | Finished | 1304.8 | 1304.8 | 100 | 20 | 100 | 100 | 20 | 100
10 | aanpassing magazijn B-MO niv. +0 | 2014-02-03 08:00 | 2014-02-14 17:00 | 10d |  |  | 0 |  |  | 3131.5199 |  | 26d | [5 empty] | 5741.1198 |  | 100% |  | 3131.5199 | 3131.5199
6 | schilderwerken | 2014-02-03 08:00 | 2014-02-14 17:00 | 10d |  |  | 0 |  |  | 2609.5999 |  | 13d 4h | [5 empty] | 3131.5199 |  | 100% |  | 2609.5999 | 2609.5999
4 | schilderwerken - deel 1 | 2014-02-03 08:00 | 2014-02-07 17:00 | 5d | Employee D | 0 | 0 | 32.62 | 1304.8 | 1304.8 | 2014-01-30 08:00 | 7d | 1826.7199 | 0 | 0 | 0 | 0 | 1826.7199 | 0 | 100% | Finished | 1304.8 | 1304.8 | 100 | 140 | 100 | 100 | 140 | 100
5 | schilderwerken - deel 2 | 2014-02-10 08:00 | 2014-02-14 17:00 | 5d | Employee D | 0 | 0 | 32.62 | 1304.8 | 1304.8 | 2014-02-11 13:00 | 5d | 1304.8 | 0 | 0 | 0 | 0 | 1304.8 | 0 | 100% | Finished | 1304.8 | 1304.8 | 100 | 100 | 100 | 100 | 100 | 100
9 | overige werken | 2014-02-12 08:00 | 2014-02-14 17:00 | 3d |  |  | 0 |  |  | 521.92 |  | 15d | [5 empty] | 2609.5999 |  | 100% |  | 521.92 | 521.92
7 | plaatsing boiler | 2014-02-12 08:00 | 2014-02-12 17:00 | 1d | Employee E;Employee F | 0 | 0 | 32.62 | 260.96 | 260.96 | 2014-02-24 08:00 | 9d | 2348.6399 | 0 | 0 | 0 | 0 | 2348.6399 | 0 | 100% | Finished | 260.96 | 260.96 | 100 | 900 | 100 | 100 | 900 | 100
8 | verplaatsen deurstop | 2014-02-14 08:00 | 2014-02-14 17:00 | 1d | Employee G | 0 | 0 | 32.62 | 260.96 | 260.96 | 2014-02-14 08:00 | 1d | 260.96 | 0 | 0 | 0 | 0 | 260.96 | 0 | 100% | Finished | 260.96 | 260.96 | 100 | 100 | 100 | 100 | 100 | 100
12 | travel center | 2014-02-17 08:00 | 2014-03-03 17:00 | 11d |  |  | 0 |  |  | 2870.5599 |  | 10d | [5 empty] | 2609.5999 |  | 100% |  | 2870.5599 | 2870.5599
11 | travel center - vernieuwen urinoirs | 2014-02-17 08:00 | 2014-03-03 17:00 | 11d | Employee E;Employee F | 0 | 0 | 32.62 | 2870.5599 | 2870.5599 | 2014-03-10 08:00 | 10d | 2609.5999 | 0 | 0 | 0 | 0 | 2609.5999 | 0 | 100% | Finished | 2870.5599 | 2870.5599 | 100 | 90.9091 | 100 | 100 | 90.9091 | 100
14 | herstellingswerken restaurant | 2014-03-10 08:00 | 2014-03-12 17:00 | 3d |  |  | 0 |  |  | 782.88 |  | 3d | [5 empty] | 782.88 |  | 100% |  | 782.88 | 782.88
13 | schilderen radiatoren | 2014-03-10 08:00 | 2014-03-12 17:00 | 3d | Employee B | 0 | 0 | 32.62 | 782.88 | 782.88 | 2014-03-10 08:00 | 3d | 782.88 | 0 | 0 | 0 | 0 | 782.88 | 0 | 100% | Finished | 782.88 | 782.88 | 100 | 100 | 100 | 100 | 100 | 100
16 | portiersloge | 2014-03-11 08:00 | 2014-03-14 17:00 | 4d |  |  | 0 |  |  | 1043.84 |  | 5d | [5 empty] | 1304.8 |  | 100% |  | 1043.84 | 1043.84
15 | schilderwerken portiersloge | 2014-03-11 08:00 | 2014-03-14 17:00 | 4d | Employee D | 0 | 0 | 32.62 | 1043.84 | 1043.84 | 2014-03-11 08:00 | 5d | 1304.8 | 0 | 0 | 0 | 0 | 1304.8 | 0 | 100% | Finished | 1043.84 | 1043.84 | 100 | 125 | 100 | 100 | 125 | 100
22 | lok. 211 | 2014-03-17 08:00 | 2014-03-31 17:00 | 11d |  |  | 0 |  |  | 6002.0798 |  | 8d | [5 empty] | 5219.1998 |  | 100% |  | 6002.0798 | 6002.0798
21 | schilderen lok. 211 | 2014-03-17 08:00 | 2014-03-21 17:00 | 5d | Employee D | 0 | 0 | 32.62 | 1304.8 | 1304.8 | 2014-03-17 08:00 | 7d | 1826.7199 | 0 | 0 | 0 | 0 | 1826.7199 | 0 | 100% | Finished | 1304.8 | 1304.8 | 100 | 140 | 100 | 100 | 140 | 100
19 | herstelling schilderwerk | 2014-03-17 08:00 | 2014-03-26 17:00 | 8d | Employee B | 0 | 0 | 32.62 | 2087.6799 | 2087.6799 | 2014-03-17 08:00 | 8d | 2087.6799 | 0 | 0 | 0 | 0 | 2087.6799 | 0 | 100% | Finished | 2087.6799 | 2087.6799 | 100 | 100 | 100 | 100 | 100 | 100
20 | schilderen automatische deuren | 2014-03-18 08:00 | 2014-03-31 17:00 | 10d | Employee D | 0 | 0 | 32.62 | 2609.5999 | 2609.5999 | 2014-03-18 08:00 | 5d | 1304.8 | 0 | 0 | 0 | 0 | 1304.8 | 0 | 100% | Finished | 2609.5999 | 2609.5999 | 100 | 50 | 100 | 100 | 50 | 100
29 | renovatie toiletten VOO +1 | 2014-04-14 08:00 | 2014-04-30 17:00 | 13d |  |  | 0 |  |  | 3914.3999 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
23 | aanpassing verlichting | 2014-04-14 08:00 | 2014-04-14 17:00 | 1d | Employee H | 0 | 0 | 32.62 | 260.96 | 260.96 |  | 0 | 0 | 260.96 | 1d | 0 | 0 | 0 | 260.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | afbraak bestaande plafonds | 2014-04-14 08:00 | 2014-04-14 17:00 | 1d | Employee H;Employee I | 0 | 0 | 32.62 | 260.96 | 260.96 |  | 0 | 0 | 260.96 | 1d | 0 | 0 | 0 | 260.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | demontage elec uit bestaande plafonds | 2014-04-14 08:00 | 2014-04-14 17:00 | 1d | Employee K;Employee J | 0 | 0 | 32.62 | 260.96 | 260.96 |  | 0 | 0 | 260.96 | 1d | 0 | 0 | 0 | 260.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | opbouw nieuw vals plafond | 2014-04-15 08:00 | 2014-04-17 17:00 | 3d | Employee I;Employee H | 0 | 0 | 32.62 | 782.88 | 782.88 |  | 0 | 0 | 782.88 | 3d | 0 | 0 | 0 | 782.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | schilderwerken | 2014-04-22 08:00 | 2014-04-30 17:00 | 7d | Employee B | 0 | 0 | 32.62 | 1826.7199 | 1826.7199 |  | 0 | 0 | 1826.7199 | 7d | 0 | 0 | 0 | 1826.7199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | herstelling bestaand vals plafond in toiletten | 2014-04-18 08:00 | 2014-04-21 17:00 | 2d | Employee I;Employee H | 0 | 0 | 32.62 | 521.92 | 521.92 |  | 0 | 0 | 521.92 | 2d | 0 | 0 | 0 | 521.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2014-05-13 18:00 |  | TP Name | Tracking 5
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Station Antwerp | 2014-01-27 08:00 | 2014-04-30 17:00 | 68d |  |  | 0 |  |  | 22703.5193 |  | 78d | [5 empty] | 23779.9792 |  | 90.95% |  | 20647.887 | 22703.5193
3 | zaal Andries | 2014-01-27 08:00 | 2014-03-19 17:00 | 38d |  |  | 0 |  |  | 4958.2398 |  | 34d | [5 empty] | 6263.0398 |  | 100% |  | 4958.2398 | 4958.2398
1 | schilderen traphal zaal Andries | 2014-01-27 08:00 | 2014-02-13 17:00 | 14d | Employee B;Employee C;Employee A | 0 | 0 | 32.62 | 3653.4399 | 3653.4399 | 2014-01-27 08:00 | 23d | 6002.0798 | 0 | 0 | 0 | 0 | 6002.0798 | 0 | 100% | Finished | 3653.4399 | 3653.4399 | 100 | 164.2857 | 100 | 100 | 164.2857 | 100
2 | trapje naar beneden schilderen | 2014-03-13 08:00 | 2014-03-19 17:00 | 5d | Employee B | 0 | 0 | 32.62 | 1304.8 | 1304.8 | 2014-03-13 08:00 | 1d | 260.96 | 0 | 0 | 0 | 0 | 260.96 | 0 | 100% | Finished | 1304.8 | 1304.8 | 100 | 20 | 100 | 100 | 20 | 100
10 | aanpassing magazijn B-MO niv. +0 | 2014-02-03 08:00 | 2014-02-14 17:00 | 10d |  |  | 0 |  |  | 3131.5199 |  | 26d | [5 empty] | 5741.1198 |  | 100% |  | 3131.5199 | 3131.5199
6 | schilderwerken | 2014-02-03 08:00 | 2014-02-14 17:00 | 10d |  |  | 0 |  |  | 2609.5999 |  | 13d 4h | [5 empty] | 3131.5199 |  | 100% |  | 2609.5999 | 2609.5999
4 | schilderwerken - deel 1 | 2014-02-03 08:00 | 2014-02-07 17:00 | 5d | Employee D | 0 | 0 | 32.62 | 1304.8 | 1304.8 | 2014-01-30 08:00 | 7d | 1826.7199 | 0 | 0 | 0 | 0 | 1826.7199 | 0 | 100% | Finished | 1304.8 | 1304.8 | 100 | 140 | 100 | 100 | 140 | 100
5 | schilderwerken - deel 2 | 2014-02-10 08:00 | 2014-02-14 17:00 | 5d | Employee D | 0 | 0 | 32.62 | 1304.8 | 1304.8 | 2014-02-11 13:00 | 5d | 1304.8 | 0 | 0 | 0 | 0 | 1304.8 | 0 | 100% | Finished | 1304.8 | 1304.8 | 100 | 100 | 100 | 100 | 100 | 100
9 | overige werken | 2014-02-12 08:00 | 2014-02-14 17:00 | 3d |  |  | 0 |  |  | 521.92 |  | 15d | [5 empty] | 2609.5999 |  | 100% |  | 521.92 | 521.92
7 | plaatsing boiler | 2014-02-12 08:00 | 2014-02-12 17:00 | 1d | Employee E;Employee F | 0 | 0 | 32.62 | 260.96 | 260.96 | 2014-02-24 08:00 | 9d | 2348.6399 | 0 | 0 | 0 | 0 | 2348.6399 | 0 | 100% | Finished | 260.96 | 260.96 | 100 | 900 | 100 | 100 | 900 | 100
8 | verplaatsen deurstop | 2014-02-14 08:00 | 2014-02-14 17:00 | 1d | Employee G | 0 | 0 | 32.62 | 260.96 | 260.96 | 2014-02-14 08:00 | 1d | 260.96 | 0 | 0 | 0 | 0 | 260.96 | 0 | 100% | Finished | 260.96 | 260.96 | 100 | 100 | 100 | 100 | 100 | 100
12 | travel center | 2014-02-17 08:00 | 2014-03-03 17:00 | 11d |  |  | 0 |  |  | 2870.5599 |  | 10d | [5 empty] | 2609.5999 |  | 100% |  | 2870.5599 | 2870.5599
11 | travel center - vernieuwen urinoirs | 2014-02-17 08:00 | 2014-03-03 17:00 | 11d | Employee E;Employee F | 0 | 0 | 32.62 | 2870.5599 | 2870.5599 | 2014-03-10 08:00 | 10d | 2609.5999 | 0 | 0 | 0 | 0 | 2609.5999 | 0 | 100% | Finished | 2870.5599 | 2870.5599 | 100 | 90.9091 | 100 | 100 | 90.9091 | 100
14 | herstellingswerken restaurant | 2014-03-10 08:00 | 2014-03-12 17:00 | 3d |  |  | 0 |  |  | 782.88 |  | 3d | [5 empty] | 782.88 |  | 100% |  | 782.88 | 782.88
13 | schilderen radiatoren | 2014-03-10 08:00 | 2014-03-12 17:00 | 3d | Employee B | 0 | 0 | 32.62 | 782.88 | 782.88 | 2014-03-10 08:00 | 3d | 782.88 | 0 | 0 | 0 | 0 | 782.88 | 0 | 100% | Finished | 782.88 | 782.88 | 100 | 100 | 100 | 100 | 100 | 100
16 | portiersloge | 2014-03-11 08:00 | 2014-03-14 17:00 | 4d |  |  | 0 |  |  | 1043.84 |  | 5d | [5 empty] | 1304.8 |  | 100% |  | 1043.84 | 1043.84
15 | schilderwerken portiersloge | 2014-03-11 08:00 | 2014-03-14 17:00 | 4d | Employee D | 0 | 0 | 32.62 | 1043.84 | 1043.84 | 2014-03-11 08:00 | 5d | 1304.8 | 0 | 0 | 0 | 0 | 1304.8 | 0 | 100% | Finished | 1043.84 | 1043.84 | 100 | 125 | 100 | 100 | 125 | 100
22 | lok. 211 | 2014-03-17 08:00 | 2014-03-31 17:00 | 11d |  |  | 0 |  |  | 6002.0798 |  | 8d | [5 empty] | 5219.1998 |  | 100% |  | 6002.0798 | 6002.0798
21 | schilderen lok. 211 | 2014-03-17 08:00 | 2014-03-21 17:00 | 5d | Employee D | 0 | 0 | 32.62 | 1304.8 | 1304.8 | 2014-03-17 08:00 | 7d | 1826.7199 | 0 | 0 | 0 | 0 | 1826.7199 | 0 | 100% | Finished | 1304.8 | 1304.8 | 100 | 140 | 100 | 100 | 140 | 100
19 | herstelling schilderwerk | 2014-03-17 08:00 | 2014-03-26 17:00 | 8d | Employee B | 0 | 0 | 32.62 | 2087.6799 | 2087.6799 | 2014-03-17 08:00 | 8d | 2087.6799 | 0 | 0 | 0 | 0 | 2087.6799 | 0 | 100% | Finished | 2087.6799 | 2087.6799 | 100 | 100 | 100 | 100 | 100 | 100
20 | schilderen automatische deuren | 2014-03-18 08:00 | 2014-03-31 17:00 | 10d | Employee D | 0 | 0 | 32.62 | 2609.5999 | 2609.5999 | 2014-03-18 08:00 | 5d | 1304.8 | 0 | 0 | 0 | 0 | 1304.8 | 0 | 100% | Finished | 2609.5999 | 2609.5999 | 100 | 50 | 100 | 100 | 50 | 100
29 | renovatie toiletten VOO +1 | 2014-04-14 08:00 | 2014-04-30 17:00 | 13d |  |  | 0 |  |  | 3914.3999 |  | 7d | [5 empty] | 1859.3399 |  | 47.49% |  | 1858.7677 | 3914.3999
23 | aanpassing verlichting | 2014-04-14 08:00 | 2014-04-14 17:00 | 1d | Employee H | 0 | 0 | 32.62 | 260.96 | 260.96 |  | 0 | 0 | 260.96 | 1d | 0 | 0 | 0 | 260.96 | 0% | Not Started | 0 | 260.96 | 100 |  | 0 | 100 |  | 0
24 | afbraak bestaande plafonds | 2014-04-14 08:00 | 2014-04-14 17:00 | 1d | Employee H;Employee I | 0 | 0 | 32.62 | 260.96 | 260.96 | 2014-05-06 08:00 | 1d | 260.96 | 0 | 0 | 0 | 0 | 260.96 | 0 | 100% | Finished | 260.96 | 260.96 | 100 | 100 | 100 | 100 | 100 | 100
25 | demontage elec uit bestaande plafonds | 2014-04-14 08:00 | 2014-04-14 17:00 | 1d | Employee K;Employee J | 0 | 0 | 32.62 | 260.96 | 260.96 | 2014-05-06 08:00 | 1d | 260.96 | 0 | 0 | 0 | 0 | 260.96 | 0 | 100% | Finished | 260.96 | 260.96 | 100 | 100 | 100 | 100 | 100 | 100
26 | opbouw nieuw vals plafond | 2014-04-15 08:00 | 2014-04-17 17:00 | 3d | Employee I;Employee H | 0 | 0 | 32.62 | 782.88 | 782.88 | 2014-05-07 08:00 | 3d | 782.88 | 0 | 0 | 0 | 0 | 782.88 | 0 | 100% | Finished | 782.88 | 782.88 | 100 | 100 | 100 | 100 | 100 | 100
27 | schilderwerken | 2014-04-22 08:00 | 2014-04-30 17:00 | 7d | Employee B | 0 | 0 | 32.62 | 1826.7199 | 1826.7199 | 2014-05-09 08:00 | 1h | 32.62 | 1826.7199 | 7d | 0 | 0 | 32.62 | 1826.7199 | 1.754% | Started | 32.0477 | 1826.7199 | 100 | 1.7857 | 1.7544 | 100 | 1.7857 | 1.7544
28 | herstelling bestaand vals plafond in toiletten | 2014-04-18 08:00 | 2014-04-21 17:00 | 2d | Employee I;Employee H | 0 | 0 | 32.62 | 521.92 | 521.92 | 2014-05-13 08:00 | 2d | 521.92 | 0 | 0 | 0 | 0 | 521.92 | 0 | 100% | Finished | 521.92 | 521.92 | 100 | 100 | 100 | 100 | 100 | 100

## TP6
| TP Status Date | 2014-05-20 18:00 |  | TP Name | Closure
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Station Antwerp | 2014-01-27 08:00 | 2014-04-30 17:00 | 68d |  |  | 0 |  |  | 22703.5193 |  | 81d | [5 empty] | 25313.1192 |  | 100% |  | 22703.5193 | 22703.5193
3 | zaal Andries | 2014-01-27 08:00 | 2014-03-19 17:00 | 38d |  |  | 0 |  |  | 4958.2398 |  | 34d | [5 empty] | 6263.0398 |  | 100% |  | 4958.2398 | 4958.2398
1 | schilderen traphal zaal Andries | 2014-01-27 08:00 | 2014-02-13 17:00 | 14d | Employee B;Employee C;Employee A | 0 | 0 | 32.62 | 3653.4399 | 3653.4399 | 2014-01-27 08:00 | 23d | 6002.0798 | 0 | 0 | 0 | 0 | 6002.0798 | 0 | 100% | Finished | 3653.4399 | 3653.4399 | 100 | 164.2857 | 100 | 100 | 164.2857 | 100
2 | trapje naar beneden schilderen | 2014-03-13 08:00 | 2014-03-19 17:00 | 5d | Employee B | 0 | 0 | 32.62 | 1304.8 | 1304.8 | 2014-03-13 08:00 | 1d | 260.96 | 0 | 0 | 0 | 0 | 260.96 | 0 | 100% | Finished | 1304.8 | 1304.8 | 100 | 20 | 100 | 100 | 20 | 100
10 | aanpassing magazijn B-MO niv. +0 | 2014-02-03 08:00 | 2014-02-14 17:00 | 10d |  |  | 0 |  |  | 3131.5199 |  | 26d | [5 empty] | 5741.1198 |  | 100% |  | 3131.5199 | 3131.5199
6 | schilderwerken | 2014-02-03 08:00 | 2014-02-14 17:00 | 10d |  |  | 0 |  |  | 2609.5999 |  | 13d 4h | [5 empty] | 3131.5199 |  | 100% |  | 2609.5999 | 2609.5999
4 | schilderwerken - deel 1 | 2014-02-03 08:00 | 2014-02-07 17:00 | 5d | Employee D | 0 | 0 | 32.62 | 1304.8 | 1304.8 | 2014-01-30 08:00 | 7d | 1826.7199 | 0 | 0 | 0 | 0 | 1826.7199 | 0 | 100% | Finished | 1304.8 | 1304.8 | 100 | 140 | 100 | 100 | 140 | 100
5 | schilderwerken - deel 2 | 2014-02-10 08:00 | 2014-02-14 17:00 | 5d | Employee D | 0 | 0 | 32.62 | 1304.8 | 1304.8 | 2014-02-11 13:00 | 5d | 1304.8 | 0 | 0 | 0 | 0 | 1304.8 | 0 | 100% | Finished | 1304.8 | 1304.8 | 100 | 100 | 100 | 100 | 100 | 100
9 | overige werken | 2014-02-12 08:00 | 2014-02-14 17:00 | 3d |  |  | 0 |  |  | 521.92 |  | 15d | [5 empty] | 2609.5999 |  | 100% |  | 521.92 | 521.92
7 | plaatsing boiler | 2014-02-12 08:00 | 2014-02-12 17:00 | 1d | Employee E;Employee F | 0 | 0 | 32.62 | 260.96 | 260.96 | 2014-02-24 08:00 | 9d | 2348.6399 | 0 | 0 | 0 | 0 | 2348.6399 | 0 | 100% | Finished | 260.96 | 260.96 | 100 | 900 | 100 | 100 | 900 | 100
8 | verplaatsen deurstop | 2014-02-14 08:00 | 2014-02-14 17:00 | 1d | Employee G | 0 | 0 | 32.62 | 260.96 | 260.96 | 2014-02-14 08:00 | 1d | 260.96 | 0 | 0 | 0 | 0 | 260.96 | 0 | 100% | Finished | 260.96 | 260.96 | 100 | 100 | 100 | 100 | 100 | 100
12 | travel center | 2014-02-17 08:00 | 2014-03-03 17:00 | 11d |  |  | 0 |  |  | 2870.5599 |  | 10d | [5 empty] | 2609.5999 |  | 100% |  | 2870.5599 | 2870.5599
11 | travel center - vernieuwen urinoirs | 2014-02-17 08:00 | 2014-03-03 17:00 | 11d | Employee E;Employee F | 0 | 0 | 32.62 | 2870.5599 | 2870.5599 | 2014-03-10 08:00 | 10d | 2609.5999 | 0 | 0 | 0 | 0 | 2609.5999 | 0 | 100% | Finished | 2870.5599 | 2870.5599 | 100 | 90.9091 | 100 | 100 | 90.9091 | 100
14 | herstellingswerken restaurant | 2014-03-10 08:00 | 2014-03-12 17:00 | 3d |  |  | 0 |  |  | 782.88 |  | 3d | [5 empty] | 782.88 |  | 100% |  | 782.88 | 782.88
13 | schilderen radiatoren | 2014-03-10 08:00 | 2014-03-12 17:00 | 3d | Employee B | 0 | 0 | 32.62 | 782.88 | 782.88 | 2014-03-10 08:00 | 3d | 782.88 | 0 | 0 | 0 | 0 | 782.88 | 0 | 100% | Finished | 782.88 | 782.88 | 100 | 100 | 100 | 100 | 100 | 100
16 | portiersloge | 2014-03-11 08:00 | 2014-03-14 17:00 | 4d |  |  | 0 |  |  | 1043.84 |  | 5d | [5 empty] | 1304.8 |  | 100% |  | 1043.84 | 1043.84
15 | schilderwerken portiersloge | 2014-03-11 08:00 | 2014-03-14 17:00 | 4d | Employee D | 0 | 0 | 32.62 | 1043.84 | 1043.84 | 2014-03-11 08:00 | 5d | 1304.8 | 0 | 0 | 0 | 0 | 1304.8 | 0 | 100% | Finished | 1043.84 | 1043.84 | 100 | 125 | 100 | 100 | 125 | 100
22 | lok. 211 | 2014-03-17 08:00 | 2014-03-31 17:00 | 11d |  |  | 0 |  |  | 6002.0798 |  | 8d | [5 empty] | 5219.1998 |  | 100% |  | 6002.0798 | 6002.0798
21 | schilderen lok. 211 | 2014-03-17 08:00 | 2014-03-21 17:00 | 5d | Employee D | 0 | 0 | 32.62 | 1304.8 | 1304.8 | 2014-03-17 08:00 | 7d | 1826.7199 | 0 | 0 | 0 | 0 | 1826.7199 | 0 | 100% | Finished | 1304.8 | 1304.8 | 100 | 140 | 100 | 100 | 140 | 100
19 | herstelling schilderwerk | 2014-03-17 08:00 | 2014-03-26 17:00 | 8d | Employee B | 0 | 0 | 32.62 | 2087.6799 | 2087.6799 | 2014-03-17 08:00 | 8d | 2087.6799 | 0 | 0 | 0 | 0 | 2087.6799 | 0 | 100% | Finished | 2087.6799 | 2087.6799 | 100 | 100 | 100 | 100 | 100 | 100
20 | schilderen automatische deuren | 2014-03-18 08:00 | 2014-03-31 17:00 | 10d | Employee D | 0 | 0 | 32.62 | 2609.5999 | 2609.5999 | 2014-03-18 08:00 | 5d | 1304.8 | 0 | 0 | 0 | 0 | 1304.8 | 0 | 100% | Finished | 2609.5999 | 2609.5999 | 100 | 50 | 100 | 100 | 50 | 100
29 | renovatie toiletten VOO +1 | 2014-04-14 08:00 | 2014-04-30 17:00 | 13d |  |  | 0 |  |  | 3914.3999 |  | 10d | [5 empty] | 3392.4799 |  | 100% |  | 3914.3999 | 3914.3999
23 | aanpassing verlichting | 2014-04-14 08:00 | 2014-04-14 17:00 | 1d | Employee H | 0 | 0 | 32.62 | 260.96 | 260.96 | 2014-05-19 08:00 | 1d | 260.96 | 0 | 0 | 0 | 0 | 260.96 | 0 | 100% | Finished | 260.96 | 260.96 | 100 | 100 | 100 | 100 | 100 | 100
24 | afbraak bestaande plafonds | 2014-04-14 08:00 | 2014-04-14 17:00 | 1d | Employee H;Employee I | 0 | 0 | 32.62 | 260.96 | 260.96 | 2014-05-06 08:00 | 1d | 260.96 | 0 | 0 | 0 | 0 | 260.96 | 0 | 100% | Finished | 260.96 | 260.96 | 100 | 100 | 100 | 100 | 100 | 100
25 | demontage elec uit bestaande plafonds | 2014-04-14 08:00 | 2014-04-14 17:00 | 1d | Employee K;Employee J | 0 | 0 | 32.62 | 260.96 | 260.96 | 2014-05-06 08:00 | 1d | 260.96 | 0 | 0 | 0 | 0 | 260.96 | 0 | 100% | Finished | 260.96 | 260.96 | 100 | 100 | 100 | 100 | 100 | 100
26 | opbouw nieuw vals plafond | 2014-04-15 08:00 | 2014-04-17 17:00 | 3d | Employee I;Employee H | 0 | 0 | 32.62 | 782.88 | 782.88 | 2014-05-07 08:00 | 3d | 782.88 | 0 | 0 | 0 | 0 | 782.88 | 0 | 100% | Finished | 782.88 | 782.88 | 100 | 100 | 100 | 100 | 100 | 100
27 | schilderwerken | 2014-04-22 08:00 | 2014-04-30 17:00 | 7d | Employee B | 0 | 0 | 32.62 | 1826.7199 | 1826.7199 | 2014-05-09 08:00 | 5d | 1304.8 | 0 | 0 | 0 | 0 | 1304.8 | 0 | 100% | Finished | 1826.7199 | 1826.7199 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
28 | herstelling bestaand vals plafond in toiletten | 2014-04-18 08:00 | 2014-04-21 17:00 | 2d | Employee I;Employee H | 0 | 0 | 32.62 | 521.92 | 521.92 | 2014-05-13 08:00 | 2d | 521.92 | 0 | 0 | 0 | 0 | 521.92 | 0 | 100% | Finished | 521.92 | 521.92 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking 1 | 2014-01-27 08:00 | 2014-02-10 18:00 | 4436.3199 | 3716.0704 | 5219.1998 | 2014-02-07 12:00 | -720.2495 | 83.76% | -1503.1295 | 71.2% | -1d 4h | 86.36% | 98.14% | 2014-05-05 09:00 | 2014-05-20 09:00 | 2014-07-03 17:00 | 2014-05-02 15:00 | 2014-05-20 09:00 | 2014-06-27 14:00 | 2014-05-02 12:00 | 2014-05-15 15:00 | 2014-06-24 09:00 | 24206.6487 | 31886.9644 | 27886.7997 | 27204.667 | 37055.7157 | 36097.6641 | 30977.8361 | 30797.4713 | 0.86364 | 0.712 | 0.83765 | 0.98143 | -1.5 | 0.712 | 1 | 0.86364 | 1
Tracking 2 | 2014-02-10 18:00 | 2014-02-24 18:00 | 8350.7197 | 6011.7451 | 9655.5197 | 2014-02-13 12:00 | -2338.9746 | 71.99% | -3643.7746 | 62.26% | -7d 4h | 64.29% | 89.29% | 2014-05-09 17:00 | 2014-06-06 12:00 | 2014-08-26 15:00 | 2014-05-08 16:00 | 2014-06-06 12:00 | 2014-08-07 17:00 | 2014-05-12 12:00 | 2014-06-23 15:00 | 2014-09-03 09:00 | 26347.2938 | 36464.3333 | 32841.5207 | 35620.5017 | 46894.7715 | 51358.1187 | 35651.9451 | 36291.2076 | 0.64286 | 0.62262 | 0.71991 | 0.89291 | -7.5 | 0.62262 | 1 | 0.64286 | 1
Tracking 3 | 2014-02-24 18:00 | 2014-03-10 18:00 | 9916.4797 | 7364.8709 | 12265.1196 | 2014-02-19 09:00 | -2551.6088 | 74.27% | -4900.2487 | 60.05% | -13d 7h | 55.24% | 96.79% | 2014-05-12 14:00 | 2014-06-03 12:00 | 2014-08-27 12:00 | 2014-05-12 17:00 | 2014-06-03 12:00 | 2014-07-29 16:00 | 2014-05-20 16:00 | 2014-07-17 09:00 | 2014-10-10 11:00 | 27603.768 | 37809.4041 | 32917.9453 | 40031.432 | 46659.3923 | 58505.8681 | 36654.1349 | 38224.8957 | 0.55242 | 0.60047 | 0.74269 | 0.9679 | -13.875 | 0.60047 | 1 | 0.55242 | 1
Tracking 4 | 2014-03-10 18:00 | 2014-03-31 18:00 | 18789.1194 | 18789.1194 | 21920.6393 | 2014-03-31 17:00 | 0 | 100% | -3131.5199 | 85.71% | 0 | 100% | 100% | 2014-04-30 17:00 | 2014-04-30 17:00 | 2014-05-16 11:00 | 2014-04-30 17:00 | 2014-04-30 17:00 | 2014-05-06 14:00 | 2014-04-30 17:00 | 2014-04-30 17:00 | 2014-05-06 14:00 | 25835.0392 | 26487.4391 | 25835.0392 | 25835.0392 | 26487.4391 | 26487.4391 | 26340.123 | 26340.123 | 1 | 0.85714 | 1 | 1 | 0 | 0.85714 | 1 | 1 | 1
Tracking 5 | 2014-03-31 18:00 | 2014-05-13 18:00 | 22703.5193 | 20647.887 | 23779.9792 | 2014-04-18 17:00 | -2055.6322 | 90.95% | -3132.0922 | 86.83% | -17d | 77.92% | 98.73% | 2014-05-09 09:00 | 2014-05-09 15:00 | 2014-05-27 09:00 | 2014-05-22 17:00 | 2014-05-23 14:00 | 2014-05-26 16:00 | 2014-05-23 17:00 | 2014-05-28 10:00 | 2014-05-29 16:00 | 25835.6114 | 26147.4317 | 26040.2631 | 26418.0406 | 26383.1271 | 26818.2099 | 26125.1926 | 26197.0191 | 0.77922 | 0.86829 | 0.90946 | 0.98734 | -17 | 0.86829 | 1 | 0.77922 | 1
Closure | 2014-05-13 18:00 | 2014-05-20 18:00 | 22703.5193 | 22703.5193 | 25313.1192 | 2014-04-30 17:00 | 0 | 100% | -2609.5999 | 89.69% | -14d | 82.93% | 100% | 2014-04-30 17:00 | 2014-04-30 17:00 | 2014-05-12 16:00 | 2014-05-20 17:00 | 2014-05-20 17:00 | 2014-05-20 17:00 | 2014-05-20 17:00 | 2014-05-20 17:00 | 2014-05-20 17:00 | 25313.1192 | 25313.1192 | 25313.1192 | 25313.1192 | 25313.1192 | 25313.1192 | 25313.1192 | 25313.1192 | 0.82927 | 0.89691 | 1 | 1 | -14 | 0.89691 | 1 | 0.82927 | 1