## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Website Tennis Vlaanderen | 1 |  |  | 2013-05-24 08:00 | 2014-02-28 17:00 | 201d |  |  | 0 |  |  | 219275 | 280.375
28 | aanvang | 1.1 |  |  | 2013-05-24 13:00 | 2013-07-11 17:00 | 34d 4h |  |  | 0 |  |  | 32100 | 48.1667
1 | start implementatie project | 1.1.1 |  |  | 2013-06-11 08:00 | 2013-06-12 12:00 | 1d 4h | developer | 1050 | 0 | 0 | 0 | 1050 | 1.1667
2 | project management plan inclusief acceptatiecriteria | 1.1.2 |  |  | 2013-05-24 13:00 | 2013-07-11 17:00 | 34d 4h | project manager | 31050 | 0 | 0 | 0 | 31050 | 48.1667
29 | detaillering | 1.2 |  |  | 2013-05-24 08:00 | 2013-09-17 17:00 | 83d |  |  | 0 |  |  | 42800 | 116.375
3 | start functionele analyse/wireframes | 1.2.1 |  | FS5 | 2013-05-24 08:00 | 2013-06-12 17:00 | 14d | senior consultant | 11200 | 0 | 0 | 0 | 11200 | 19.375
4 | deliverable wireframes Amplexor | 1.2.2 |  | FS8 | 2013-07-16 08:00 | 2013-08-19 17:00 | 25d | senior consultant | 20000 | 0 | 0 | 0 | 20000 | 34.375
5 | functioneel & technisch ontwerp | 1.2.3 | 8SF;3FS |  | 2013-08-12 13:00 | 2013-08-30 17:00 | 14d 4h | senior consultant | 11600 | 0 | 0 | 0 | 11600 | 18.1667
6 | volledige oplevering HIG | 1.2.4 |  |  | 2013-09-17 17:00 | 2013-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
35 | bouw | 1.3 |  |  | 2013-08-07 08:00 | 2014-02-28 17:00 | 148d |  |  | 0 |  |  | 144375 | 205.375
7 | installatie en algemene opzet | 1.3.1 |  |  | 2013-08-07 08:00 | 2013-08-23 17:00 | 13d | senior developer | 9750 | 0 | 0 | 0 | 9750 | 16.375
30 | sprints naar release 1 | 1.3.2 |  |  | 2013-08-29 08:00 | 2013-10-30 17:00 | 45d |  |  | 0 |  |  | 63000 | 62.375
8 | WCM-luik: search, inloggen, infotheek, basisrechten, ... | 1.3.2.1 | 4FS | FS9;SF5 | 2013-08-29 08:00 | 2013-10-30 17:00 | 45d | developer;extra developer | 63000 | 0 | 0 | 0 | 63000 | 62.375
31 | transitie (tussentijds) | 1.3.3 |  |  | 2013-10-31 08:00 | 2014-01-17 17:00 | 57d |  |  | 0 |  |  | 8625 | 78.375
9 | deploy 1 naar ACC-omgeving | 1.3.3.1 | 8FS | FS10 | 2013-10-31 08:00 | 2013-10-31 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 | 0.375
10 | deploy 2 naar ACC-omgeving | 1.3.3.2 | 9FS | FS11 | 2013-11-25 08:00 | 2013-11-25 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 | 0.375
11 | rework | 1.3.3.3 | 10FS |  | 2013-12-06 08:00 | 2013-12-12 12:00 | 4d 4h | developer | 3150 | 0 | 0 | 0 | 3150 | 6.1667
12 | deploy 3 naar ACC-omgeving | 1.3.3.4 |  | FS14 | 2013-12-17 08:00 | 2013-12-17 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 | 0.375
13 | acceptatie release 1 - einde testfase | 1.3.3.5 |  | FS20 | 2014-01-16 17:00 | 2014-01-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
14 | deploy 4 naar ACC-omgeving | 1.3.3.6 | 12FS | FS19 | 2014-01-13 08:00 | 2014-01-17 12:00 | 4d 4h | senior developer | 3375 | 0 | 0 | 0 | 3375 | 4.1667
15 | installatie PROD-server | 1.3.3.7 |  |  | 2014-01-16 17:00 | 2014-01-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
16 | start authoring door klant (alleen site) | 1.3.3.8 |  |  | 2014-01-17 17:00 | 2014-01-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
32 | vervollediging naar release voor go live | 1.3.4 |  |  | 2014-01-17 08:00 | 2014-01-31 17:00 | 11d |  |  | 0 |  |  | 2150 | 14.375
17 | productie installed, deploy 4 ook naar PROD-omgeving | 1.3.4.1 |  | FS18 | 2014-01-17 08:00 | 2014-01-17 17:00 | 1d | senior developer | 750 | 0 | 0 | 0 | 750 | 0.375
18 | bugfixing + 'profielbeheer aanmaken' | 1.3.4.2 | 17FS |  | 2014-01-31 08:00 | 2014-01-31 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 | 0.375
19 | deploy 5 naar ACC | 1.3.4.3 | 14FS | FS22 | 2014-01-31 08:00 | 2014-01-31 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 | 0.375
20 | release januari | 1.3.4.4 | 13FS |  | 2014-01-30 17:00 | 2014-01-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
33 | sprints naar release after go live | 1.3.5 |  |  | 2013-12-16 08:00 | 2014-02-28 17:00 | 55d |  |  | 0 |  |  | 60850 | 74.375
21 | ontwikkeling release 2 | 1.3.5.1 |  | FS23 | 2014-01-22 08:00 | 2014-02-27 17:00 | 27d | developer | 18900 | 0 | 0 | 0 | 18900 | 36.375
22 | extra deploy (CR1) | 1.3.5.2 | 19FS | FS26 | 2014-02-27 08:00 | 2014-02-27 17:00 | 1d | senior developer | 750 | 0 | 0 | 0 | 750 | 0.375
23 | release februari | 1.3.5.3 | 21FS |  | 2014-02-27 17:00 | 2014-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
24 | testfase | 1.3.5.4 |  |  | 2013-12-16 08:00 | 2014-01-17 17:00 | 25d | senior developer | 18750 | 0 | 0 | 0 | 18750 | 32.375
25 | rework | 1.3.5.5 |  |  | 2013-12-17 08:00 | 2014-01-24 17:00 | 29d | senior developer | 21750 | 0 | 0 | 0 | 21750 | 38.375
26 | deploy 6 naar PROD-omgeving | 1.3.5.6 | 22FS |  | 2014-02-28 08:00 | 2014-02-28 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 | 0.375
37 | productie | 1.4 |  |  | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  |  | 0 |  |  | 0
36 | uiterste deadline - officiële voorstelling | 1.4.1 |  |  | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | senior consultant | Renewable | 1 | 0 | 100 | 3;4;5; | 42800
2 | senior developer | Renewable | 1 | 0 | 93.75 | 7;14;17;22;24;25; | 55125
3 | developer | Renewable | 1 | 0 | 87.5 | 1;8;9;10;11;12;18;19;21;26; | 58800
4 | project manager | Renewable | 1 | 0 | 112.5 | 2; | 31050
5 | extra developer | Renewable | 1 | 0 | 87.5 | 8; | 31500

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Website Tennis Vlaanderen | 1608h |  |  |  |  | 99 | 100 | 101
28 | aanvang | 276h |  |  |  |  | 99 | 100 | 101
1 | start implementatie project | 12h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | project management plan inclusief acceptatiecriteria | 276h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | detaillering | 664h |  |  |  |  | 99 | 100 | 101
3 | start functionele analyse/wireframes | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | deliverable wireframes Amplexor | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | functioneel & technisch ontwerp | 116h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | volledige oplevering HIG | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | bouw | 1184h |  |  |  |  | 99 | 100 | 101
7 | installatie en algemene opzet | 104h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | sprints naar release 1 | 360h |  |  |  |  | 99 | 100 | 101
8 | WCM-luik: search, inloggen, infotheek, basisrechten, ... | 360h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | transitie (tussentijds) | 456h |  |  |  |  | 99 | 100 | 101
9 | deploy 1 naar ACC-omgeving | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | deploy 2 naar ACC-omgeving | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | rework | 36h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | deploy 3 naar ACC-omgeving | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | acceptatie release 1 - einde testfase | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | deploy 4 naar ACC-omgeving | 36h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | installatie PROD-server | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | start authoring door klant (alleen site) | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | vervollediging naar release voor go live | 88h |  |  |  |  | 99 | 100 | 101
17 | productie installed, deploy 4 ook naar PROD-omgeving | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | bugfixing + 'profielbeheer aanmaken' | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | deploy 5 naar ACC | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | release januari | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | sprints naar release after go live | 440h |  |  |  |  | 99 | 100 | 101
21 | ontwikkeling release 2 | 216h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | extra deploy (CR1) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | release februari | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | testfase | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | rework | 232h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | deploy 6 naar PROD-omgeving | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | productie | 0 |  |  |  |  | 99 | 100 | 101
36 | uiterste deadline - officiële voorstelling | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2013-07-04 22:00 |  | TP Name | Tracking 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Website Tennis Vlaanderen | 2013-05-24 08:00 | 2014-02-28 17:00 | 201d |  |  | 0 |  |  | 219275 |  | 30d | [5 empty] | 38800 |  | 9.551% |  | 20944 | 38800
28 | aanvang | 2013-05-24 13:00 | 2013-07-11 17:00 | 34d 4h |  |  | 0 |  |  | 32100 |  | 29d 4h | [5 empty] | 27600 |  | 30.36% |  | 9744 | 27600
1 | start implementatie project | 2013-06-11 08:00 | 2013-06-12 12:00 | 1d 4h | developer | 1050 | 0 | 0 | 0 | 1050 | 2013-06-11 08:00 | 1d 4h | 1050 | 0 | 0 | 0 | 0 | 1050 | 0 | 100% | Finished | 1050 | 1050 | 100 | 100 | 100 | 100 | 100 | 100
2 | project management plan inclusief acceptatiecriteria | 2013-05-24 13:00 | 2013-07-11 17:00 | 34d 4h | project manager | 31050 | 0 | 0 | 0 | 31050 | 2013-05-24 13:00 | 29d 4h | 26550 | 13500 | 15d | 0 | 0 | 26550 | 13500 | 28% | Started | 8694 | 26550 | 100 | 85.5072 | 28 | 100 | 85.5072 | 28
29 | detaillering | 2013-05-24 08:00 | 2013-09-17 17:00 | 83d |  |  | 0 |  |  | 42800 |  | 30d | [5 empty] | 11200 |  | 26.17% |  | 11200 | 11200
3 | start functionele analyse/wireframes | 2013-05-24 08:00 | 2013-06-12 17:00 | 14d | senior consultant | 11200 | 0 | 0 | 0 | 11200 | 2013-05-24 08:00 | 14d | 11200 | 0 | 0 | 0 | 0 | 11200 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 100 | 100
4 | deliverable wireframes Amplexor | 2013-07-16 08:00 | 2013-08-19 17:00 | 25d | senior consultant | 20000 | 0 | 0 | 0 | 20000 |  | 0 | 0 | 20000 | 25d | 0 | 0 | 0 | 20000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | functioneel & technisch ontwerp | 2013-08-12 13:00 | 2013-08-30 17:00 | 14d 4h | senior consultant | 11600 | 0 | 0 | 0 | 11600 |  | 0 | 0 | 11600 | 14d 4h | 0 | 0 | 0 | 11600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | volledige oplevering HIG | 2013-09-17 17:00 | 2013-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | bouw | 2013-08-07 08:00 | 2014-02-28 17:00 | 148d |  |  | 0 |  |  | 144375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | installatie en algemene opzet | 2013-08-07 08:00 | 2013-08-23 17:00 | 13d | senior developer | 9750 | 0 | 0 | 0 | 9750 |  | 0 | 0 | 9750 | 13d | 0 | 0 | 0 | 9750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | sprints naar release 1 | 2013-08-29 08:00 | 2013-10-30 17:00 | 45d |  |  | 0 |  |  | 63000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | WCM-luik: search, inloggen, infotheek, basisrechten, ... | 2013-08-29 08:00 | 2013-10-30 17:00 | 45d | developer;extra developer | 63000 | 0 | 0 | 0 | 63000 |  | 0 | 0 | 63000 | 45d | 0 | 0 | 0 | 63000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | transitie (tussentijds) | 2013-10-31 08:00 | 2014-01-17 17:00 | 57d |  |  | 0 |  |  | 8625 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
9 | deploy 1 naar ACC-omgeving | 2013-10-31 08:00 | 2013-10-31 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 |  | 0 | 0 | 700 | 1d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | deploy 2 naar ACC-omgeving | 2013-11-25 08:00 | 2013-11-25 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 |  | 0 | 0 | 700 | 1d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | rework | 2013-12-06 08:00 | 2013-12-12 12:00 | 4d 4h | developer | 3150 | 0 | 0 | 0 | 3150 |  | 0 | 0 | 3150 | 4d 4h | 0 | 0 | 0 | 3150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | deploy 3 naar ACC-omgeving | 2013-12-17 08:00 | 2013-12-17 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 |  | 0 | 0 | 700 | 1d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | acceptatie release 1 - einde testfase | 2014-01-16 17:00 | 2014-01-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | deploy 4 naar ACC-omgeving | 2014-01-13 08:00 | 2014-01-17 12:00 | 4d 4h | senior developer | 3375 | 0 | 0 | 0 | 3375 |  | 0 | 0 | 3375 | 4d 4h | 0 | 0 | 0 | 3375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | installatie PROD-server | 2014-01-16 17:00 | 2014-01-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | start authoring door klant (alleen site) | 2014-01-17 17:00 | 2014-01-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | vervollediging naar release voor go live | 2014-01-17 08:00 | 2014-01-31 17:00 | 11d |  |  | 0 |  |  | 2150 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
17 | productie installed, deploy 4 ook naar PROD-omgeving | 2014-01-17 08:00 | 2014-01-17 17:00 | 1d | senior developer | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | bugfixing + 'profielbeheer aanmaken' | 2014-01-31 08:00 | 2014-01-31 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 |  | 0 | 0 | 700 | 1d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | deploy 5 naar ACC | 2014-01-31 08:00 | 2014-01-31 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 |  | 0 | 0 | 700 | 1d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | release januari | 2014-01-30 17:00 | 2014-01-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | sprints naar release after go live | 2013-12-16 08:00 | 2014-02-28 17:00 | 55d |  |  | 0 |  |  | 60850 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | ontwikkeling release 2 | 2014-01-22 08:00 | 2014-02-27 17:00 | 27d | developer | 18900 | 0 | 0 | 0 | 18900 |  | 0 | 0 | 18900 | 27d | 0 | 0 | 0 | 18900 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | extra deploy (CR1) | 2014-02-27 08:00 | 2014-02-27 17:00 | 1d | senior developer | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | release februari | 2014-02-27 17:00 | 2014-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | testfase | 2013-12-16 08:00 | 2014-01-17 17:00 | 25d | senior developer | 18750 | 0 | 0 | 0 | 18750 |  | 0 | 0 | 18750 | 25d | 0 | 0 | 0 | 18750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | rework | 2013-12-17 08:00 | 2014-01-24 17:00 | 29d | senior developer | 21750 | 0 | 0 | 0 | 21750 |  | 0 | 0 | 21750 | 29d | 0 | 0 | 0 | 21750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | deploy 6 naar PROD-omgeving | 2014-02-28 08:00 | 2014-02-28 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 |  | 0 | 0 | 700 | 1d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | productie | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | uiterste deadline - officiële voorstelling | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2013-10-10 22:00 |  | TP Name | Tracking 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Website Tennis Vlaanderen | 2013-05-24 08:00 | 2014-02-28 17:00 | 201d |  |  | 0 |  |  | 219275 |  | 100d | [5 empty] | 207000 |  | 54.49% |  | 119474.8454 | 128050
28 | aanvang | 2013-05-24 13:00 | 2013-07-11 17:00 | 34d 4h |  |  | 0 |  |  | 32100 |  | 99d 4h | [5 empty] | 91050 |  | 92.83% |  | 29799.9995 | 32100
1 | start implementatie project | 2013-06-11 08:00 | 2013-06-12 12:00 | 1d 4h | developer | 1050 | 0 | 0 | 0 | 1050 | 2013-06-11 08:00 | 1d 4h | 1050 | 0 | 0 | 0 | 0 | 1050 | 0 | 100% | Finished | 1050 | 1050 | 100 | 100 | 100 | 100 | 100 | 100
2 | project management plan inclusief acceptatiecriteria | 2013-05-24 13:00 | 2013-07-11 17:00 | 34d 4h | project manager | 31050 | 0 | 0 | 0 | 31050 | 2013-05-24 13:00 | 100d | 90000 | 7200 | 8d | 0 | 0 | 90000 | 7200 | 92.59% | Started | 28749.9995 | 31050 | 100 | 289.8551 | 92.5926 | 100 | 289.8551 | 92.5926
29 | detaillering | 2013-05-24 08:00 | 2013-09-17 17:00 | 83d |  |  | 0 |  |  | 42800 |  | 100d | [5 empty] | 62800 |  | 87.54% |  | 37468.323 | 42800
3 | start functionele analyse/wireframes | 2013-05-24 08:00 | 2013-06-12 17:00 | 14d | senior consultant | 11200 | 0 | 0 | 0 | 11200 | 2013-05-24 08:00 | 14d | 11200 | 0 | 0 | 0 | 0 | 11200 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 100 | 100
4 | deliverable wireframes Amplexor | 2013-07-16 08:00 | 2013-08-19 17:00 | 25d | senior consultant | 20000 | 0 | 0 | 0 | 20000 | 2013-07-16 08:00 | 21d | 16800 | 0 | 0 | 0 | 0 | 16800 | 0 | 100% | Finished | 20000 | 20000 | 100 | 84 | 100 | 100 | 84 | 100
5 | functioneel & technisch ontwerp | 2013-08-12 13:00 | 2013-08-30 17:00 | 14d 4h | senior consultant | 11600 | 0 | 0 | 0 | 11600 | 2013-08-12 13:00 | 43d 4h | 34800 | 29600 | 37d | 0 | 0 | 34800 | 29600 | 54.04% | Started | 6268.323 | 11600 | 100 | 300 | 54.0373 | 100 | 300 | 54.0373
6 | volledige oplevering HIG | 2013-09-17 17:00 | 2013-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-09-18 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
35 | bouw | 2013-08-07 08:00 | 2014-02-28 17:00 | 148d |  |  | 0 |  |  | 144375 |  | 47d | [5 empty] | 53150 |  | 36.16% |  | 52206.5229 | 53150
7 | installatie en algemene opzet | 2013-08-07 08:00 | 2013-08-23 17:00 | 13d | senior developer | 9750 | 0 | 0 | 0 | 9750 | 2013-08-07 08:00 | 13d | 9750 | 0 | 0 | 0 | 0 | 9750 | 0 | 100% | Finished | 9750 | 9750 | 100 | 100 | 100 | 100 | 100 | 100
30 | sprints naar release 1 | 2013-08-29 08:00 | 2013-10-30 17:00 | 45d |  |  | 0 |  |  | 63000 |  | 31d | [5 empty] | 43400 |  | 67.39% |  | 42456.5229 | 43400
8 | WCM-luik: search, inloggen, infotheek, basisrechten, ... | 2013-08-29 08:00 | 2013-10-30 17:00 | 45d | developer;extra developer | 63000 | 0 | 0 | 0 | 63000 | 2013-08-29 08:00 | 31d | 43400 | 21000 | 15d | 0 | 0 | 43400 | 21000 | 67.39% | Started | 42456.5229 | 43400 | 100 | 68.8889 | 67.3913 | 100 | 68.8889 | 67.3913
31 | transitie (tussentijds) | 2013-10-31 08:00 | 2014-01-17 17:00 | 57d |  |  | 0 |  |  | 8625 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
9 | deploy 1 naar ACC-omgeving | 2013-10-31 08:00 | 2013-10-31 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 |  | 0 | 0 | 700 | 1d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | deploy 2 naar ACC-omgeving | 2013-11-25 08:00 | 2013-11-25 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 |  | 0 | 0 | 700 | 1d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | rework | 2013-12-06 08:00 | 2013-12-12 12:00 | 4d 4h | developer | 3150 | 0 | 0 | 0 | 3150 |  | 0 | 0 | 3150 | 4d 4h | 0 | 0 | 0 | 3150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | deploy 3 naar ACC-omgeving | 2013-12-17 08:00 | 2013-12-17 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 |  | 0 | 0 | 700 | 1d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | acceptatie release 1 - einde testfase | 2014-01-16 17:00 | 2014-01-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | deploy 4 naar ACC-omgeving | 2014-01-13 08:00 | 2014-01-17 12:00 | 4d 4h | senior developer | 3375 | 0 | 0 | 0 | 3375 |  | 0 | 0 | 3375 | 4d 4h | 0 | 0 | 0 | 3375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | installatie PROD-server | 2014-01-16 17:00 | 2014-01-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | start authoring door klant (alleen site) | 2014-01-17 17:00 | 2014-01-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | vervollediging naar release voor go live | 2014-01-17 08:00 | 2014-01-31 17:00 | 11d |  |  | 0 |  |  | 2150 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
17 | productie installed, deploy 4 ook naar PROD-omgeving | 2014-01-17 08:00 | 2014-01-17 17:00 | 1d | senior developer | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | bugfixing + 'profielbeheer aanmaken' | 2014-01-31 08:00 | 2014-01-31 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 |  | 0 | 0 | 700 | 1d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | deploy 5 naar ACC | 2014-01-31 08:00 | 2014-01-31 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 |  | 0 | 0 | 700 | 1d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | release januari | 2014-01-30 17:00 | 2014-01-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | sprints naar release after go live | 2013-12-16 08:00 | 2014-02-28 17:00 | 55d |  |  | 0 |  |  | 60850 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | ontwikkeling release 2 | 2014-01-22 08:00 | 2014-02-27 17:00 | 27d | developer | 18900 | 0 | 0 | 0 | 18900 |  | 0 | 0 | 18900 | 27d | 0 | 0 | 0 | 18900 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | extra deploy (CR1) | 2014-02-27 08:00 | 2014-02-27 17:00 | 1d | senior developer | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | release februari | 2014-02-27 17:00 | 2014-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | testfase | 2013-12-16 08:00 | 2014-01-17 17:00 | 25d | senior developer | 18750 | 0 | 0 | 0 | 18750 |  | 0 | 0 | 18750 | 25d | 0 | 0 | 0 | 18750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | rework | 2013-12-17 08:00 | 2014-01-24 17:00 | 29d | senior developer | 21750 | 0 | 0 | 0 | 21750 |  | 0 | 0 | 21750 | 29d | 0 | 0 | 0 | 21750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | deploy 6 naar PROD-omgeving | 2014-02-28 08:00 | 2014-02-28 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 |  | 0 | 0 | 700 | 1d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | productie | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | uiterste deadline - officiële voorstelling | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2014-02-06 22:00 |  | TP Name | Tracking 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Website Tennis Vlaanderen | 2013-05-24 08:00 | 2014-02-28 17:00 | 201d |  |  | 0 |  |  | 219275 |  | 185d | [5 empty] | 335075 |  | 86.22% |  | 189048.0767 | 207325
28 | aanvang | 2013-05-24 13:00 | 2013-07-11 17:00 | 34d 4h |  |  | 0 |  |  | 32100 |  | 108d | [5 empty] | 98250 |  | 100% |  | 32100 | 32100
1 | start implementatie project | 2013-06-11 08:00 | 2013-06-12 12:00 | 1d 4h | developer | 1050 | 0 | 0 | 0 | 1050 | 2013-06-11 08:00 | 1d 4h | 1050 | 0 | 0 | 0 | 0 | 1050 | 0 | 100% | Finished | 1050 | 1050 | 100 | 100 | 100 | 100 | 100 | 100
2 | project management plan inclusief acceptatiecriteria | 2013-05-24 13:00 | 2013-07-11 17:00 | 34d 4h | project manager | 31050 | 0 | 0 | 0 | 31050 | 2013-05-24 13:00 | 108d | 97200 | 0 | 0 | 0 | 0 | 97200 | 0 | 100% | Finished | 31050 | 31050 | 100 | 313.0435 | 100 | 100 | 313.0435 | 100
29 | detaillering | 2013-05-24 08:00 | 2013-09-17 17:00 | 83d |  |  | 0 |  |  | 42800 |  | 137d | [5 empty] | 92400 |  | 100% |  | 42800 | 42800
3 | start functionele analyse/wireframes | 2013-05-24 08:00 | 2013-06-12 17:00 | 14d | senior consultant | 11200 | 0 | 0 | 0 | 11200 | 2013-05-24 08:00 | 14d | 11200 | 0 | 0 | 0 | 0 | 11200 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 100 | 100
4 | deliverable wireframes Amplexor | 2013-07-16 08:00 | 2013-08-19 17:00 | 25d | senior consultant | 20000 | 0 | 0 | 0 | 20000 | 2013-07-16 08:00 | 21d | 16800 | 0 | 0 | 0 | 0 | 16800 | 0 | 100% | Finished | 20000 | 20000 | 100 | 84 | 100 | 100 | 84 | 100
5 | functioneel & technisch ontwerp | 2013-08-12 13:00 | 2013-08-30 17:00 | 14d 4h | senior consultant | 11600 | 0 | 0 | 0 | 11600 | 2013-08-12 13:00 | 80d 4h | 64400 | 0 | 0 | 0 | 0 | 64400 | 0 | 100% | Finished | 11600 | 11600 | 100 | 555.1724 | 100 | 100 | 555.1724 | 100
6 | volledige oplevering HIG | 2013-09-17 17:00 | 2013-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-09-18 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
35 | bouw | 2013-08-07 08:00 | 2014-02-28 17:00 | 148d |  |  | 0 |  |  | 144375 |  | 132d | [5 empty] | 144425 |  | 79.06% |  | 114148.0767 | 132425
7 | installatie en algemene opzet | 2013-08-07 08:00 | 2013-08-23 17:00 | 13d | senior developer | 9750 | 0 | 0 | 0 | 9750 | 2013-08-07 08:00 | 13d | 9750 | 0 | 0 | 0 | 0 | 9750 | 0 | 100% | Finished | 9750 | 9750 | 100 | 100 | 100 | 100 | 100 | 100
30 | sprints naar release 1 | 2013-08-29 08:00 | 2013-10-30 17:00 | 45d |  |  | 0 |  |  | 63000 |  | 45d | [5 empty] | 63000 |  | 100% |  | 63000 | 63000
8 | WCM-luik: search, inloggen, infotheek, basisrechten, ... | 2013-08-29 08:00 | 2013-10-30 17:00 | 45d | developer;extra developer | 63000 | 0 | 0 | 0 | 63000 | 2013-08-29 08:00 | 45d | 63000 | 0 | 0 | 0 | 0 | 63000 | 0 | 100% | Finished | 63000 | 63000 | 100 | 100 | 100 | 100 | 100 | 100
31 | transitie (tussentijds) | 2013-10-31 08:00 | 2014-01-17 17:00 | 57d |  |  | 0 |  |  | 8625 |  | 57d | [5 empty] | 8625 |  | 100% |  | 8625 | 8625
9 | deploy 1 naar ACC-omgeving | 2013-10-31 08:00 | 2013-10-31 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 | 2013-10-31 08:00 | 1d | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 100% | Finished | 700 | 700 | 100 | 100 | 100 | 100 | 100 | 100
10 | deploy 2 naar ACC-omgeving | 2013-11-25 08:00 | 2013-11-25 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 | 2013-11-25 08:00 | 1d | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 100% | Finished | 700 | 700 | 100 | 100 | 100 | 100 | 100 | 100
11 | rework | 2013-12-06 08:00 | 2013-12-12 12:00 | 4d 4h | developer | 3150 | 0 | 0 | 0 | 3150 | 2013-12-06 08:00 | 4d 4h | 3150 | 0 | 0 | 0 | 0 | 3150 | 0 | 100% | Finished | 3150 | 3150 | 100 | 100 | 100 | 100 | 100 | 100
12 | deploy 3 naar ACC-omgeving | 2013-12-17 08:00 | 2013-12-17 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 | 2013-12-17 08:00 | 1d | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 100% | Finished | 700 | 700 | 100 | 100 | 100 | 100 | 100 | 100
13 | acceptatie release 1 - einde testfase | 2014-01-16 17:00 | 2014-01-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-01-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | deploy 4 naar ACC-omgeving | 2014-01-13 08:00 | 2014-01-17 12:00 | 4d 4h | senior developer | 3375 | 0 | 0 | 0 | 3375 | 2014-01-13 08:00 | 4d 4h | 3375 | 0 | 0 | 0 | 0 | 3375 | 0 | 100% | Finished | 3375 | 3375 | 100 | 100 | 100 | 100 | 100 | 100
15 | installatie PROD-server | 2014-01-16 17:00 | 2014-01-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-01-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
16 | start authoring door klant (alleen site) | 2014-01-17 17:00 | 2014-01-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-01-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
32 | vervollediging naar release voor go live | 2014-01-17 08:00 | 2014-01-31 17:00 | 11d |  |  | 0 |  |  | 2150 |  | 12d | [5 empty] | 4400 |  | 100% |  | 2150 | 2150
17 | productie installed, deploy 4 ook naar PROD-omgeving | 2014-01-17 08:00 | 2014-01-17 17:00 | 1d | senior developer | 750 | 0 | 0 | 0 | 750 | 2014-01-16 08:00 | 4d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 750 | 750 | 100 | 400 | 100 | 100 | 400 | 100
18 | bugfixing + 'profielbeheer aanmaken' | 2014-01-31 08:00 | 2014-01-31 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 | 2014-01-06 08:00 | 1d | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 100% | Finished | 700 | 700 | 100 | 100 | 100 | 100 | 100 | 100
19 | deploy 5 naar ACC | 2014-01-31 08:00 | 2014-01-31 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 | 2014-01-06 08:00 | 1d | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 100% | Finished | 700 | 700 | 100 | 100 | 100 | 100 | 100 | 100
20 | release januari | 2014-01-30 17:00 | 2014-01-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-01-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | sprints naar release after go live | 2013-12-16 08:00 | 2014-02-28 17:00 | 55d |  |  | 0 |  |  | 60850 |  | 38d | [5 empty] | 58650 |  | 50.33% |  | 30623.0767 | 48900
21 | ontwikkeling release 2 | 2014-01-22 08:00 | 2014-02-27 17:00 | 27d | developer | 18900 | 0 | 0 | 0 | 18900 | 2014-01-22 08:00 | 12d | 8400 | 9800 | 14d | 0 | 0 | 8400 | 9800 | 46.15% | Started | 8723.077 | 8400 | 100 | 44.4444 | 46.1538 | 100 | 44.4444 | 46.1538
22 | extra deploy (CR1) | 2014-02-27 08:00 | 2014-02-27 17:00 | 1d | senior developer | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | release februari | 2014-02-27 17:00 | 2014-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | testfase | 2013-12-16 08:00 | 2014-01-17 17:00 | 25d | senior developer | 18750 | 0 | 0 | 0 | 18750 | 2013-12-30 08:00 | 29d | 21750 | 750 | 1d | 0 | 0 | 21750 | 750 | 53% | Started | 9937.4995 | 18750 | 100 | 116 | 53 | 100 | 116 | 53
25 | rework | 2013-12-17 08:00 | 2014-01-24 17:00 | 29d | senior developer | 21750 | 0 | 0 | 0 | 21750 | 2013-12-17 08:00 | 38d | 28500 | 93.75 | 1h | 0 | 0 | 28500 | 93.75 | 55% | Started | 11962.5003 | 21750 | 100 | 131.0345 | 55 | 100 | 131.0345 | 55
26 | deploy 6 naar PROD-omgeving | 2014-02-28 08:00 | 2014-02-28 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 |  | 0 | 0 | 700 | 1d | 0 | 0 | 0 | 700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | productie | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | uiterste deadline - officiële voorstelling | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2014-03-31 22:00 |  | TP Name | Closure
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Website Tennis Vlaanderen | 2013-05-24 08:00 | 2014-02-28 17:00 | 201d |  |  | 0 |  |  | 219275 |  | 212d | [5 empty] | 382475 |  | 100% |  | 219275 | 219275
28 | aanvang | 2013-05-24 13:00 | 2013-07-11 17:00 | 34d 4h |  |  | 0 |  |  | 32100 |  | 108d | [5 empty] | 98250 |  | 100% |  | 32100 | 32100
1 | start implementatie project | 2013-06-11 08:00 | 2013-06-12 12:00 | 1d 4h | developer | 1050 | 0 | 0 | 0 | 1050 | 2013-06-11 08:00 | 1d 4h | 1050 | 0 | 0 | 0 | 0 | 1050 | 0 | 100% | Finished | 1050 | 1050 | 100 | 100 | 100 | 100 | 100 | 100
2 | project management plan inclusief acceptatiecriteria | 2013-05-24 13:00 | 2013-07-11 17:00 | 34d 4h | project manager | 31050 | 0 | 0 | 0 | 31050 | 2013-05-24 13:00 | 108d | 97200 | 0 | 0 | 0 | 0 | 97200 | 0 | 100% | Finished | 31050 | 31050 | 100 | 313.0435 | 100 | 100 | 313.0435 | 100
29 | detaillering | 2013-05-24 08:00 | 2013-09-17 17:00 | 83d |  |  | 0 |  |  | 42800 |  | 137d | [5 empty] | 92400 |  | 100% |  | 42800 | 42800
3 | start functionele analyse/wireframes | 2013-05-24 08:00 | 2013-06-12 17:00 | 14d | senior consultant | 11200 | 0 | 0 | 0 | 11200 | 2013-05-24 08:00 | 14d | 11200 | 0 | 0 | 0 | 0 | 11200 | 0 | 100% | Finished | 11200 | 11200 | 100 | 100 | 100 | 100 | 100 | 100
4 | deliverable wireframes Amplexor | 2013-07-16 08:00 | 2013-08-19 17:00 | 25d | senior consultant | 20000 | 0 | 0 | 0 | 20000 | 2013-07-16 08:00 | 21d | 16800 | 0 | 0 | 0 | 0 | 16800 | 0 | 100% | Finished | 20000 | 20000 | 100 | 84 | 100 | 100 | 84 | 100
5 | functioneel & technisch ontwerp | 2013-08-12 13:00 | 2013-08-30 17:00 | 14d 4h | senior consultant | 11600 | 0 | 0 | 0 | 11600 | 2013-08-12 13:00 | 80d 4h | 64400 | 0 | 0 | 0 | 0 | 64400 | 0 | 100% | Finished | 11600 | 11600 | 100 | 555.1724 | 100 | 100 | 555.1724 | 100
6 | volledige oplevering HIG | 2013-09-17 17:00 | 2013-09-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-09-18 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
35 | bouw | 2013-08-07 08:00 | 2014-02-28 17:00 | 148d |  |  | 0 |  |  | 144375 |  | 159d | [5 empty] | 191825 |  | 100% |  | 144375 | 144375
7 | installatie en algemene opzet | 2013-08-07 08:00 | 2013-08-23 17:00 | 13d | senior developer | 9750 | 0 | 0 | 0 | 9750 | 2013-08-07 08:00 | 13d | 9750 | 0 | 0 | 0 | 0 | 9750 | 0 | 100% | Finished | 9750 | 9750 | 100 | 100 | 100 | 100 | 100 | 100
30 | sprints naar release 1 | 2013-08-29 08:00 | 2013-10-30 17:00 | 45d |  |  | 0 |  |  | 63000 |  | 45d | [5 empty] | 63000 |  | 100% |  | 63000 | 63000
8 | WCM-luik: search, inloggen, infotheek, basisrechten, ... | 2013-08-29 08:00 | 2013-10-30 17:00 | 45d | developer;extra developer | 63000 | 0 | 0 | 0 | 63000 | 2013-08-29 08:00 | 45d | 63000 | 0 | 0 | 0 | 0 | 63000 | 0 | 100% | Finished | 63000 | 63000 | 100 | 100 | 100 | 100 | 100 | 100
31 | transitie (tussentijds) | 2013-10-31 08:00 | 2014-01-17 17:00 | 57d |  |  | 0 |  |  | 8625 |  | 57d | [5 empty] | 8625 |  | 100% |  | 8625 | 8625
9 | deploy 1 naar ACC-omgeving | 2013-10-31 08:00 | 2013-10-31 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 | 2013-10-31 08:00 | 1d | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 100% | Finished | 700 | 700 | 100 | 100 | 100 | 100 | 100 | 100
10 | deploy 2 naar ACC-omgeving | 2013-11-25 08:00 | 2013-11-25 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 | 2013-11-25 08:00 | 1d | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 100% | Finished | 700 | 700 | 100 | 100 | 100 | 100 | 100 | 100
11 | rework | 2013-12-06 08:00 | 2013-12-12 12:00 | 4d 4h | developer | 3150 | 0 | 0 | 0 | 3150 | 2013-12-06 08:00 | 4d 4h | 3150 | 0 | 0 | 0 | 0 | 3150 | 0 | 100% | Finished | 3150 | 3150 | 100 | 100 | 100 | 100 | 100 | 100
12 | deploy 3 naar ACC-omgeving | 2013-12-17 08:00 | 2013-12-17 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 | 2013-12-17 08:00 | 1d | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 100% | Finished | 700 | 700 | 100 | 100 | 100 | 100 | 100 | 100
13 | acceptatie release 1 - einde testfase | 2014-01-16 17:00 | 2014-01-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-01-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
14 | deploy 4 naar ACC-omgeving | 2014-01-13 08:00 | 2014-01-17 12:00 | 4d 4h | senior developer | 3375 | 0 | 0 | 0 | 3375 | 2014-01-13 08:00 | 4d 4h | 3375 | 0 | 0 | 0 | 0 | 3375 | 0 | 100% | Finished | 3375 | 3375 | 100 | 100 | 100 | 100 | 100 | 100
15 | installatie PROD-server | 2014-01-16 17:00 | 2014-01-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-01-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
16 | start authoring door klant (alleen site) | 2014-01-17 17:00 | 2014-01-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-01-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
32 | vervollediging naar release voor go live | 2014-01-17 08:00 | 2014-01-31 17:00 | 11d |  |  | 0 |  |  | 2150 |  | 12d | [5 empty] | 4400 |  | 100% |  | 2150 | 2150
17 | productie installed, deploy 4 ook naar PROD-omgeving | 2014-01-17 08:00 | 2014-01-17 17:00 | 1d | senior developer | 750 | 0 | 0 | 0 | 750 | 2014-01-16 08:00 | 4d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 750 | 750 | 100 | 400 | 100 | 100 | 400 | 100
18 | bugfixing + 'profielbeheer aanmaken' | 2014-01-31 08:00 | 2014-01-31 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 | 2014-01-06 08:00 | 1d | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 100% | Finished | 700 | 700 | 100 | 100 | 100 | 100 | 100 | 100
19 | deploy 5 naar ACC | 2014-01-31 08:00 | 2014-01-31 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 | 2014-01-06 08:00 | 1d | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 100% | Finished | 700 | 700 | 100 | 100 | 100 | 100 | 100 | 100
20 | release januari | 2014-01-30 17:00 | 2014-01-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-01-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | sprints naar release after go live | 2013-12-16 08:00 | 2014-02-28 17:00 | 55d |  |  | 0 |  |  | 60850 |  | 65d | [5 empty] | 106050 |  | 100% |  | 60850 | 60850
21 | ontwikkeling release 2 | 2014-01-22 08:00 | 2014-02-27 17:00 | 27d | developer | 18900 | 0 | 0 | 0 | 18900 | 2014-01-22 08:00 | 23d | 16100 | 0 | 0 | 0 | 0 | 16100 | 0 | 100% | Finished | 18900 | 18900 | 100 | 85.1852 | 100 | 100 | 85.1852 | 100
22 | extra deploy (CR1) | 2014-02-27 08:00 | 2014-02-27 17:00 | 1d | senior developer | 750 | 0 | 0 | 0 | 750 | 2014-02-27 08:00 | 6d | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 100% | Finished | 750 | 750 | 100 | 600 | 100 | 100 | 600 | 100
23 | release februari | 2014-02-27 17:00 | 2014-02-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
24 | testfase | 2013-12-16 08:00 | 2014-01-17 17:00 | 25d | senior developer | 18750 | 0 | 0 | 0 | 18750 | 2013-12-30 08:00 | 51d | 38250 | 0 | 0 | 0 | 0 | 38250 | 0 | 100% | Finished | 18750 | 18750 | 100 | 204 | 100 | 100 | 204 | 100
25 | rework | 2013-12-17 08:00 | 2014-01-24 17:00 | 29d | senior developer | 21750 | 0 | 0 | 0 | 21750 | 2013-12-17 08:00 | 62d | 46500 | 0 | 0 | 0 | 0 | 46500 | 0 | 100% | Finished | 21750 | 21750 | 100 | 213.7931 | 100 | 100 | 213.7931 | 100
26 | deploy 6 naar PROD-omgeving | 2014-02-28 08:00 | 2014-02-28 17:00 | 1d | developer | 700 | 0 | 0 | 0 | 700 | 2014-03-17 08:00 | 1d | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 100% | Finished | 700 | 700 | 100 | 100 | 100 | 100 | 100 | 100
37 | productie | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | uiterste deadline - officiële voorstelling | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking 1 | 2013-05-24 08:00 | 2013-07-04 22:00 | 38800 | 20944 | 38800 | 2013-06-11 11:00 | -17856 | 53.98% | -17856 | 53.98% | -17d 5h | 41.25% | 90.44% | 2014-03-25 11:00 | 2014-10-28 11:00 | 2016-01-14 16:00 | 2014-03-20 15:00 | 2014-10-28 11:00 | 2015-12-10 10:00 | 2014-03-26 14:00 | 2015-04-07 10:00 | 2016-10-04 09:00 | 237131 | 406219.9191 | 406219.9191 | 519602.4242 | 719467.1522 | 929514.9553 | 406219.9191 | 424406.6179 | 0.4125 | 0.53979 | 0.53979 | 0.90439 | -17.625 | 0.53979 | 1 | 0.4125 | 1
Tracking 2 | 2013-07-04 22:00 | 2013-10-10 22:00 | 128050 | 119474.8454 | 207000 | 2013-10-02 15:00 | -8575.1546 | 93.3% | -87525.1546 | 57.72% | -6d 2h | 93.75% | 93.6% | 2014-03-12 16:00 | 2014-03-21 11:00 | 2014-10-29 10:00 | 2014-03-11 15:00 | 2014-03-21 11:00 | 2014-07-17 17:00 | 2014-03-11 10:00 | 2014-03-20 11:00 | 2014-07-16 10:00 | 306800.1546 | 379911.9795 | 313963.1834 | 313453.4983 | 392322.5162 | 391439.4448 | 360930.6102 | 360718.7791 | 0.9375 | 0.57717 | 0.93303 | 0.93603 | -6.25 | 0.57717 | 1 | 0.9375 | 1
Tracking 3 | 2013-10-10 22:00 | 2014-02-06 22:00 | 207325 | 189048.0767 | 335075 | 2014-01-15 17:00 | -18276.9233 | 91.18% | -146026.9233 | 56.42% | -16d | 91.35% | 93.73% | 2014-03-25 15:00 | 2014-03-28 11:00 | 2014-11-21 15:00 | 2014-03-25 10:00 | 2014-03-28 11:00 | 2014-05-06 15:00 | 2014-03-24 17:00 | 2014-03-27 17:00 | 2014-05-06 09:00 | 365301.9233 | 388650.1884 | 368224.2231 | 368163.6439 | 393829.7683 | 393722.3956 | 382772.1592 | 382747.0427 | 0.91351 | 0.5642 | 0.91184 | 0.93727 | -16 | 0.5642 | 1 | 0.91351 | 1
Closure | 2014-02-06 22:00 | 2014-03-31 22:00 | 219275 | 219275 | 382475 | 2014-02-28 17:00 | 0 | 100% | -163200 | 57.33% | -21d | 90.54% | 100% | 2014-02-28 17:00 | 2014-02-28 17:00 | 2014-09-26 14:00 | 2014-03-31 17:00 | 2014-03-31 17:00 | 2014-03-31 17:00 | 2014-03-31 17:00 | 2014-03-31 17:00 | 2014-03-31 17:00 | 382475 | 382475 | 382475 | 382475 | 382475 | 382475 | 382475 | 382475 | 0.90541 | 0.57331 | 1 | 1 | -21 | 0.57331 | 1 | 0.90541 | 1