## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | Construction house | 1 |  |  | 2017-01-02 08:00 | 2017-06-15 16:00 | 114d 7h |  |  | 91100 |  |  | 201405.6
1 | Organization construction site | 1.1 |  | FS2 | 2017-01-02 08:00 | 2017-01-02 17:00 | 1d | Excavation/fundation crew[4.00 #4] | 1440 | 0 | 0 | 0 | 1440
2 | Excavation | 1.2 | 1FS | FS3+2d | 2017-01-04 13:00 | 2017-01-10 17:00 | 4d 4h | Excavation/fundation crew[4.00 #4] | 6480 | 0 | 0 | 0 | 6480
3 | Fundation | 1.3 | 2FS+2d | FS4+1d | 2017-01-13 08:00 | 2017-01-17 17:00 | 3d | Excavation/fundation crew[4.00 #4] | 4320 | 1200 | 0 | 0 | 5520
4 | Floor basement | 1.4 | 3FS+1d | FS5 | 2017-01-20 08:00 | 2017-01-23 17:00 | 2d | Masonry[4.00 #4] | 2598.4 | 800 | 0 | 0 | 3398.4
5 | masonry basement | 1.5 | 4FS | FS6;FS7 | 2017-01-25 08:00 | 2017-01-30 17:00 | 4d | Masonry[4.00 #4] | 5196.8 | 1500 | 0 | 0 | 6696.8
6 | Sewage | 1.6 | 5FS | FS7 | 2017-01-31 08:00 | 2017-02-01 11:00 | 1d 3h | Excavation/fundation crew[4.00 #4] | 1980 | 500 | 0 | 0 | 2480
7 | Pier and beam/joist basement | 1.7 | 5FS;6FS | FS8 | 2017-02-01 11:00 | 2017-02-02 16:00 | 1d 4h | Masonry[4.00 #4] | 1948.8 | 1500 | 0 | 0 | 3448.8
8 | Masonry ground level + first level | 1.8 | 7FS | FS10;FS9;FS26+2w 4d | 2017-02-02 16:00 | 2017-03-14 16:00 | 28d | Masonry[4.00 #4] | 36377.6 | 14000 | 0 | 0 | 50377.6
9 | Sills | 1.9 | 8FS | FS16 | 2017-03-14 16:00 | 2017-03-16 09:00 | 1d 2h | Floor/Sills worker[2.00 #2] | 840 | 700 | 0 | 0 | 1540
10 | Roof construction | 1.10 | 8FS | FS11;FS13;FS14;FS15;FS16 | 2017-03-14 16:00 | 2017-03-30 16:00 | 12d | Roof worker[3.00 #3] | 11577.6 | 8000 | 0 | 0 | 19577.6
11 | Gutter instalment | 1.11 | 10FS |  | 2017-04-03 16:00 | 2017-04-05 16:00 | 2d | Plumber | 688 | 1000 | 0 | 0 | 1688
12 | Inner joinery | 1.12 | 16FS | FS15 | 2017-04-04 16:00 | 2017-04-06 16:00 | 2d | Joiner (jointing/doors/windows)[2.00 #2] | 1328 | 1500 | 0 | 0 | 2828
13 | Ventilation provisions | 1.13 | 10FS | FS18 | 2017-03-30 16:00 | 2017-04-03 16:00 | 2d | Plumber | 688 | 4000 | 0 | 0 | 4688
14 | plumbing | 1.14 | 10FS | FS18 | 2017-04-05 16:00 | 2017-04-10 16:00 | 3d | Plumber | 1032 | 800 | 0 | 0 | 1832
15 | electricity | 1.15 | 10FS;12FS | FS18 | 2017-04-06 16:00 | 2017-04-11 16:00 | 3d | Electrician | 1036.8 | 500 | 0 | 0 | 1536.8
16 | Outer doors and windows | 1.16 | 10FS;9FS | FS12;FS17;FS18 | 2017-03-30 16:00 | 2017-04-04 16:00 | 3d | Joiner (jointing/doors/windows)[2.00 #2] | 1992 | 10000 | 0 | 0 | 11992
17 | Inner window sills | 1.17 | 16FS | FS18 | 2017-04-04 16:00 | 2017-04-05 16:00 | 1d | Floor/Sills worker[2.00 #2] | 672 | 800 | 0 | 0 | 1472
18 | Plastering | 1.18 | 13FS;14FS;15FS;16FS;17FS | FS19;FS20 | 2017-04-11 16:00 | 2017-05-02 16:00 | 13d | Plastering[2.00 #2] | 8216 | 1500 | 0 | 0 | 9716
19 | Floor insulation | 1.19 | 18FS | FS20 | 2017-05-02 16:00 | 2017-05-03 16:00 | 1d | Floor/Sills worker[2.00 #2] | 672 | 2500 | 0 | 0 | 3172
20 | Screed | 1.20 | 19FS;18FS | FS24;FS22+4w;FS25;FS27;FS28;FS29;FS21+1w 2d | 2017-05-03 16:00 | 2017-05-09 11:00 | 3d 4h | Floor/Sills worker[2.00 #2] | 2352 | 1600 | 0 | 0 | 3952
21 | Tiling floor (basement + ground level) | 1.21 | 20FS+1w 2d;24FS | FS23;FS27;FS28;FS29 | 2017-05-18 11:00 | 2017-05-30 11:00 | 7d | Floor/Sills worker[2.00 #2] | 4704 | 6500 | 0 | 0 | 11204
22 | Llaminated floor (First level) | 1.22 | 20FS+4w;23FS;24FS | FS27;FS28;FS29 | 2017-06-08 11:00 | 2017-06-12 16:00 | 2d 4h | Joiner (jointing/doors/windows)[2.00 #2] | 1660 | 3200 | 0 | 0 | 4860
23 | Wooden staircase placement | 1.23 | 21FS | FS22 | 2017-05-30 11:00 | 2017-06-01 11:00 | 2d | Joiner (jointing/doors/windows)[2.00 #2] | 1328 | 2000 | 0 | 0 | 3328
24 | Central heating, Sanitary | 1.24 | 20FS | FS22;FS28;FS29;FS21 | 2017-05-09 11:00 | 2017-05-12 11:00 | 3d | Plumber | 1032 | 6500 | 0 | 0 | 7532
25 | Finish electricity | 1.25 | 20FS | FS28;FS29 | 2017-05-09 11:00 | 2017-05-12 11:00 | 3d | Electrician | 1036.8 | 3500 | 0 | 0 | 4536.8
26 | Pointing the wall | 1.26 | 8FS+2w 4d |  | 2017-04-03 16:00 | 2017-04-07 16:00 | 4d | Masonry[4.00 #4] | 5196.8 | 500 | 0 | 0 | 5696.8
27 | Inner doors | 1.27 | 20FS;21FS;22FS |  | 2017-06-12 16:00 | 2017-06-15 16:00 | 3d | Joiner (jointing/doors/windows)[2.00 #2] | 1992 | 2500 | 0 | 0 | 4492
28 | Bathroom installment | 1.28 | 24FS;25FS;22FS;21FS;20FS |  | 2017-06-14 16:00 | 2017-06-15 16:00 | 1d | Bathroom/kitchen installer[2.00 #2] | 640 | 2000 | 0 | 0 | 2640
29 | Kitchen installment | 1.29 | 24FS;25FS;22FS;21FS;20FS |  | 2017-06-12 16:00 | 2017-06-14 16:00 | 2d | Bathroom/kitchen installer[2.00 #2] | 1280 | 12000 | 0 | 0 | 13280

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Excavation/fundation crew | Renewable | 4 100% | 0 | 45 | 1[4.00 Excavation/fundation crew];2[4.00 Excavation/fundation crew];3[4.00 Excavation/fundation crew];6[4.00 Excavation/fundation crew]; | 14220
2 | Masonry | Renewable | 4 100% | 0 | 40.6 | 4[4.00 Masonry];5[4.00 Masonry];7[4.00 Masonry];8[4.00 Masonry];26[4.00 Masonry]; | 51318.3984
3 | Roof worker | Renewable | 3 100% | 0 | 40.2 | 10[3.00 Roof worker]; | 11577.6006
4 | Electrician | Renewable | 1 100% | 0 | 43.2 | 15;25; | 2073.6001
5 | Plumber | Renewable | 1 100% | 0 | 43 | 11;13;14;24; | 3440
6 | Joiner (jointing/doors/windows) | Renewable | 2 100% | 0 | 41.5 | 12[2.00 Joiner (jointing/doors/windows)];16[2.00 Joiner (jointing/doors/windows)];22[2.00 Joiner (jointing/doors/windows)];23[2.00 Joiner (jointing/doors/windows)];27[2.00 Joiner (jointing/doors/windows)]; | 8300
7 | Floor/Sills worker | Renewable | 2 100% | 0 | 42 | 9[2.00 Floor/Sills worker];17[2.00 Floor/Sills worker];19[2.00 Floor/Sills worker];20[2.00 Floor/Sills worker];21[2.00 Floor/Sills worker]; | 9240
8 | Plastering | Renewable | 2 100% | 0 | 39.5 | 18[2.00 Plastering]; | 8216
9 | Bathroom/kitchen installer | Renewable | 2 100% | 0 | 40 | 28[2.00 Bathroom/kitchen installer];29[2.00 Bathroom/kitchen installer]; | 1920

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | Construction house | 919h
1 | Organization construction site | 8h | standard - symmetric | 80 | 100 | 120
2 | Excavation | 36h | standard - symmetric | 80 | 100 | 120
3 | Fundation | 24h | standard - symmetric | 80 | 100 | 120
4 | Floor basement | 16h | standard - symmetric | 80 | 100 | 120
5 | masonry basement | 32h | standard - symmetric | 80 | 100 | 120
6 | Sewage | 11h | standard - symmetric | 80 | 100 | 120
7 | Pier and beam/joist basement | 12h | standard - symmetric | 80 | 100 | 120
8 | Masonry ground level + first level | 224h | standard - symmetric | 80 | 100 | 120
9 | Sills | 10h | standard - symmetric | 80 | 100 | 120
10 | Roof construction | 96h | standard - symmetric | 80 | 100 | 120
11 | Gutter instalment | 16h | standard - symmetric | 80 | 100 | 120
12 | Inner joinery | 16h | standard - symmetric | 80 | 100 | 120
13 | Ventilation provisions | 16h | standard - symmetric | 80 | 100 | 120
14 | plumbing | 24h | standard - symmetric | 80 | 100 | 120
15 | electricity | 24h | standard - symmetric | 80 | 100 | 120
16 | Outer doors and windows | 24h | standard - symmetric | 80 | 100 | 120
17 | Inner window sills | 8h | standard - symmetric | 80 | 100 | 120
18 | Plastering | 104h | standard - symmetric | 80 | 100 | 120
19 | Floor insulation | 8h | standard - symmetric | 80 | 100 | 120
20 | Screed | 28h | standard - symmetric | 80 | 100 | 120
21 | Tiling floor (basement + ground level) | 56h | standard - symmetric | 80 | 100 | 120
22 | Llaminated floor (First level) | 20h | standard - symmetric | 80 | 100 | 120
23 | Wooden staircase placement | 16h | standard - symmetric | 80 | 100 | 120
24 | Central heating, Sanitary | 24h | standard - symmetric | 80 | 100 | 120
25 | Finish electricity | 24h | standard - symmetric | 80 | 100 | 120
26 | Pointing the wall | 32h | standard - symmetric | 80 | 100 | 120
27 | Inner doors | 24h | standard - symmetric | 80 | 100 | 120
28 | Bathroom installment | 8h | standard - symmetric | 80 | 100 | 120
29 | Kitchen installment | 16h | standard - symmetric | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes | 2017-04-17
1:00 - 2:00 | No | Tuesday | Yes | 2017-05-01
2:00 - 3:00 | No | Wednesday | Yes | 2017-05-25
3:00 - 4:00 | No | Thursday | Yes | 2017-06-05
4:00 - 5:00 | No | Friday | Yes | 2017-07-10
5:00 - 6:00 | No | Saturday | No | 2017-07-11
6:00 - 7:00 | No | Sunday | No | 2017-07-12
7:00 - 8:00 | No |  |  | 2017-07-13
8:00 - 9:00 | Yes |  |  | 2017-07-14
9:00 - 10:00 | Yes |  |  | 2017-07-17
10:00 - 11:00 | Yes |  |  | 2017-07-18
11:00 - 12:00 | Yes |  |  | 2017-07-19
12:00 - 13:00 | No |  |  | 2017-07-20
13:00 - 14:00 | Yes |  |  | 2017-07-21
14:00 - 15:00 | Yes |  |  | 2017-07-24
15:00 - 16:00 | Yes |  |  | 2017-07-25
16:00 - 17:00 | Yes |  |  | 2017-07-26
17:00 - 18:00 | No |  |  | 2017-07-27
18:00 - 19:00 | No |  |  | 2017-07-28
19:00 - 20:00 | No |  |  | 2017-08-15
20:00 - 21:00 | No |  |  | 2017-11-01
21:00 - 22:00 | No |  |  | 2017-12-25
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t))