## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | projectKopie | 1 |  |  | 2016-11-16 08:00 | 2018-03-20 17:00 | 350d |  |  | 1546034 |  |  | 1703349.9999 | 489.375
41 | Onderzoek | 1.1 |  |  | 2016-11-16 08:00 | 2017-01-25 17:00 | 51d |  |  | 0 |  |  | 23776 | 70.375
2 | Analysis of bikes and bikes usage in gent by students | 1.1.1 |  | FS3;FS4 | 2016-11-16 08:00 | 2016-12-05 17:00 | 14d | Engineer[2.00 #2] | 10080 | 0 | 0 | 0 | 10080 | 19.375
3 | Properties of the bike | 1.1.2 | 2FS |  | 2016-12-06 08:00 | 2016-12-09 17:00 | 4d | Engineer | 1440 | 0 | 0 | 0 | 1440 | 3.375
4 | Determine amount of bikes needed and hot spots | 1.1.3 | 2FS | FS5;FS9 | 2016-12-06 08:00 | 2016-12-12 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 6.375
5 | research for possibledocking stations | 1.1.4 | 4FS | FS6 | 2016-12-13 08:00 | 2017-01-09 17:00 | 20d | Engineer | 7200 | 0 | 0 | 0 | 7200 | 27.375
6 | Resarch amount of staff needed (extra contractors) | 1.1.5 | 5FS | FS7 | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 6.375
7 | feasibility study | 1.1.6 | 6FS | FS13 | 2017-01-17 08:00 | 2017-01-25 17:00 | 7d | Admin | 1456 | 0 | 0 | 0 | 1456 | 8.375
42 | Vans | 1.2 |  |  | 2016-12-13 08:00 | 2017-01-26 17:00 | 33d |  |  | 45000 |  |  | 47880 | 44.375
9 | determine type and amound of vans | 1.2.1 | 4FS | FS10 | 2016-12-13 08:00 | 2016-12-15 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 2.375
10 | buy vans | 1.2.2 | 9FS | FS11 | 2016-12-16 08:00 | 2017-01-05 17:00 | 15d |  | 0 | 45000 | 0 | 0 | 45000 | 20.375
11 | adjust vans | 1.2.3 | 10FS | FS26 | 2017-01-06 08:00 | 2017-01-26 17:00 | 15d | Arb | 2880 | 0 | 0 | 0 | 2880 | 20.375
43 | Meeting | 1.3 |  |  | 2017-01-26 08:00 | 2017-05-03 17:00 | 70d |  |  | 2112 |  |  | 23452 | 97.375
13 | Asking town for permission | 1.3.1 | 7FS | FS14;FS15;FS16;FS17;FS18;FS20 | 2017-01-26 08:00 | 2017-03-08 17:00 | 30d | Aankoop | 8160 | 0 | 0 | 0 | 8160 | 41.375
14 | Asking town for blue prints porwer network | 1.3.2 | 13FS | FS36 | 2017-03-09 08:00 | 2017-04-05 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 | 27.375
15 | meeting with bike suppliers and contracting | 1.3.3 | 13FS | FS28 | 2017-03-09 08:00 | 2017-05-03 17:00 | 40d | Admin[0.50 #2] | 4160 | 0 | 0 | 0 | 4160 | 55.375
16 | meeting with docking stations and tower suppliers and contracting | 1.3.4 | 13FS | FS29 | 2017-03-09 08:00 | 2017-04-26 17:00 | 35d | Aankoop[0.50 #2] | 4760 | 0 | 0 | 0 | 4760 | 48.375
17 | meeting with duct suppliers & cable supliers & contracting | 1.3.5 | 13FS | FS30 | 2017-03-09 08:00 | 2017-03-29 17:00 | 15d | Engineer[0.50 #2];Admin[0.50 #2] | 4260 | 0 | 0 | 0 | 4260 | 20.375
18 | meeting concrete suppliers | 1.3.6 | 13FS | FS36 | 2017-03-09 08:00 | 2017-03-22 17:00 | 10d |  | 0 | 2112 | 0 | 0 | 2112 | 13.375
44 | Ict | 1.4 |  |  | 2017-03-09 08:00 | 2017-07-07 17:00 | 87d |  |  | 168000 |  |  | 175560 | 120.375
20 | ICT contracter search | 1.4.1 | 13FS | FS21;FS22 | 2017-03-09 08:00 | 2017-04-03 17:00 | 18d | Admin[0.50 #2];Aankoop[0.50 #2];Engineer2[0.50 #5] | 7560 | 0 | 0 | 0 | 7560 | 25.375
21 | Developing app | 1.4.2 | 20FS | FS23 | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 78.375
22 | developing pay system | 1.4.3 | 20FS | FS24 | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 78.375
23 | Testing & approve app | 1.4.4 | 21FS |  | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 15.375
24 | Testing & approve pay system | 1.4.5 | 22FS |  | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 15.375
45 | Repair place | 1.5 |  |  | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d |  |  | 0 |  |  | 17664 | 32.375
26 | construct bike repearing place | 1.5.1 | 11FS | FS33 | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d | Arb[4.00 #4] | 17664 | 0 | 0 | 0 | 17664 | 32.375
46 | Delivery | 1.6 |  |  | 2017-03-30 08:00 | 2017-07-12 17:00 | 75d |  |  | 460000 |  |  | 460000 | 104.375
28 | Delivery bikes parts | 1.6.1 | 15FS | FS33 | 2017-05-04 08:00 | 2017-07-12 17:00 | 50d |  | 0 | 150000 | 0 | 0 | 150000 | 69.375
29 | delivery docking station & power tower | 1.6.2 | 16FS | FS32 | 2017-04-27 08:00 | 2017-06-07 17:00 | 30d |  | 0 | 250000 | 0 | 0 | 250000 | 41.375
30 | delivery ducts | 1.6.3 | 17FS | FS34 | 2017-03-30 08:00 | 2017-04-24 17:00 | 18d |  | 0 | 60000 | 0 | 0 | 60000 | 25.375
47 | Assembly | 1.7 |  |  | 2017-04-25 08:00 | 2017-08-31 17:00 | 93d |  |  | 0 |  |  | 72575.9999 | 128.375
32 | assembly docking station & power tower | 1.7.1 | 29FS | FS37 | 2017-06-08 08:00 | 2017-08-09 17:00 | 45d | Engineer[0.88 #2];Arb[2.00 #4] | 31535.9999 | 0 | 0 | 0 | 31535.9999 | 62.375
33 | assembly bikes & Testing | 1.7.2 | 28FS;26FS |  | 2017-07-13 08:00 | 2017-08-31 17:00 | 36d | Arb[4.00 #4] | 27648 | 0 | 0 | 0 | 27648 | 49.375
34 | assembly ducts | 1.7.3 | 30FS |  | 2017-04-25 08:00 | 2017-05-18 17:00 | 18d | Engineer;Arb[2.00 #4] | 13392 | 0 | 0 | 0 | 13392 | 23.375
48 | Construction total | 1.8 |  |  | 2017-04-06 08:00 | 2017-10-02 17:00 | 128d |  |  | 770922 |  |  | 770922 | 179.375
36 | Construction 1 | 1.8.1 | 18FS;14FS |  | 2017-04-06 08:00 | 2017-07-04 17:00 | 64d |  | 0 | 587706 | 0 | 0 | 587706 | 89.375
37 | Construction 2 | 1.8.2 | 32FS | FS39 | 2017-08-10 08:00 | 2017-10-02 17:00 | 38d |  | 0 | 183216 | 0 | 0 | 183216 | 53.375
49 | Final phase | 1.9 |  |  | 2017-10-03 08:00 | 2017-11-28 17:00 | 41d |  |  | 0 |  |  | 11520 | 56.375
39 | Placing bikes | 1.9.1 | 37FS | FS40 | 2017-10-03 08:00 | 2017-10-23 17:00 | 15d | Arb[4.00 #4] | 11520 | 0 | 0 | 0 | 11520 | 20.375
40 | Final testing the total system | 1.9.2 | 39FS | FS50 | 2017-10-24 08:00 | 2017-11-28 17:00 | 26d |  | 0 | 0 | 0 | 0 | 0 | 35.375
50 | Project buffer | 1.10 | 40FS |  | 2017-11-29 08:00 | 2018-03-20 17:00 | 80d |  | 0 | 100000 | 0 | 0 | 100000 | 111.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost |  | Cost (%)
1 | Engineer | Renewable | 2 | 0 | 45 | 2[2.00 Engineer];3;4;5;6;17[0.50 Engineer];32[0.88 Engineer];34; | 45756 | 157316 | 29.0854
2 | Electr | Renewable | 5 | 0 | 32 |  | 0 |  | 0
3 | Arb | Renewable | 4 | 0 | 24 | 11;26[4.00 Arb];32[2.00 Arb];33[4.00 Arb];34[2.00 Arb];39[4.00 Arb]; | 83904 |  | 53.3347
4 | Admin | Renewable | 2 | 0 | 26 | 7;15[0.50 Admin];17[0.50 Admin];20[0.50 Admin]; | 9048 |  | 5.7515
5 | Aankoop | Renewable | 2 | 0 | 34 | 13;16[0.50 Aankoop];20[0.50 Aankoop]; | 15368 |  | 9.7689
6 | Concrete Worker | Renewable | 4 | 0 | 36 |  | 0 |  | 0
7 | Construction Labor | Renewable | 20 | 0 | 36 |  | 0 |  | 0
8 | Engineer2 | Renewable | 5 | 0 | 45 | 20[0.50 Engineer]; | 3240 |  | 2.0595
0

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | projectKopie | 2800h |  |  |  |  | 99 | 100 | 101
41 | Onderzoek | 408h |  |  |  |  | 99 | 100 | 101
2 | Analysis of bikes and bikes usage in gent by students | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Properties of the bike | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Determine amount of bikes needed and hot spots | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | research for possibledocking stations | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Resarch amount of staff needed (extra contractors) | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | feasibility study | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | Vans | 264h |  |  |  |  | 99 | 100 | 101
9 | determine type and amound of vans | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | buy vans | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | adjust vans | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | Meeting | 560h |  |  |  |  | 99 | 100 | 101
13 | Asking town for permission | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Asking town for blue prints porwer network | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | meeting with bike suppliers and contracting | 320h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | meeting with docking stations and tower suppliers and contracting | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | meeting with duct suppliers & cable supliers & contracting | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | meeting concrete suppliers | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | Ict | 696h |  |  |  |  | 99 | 100 | 101
20 | ICT contracter search | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Developing app | 456h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | developing pay system | 456h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Testing & approve app | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Testing & approve pay system | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | Repair place | 184h |  |  |  |  | 99 | 100 | 101
26 | construct bike repearing place | 184h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | Delivery | 600h |  |  |  |  | 99 | 100 | 101
28 | Delivery bikes parts | 400h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | delivery docking station & power tower | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | delivery ducts | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | Assembly | 744h |  |  |  |  | 99 | 100 | 101
32 | assembly docking station & power tower | 360h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | assembly bikes & Testing | 288h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | assembly ducts | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | Construction total | 1024h |  |  |  |  | 99 | 100 | 101
36 | Construction 1 | 512h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Construction 2 | 304h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
49 | Final phase | 328h |  |  |  |  | 99 | 100 | 101
39 | Placing bikes | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | Final testing the total system | 208h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | Project buffer | 640h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2016-12-06 17:00 |  | TP Name | 6/12/2016 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | projectKopie | 2016-11-16 08:00 | 2018-03-20 17:00 | 350d |  |  | 1546034 |  |  | 1703349.9999 |  | 15d | [5 empty] | 10800 |  | 0.4581% |  | 7803.8707 | 10800
41 | Onderzoek | 2016-11-16 08:00 | 2017-01-25 17:00 | 51d |  |  | 0 |  |  | 23776 |  | 15d | [5 empty] | 10800 |  | 32.82% |  | 7803.8707 | 10800
2 | Analysis of bikes and bikes usage in gent by students | 2016-11-16 08:00 | 2016-12-05 17:00 | 14d | Engineer[2.00 #2] | 10080 | 0 | 0 | 0 | 10080 | 2016-11-16 08:00 | 15d | 10800 | 3150 | 4d 3h | 0 | 0 | 10800 | 3150 | 77.42% | Started | 7803.8707 | 10080
3 | Properties of the bike | 2016-12-06 08:00 | 2016-12-09 17:00 | 4d | Engineer | 1440 | 0 | 0 | 0 | 1440 |  | 0 | 0 | 1440 | 4d | 0 | 0 | 0 | 1440 | 0% | Not Started | 0 | 360
4 | Determine amount of bikes needed and hot spots | 2016-12-06 08:00 | 2016-12-12 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 |  | 0 | 0 | 1800 | 5d | 0 | 0 | 0 | 1800 | 0% | Not Started | 0 | 360
5 | research for possibledocking stations | 2016-12-13 08:00 | 2017-01-09 17:00 | 20d | Engineer | 7200 | 0 | 0 | 0 | 7200 |  | 0 | 0 | 7200 | 20d | 0 | 0 | 0 | 7200 | 0% | Not Started | 0 | 0
6 | Resarch amount of staff needed (extra contractors) | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 |  | 0 | 0 | 1800 | 5d | 0 | 0 | 0 | 1800 | 0% | Not Started | 0 | 0
7 | feasibility study | 2017-01-17 08:00 | 2017-01-25 17:00 | 7d | Admin | 1456 | 0 | 0 | 0 | 1456 |  | 0 | 0 | 1456 | 7d | 0 | 0 | 0 | 1456 | 0% | Not Started | 0 | 0
42 | Vans | 2016-12-13 08:00 | 2017-01-26 17:00 | 33d |  |  | 45000 |  |  | 47880 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
9 | determine type and amound of vans | 2016-12-13 08:00 | 2016-12-15 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 3d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
10 | buy vans | 2016-12-16 08:00 | 2017-01-05 17:00 | 15d |  | 0 | 45000 | 0 | 0 | 45000 |  | 0 | 0 | 45000 | 15d | 0 | 0 | 0 | 45000 | 0% | Not Started | 0 | 0
11 | adjust vans | 2017-01-06 08:00 | 2017-01-26 17:00 | 15d | Arb | 2880 | 0 | 0 | 0 | 2880 |  | 0 | 0 | 2880 | 15d | 0 | 0 | 0 | 2880 | 0% | Not Started | 0 | 0
43 | Meeting | 2017-01-26 08:00 | 2017-05-03 17:00 | 70d |  |  | 2112 |  |  | 23452 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
13 | Asking town for permission | 2017-01-26 08:00 | 2017-03-08 17:00 | 30d | Aankoop | 8160 | 0 | 0 | 0 | 8160 |  | 0 | 0 | 8160 | 30d | 0 | 0 | 0 | 8160 | 0% | Not Started | 0 | 0
14 | Asking town for blue prints porwer network | 2017-03-09 08:00 | 2017-04-05 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 20d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
15 | meeting with bike suppliers and contracting | 2017-03-09 08:00 | 2017-05-03 17:00 | 40d | Admin[0.50 #2] | 4160 | 0 | 0 | 0 | 4160 |  | 0 | 0 | 4160 | 40d | 0 | 0 | 0 | 4160 | 0% | Not Started | 0 | 0
16 | meeting with docking stations and tower suppliers and contracting | 2017-03-09 08:00 | 2017-04-26 17:00 | 35d | Aankoop[0.50 #2] | 4760 | 0 | 0 | 0 | 4760 |  | 0 | 0 | 4760 | 35d | 0 | 0 | 0 | 4760 | 0% | Not Started | 0 | 0
17 | meeting with duct suppliers & cable supliers & contracting | 2017-03-09 08:00 | 2017-03-29 17:00 | 15d | Engineer[0.50 #2];Admin[0.50 #2] | 4260 | 0 | 0 | 0 | 4260 |  | 0 | 0 | 4260 | 15d | 0 | 0 | 0 | 4260 | 0% | Not Started | 0 | 0
18 | meeting concrete suppliers | 2017-03-09 08:00 | 2017-03-22 17:00 | 10d |  | 0 | 2112 | 0 | 0 | 2112 |  | 0 | 0 | 2112 | 10d | 0 | 0 | 0 | 2112 | 0% | Not Started | 0 | 0
44 | Ict | 2017-03-09 08:00 | 2017-07-07 17:00 | 87d |  |  | 168000 |  |  | 175560 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | ICT contracter search | 2017-03-09 08:00 | 2017-04-03 17:00 | 18d | Admin[0.50 #2];Aankoop[0.50 #2];Engineer[0.50 #5] | 7560 | 0 | 0 | 0 | 7560 |  | 0 | 0 | 7560 | 18d | 0 | 0 | 0 | 7560 | 0% | Not Started | 0 | 0
21 | Developing app | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 57d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
22 | developing pay system | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 57d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
23 | Testing & approve app | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 |  | 0 | 0 | 84000 | 12d | 0 | 0 | 0 | 84000 | 0% | Not Started | 0 | 0
24 | Testing & approve pay system | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 |  | 0 | 0 | 84000 | 12d | 0 | 0 | 0 | 84000 | 0% | Not Started | 0 | 0
45 | Repair place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d |  |  | 0 |  |  | 17664 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | construct bike repearing place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d | Arb[4.00 #4] | 17664 | 0 | 0 | 0 | 17664 |  | 0 | 0 | 17664 | 23d | 0 | 0 | 0 | 17664 | 0% | Not Started | 0 | 0
46 | Delivery | 2017-03-30 08:00 | 2017-07-12 17:00 | 75d |  |  | 460000 |  |  | 460000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
28 | Delivery bikes parts | 2017-05-04 08:00 | 2017-07-12 17:00 | 50d |  | 0 | 150000 | 0 | 0 | 150000 |  | 0 | 0 | 150000 | 50d | 0 | 0 | 0 | 150000 | 0% | Not Started | 0 | 0
29 | delivery docking station & power tower | 2017-04-27 08:00 | 2017-06-07 17:00 | 30d |  | 0 | 250000 | 0 | 0 | 250000 |  | 0 | 0 | 250000 | 30d | 0 | 0 | 0 | 250000 | 0% | Not Started | 0 | 0
30 | delivery ducts | 2017-03-30 08:00 | 2017-04-24 17:00 | 18d |  | 0 | 60000 | 0 | 0 | 60000 |  | 0 | 0 | 60000 | 18d | 0 | 0 | 0 | 60000 | 0% | Not Started | 0 | 0
47 | Assembly | 2017-04-25 08:00 | 2017-08-31 17:00 | 93d |  |  | 0 |  |  | 72575.9999 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | assembly docking station & power tower | 2017-06-08 08:00 | 2017-08-09 17:00 | 45d | Engineer[0.88 #2];Arb[2.00 #4] | 31535.9999 | 0 | 0 | 0 | 31535.9999 |  | 0 | 0 | 31535.9999 | 45d | 0 | 0 | 0 | 31535.9999 | 0% | Not Started | 0 | 0
33 | assembly bikes & Testing | 2017-07-13 08:00 | 2017-08-31 17:00 | 36d | Arb[4.00 #4] | 27648 | 0 | 0 | 0 | 27648 |  | 0 | 0 | 27648 | 36d | 0 | 0 | 0 | 27648 | 0% | Not Started | 0 | 0
34 | assembly ducts | 2017-04-25 08:00 | 2017-05-18 17:00 | 18d | Engineer;Arb[2.00 #4] | 13392 | 0 | 0 | 0 | 13392 |  | 0 | 0 | 13392 | 18d | 0 | 0 | 0 | 13392 | 0% | Not Started | 0 | 0
48 | Construction total | 2017-04-06 08:00 | 2017-10-02 17:00 | 128d |  |  | 770922 |  |  | 770922 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | Construction 1 | 2017-04-06 08:00 | 2017-07-04 17:00 | 64d |  | 0 | 587706 | 0 | 0 | 587706 |  | 0 | 0 | 587706 | 64d | 0 | 0 | 0 | 587706 | 0% | Not Started | 0 | 0
37 | Construction 2 | 2017-08-10 08:00 | 2017-10-02 17:00 | 38d |  | 0 | 183216 | 0 | 0 | 183216 |  | 0 | 0 | 183216 | 38d | 0 | 0 | 0 | 183216 | 0% | Not Started | 0 | 0
49 | Final phase | 2017-10-03 08:00 | 2017-11-28 17:00 | 41d |  |  | 0 |  |  | 11520 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | Placing bikes | 2017-10-03 08:00 | 2017-10-23 17:00 | 15d | Arb[4.00 #4] | 11520 | 0 | 0 | 0 | 11520 |  | 0 | 0 | 11520 | 15d | 0 | 0 | 0 | 11520 | 0% | Not Started | 0 | 0
40 | Final testing the total system | 2017-10-24 08:00 | 2017-11-28 17:00 | 26d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 26d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
50 | Project buffer | 2017-11-29 08:00 | 2018-03-20 17:00 | 80d |  | 0 | 100000 | 0 | 0 | 100000 |  | 0 | 0 | 100000 | 80d | 0 | 0 | 0 | 100000 | 0% | Not Started | 0 | 0

## TP2
| TP Status Date | 2016-12-27 17:00 |  | TP Name | 27/12/2016 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | projectKopie | 2016-11-16 08:00 | 2018-03-20 17:00 | 350d |  |  | 1546034 |  |  | 1703349.9999 |  | 30d | [5 empty] | 63630 |  | 3.627% |  | 61786.6667 | 62280
41 | Onderzoek | 2016-11-16 08:00 | 2017-01-25 17:00 | 51d |  |  | 0 |  |  | 23776 |  | 30d | [5 empty] | 18630 |  | 70.6% |  | 16786.6667 | 17280
2 | Analysis of bikes and bikes usage in gent by students | 2016-11-16 08:00 | 2016-12-05 17:00 | 14d | Engineer[2.00 #2] | 10080 | 0 | 0 | 0 | 10080 | 2016-11-16 08:00 | 19d 3h | 13950 | 0 | 0 | 0 | 0 | 13950 | 0 | 100% | Finished | 10080 | 10080
3 | Properties of the bike | 2016-12-06 08:00 | 2016-12-09 17:00 | 4d | Engineer | 1440 | 0 | 0 | 0 | 1440 | 2016-12-13 11:00 | 2d 3h | 855 | 0 | 0 | 0 | 0 | 855 | 0 | 100% | Finished | 1440 | 1440
4 | Determine amount of bikes needed and hot spots | 2016-12-06 08:00 | 2016-12-12 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2016-12-13 11:00 | 4d 1h | 1485 | 0 | 0 | 0 | 0 | 1485 | 0 | 100% | Finished | 1800 | 1800
5 | research for possibledocking stations | 2016-12-13 08:00 | 2017-01-09 17:00 | 20d | Engineer | 7200 | 0 | 0 | 0 | 7200 | 2016-12-19 13:00 | 6d 4h | 2340 | 2520 | 7d | 0 | 0 | 2340 | 2520 | 48.15% | Started | 3466.6667 | 3960
6 | Resarch amount of staff needed (extra contractors) | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 |  | 0 | 0 | 1800 | 5d | 0 | 0 | 0 | 1800 | 0% | Not Started | 0 | 0
7 | feasibility study | 2017-01-17 08:00 | 2017-01-25 17:00 | 7d | Admin | 1456 | 0 | 0 | 0 | 1456 |  | 0 | 0 | 1456 | 7d | 0 | 0 | 0 | 1456 | 0% | Not Started | 0 | 0
42 | Vans | 2016-12-13 08:00 | 2017-01-26 17:00 | 33d |  |  | 45000 |  |  | 47880 |  | 6d 4h | [5 empty] | 45000 |  | 93.98% |  | 45000 | 45000
9 | determine type and amound of vans | 2016-12-13 08:00 | 2016-12-15 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 2016-12-19 13:00 | 3d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
10 | buy vans | 2016-12-16 08:00 | 2017-01-05 17:00 | 15d |  | 0 | 45000 | 0 | 0 | 45000 | 2016-12-22 13:00 | 3d 4h | 45000 | 0 | 10d 5h | 0 | 0 | 45000 | 0 | 24.78% | Started | 45000 | 45000
11 | adjust vans | 2017-01-06 08:00 | 2017-01-26 17:00 | 15d | Arb | 2880 | 0 | 0 | 0 | 2880 |  | 0 | 0 | 2880 | 15d | 0 | 0 | 0 | 2880 | 0% | Not Started | 0 | 0
43 | Meeting | 2017-01-26 08:00 | 2017-05-03 17:00 | 70d |  |  | 2112 |  |  | 23452 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
13 | Asking town for permission | 2017-01-26 08:00 | 2017-03-08 17:00 | 30d | Aankoop | 8160 | 0 | 0 | 0 | 8160 |  | 0 | 0 | 8160 | 30d | 0 | 0 | 0 | 8160 | 0% | Not Started | 0 | 0
14 | Asking town for blue prints porwer network | 2017-03-09 08:00 | 2017-04-05 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 20d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
15 | meeting with bike suppliers and contracting | 2017-03-09 08:00 | 2017-05-03 17:00 | 40d | Admin[0.50 #2] | 4160 | 0 | 0 | 0 | 4160 |  | 0 | 0 | 4160 | 40d | 0 | 0 | 0 | 4160 | 0% | Not Started | 0 | 0
16 | meeting with docking stations and tower suppliers and contracting | 2017-03-09 08:00 | 2017-04-26 17:00 | 35d | Aankoop[0.50 #2] | 4760 | 0 | 0 | 0 | 4760 |  | 0 | 0 | 4760 | 35d | 0 | 0 | 0 | 4760 | 0% | Not Started | 0 | 0
17 | meeting with duct suppliers & cable supliers & contracting | 2017-03-09 08:00 | 2017-03-29 17:00 | 15d | Engineer[0.50 #2];Admin[0.50 #2] | 4260 | 0 | 0 | 0 | 4260 |  | 0 | 0 | 4260 | 15d | 0 | 0 | 0 | 4260 | 0% | Not Started | 0 | 0
18 | meeting concrete suppliers | 2017-03-09 08:00 | 2017-03-22 17:00 | 10d |  | 0 | 2112 | 0 | 0 | 2112 |  | 0 | 0 | 2112 | 10d | 0 | 0 | 0 | 2112 | 0% | Not Started | 0 | 0
44 | Ict | 2017-03-09 08:00 | 2017-07-07 17:00 | 87d |  |  | 168000 |  |  | 175560 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | ICT contracter search | 2017-03-09 08:00 | 2017-04-03 17:00 | 18d | Admin[0.50 #2];Aankoop[0.50 #2];Engineer[0.50 #5] | 7560 | 0 | 0 | 0 | 7560 |  | 0 | 0 | 7560 | 18d | 0 | 0 | 0 | 7560 | 0% | Not Started | 0 | 0
21 | Developing app | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 57d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
22 | developing pay system | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 57d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
23 | Testing & approve app | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 |  | 0 | 0 | 84000 | 12d | 0 | 0 | 0 | 84000 | 0% | Not Started | 0 | 0
24 | Testing & approve pay system | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 |  | 0 | 0 | 84000 | 12d | 0 | 0 | 0 | 84000 | 0% | Not Started | 0 | 0
45 | Repair place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d |  |  | 0 |  |  | 17664 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | construct bike repearing place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d | Arb[4.00 #4] | 17664 | 0 | 0 | 0 | 17664 |  | 0 | 0 | 17664 | 23d | 0 | 0 | 0 | 17664 | 0% | Not Started | 0 | 0
46 | Delivery | 2017-03-30 08:00 | 2017-07-12 17:00 | 75d |  |  | 460000 |  |  | 460000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
28 | Delivery bikes parts | 2017-05-04 08:00 | 2017-07-12 17:00 | 50d |  | 0 | 150000 | 0 | 0 | 150000 |  | 0 | 0 | 150000 | 50d | 0 | 0 | 0 | 150000 | 0% | Not Started | 0 | 0
29 | delivery docking station & power tower | 2017-04-27 08:00 | 2017-06-07 17:00 | 30d |  | 0 | 250000 | 0 | 0 | 250000 |  | 0 | 0 | 250000 | 30d | 0 | 0 | 0 | 250000 | 0% | Not Started | 0 | 0
30 | delivery ducts | 2017-03-30 08:00 | 2017-04-24 17:00 | 18d |  | 0 | 60000 | 0 | 0 | 60000 |  | 0 | 0 | 60000 | 18d | 0 | 0 | 0 | 60000 | 0% | Not Started | 0 | 0
47 | Assembly | 2017-04-25 08:00 | 2017-08-31 17:00 | 93d |  |  | 0 |  |  | 72575.9999 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | assembly docking station & power tower | 2017-06-08 08:00 | 2017-08-09 17:00 | 45d | Engineer[0.88 #2];Arb[2.00 #4] | 31535.9999 | 0 | 0 | 0 | 31535.9999 |  | 0 | 0 | 31535.9999 | 45d | 0 | 0 | 0 | 31535.9999 | 0% | Not Started | 0 | 0
33 | assembly bikes & Testing | 2017-07-13 08:00 | 2017-08-31 17:00 | 36d | Arb[4.00 #4] | 27648 | 0 | 0 | 0 | 27648 |  | 0 | 0 | 27648 | 36d | 0 | 0 | 0 | 27648 | 0% | Not Started | 0 | 0
34 | assembly ducts | 2017-04-25 08:00 | 2017-05-18 17:00 | 18d | Engineer;Arb[2.00 #4] | 13392 | 0 | 0 | 0 | 13392 |  | 0 | 0 | 13392 | 18d | 0 | 0 | 0 | 13392 | 0% | Not Started | 0 | 0
48 | Construction total | 2017-04-06 08:00 | 2017-10-02 17:00 | 128d |  |  | 770922 |  |  | 770922 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | Construction 1 | 2017-04-06 08:00 | 2017-07-04 17:00 | 64d |  | 0 | 587706 | 0 | 0 | 587706 |  | 0 | 0 | 587706 | 64d | 0 | 0 | 0 | 587706 | 0% | Not Started | 0 | 0
37 | Construction 2 | 2017-08-10 08:00 | 2017-10-02 17:00 | 38d |  | 0 | 183216 | 0 | 0 | 183216 |  | 0 | 0 | 183216 | 38d | 0 | 0 | 0 | 183216 | 0% | Not Started | 0 | 0
49 | Final phase | 2017-10-03 08:00 | 2017-11-28 17:00 | 41d |  |  | 0 |  |  | 11520 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | Placing bikes | 2017-10-03 08:00 | 2017-10-23 17:00 | 15d | Arb[4.00 #4] | 11520 | 0 | 0 | 0 | 11520 |  | 0 | 0 | 11520 | 15d | 0 | 0 | 0 | 11520 | 0% | Not Started | 0 | 0
40 | Final testing the total system | 2017-10-24 08:00 | 2017-11-28 17:00 | 26d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 26d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
50 | Project buffer | 2017-11-29 08:00 | 2018-03-20 17:00 | 80d |  | 0 | 100000 | 0 | 0 | 100000 |  | 0 | 0 | 100000 | 80d | 0 | 0 | 0 | 100000 | 0% | Not Started | 0 | 0

## TP3
| TP Status Date | 2017-01-17 17:00 |  | TP Name | 17/01/2017 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | projectKopie | 2016-11-16 08:00 | 2018-03-20 17:00 | 350d |  |  | 1546034 |  |  | 1703349.9999 |  | 45d | [5 empty] | 69547 |  | 4.047% |  | 68927.0353 | 69064
41 | Onderzoek | 2016-11-16 08:00 | 2017-01-25 17:00 | 51d |  |  | 0 |  |  | 23776 |  | 45d | [5 empty] | 23707 |  | 96.48% |  | 22938.8 | 22528
2 | Analysis of bikes and bikes usage in gent by students | 2016-11-16 08:00 | 2016-12-05 17:00 | 14d | Engineer[2.00 #2] | 10080 | 0 | 0 | 0 | 10080 | 2016-11-16 08:00 | 19d 3h | 13950 | 0 | 0 | 0 | 0 | 13950 | 0 | 100% | Finished | 10080 | 10080
3 | Properties of the bike | 2016-12-06 08:00 | 2016-12-09 17:00 | 4d | Engineer | 1440 | 0 | 0 | 0 | 1440 | 2016-12-13 11:00 | 2d 3h | 855 | 0 | 0 | 0 | 0 | 855 | 0 | 100% | Finished | 1440 | 1440
4 | Determine amount of bikes needed and hot spots | 2016-12-06 08:00 | 2016-12-12 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2016-12-13 11:00 | 4d 1h | 1485 | 0 | 0 | 0 | 0 | 1485 | 0 | 100% | Finished | 1800 | 1800
5 | research for possibledocking stations | 2016-12-13 08:00 | 2017-01-09 17:00 | 20d | Engineer | 7200 | 0 | 0 | 0 | 7200 | 2016-12-19 13:00 | 13d 4h | 4860 | 0 | 0 | 0 | 0 | 4860 | 0 | 100% | Finished | 7200 | 7200
6 | Resarch amount of staff needed (extra contractors) | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2017-01-06 08:00 | 5d 7h | 2115 | 0 | 0 | 0 | 0 | 2115 | 0 | 100% | Finished | 1800 | 1800
7 | feasibility study | 2017-01-17 08:00 | 2017-01-25 17:00 | 7d | Admin | 1456 | 0 | 0 | 0 | 1456 | 2017-01-13 16:00 | 2d 1h | 442 | 598 | 2d 7h | 0 | 0 | 442 | 598 | 42.5% | Started | 618.8 | 208
42 | Vans | 2016-12-13 08:00 | 2017-01-26 17:00 | 33d |  |  | 45000 |  |  | 47880 |  | 21d 4h | [5 empty] | 45840 |  | 96.05% |  | 45988.2353 | 46536
9 | determine type and amound of vans | 2016-12-13 08:00 | 2016-12-15 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 2016-12-19 13:00 | 3d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
10 | buy vans | 2016-12-16 08:00 | 2017-01-05 17:00 | 15d |  | 0 | 45000 | 0 | 0 | 45000 | 2016-12-22 13:00 | 14d 1h | 45000 | 0 | 0 | 0 | 0 | 45000 | 0 | 100% | Finished | 45000 | 45000
11 | adjust vans | 2017-01-06 08:00 | 2017-01-26 17:00 | 15d | Arb | 2880 | 0 | 0 | 0 | 2880 | 2017-01-11 14:00 | 4d 3h | 840 | 1608 | 8d 3h | 0 | 0 | 840 | 1608 | 34.31% | Started | 988.2353 | 1536
43 | Meeting | 2017-01-26 08:00 | 2017-05-03 17:00 | 70d |  |  | 2112 |  |  | 23452 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
13 | Asking town for permission | 2017-01-26 08:00 | 2017-03-08 17:00 | 30d | Aankoop | 8160 | 0 | 0 | 0 | 8160 |  | 0 | 0 | 8160 | 30d | 0 | 0 | 0 | 8160 | 0% | Not Started | 0 | 0
14 | Asking town for blue prints porwer network | 2017-03-09 08:00 | 2017-04-05 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 20d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
15 | meeting with bike suppliers and contracting | 2017-03-09 08:00 | 2017-05-03 17:00 | 40d | Admin[0.50 #2] | 4160 | 0 | 0 | 0 | 4160 |  | 0 | 0 | 4160 | 40d | 0 | 0 | 0 | 4160 | 0% | Not Started | 0 | 0
16 | meeting with docking stations and tower suppliers and contracting | 2017-03-09 08:00 | 2017-04-26 17:00 | 35d | Aankoop[0.50 #2] | 4760 | 0 | 0 | 0 | 4760 |  | 0 | 0 | 4760 | 35d | 0 | 0 | 0 | 4760 | 0% | Not Started | 0 | 0
17 | meeting with duct suppliers & cable supliers & contracting | 2017-03-09 08:00 | 2017-03-29 17:00 | 15d | Engineer[0.50 #2];Admin[0.50 #2] | 4260 | 0 | 0 | 0 | 4260 |  | 0 | 0 | 4260 | 15d | 0 | 0 | 0 | 4260 | 0% | Not Started | 0 | 0
18 | meeting concrete suppliers | 2017-03-09 08:00 | 2017-03-22 17:00 | 10d |  | 0 | 2112 | 0 | 0 | 2112 |  | 0 | 0 | 2112 | 10d | 0 | 0 | 0 | 2112 | 0% | Not Started | 0 | 0
44 | Ict | 2017-03-09 08:00 | 2017-07-07 17:00 | 87d |  |  | 168000 |  |  | 175560 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | ICT contracter search | 2017-03-09 08:00 | 2017-04-03 17:00 | 18d | Admin[0.50 #2];Aankoop[0.50 #2];Engineer[0.50 #5] | 7560 | 0 | 0 | 0 | 7560 |  | 0 | 0 | 7560 | 18d | 0 | 0 | 0 | 7560 | 0% | Not Started | 0 | 0
21 | Developing app | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 57d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
22 | developing pay system | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 57d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
23 | Testing & approve app | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 |  | 0 | 0 | 84000 | 12d | 0 | 0 | 0 | 84000 | 0% | Not Started | 0 | 0
24 | Testing & approve pay system | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 |  | 0 | 0 | 84000 | 12d | 0 | 0 | 0 | 84000 | 0% | Not Started | 0 | 0
45 | Repair place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d |  |  | 0 |  |  | 17664 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | construct bike repearing place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d | Arb[4.00 #4] | 17664 | 0 | 0 | 0 | 17664 |  | 0 | 0 | 17664 | 23d | 0 | 0 | 0 | 17664 | 0% | Not Started | 0 | 0
46 | Delivery | 2017-03-30 08:00 | 2017-07-12 17:00 | 75d |  |  | 460000 |  |  | 460000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
28 | Delivery bikes parts | 2017-05-04 08:00 | 2017-07-12 17:00 | 50d |  | 0 | 150000 | 0 | 0 | 150000 |  | 0 | 0 | 150000 | 50d | 0 | 0 | 0 | 150000 | 0% | Not Started | 0 | 0
29 | delivery docking station & power tower | 2017-04-27 08:00 | 2017-06-07 17:00 | 30d |  | 0 | 250000 | 0 | 0 | 250000 |  | 0 | 0 | 250000 | 30d | 0 | 0 | 0 | 250000 | 0% | Not Started | 0 | 0
30 | delivery ducts | 2017-03-30 08:00 | 2017-04-24 17:00 | 18d |  | 0 | 60000 | 0 | 0 | 60000 |  | 0 | 0 | 60000 | 18d | 0 | 0 | 0 | 60000 | 0% | Not Started | 0 | 0
47 | Assembly | 2017-04-25 08:00 | 2017-08-31 17:00 | 93d |  |  | 0 |  |  | 72575.9999 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | assembly docking station & power tower | 2017-06-08 08:00 | 2017-08-09 17:00 | 45d | Engineer[0.88 #2];Arb[2.00 #4] | 31535.9999 | 0 | 0 | 0 | 31535.9999 |  | 0 | 0 | 31535.9999 | 45d | 0 | 0 | 0 | 31535.9999 | 0% | Not Started | 0 | 0
33 | assembly bikes & Testing | 2017-07-13 08:00 | 2017-08-31 17:00 | 36d | Arb[4.00 #4] | 27648 | 0 | 0 | 0 | 27648 |  | 0 | 0 | 27648 | 36d | 0 | 0 | 0 | 27648 | 0% | Not Started | 0 | 0
34 | assembly ducts | 2017-04-25 08:00 | 2017-05-18 17:00 | 18d | Engineer;Arb[2.00 #4] | 13392 | 0 | 0 | 0 | 13392 |  | 0 | 0 | 13392 | 18d | 0 | 0 | 0 | 13392 | 0% | Not Started | 0 | 0
48 | Construction total | 2017-04-06 08:00 | 2017-10-02 17:00 | 128d |  |  | 770922 |  |  | 770922 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | Construction 1 | 2017-04-06 08:00 | 2017-07-04 17:00 | 64d |  | 0 | 587706 | 0 | 0 | 587706 |  | 0 | 0 | 587706 | 64d | 0 | 0 | 0 | 587706 | 0% | Not Started | 0 | 0
37 | Construction 2 | 2017-08-10 08:00 | 2017-10-02 17:00 | 38d |  | 0 | 183216 | 0 | 0 | 183216 |  | 0 | 0 | 183216 | 38d | 0 | 0 | 0 | 183216 | 0% | Not Started | 0 | 0
49 | Final phase | 2017-10-03 08:00 | 2017-11-28 17:00 | 41d |  |  | 0 |  |  | 11520 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | Placing bikes | 2017-10-03 08:00 | 2017-10-23 17:00 | 15d | Arb[4.00 #4] | 11520 | 0 | 0 | 0 | 11520 |  | 0 | 0 | 11520 | 15d | 0 | 0 | 0 | 11520 | 0% | Not Started | 0 | 0
40 | Final testing the total system | 2017-10-24 08:00 | 2017-11-28 17:00 | 26d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 26d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
50 | Project buffer | 2017-11-29 08:00 | 2018-03-20 17:00 | 80d |  | 0 | 100000 | 0 | 0 | 100000 |  | 0 | 0 | 100000 | 80d | 0 | 0 | 0 | 100000 | 0% | Not Started | 0 | 0

## TP4
| TP Status Date | 2017-02-07 17:00 |  | TP Name | 7/02/2017 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | projectKopie | 2016-11-16 08:00 | 2018-03-20 17:00 | 350d |  |  | 1546034 |  |  | 1703349.9999 |  | 60d | [5 empty] | 80139 |  | 4.605% |  | 78440.8371 | 80248
41 | Onderzoek | 2016-11-16 08:00 | 2017-01-25 17:00 | 51d |  |  | 0 |  |  | 23776 |  | 47d 7h | [5 empty] | 24305 |  | 100% |  | 23776 | 23776
2 | Analysis of bikes and bikes usage in gent by students | 2016-11-16 08:00 | 2016-12-05 17:00 | 14d | Engineer[2.00 #2] | 10080 | 0 | 0 | 0 | 10080 | 2016-11-16 08:00 | 19d 3h | 13950 | 0 | 0 | 0 | 0 | 13950 | 0 | 100% | Finished | 10080 | 10080
3 | Properties of the bike | 2016-12-06 08:00 | 2016-12-09 17:00 | 4d | Engineer | 1440 | 0 | 0 | 0 | 1440 | 2016-12-13 11:00 | 2d 3h | 855 | 0 | 0 | 0 | 0 | 855 | 0 | 100% | Finished | 1440 | 1440
4 | Determine amount of bikes needed and hot spots | 2016-12-06 08:00 | 2016-12-12 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2016-12-13 11:00 | 4d 1h | 1485 | 0 | 0 | 0 | 0 | 1485 | 0 | 100% | Finished | 1800 | 1800
5 | research for possibledocking stations | 2016-12-13 08:00 | 2017-01-09 17:00 | 20d | Engineer | 7200 | 0 | 0 | 0 | 7200 | 2016-12-19 13:00 | 13d 4h | 4860 | 0 | 0 | 0 | 0 | 4860 | 0 | 100% | Finished | 7200 | 7200
6 | Resarch amount of staff needed (extra contractors) | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2017-01-06 08:00 | 5d 7h | 2115 | 0 | 0 | 0 | 0 | 2115 | 0 | 100% | Finished | 1800 | 1800
7 | feasibility study | 2017-01-17 08:00 | 2017-01-25 17:00 | 7d | Admin | 1456 | 0 | 0 | 0 | 1456 | 2017-01-13 16:00 | 5d | 1040 | 0 | 0 | 0 | 0 | 1040 | 0 | 100% | Finished | 1456 | 1456
42 | Vans | 2016-12-13 08:00 | 2017-01-26 17:00 | 33d |  |  | 45000 |  |  | 47880 |  | 29d 7h | [5 empty] | 47448 |  | 100% |  | 47880 | 47880
9 | determine type and amound of vans | 2016-12-13 08:00 | 2016-12-15 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 2016-12-19 13:00 | 3d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
10 | buy vans | 2016-12-16 08:00 | 2017-01-05 17:00 | 15d |  | 0 | 45000 | 0 | 0 | 45000 | 2016-12-22 13:00 | 14d 1h | 45000 | 0 | 0 | 0 | 0 | 45000 | 0 | 100% | Finished | 45000 | 45000
11 | adjust vans | 2017-01-06 08:00 | 2017-01-26 17:00 | 15d | Arb | 2880 | 0 | 0 | 0 | 2880 | 2017-01-11 14:00 | 12d 6h | 2448 | 0 | 0 | 0 | 0 | 2448 | 0 | 100% | Finished | 2880 | 2880
43 | Meeting | 2017-01-26 08:00 | 2017-05-03 17:00 | 70d |  |  | 2112 |  |  | 23452 |  | 12d 1h | [5 empty] | 3298 |  | 11.03% |  | 2586.6668 | 2448
13 | Asking town for permission | 2017-01-26 08:00 | 2017-03-08 17:00 | 30d | Aankoop | 8160 | 0 | 0 | 0 | 8160 | 2017-01-20 16:00 | 12d 1h | 3298 | 7106 | 26d 1h | 0 | 0 | 3298 | 7106 | 31.7% | Started | 2586.6668 | 2448
14 | Asking town for blue prints porwer network | 2017-03-09 08:00 | 2017-04-05 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 20d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
15 | meeting with bike suppliers and contracting | 2017-03-09 08:00 | 2017-05-03 17:00 | 40d | Admin[0.50 #2] | 4160 | 0 | 0 | 0 | 4160 |  | 0 | 0 | 4160 | 40d | 0 | 0 | 0 | 4160 | 0% | Not Started | 0 | 0
16 | meeting with docking stations and tower suppliers and contracting | 2017-03-09 08:00 | 2017-04-26 17:00 | 35d | Aankoop[0.50 #2] | 4760 | 0 | 0 | 0 | 4760 |  | 0 | 0 | 4760 | 35d | 0 | 0 | 0 | 4760 | 0% | Not Started | 0 | 0
17 | meeting with duct suppliers & cable supliers & contracting | 2017-03-09 08:00 | 2017-03-29 17:00 | 15d | Engineer[0.50 #2];Admin[0.50 #2] | 4260 | 0 | 0 | 0 | 4260 |  | 0 | 0 | 4260 | 15d | 0 | 0 | 0 | 4260 | 0% | Not Started | 0 | 0
18 | meeting concrete suppliers | 2017-03-09 08:00 | 2017-03-22 17:00 | 10d |  | 0 | 2112 | 0 | 0 | 2112 |  | 0 | 0 | 2112 | 10d | 0 | 0 | 0 | 2112 | 0% | Not Started | 0 | 0
44 | Ict | 2017-03-09 08:00 | 2017-07-07 17:00 | 87d |  |  | 168000 |  |  | 175560 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | ICT contracter search | 2017-03-09 08:00 | 2017-04-03 17:00 | 18d | Admin[0.50 #2];Aankoop[0.50 #2];Engineer[0.50 #5] | 7560 | 0 | 0 | 0 | 7560 |  | 0 | 0 | 7560 | 18d | 0 | 0 | 0 | 7560 | 0% | Not Started | 0 | 0
21 | Developing app | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 57d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
22 | developing pay system | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 57d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
23 | Testing & approve app | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 |  | 0 | 0 | 84000 | 12d | 0 | 0 | 0 | 84000 | 0% | Not Started | 0 | 0
24 | Testing & approve pay system | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 |  | 0 | 0 | 84000 | 12d | 0 | 0 | 0 | 84000 | 0% | Not Started | 0 | 0
45 | Repair place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d |  |  | 0 |  |  | 17664 |  | 6d 5h | [5 empty] | 5088 |  | 23.77% |  | 4198.1703 | 6144
26 | construct bike repearing place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d | Arb[4.00 #4] | 17664 | 0 | 0 | 0 | 17664 | 2017-01-30 11:00 | 6d 5h | 5088 | 16320 | 21d 2h | 0 | 0 | 5088 | 16320 | 23.77% | Started | 4198.1703 | 6144
46 | Delivery | 2017-03-30 08:00 | 2017-07-12 17:00 | 75d |  |  | 460000 |  |  | 460000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
28 | Delivery bikes parts | 2017-05-04 08:00 | 2017-07-12 17:00 | 50d |  | 0 | 150000 | 0 | 0 | 150000 |  | 0 | 0 | 150000 | 50d | 0 | 0 | 0 | 150000 | 0% | Not Started | 0 | 0
29 | delivery docking station & power tower | 2017-04-27 08:00 | 2017-06-07 17:00 | 30d |  | 0 | 250000 | 0 | 0 | 250000 |  | 0 | 0 | 250000 | 30d | 0 | 0 | 0 | 250000 | 0% | Not Started | 0 | 0
30 | delivery ducts | 2017-03-30 08:00 | 2017-04-24 17:00 | 18d |  | 0 | 60000 | 0 | 0 | 60000 |  | 0 | 0 | 60000 | 18d | 0 | 0 | 0 | 60000 | 0% | Not Started | 0 | 0
47 | Assembly | 2017-04-25 08:00 | 2017-08-31 17:00 | 93d |  |  | 0 |  |  | 72575.9999 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | assembly docking station & power tower | 2017-06-08 08:00 | 2017-08-09 17:00 | 45d | Engineer[0.88 #2];Arb[2.00 #4] | 31535.9999 | 0 | 0 | 0 | 31535.9999 |  | 0 | 0 | 31535.9999 | 45d | 0 | 0 | 0 | 31535.9999 | 0% | Not Started | 0 | 0
33 | assembly bikes & Testing | 2017-07-13 08:00 | 2017-08-31 17:00 | 36d | Arb[4.00 #4] | 27648 | 0 | 0 | 0 | 27648 |  | 0 | 0 | 27648 | 36d | 0 | 0 | 0 | 27648 | 0% | Not Started | 0 | 0
34 | assembly ducts | 2017-04-25 08:00 | 2017-05-18 17:00 | 18d | Engineer;Arb[2.00 #4] | 13392 | 0 | 0 | 0 | 13392 |  | 0 | 0 | 13392 | 18d | 0 | 0 | 0 | 13392 | 0% | Not Started | 0 | 0
48 | Construction total | 2017-04-06 08:00 | 2017-10-02 17:00 | 128d |  |  | 770922 |  |  | 770922 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | Construction 1 | 2017-04-06 08:00 | 2017-07-04 17:00 | 64d |  | 0 | 587706 | 0 | 0 | 587706 |  | 0 | 0 | 587706 | 64d | 0 | 0 | 0 | 587706 | 0% | Not Started | 0 | 0
37 | Construction 2 | 2017-08-10 08:00 | 2017-10-02 17:00 | 38d |  | 0 | 183216 | 0 | 0 | 183216 |  | 0 | 0 | 183216 | 38d | 0 | 0 | 0 | 183216 | 0% | Not Started | 0 | 0
49 | Final phase | 2017-10-03 08:00 | 2017-11-28 17:00 | 41d |  |  | 0 |  |  | 11520 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | Placing bikes | 2017-10-03 08:00 | 2017-10-23 17:00 | 15d | Arb[4.00 #4] | 11520 | 0 | 0 | 0 | 11520 |  | 0 | 0 | 11520 | 15d | 0 | 0 | 0 | 11520 | 0% | Not Started | 0 | 0
40 | Final testing the total system | 2017-10-24 08:00 | 2017-11-28 17:00 | 26d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 26d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
50 | Project buffer | 2017-11-29 08:00 | 2018-03-20 17:00 | 80d |  | 0 | 100000 | 0 | 0 | 100000 |  | 0 | 0 | 100000 | 80d | 0 | 0 | 0 | 100000 | 0% | Not Started | 0 | 0

## TP5
| TP Status Date | 2017-02-28 17:00 |  | TP Name | 28/02/2017 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | projectKopie | 2016-11-16 08:00 | 2018-03-20 17:00 | 350d |  |  | 1546034 |  |  | 1703349.9999 |  | 75d | [5 empty] | 95739 |  | 5.351% |  | 91146.1281 | 95848
41 | Onderzoek | 2016-11-16 08:00 | 2017-01-25 17:00 | 51d |  |  | 0 |  |  | 23776 |  | 47d 7h | [5 empty] | 24305 |  | 100% |  | 23776 | 23776
2 | Analysis of bikes and bikes usage in gent by students | 2016-11-16 08:00 | 2016-12-05 17:00 | 14d | Engineer[2.00 #2] | 10080 | 0 | 0 | 0 | 10080 | 2016-11-16 08:00 | 19d 3h | 13950 | 0 | 0 | 0 | 0 | 13950 | 0 | 100% | Finished | 10080 | 10080
3 | Properties of the bike | 2016-12-06 08:00 | 2016-12-09 17:00 | 4d | Engineer | 1440 | 0 | 0 | 0 | 1440 | 2016-12-13 11:00 | 2d 3h | 855 | 0 | 0 | 0 | 0 | 855 | 0 | 100% | Finished | 1440 | 1440
4 | Determine amount of bikes needed and hot spots | 2016-12-06 08:00 | 2016-12-12 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2016-12-13 11:00 | 4d 1h | 1485 | 0 | 0 | 0 | 0 | 1485 | 0 | 100% | Finished | 1800 | 1800
5 | research for possibledocking stations | 2016-12-13 08:00 | 2017-01-09 17:00 | 20d | Engineer | 7200 | 0 | 0 | 0 | 7200 | 2016-12-19 13:00 | 13d 4h | 4860 | 0 | 0 | 0 | 0 | 4860 | 0 | 100% | Finished | 7200 | 7200
6 | Resarch amount of staff needed (extra contractors) | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2017-01-06 08:00 | 5d 7h | 2115 | 0 | 0 | 0 | 0 | 2115 | 0 | 100% | Finished | 1800 | 1800
7 | feasibility study | 2017-01-17 08:00 | 2017-01-25 17:00 | 7d | Admin | 1456 | 0 | 0 | 0 | 1456 | 2017-01-13 16:00 | 5d | 1040 | 0 | 0 | 0 | 0 | 1040 | 0 | 100% | Finished | 1456 | 1456
42 | Vans | 2016-12-13 08:00 | 2017-01-26 17:00 | 33d |  |  | 45000 |  |  | 47880 |  | 29d 7h | [5 empty] | 47448 |  | 100% |  | 47880 | 47880
9 | determine type and amound of vans | 2016-12-13 08:00 | 2016-12-15 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 2016-12-19 13:00 | 3d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
10 | buy vans | 2016-12-16 08:00 | 2017-01-05 17:00 | 15d |  | 0 | 45000 | 0 | 0 | 45000 | 2016-12-22 13:00 | 14d 1h | 45000 | 0 | 0 | 0 | 0 | 45000 | 0 | 100% | Finished | 45000 | 45000
11 | adjust vans | 2017-01-06 08:00 | 2017-01-26 17:00 | 15d | Arb | 2880 | 0 | 0 | 0 | 2880 | 2017-01-11 14:00 | 12d 6h | 2448 | 0 | 0 | 0 | 0 | 2448 | 0 | 100% | Finished | 2880 | 2880
43 | Meeting | 2017-01-26 08:00 | 2017-05-03 17:00 | 70d |  |  | 2112 |  |  | 23452 |  | 27d 1h | [5 empty] | 7378 |  | 24.67% |  | 5786.6666 | 6528
13 | Asking town for permission | 2017-01-26 08:00 | 2017-03-08 17:00 | 30d | Aankoop | 8160 | 0 | 0 | 0 | 8160 | 2017-01-20 16:00 | 27d 1h | 7378 | 3026 | 11d 1h | 0 | 0 | 7378 | 3026 | 70.92% | Started | 5786.6666 | 6528
14 | Asking town for blue prints porwer network | 2017-03-09 08:00 | 2017-04-05 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 20d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
15 | meeting with bike suppliers and contracting | 2017-03-09 08:00 | 2017-05-03 17:00 | 40d | Admin[0.50 #2] | 4160 | 0 | 0 | 0 | 4160 |  | 0 | 0 | 4160 | 40d | 0 | 0 | 0 | 4160 | 0% | Not Started | 0 | 0
16 | meeting with docking stations and tower suppliers and contracting | 2017-03-09 08:00 | 2017-04-26 17:00 | 35d | Aankoop[0.50 #2] | 4760 | 0 | 0 | 0 | 4760 |  | 0 | 0 | 4760 | 35d | 0 | 0 | 0 | 4760 | 0% | Not Started | 0 | 0
17 | meeting with duct suppliers & cable supliers & contracting | 2017-03-09 08:00 | 2017-03-29 17:00 | 15d | Engineer[0.50 #2];Admin[0.50 #2] | 4260 | 0 | 0 | 0 | 4260 |  | 0 | 0 | 4260 | 15d | 0 | 0 | 0 | 4260 | 0% | Not Started | 0 | 0
18 | meeting concrete suppliers | 2017-03-09 08:00 | 2017-03-22 17:00 | 10d |  | 0 | 2112 | 0 | 0 | 2112 |  | 0 | 0 | 2112 | 10d | 0 | 0 | 0 | 2112 | 0% | Not Started | 0 | 0
44 | Ict | 2017-03-09 08:00 | 2017-07-07 17:00 | 87d |  |  | 168000 |  |  | 175560 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | ICT contracter search | 2017-03-09 08:00 | 2017-04-03 17:00 | 18d | Admin[0.50 #2];Aankoop[0.50 #2];Engineer[0.50 #5] | 7560 | 0 | 0 | 0 | 7560 |  | 0 | 0 | 7560 | 18d | 0 | 0 | 0 | 7560 | 0% | Not Started | 0 | 0
21 | Developing app | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 57d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
22 | developing pay system | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 57d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
23 | Testing & approve app | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 |  | 0 | 0 | 84000 | 12d | 0 | 0 | 0 | 84000 | 0% | Not Started | 0 | 0
24 | Testing & approve pay system | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 |  | 0 | 0 | 84000 | 12d | 0 | 0 | 0 | 84000 | 0% | Not Started | 0 | 0
45 | Repair place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d |  |  | 0 |  |  | 17664 |  | 21d 5h | [5 empty] | 16608 |  | 77.58% |  | 13703.4615 | 17664
26 | construct bike repearing place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d | Arb[4.00 #4] | 17664 | 0 | 0 | 0 | 17664 | 2017-01-30 11:00 | 21d 5h | 16608 | 4800 | 6d 2h | 0 | 0 | 16608 | 4800 | 77.58% | Started | 13703.4615 | 17664
46 | Delivery | 2017-03-30 08:00 | 2017-07-12 17:00 | 75d |  |  | 460000 |  |  | 460000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
28 | Delivery bikes parts | 2017-05-04 08:00 | 2017-07-12 17:00 | 50d |  | 0 | 150000 | 0 | 0 | 150000 |  | 0 | 0 | 150000 | 50d | 0 | 0 | 0 | 150000 | 0% | Not Started | 0 | 0
29 | delivery docking station & power tower | 2017-04-27 08:00 | 2017-06-07 17:00 | 30d |  | 0 | 250000 | 0 | 0 | 250000 |  | 0 | 0 | 250000 | 30d | 0 | 0 | 0 | 250000 | 0% | Not Started | 0 | 0
30 | delivery ducts | 2017-03-30 08:00 | 2017-04-24 17:00 | 18d |  | 0 | 60000 | 0 | 0 | 60000 |  | 0 | 0 | 60000 | 18d | 0 | 0 | 0 | 60000 | 0% | Not Started | 0 | 0
47 | Assembly | 2017-04-25 08:00 | 2017-08-31 17:00 | 93d |  |  | 0 |  |  | 72575.9999 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | assembly docking station & power tower | 2017-06-08 08:00 | 2017-08-09 17:00 | 45d | Engineer[0.88 #2];Arb[2.00 #4] | 31535.9999 | 0 | 0 | 0 | 31535.9999 |  | 0 | 0 | 31535.9999 | 45d | 0 | 0 | 0 | 31535.9999 | 0% | Not Started | 0 | 0
33 | assembly bikes & Testing | 2017-07-13 08:00 | 2017-08-31 17:00 | 36d | Arb[4.00 #4] | 27648 | 0 | 0 | 0 | 27648 |  | 0 | 0 | 27648 | 36d | 0 | 0 | 0 | 27648 | 0% | Not Started | 0 | 0
34 | assembly ducts | 2017-04-25 08:00 | 2017-05-18 17:00 | 18d | Engineer;Arb[2.00 #4] | 13392 | 0 | 0 | 0 | 13392 |  | 0 | 0 | 13392 | 18d | 0 | 0 | 0 | 13392 | 0% | Not Started | 0 | 0
48 | Construction total | 2017-04-06 08:00 | 2017-10-02 17:00 | 128d |  |  | 770922 |  |  | 770922 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | Construction 1 | 2017-04-06 08:00 | 2017-07-04 17:00 | 64d |  | 0 | 587706 | 0 | 0 | 587706 |  | 0 | 0 | 587706 | 64d | 0 | 0 | 0 | 587706 | 0% | Not Started | 0 | 0
37 | Construction 2 | 2017-08-10 08:00 | 2017-10-02 17:00 | 38d |  | 0 | 183216 | 0 | 0 | 183216 |  | 0 | 0 | 183216 | 38d | 0 | 0 | 0 | 183216 | 0% | Not Started | 0 | 0
49 | Final phase | 2017-10-03 08:00 | 2017-11-28 17:00 | 41d |  |  | 0 |  |  | 11520 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | Placing bikes | 2017-10-03 08:00 | 2017-10-23 17:00 | 15d | Arb[4.00 #4] | 11520 | 0 | 0 | 0 | 11520 |  | 0 | 0 | 11520 | 15d | 0 | 0 | 0 | 11520 | 0% | Not Started | 0 | 0
40 | Final testing the total system | 2017-10-24 08:00 | 2017-11-28 17:00 | 26d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 26d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
50 | Project buffer | 2017-11-29 08:00 | 2018-03-20 17:00 | 80d |  | 0 | 100000 | 0 | 0 | 100000 |  | 0 | 0 | 100000 | 80d | 0 | 0 | 0 | 100000 | 0% | Not Started | 0 | 0

## TP6
| TP Status Date | 2017-03-21 17:00 |  | TP Name | 21/03/2017 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | projectKopie | 2016-11-16 08:00 | 2018-03-20 17:00 | 350d |  |  | 1546034 |  |  | 1703349.9999 |  | 90d | [5 empty] | 109335 |  | 6.06% |  | 103221.4413 | 108088
41 | Onderzoek | 2016-11-16 08:00 | 2017-01-25 17:00 | 51d |  |  | 0 |  |  | 23776 |  | 47d 7h | [5 empty] | 24305 |  | 100% |  | 23776 | 23776
2 | Analysis of bikes and bikes usage in gent by students | 2016-11-16 08:00 | 2016-12-05 17:00 | 14d | Engineer[2.00 #2] | 10080 | 0 | 0 | 0 | 10080 | 2016-11-16 08:00 | 19d 3h | 13950 | 0 | 0 | 0 | 0 | 13950 | 0 | 100% | Finished | 10080 | 10080
3 | Properties of the bike | 2016-12-06 08:00 | 2016-12-09 17:00 | 4d | Engineer | 1440 | 0 | 0 | 0 | 1440 | 2016-12-13 11:00 | 2d 3h | 855 | 0 | 0 | 0 | 0 | 855 | 0 | 100% | Finished | 1440 | 1440
4 | Determine amount of bikes needed and hot spots | 2016-12-06 08:00 | 2016-12-12 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2016-12-13 11:00 | 4d 1h | 1485 | 0 | 0 | 0 | 0 | 1485 | 0 | 100% | Finished | 1800 | 1800
5 | research for possibledocking stations | 2016-12-13 08:00 | 2017-01-09 17:00 | 20d | Engineer | 7200 | 0 | 0 | 0 | 7200 | 2016-12-19 13:00 | 13d 4h | 4860 | 0 | 0 | 0 | 0 | 4860 | 0 | 100% | Finished | 7200 | 7200
6 | Resarch amount of staff needed (extra contractors) | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2017-01-06 08:00 | 5d 7h | 2115 | 0 | 0 | 0 | 0 | 2115 | 0 | 100% | Finished | 1800 | 1800
7 | feasibility study | 2017-01-17 08:00 | 2017-01-25 17:00 | 7d | Admin | 1456 | 0 | 0 | 0 | 1456 | 2017-01-13 16:00 | 5d | 1040 | 0 | 0 | 0 | 0 | 1040 | 0 | 100% | Finished | 1456 | 1456
42 | Vans | 2016-12-13 08:00 | 2017-01-26 17:00 | 33d |  |  | 45000 |  |  | 47880 |  | 29d 7h | [5 empty] | 47448 |  | 100% |  | 47880 | 47880
9 | determine type and amound of vans | 2016-12-13 08:00 | 2016-12-15 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 2016-12-19 13:00 | 3d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
10 | buy vans | 2016-12-16 08:00 | 2017-01-05 17:00 | 15d |  | 0 | 45000 | 0 | 0 | 45000 | 2016-12-22 13:00 | 14d 1h | 45000 | 0 | 0 | 0 | 0 | 45000 | 0 | 100% | Finished | 45000 | 45000
11 | adjust vans | 2017-01-06 08:00 | 2017-01-26 17:00 | 15d | Arb | 2880 | 0 | 0 | 0 | 2880 | 2017-01-11 14:00 | 12d 6h | 2448 | 0 | 0 | 0 | 0 | 2448 | 0 | 100% | Finished | 2880 | 2880
43 | Meeting | 2017-01-26 08:00 | 2017-05-03 17:00 | 70d |  |  | 2112 |  |  | 23452 |  | 42d 1h | [5 empty] | 14546.5 |  | 54.47% |  | 12774.7105 | 14988
13 | Asking town for permission | 2017-01-26 08:00 | 2017-03-08 17:00 | 30d | Aankoop | 8160 | 0 | 0 | 0 | 8160 | 2017-01-20 16:00 | 38d 2h | 10404 | 0 | 0 | 0 | 0 | 10404 | 0 | 100% | Finished | 8160 | 8160
14 | Asking town for blue prints porwer network | 2017-03-09 08:00 | 2017-04-05 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 | 2017-03-16 09:00 | 3d 7h | 0 | 0 | 19d 6h | 0 | 0 | 0 | 0 | 16.4% | Started | 0 | 0
15 | meeting with bike suppliers and contracting | 2017-03-09 08:00 | 2017-05-03 17:00 | 40d | Admin[0.50 #2] | 4160 | 0 | 0 | 0 | 4160 | 2017-03-16 09:00 | 3d 7h | 403 | 2210 | 21d 2h | 0 | 0 | 403 | 2210 | 15.42% | Started | 641.592 | 936
16 | meeting with docking stations and tower suppliers and contracting | 2017-03-09 08:00 | 2017-04-26 17:00 | 35d | Aankoop[0.50 #2] | 4760 | 0 | 0 | 0 | 4760 | 2017-03-16 09:00 | 3d 7h | 527 | 2771 | 20d 3h | 0 | 0 | 527 | 2771 | 15.98% | Started | 760.6185 | 1224
17 | meeting with duct suppliers & cable supliers & contracting | 2017-03-09 08:00 | 2017-03-29 17:00 | 15d | Engineer[0.50 #2];Admin[0.50 #2] | 4260 | 0 | 0 | 0 | 4260 | 2017-03-16 09:00 | 3d 7h | 1100.5 | 3159.5 | 11d 1h | 0 | 0 | 1100.5 | 3159.5 | 25.83% | Started | 1100.5 | 2556
18 | meeting concrete suppliers | 2017-03-09 08:00 | 2017-03-22 17:00 | 10d |  | 0 | 2112 | 0 | 0 | 2112 | 2017-03-16 09:00 | 3d 7h | 2112 | 0 | 6d 1h | 0 | 0 | 2112 | 0 | 38.75% | Started | 2112 | 2112
44 | Ict | 2017-03-09 08:00 | 2017-07-07 17:00 | 87d |  |  | 168000 |  |  | 175560 |  | 3d 7h | [5 empty] | 1627.5 |  | 0.6418% |  | 1126.7308 | 3780
20 | ICT contracter search | 2017-03-09 08:00 | 2017-04-03 17:00 | 18d | Admin[0.50 #2];Aankoop[0.50 #2];Engineer[0.50 #5] | 7560 | 0 | 0 | 0 | 7560 | 2017-03-16 09:00 | 3d 7h | 1627.5 | 9292.5 | 22d 1h | 0 | 0 | 1627.5 | 9292.5 | 14.9% | Started | 1126.7308 | 3780
21 | Developing app | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 57d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
22 | developing pay system | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 57d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
23 | Testing & approve app | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 |  | 0 | 0 | 84000 | 12d | 0 | 0 | 0 | 84000 | 0% | Not Started | 0 | 0
24 | Testing & approve pay system | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 |  | 0 | 0 | 84000 | 12d | 0 | 0 | 0 | 84000 | 0% | Not Started | 0 | 0
45 | Repair place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d |  |  | 0 |  |  | 17664 |  | 27d 7h | [5 empty] | 21408 |  | 100% |  | 17664 | 17664
26 | construct bike repearing place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d | Arb[4.00 #4] | 17664 | 0 | 0 | 0 | 17664 | 2017-01-30 11:00 | 27d 7h | 21408 | 0 | 0 | 0 | 0 | 21408 | 0 | 100% | Finished | 17664 | 17664
46 | Delivery | 2017-03-30 08:00 | 2017-07-12 17:00 | 75d |  |  | 460000 |  |  | 460000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
28 | Delivery bikes parts | 2017-05-04 08:00 | 2017-07-12 17:00 | 50d |  | 0 | 150000 | 0 | 0 | 150000 |  | 0 | 0 | 150000 | 50d | 0 | 0 | 0 | 150000 | 0% | Not Started | 0 | 0
29 | delivery docking station & power tower | 2017-04-27 08:00 | 2017-06-07 17:00 | 30d |  | 0 | 250000 | 0 | 0 | 250000 |  | 0 | 0 | 250000 | 30d | 0 | 0 | 0 | 250000 | 0% | Not Started | 0 | 0
30 | delivery ducts | 2017-03-30 08:00 | 2017-04-24 17:00 | 18d |  | 0 | 60000 | 0 | 0 | 60000 |  | 0 | 0 | 60000 | 18d | 0 | 0 | 0 | 60000 | 0% | Not Started | 0 | 0
47 | Assembly | 2017-04-25 08:00 | 2017-08-31 17:00 | 93d |  |  | 0 |  |  | 72575.9999 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | assembly docking station & power tower | 2017-06-08 08:00 | 2017-08-09 17:00 | 45d | Engineer[0.88 #2];Arb[2.00 #4] | 31535.9999 | 0 | 0 | 0 | 31535.9999 |  | 0 | 0 | 31535.9999 | 45d | 0 | 0 | 0 | 31535.9999 | 0% | Not Started | 0 | 0
33 | assembly bikes & Testing | 2017-07-13 08:00 | 2017-08-31 17:00 | 36d | Arb[4.00 #4] | 27648 | 0 | 0 | 0 | 27648 |  | 0 | 0 | 27648 | 36d | 0 | 0 | 0 | 27648 | 0% | Not Started | 0 | 0
34 | assembly ducts | 2017-04-25 08:00 | 2017-05-18 17:00 | 18d | Engineer;Arb[2.00 #4] | 13392 | 0 | 0 | 0 | 13392 |  | 0 | 0 | 13392 | 18d | 0 | 0 | 0 | 13392 | 0% | Not Started | 0 | 0
48 | Construction total | 2017-04-06 08:00 | 2017-10-02 17:00 | 128d |  |  | 770922 |  |  | 770922 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
36 | Construction 1 | 2017-04-06 08:00 | 2017-07-04 17:00 | 64d |  | 0 | 587706 | 0 | 0 | 587706 |  | 0 | 0 | 587706 | 64d | 0 | 0 | 0 | 587706 | 0% | Not Started | 0 | 0
37 | Construction 2 | 2017-08-10 08:00 | 2017-10-02 17:00 | 38d |  | 0 | 183216 | 0 | 0 | 183216 |  | 0 | 0 | 183216 | 38d | 0 | 0 | 0 | 183216 | 0% | Not Started | 0 | 0
49 | Final phase | 2017-10-03 08:00 | 2017-11-28 17:00 | 41d |  |  | 0 |  |  | 11520 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | Placing bikes | 2017-10-03 08:00 | 2017-10-23 17:00 | 15d | Arb[4.00 #4] | 11520 | 0 | 0 | 0 | 11520 |  | 0 | 0 | 11520 | 15d | 0 | 0 | 0 | 11520 | 0% | Not Started | 0 | 0
40 | Final testing the total system | 2017-10-24 08:00 | 2017-11-28 17:00 | 26d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 26d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
50 | Project buffer | 2017-11-29 08:00 | 2018-03-20 17:00 | 80d |  | 0 | 100000 | 0 | 0 | 100000 |  | 0 | 0 | 100000 | 80d | 0 | 0 | 0 | 100000 | 0% | Not Started | 0 | 0

## TP7
| TP Status Date | 2017-04-11 17:00 |  | TP Name | 11/04/2017 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | projectKopie | 2016-11-16 08:00 | 2018-03-20 17:00 | 350d |  |  | 1546034 |  |  | 1703349.9999 |  | 105d | [5 empty] | 182394.5 |  | 10.34% |  | 176170.3921 | 764878
41 | Onderzoek | 2016-11-16 08:00 | 2017-01-25 17:00 | 51d |  |  | 0 |  |  | 23776 |  | 47d 7h | [5 empty] | 24305 |  | 100% |  | 23776 | 23776
2 | Analysis of bikes and bikes usage in gent by students | 2016-11-16 08:00 | 2016-12-05 17:00 | 14d | Engineer[2.00 #2] | 10080 | 0 | 0 | 0 | 10080 | 2016-11-16 08:00 | 19d 3h | 13950 | 0 | 0 | 0 | 0 | 13950 | 0 | 100% | Finished | 10080 | 10080
3 | Properties of the bike | 2016-12-06 08:00 | 2016-12-09 17:00 | 4d | Engineer | 1440 | 0 | 0 | 0 | 1440 | 2016-12-13 11:00 | 2d 3h | 855 | 0 | 0 | 0 | 0 | 855 | 0 | 100% | Finished | 1440 | 1440
4 | Determine amount of bikes needed and hot spots | 2016-12-06 08:00 | 2016-12-12 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2016-12-13 11:00 | 4d 1h | 1485 | 0 | 0 | 0 | 0 | 1485 | 0 | 100% | Finished | 1800 | 1800
5 | research for possibledocking stations | 2016-12-13 08:00 | 2017-01-09 17:00 | 20d | Engineer | 7200 | 0 | 0 | 0 | 7200 | 2016-12-19 13:00 | 13d 4h | 4860 | 0 | 0 | 0 | 0 | 4860 | 0 | 100% | Finished | 7200 | 7200
6 | Resarch amount of staff needed (extra contractors) | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2017-01-06 08:00 | 5d 7h | 2115 | 0 | 0 | 0 | 0 | 2115 | 0 | 100% | Finished | 1800 | 1800
7 | feasibility study | 2017-01-17 08:00 | 2017-01-25 17:00 | 7d | Admin | 1456 | 0 | 0 | 0 | 1456 | 2017-01-13 16:00 | 5d | 1040 | 0 | 0 | 0 | 0 | 1040 | 0 | 100% | Finished | 1456 | 1456
42 | Vans | 2016-12-13 08:00 | 2017-01-26 17:00 | 33d |  |  | 45000 |  |  | 47880 |  | 29d 7h | [5 empty] | 47448 |  | 100% |  | 47880 | 47880
9 | determine type and amound of vans | 2016-12-13 08:00 | 2016-12-15 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 2016-12-19 13:00 | 3d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
10 | buy vans | 2016-12-16 08:00 | 2017-01-05 17:00 | 15d |  | 0 | 45000 | 0 | 0 | 45000 | 2016-12-22 13:00 | 14d 1h | 45000 | 0 | 0 | 0 | 0 | 45000 | 0 | 100% | Finished | 45000 | 45000
11 | adjust vans | 2017-01-06 08:00 | 2017-01-26 17:00 | 15d | Arb | 2880 | 0 | 0 | 0 | 2880 | 2017-01-11 14:00 | 12d 6h | 2448 | 0 | 0 | 0 | 0 | 2448 | 0 | 100% | Finished | 2880 | 2880
43 | Meeting | 2017-01-26 08:00 | 2017-05-03 17:00 | 70d |  |  | 2112 |  |  | 23452 |  | 57d 1h | [5 empty] | 21306 |  | 91.09% |  | 21362.1226 | 20292
13 | Asking town for permission | 2017-01-26 08:00 | 2017-03-08 17:00 | 30d | Aankoop | 8160 | 0 | 0 | 0 | 8160 | 2017-01-20 16:00 | 38d 2h | 10404 | 0 | 0 | 0 | 0 | 10404 | 0 | 100% | Finished | 8160 | 8160
14 | Asking town for blue prints porwer network | 2017-03-09 08:00 | 2017-04-05 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 | 2017-03-16 09:00 | 18d 7h | 0 | 0 | 4d 6h | 0 | 0 | 0 | 0 | 79.89% | Started | 0 | 0
15 | meeting with bike suppliers and contracting | 2017-03-09 08:00 | 2017-05-03 17:00 | 40d | Admin[0.50 #2] | 4160 | 0 | 0 | 0 | 4160 | 2017-03-16 09:00 | 18d 7h | 1963 | 650 | 6d 2h | 0 | 0 | 1963 | 650 | 75.12% | Started | 3125.1741 | 2496
16 | meeting with docking stations and tower suppliers and contracting | 2017-03-09 08:00 | 2017-04-26 17:00 | 35d | Aankoop[0.50 #2] | 4760 | 0 | 0 | 0 | 4760 | 2017-03-16 09:00 | 18d 7h | 2567 | 731 | 5d 3h | 0 | 0 | 2567 | 731 | 77.84% | Started | 3704.9485 | 3264
17 | meeting with duct suppliers & cable supliers & contracting | 2017-03-09 08:00 | 2017-03-29 17:00 | 15d | Engineer[0.50 #2];Admin[0.50 #2] | 4260 | 0 | 0 | 0 | 4260 | 2017-03-16 09:00 | 15d | 4260 | 0 | 0 | 0 | 0 | 4260 | 0 | 100% | Finished | 4260 | 4260
18 | meeting concrete suppliers | 2017-03-09 08:00 | 2017-03-22 17:00 | 10d |  | 0 | 2112 | 0 | 0 | 2112 | 2017-03-16 09:00 | 10d | 2112 | 0 | 0 | 0 | 0 | 2112 | 0 | 100% | Finished | 2112 | 2112
44 | Ict | 2017-03-09 08:00 | 2017-07-07 17:00 | 87d |  |  | 168000 |  |  | 175560 |  | 18d 7h | [5 empty] | 7927.5 |  | 3.126% |  | 5488.2694 | 7560
20 | ICT contracter search | 2017-03-09 08:00 | 2017-04-03 17:00 | 18d | Admin[0.50 #2];Aankoop[0.50 #2];Engineer[0.50 #5] | 7560 | 0 | 0 | 0 | 7560 | 2017-03-16 09:00 | 18d 7h | 7927.5 | 2992.5 | 7d 1h | 0 | 0 | 7927.5 | 2992.5 | 72.6% | Started | 5488.2694 | 7560
21 | Developing app | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 57d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
22 | developing pay system | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 57d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
23 | Testing & approve app | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 |  | 0 | 0 | 84000 | 12d | 0 | 0 | 0 | 84000 | 0% | Not Started | 0 | 0
24 | Testing & approve pay system | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 |  | 0 | 0 | 84000 | 12d | 0 | 0 | 0 | 84000 | 0% | Not Started | 0 | 0
45 | Repair place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d |  |  | 0 |  |  | 17664 |  | 27d 7h | [5 empty] | 21408 |  | 100% |  | 17664 | 17664
26 | construct bike repearing place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d | Arb[4.00 #4] | 17664 | 0 | 0 | 0 | 17664 | 2017-01-30 11:00 | 27d 7h | 21408 | 0 | 0 | 0 | 0 | 21408 | 0 | 100% | Finished | 17664 | 17664
46 | Delivery | 2017-03-30 08:00 | 2017-07-12 17:00 | 75d |  |  | 460000 |  |  | 460000 |  | 3d 7h | [5 empty] | 60000 |  | 13.04% |  | 60000 | 60000
28 | Delivery bikes parts | 2017-05-04 08:00 | 2017-07-12 17:00 | 50d |  | 0 | 150000 | 0 | 0 | 150000 |  | 0 | 0 | 150000 | 50d | 0 | 0 | 0 | 150000 | 0% | Not Started | 0 | 0
29 | delivery docking station & power tower | 2017-04-27 08:00 | 2017-06-07 17:00 | 30d |  | 0 | 250000 | 0 | 0 | 250000 |  | 0 | 0 | 250000 | 30d | 0 | 0 | 0 | 250000 | 0% | Not Started | 0 | 0
30 | delivery ducts | 2017-03-30 08:00 | 2017-04-24 17:00 | 18d |  | 0 | 60000 | 0 | 0 | 60000 | 2017-04-06 09:00 | 3d 7h | 60000 | 0 | 9d 6h | 0 | 0 | 60000 | 0 | 28.44% | Started | 60000 | 60000
47 | Assembly | 2017-04-25 08:00 | 2017-08-31 17:00 | 93d |  |  | 0 |  |  | 72575.9999 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | assembly docking station & power tower | 2017-06-08 08:00 | 2017-08-09 17:00 | 45d | Engineer[0.88 #2];Arb[2.00 #4] | 31535.9999 | 0 | 0 | 0 | 31535.9999 |  | 0 | 0 | 31535.9999 | 45d | 0 | 0 | 0 | 31535.9999 | 0% | Not Started | 0 | 0
33 | assembly bikes & Testing | 2017-07-13 08:00 | 2017-08-31 17:00 | 36d | Arb[4.00 #4] | 27648 | 0 | 0 | 0 | 27648 |  | 0 | 0 | 27648 | 36d | 0 | 0 | 0 | 27648 | 0% | Not Started | 0 | 0
34 | assembly ducts | 2017-04-25 08:00 | 2017-05-18 17:00 | 18d | Engineer;Arb[2.00 #4] | 13392 | 0 | 0 | 0 | 13392 |  | 0 | 0 | 13392 | 18d | 0 | 0 | 0 | 13392 | 0% | Not Started | 0 | 0
48 | Construction total | 2017-04-06 08:00 | 2017-10-02 17:00 | 128d |  |  | 770922 |  |  | 770922 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 587706
36 | Construction 1 | 2017-04-06 08:00 | 2017-07-04 17:00 | 64d |  | 0 | 587706 | 0 | 0 | 587706 |  | 0 | 0 | 587706 | 64d | 0 | 0 | 0 | 587706 | 0% | Not Started | 0 | 587706
37 | Construction 2 | 2017-08-10 08:00 | 2017-10-02 17:00 | 38d |  | 0 | 183216 | 0 | 0 | 183216 |  | 0 | 0 | 183216 | 38d | 0 | 0 | 0 | 183216 | 0% | Not Started | 0 | 0
49 | Final phase | 2017-10-03 08:00 | 2017-11-28 17:00 | 41d |  |  | 0 |  |  | 11520 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | Placing bikes | 2017-10-03 08:00 | 2017-10-23 17:00 | 15d | Arb[4.00 #4] | 11520 | 0 | 0 | 0 | 11520 |  | 0 | 0 | 11520 | 15d | 0 | 0 | 0 | 11520 | 0% | Not Started | 0 | 0
40 | Final testing the total system | 2017-10-24 08:00 | 2017-11-28 17:00 | 26d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 26d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
50 | Project buffer | 2017-11-29 08:00 | 2018-03-20 17:00 | 80d |  | 0 | 100000 | 0 | 0 | 100000 |  | 0 | 0 | 100000 | 80d | 0 | 0 | 0 | 100000 | 0% | Not Started | 0 | 0

## TP8
| TP Status Date | 2017-05-02 17:00 |  | TP Name | 2/05/2017 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | projectKopie | 2016-11-16 08:00 | 2018-03-20 17:00 | 350d |  |  | 1546034 |  |  | 1703349.9999 |  | 120d | [5 empty] | 1178380 |  | 68.79% |  | 1171812.9261 | 1022398
41 | Onderzoek | 2016-11-16 08:00 | 2017-01-25 17:00 | 51d |  |  | 0 |  |  | 23776 |  | 47d 7h | [5 empty] | 24305 |  | 100% |  | 23776 | 23776
2 | Analysis of bikes and bikes usage in gent by students | 2016-11-16 08:00 | 2016-12-05 17:00 | 14d | Engineer[2.00 #2] | 10080 | 0 | 0 | 0 | 10080 | 2016-11-16 08:00 | 19d 3h | 13950 | 0 | 0 | 0 | 0 | 13950 | 0 | 100% | Finished | 10080 | 10080
3 | Properties of the bike | 2016-12-06 08:00 | 2016-12-09 17:00 | 4d | Engineer | 1440 | 0 | 0 | 0 | 1440 | 2016-12-13 11:00 | 2d 3h | 855 | 0 | 0 | 0 | 0 | 855 | 0 | 100% | Finished | 1440 | 1440
4 | Determine amount of bikes needed and hot spots | 2016-12-06 08:00 | 2016-12-12 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2016-12-13 11:00 | 4d 1h | 1485 | 0 | 0 | 0 | 0 | 1485 | 0 | 100% | Finished | 1800 | 1800
5 | research for possibledocking stations | 2016-12-13 08:00 | 2017-01-09 17:00 | 20d | Engineer | 7200 | 0 | 0 | 0 | 7200 | 2016-12-19 13:00 | 13d 4h | 4860 | 0 | 0 | 0 | 0 | 4860 | 0 | 100% | Finished | 7200 | 7200
6 | Resarch amount of staff needed (extra contractors) | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2017-01-06 08:00 | 5d 7h | 2115 | 0 | 0 | 0 | 0 | 2115 | 0 | 100% | Finished | 1800 | 1800
7 | feasibility study | 2017-01-17 08:00 | 2017-01-25 17:00 | 7d | Admin | 1456 | 0 | 0 | 0 | 1456 | 2017-01-13 16:00 | 5d | 1040 | 0 | 0 | 0 | 0 | 1040 | 0 | 100% | Finished | 1456 | 1456
42 | Vans | 2016-12-13 08:00 | 2017-01-26 17:00 | 33d |  |  | 45000 |  |  | 47880 |  | 29d 7h | [5 empty] | 47448 |  | 100% |  | 47880 | 47880
9 | determine type and amound of vans | 2016-12-13 08:00 | 2016-12-15 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 2016-12-19 13:00 | 3d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
10 | buy vans | 2016-12-16 08:00 | 2017-01-05 17:00 | 15d |  | 0 | 45000 | 0 | 0 | 45000 | 2016-12-22 13:00 | 14d 1h | 45000 | 0 | 0 | 0 | 0 | 45000 | 0 | 100% | Finished | 45000 | 45000
11 | adjust vans | 2017-01-06 08:00 | 2017-01-26 17:00 | 15d | Arb | 2880 | 0 | 0 | 0 | 2880 | 2017-01-11 14:00 | 12d 6h | 2448 | 0 | 0 | 0 | 0 | 2448 | 0 | 100% | Finished | 2880 | 2880
43 | Meeting | 2017-01-26 08:00 | 2017-05-03 17:00 | 70d |  |  | 2112 |  |  | 23452 |  | 63d 3h | [5 empty] | 22687 |  | 100% |  | 23452 | 23348
13 | Asking town for permission | 2017-01-26 08:00 | 2017-03-08 17:00 | 30d | Aankoop | 8160 | 0 | 0 | 0 | 8160 | 2017-01-20 16:00 | 38d 2h | 10404 | 0 | 0 | 0 | 0 | 10404 | 0 | 100% | Finished | 8160 | 8160
14 | Asking town for blue prints porwer network | 2017-03-09 08:00 | 2017-04-05 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 | 2017-03-16 09:00 | 23d 5h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | meeting with bike suppliers and contracting | 2017-03-09 08:00 | 2017-05-03 17:00 | 40d | Admin[0.50 #2] | 4160 | 0 | 0 | 0 | 4160 | 2017-03-16 09:00 | 25d 1h | 2613 | 0 | 0 | 0 | 0 | 2613 | 0 | 100% | Finished | 4160 | 4056
16 | meeting with docking stations and tower suppliers and contracting | 2017-03-09 08:00 | 2017-04-26 17:00 | 35d | Aankoop[0.50 #2] | 4760 | 0 | 0 | 0 | 4760 | 2017-03-16 09:00 | 24d 2h | 3298 | 0 | 0 | 0 | 0 | 3298 | 0 | 100% | Finished | 4760 | 4760
17 | meeting with duct suppliers & cable supliers & contracting | 2017-03-09 08:00 | 2017-03-29 17:00 | 15d | Engineer[0.50 #2];Admin[0.50 #2] | 4260 | 0 | 0 | 0 | 4260 | 2017-03-16 09:00 | 15d | 4260 | 0 | 0 | 0 | 0 | 4260 | 0 | 100% | Finished | 4260 | 4260
18 | meeting concrete suppliers | 2017-03-09 08:00 | 2017-03-22 17:00 | 10d |  | 0 | 2112 | 0 | 0 | 2112 | 2017-03-16 09:00 | 10d | 2112 | 0 | 0 | 0 | 0 | 2112 | 0 | 100% | Finished | 2112 | 2112
44 | Ict | 2017-03-09 08:00 | 2017-07-07 17:00 | 87d |  |  | 168000 |  |  | 175560 |  | 33d 7h | [5 empty] | 10920 |  | 4.306% |  | 7560 | 7560
20 | ICT contracter search | 2017-03-09 08:00 | 2017-04-03 17:00 | 18d | Admin[0.50 #2];Aankoop[0.50 #2];Engineer[0.50 #5] | 7560 | 0 | 0 | 0 | 7560 | 2017-03-16 09:00 | 26d | 10920 | 0 | 0 | 0 | 0 | 10920 | 0 | 100% | Finished | 7560 | 7560
21 | Developing app | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 7d 7h | 0 | 0 | 20d 5h | 0 | 0 | 0 | 0 | 27.63% | Started | 0 | 0
22 | developing pay system | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 7d 7h | 0 | 0 | 74d 2h | 0 | 0 | 0 | 0 | 9.589% | Started | 0 | 0
23 | Testing & approve app | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 |  | 0 | 0 | 84000 | 12d | 0 | 0 | 0 | 84000 | 0% | Not Started | 0 | 0
24 | Testing & approve pay system | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 |  | 0 | 0 | 84000 | 12d | 0 | 0 | 0 | 84000 | 0% | Not Started | 0 | 0
45 | Repair place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d |  |  | 0 |  |  | 17664 |  | 27d 7h | [5 empty] | 21408 |  | 100% |  | 17664 | 17664
26 | construct bike repearing place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d | Arb[4.00 #4] | 17664 | 0 | 0 | 0 | 17664 | 2017-01-30 11:00 | 27d 7h | 21408 | 0 | 0 | 0 | 0 | 21408 | 0 | 100% | Finished | 17664 | 17664
46 | Delivery | 2017-03-30 08:00 | 2017-07-12 17:00 | 75d |  |  | 460000 |  |  | 460000 |  | 18d 7h | [5 empty] | 460000 |  | 100% |  | 460000 | 310000
28 | Delivery bikes parts | 2017-05-04 08:00 | 2017-07-12 17:00 | 50d |  | 0 | 150000 | 0 | 0 | 150000 | 2017-04-20 10:00 | 8d 6h | 150000 | 0 | 60d 1h | 0 | 0 | 150000 | 0 | 12.7% | Started | 150000 | 0
29 | delivery docking station & power tower | 2017-04-27 08:00 | 2017-06-07 17:00 | 30d |  | 0 | 250000 | 0 | 0 | 250000 | 2017-04-19 11:00 | 9d 5h | 250000 | 0 | 15d 2h | 0 | 0 | 250000 | 0 | 38.69% | Started | 250000 | 250000
30 | delivery ducts | 2017-03-30 08:00 | 2017-04-24 17:00 | 18d |  | 0 | 60000 | 0 | 0 | 60000 | 2017-04-06 09:00 | 13d 5h | 60000 | 0 | 0 | 0 | 0 | 60000 | 0 | 100% | Finished | 60000 | 60000
47 | Assembly | 2017-04-25 08:00 | 2017-08-31 17:00 | 93d |  |  | 0 |  |  | 72575.9999 |  | 5d 2h | [5 empty] | 3906 |  | 5.201% |  | 3774.9261 | 4464
32 | assembly docking station & power tower | 2017-06-08 08:00 | 2017-08-09 17:00 | 45d | Engineer[0.88 #2];Arb[2.00 #4] | 31535.9999 | 0 | 0 | 0 | 31535.9999 |  | 0 | 0 | 31535.9999 | 45d | 0 | 0 | 0 | 31535.9999 | 0% | Not Started | 0 | 0
33 | assembly bikes & Testing | 2017-07-13 08:00 | 2017-08-31 17:00 | 36d | Arb[4.00 #4] | 27648 | 0 | 0 | 0 | 27648 |  | 0 | 0 | 27648 | 36d | 0 | 0 | 0 | 27648 | 0% | Not Started | 0 | 0
34 | assembly ducts | 2017-04-25 08:00 | 2017-05-18 17:00 | 18d | Engineer;Arb[2.00 #4] | 13392 | 0 | 0 | 0 | 13392 | 2017-04-25 15:00 | 5d 2h | 3906 | 9951 | 13d 3h | 0 | 0 | 3906 | 9951 | 28.19% | Started | 3774.9261 | 4464
48 | Construction total | 2017-04-06 08:00 | 2017-10-02 17:00 | 128d |  |  | 770922 |  |  | 770922 |  | 10d 2h | [5 empty] | 587706 |  | 76.23% |  | 587706 | 587706
36 | Construction 1 | 2017-04-06 08:00 | 2017-07-04 17:00 | 64d |  | 0 | 587706 | 0 | 0 | 587706 | 2017-04-18 15:00 | 10d 2h | 587706 | 0 | 39d 3h | 0 | 0 | 587706 | 0 | 20.65% | Started | 587706 | 587706
37 | Construction 2 | 2017-08-10 08:00 | 2017-10-02 17:00 | 38d |  | 0 | 183216 | 0 | 0 | 183216 |  | 0 | 0 | 183216 | 38d | 0 | 0 | 0 | 183216 | 0% | Not Started | 0 | 0
49 | Final phase | 2017-10-03 08:00 | 2017-11-28 17:00 | 41d |  |  | 0 |  |  | 11520 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | Placing bikes | 2017-10-03 08:00 | 2017-10-23 17:00 | 15d | Arb[4.00 #4] | 11520 | 0 | 0 | 0 | 11520 |  | 0 | 0 | 11520 | 15d | 0 | 0 | 0 | 11520 | 0% | Not Started | 0 | 0
40 | Final testing the total system | 2017-10-24 08:00 | 2017-11-28 17:00 | 26d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 26d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
50 | Project buffer | 2017-11-29 08:00 | 2018-03-20 17:00 | 80d |  | 0 | 100000 | 0 | 0 | 100000 |  | 0 | 0 | 100000 | 80d | 0 | 0 | 0 | 100000 | 0% | Not Started | 0 | 0

## TP9
| TP Status Date | 2017-05-23 17:00 |  | TP Name | 23/05/2017 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | projectKopie | 2016-11-16 08:00 | 2018-03-20 17:00 | 350d |  |  | 1546034 |  |  | 1703349.9999 |  | 135d | [5 empty] | 1188331 |  | 69.36% |  | 1181430 | 1181430
41 | Onderzoek | 2016-11-16 08:00 | 2017-01-25 17:00 | 51d |  |  | 0 |  |  | 23776 |  | 47d 7h | [5 empty] | 24305 |  | 100% |  | 23776 | 23776
2 | Analysis of bikes and bikes usage in gent by students | 2016-11-16 08:00 | 2016-12-05 17:00 | 14d | Engineer[2.00 #2] | 10080 | 0 | 0 | 0 | 10080 | 2016-11-16 08:00 | 19d 3h | 13950 | 0 | 0 | 0 | 0 | 13950 | 0 | 100% | Finished | 10080 | 10080
3 | Properties of the bike | 2016-12-06 08:00 | 2016-12-09 17:00 | 4d | Engineer | 1440 | 0 | 0 | 0 | 1440 | 2016-12-13 11:00 | 2d 3h | 855 | 0 | 0 | 0 | 0 | 855 | 0 | 100% | Finished | 1440 | 1440
4 | Determine amount of bikes needed and hot spots | 2016-12-06 08:00 | 2016-12-12 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2016-12-13 11:00 | 4d 1h | 1485 | 0 | 0 | 0 | 0 | 1485 | 0 | 100% | Finished | 1800 | 1800
5 | research for possibledocking stations | 2016-12-13 08:00 | 2017-01-09 17:00 | 20d | Engineer | 7200 | 0 | 0 | 0 | 7200 | 2016-12-19 13:00 | 13d 4h | 4860 | 0 | 0 | 0 | 0 | 4860 | 0 | 100% | Finished | 7200 | 7200
6 | Resarch amount of staff needed (extra contractors) | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2017-01-06 08:00 | 5d 7h | 2115 | 0 | 0 | 0 | 0 | 2115 | 0 | 100% | Finished | 1800 | 1800
7 | feasibility study | 2017-01-17 08:00 | 2017-01-25 17:00 | 7d | Admin | 1456 | 0 | 0 | 0 | 1456 | 2017-01-13 16:00 | 5d | 1040 | 0 | 0 | 0 | 0 | 1040 | 0 | 100% | Finished | 1456 | 1456
42 | Vans | 2016-12-13 08:00 | 2017-01-26 17:00 | 33d |  |  | 45000 |  |  | 47880 |  | 29d 7h | [5 empty] | 47448 |  | 100% |  | 47880 | 47880
9 | determine type and amound of vans | 2016-12-13 08:00 | 2016-12-15 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 2016-12-19 13:00 | 3d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
10 | buy vans | 2016-12-16 08:00 | 2017-01-05 17:00 | 15d |  | 0 | 45000 | 0 | 0 | 45000 | 2016-12-22 13:00 | 14d 1h | 45000 | 0 | 0 | 0 | 0 | 45000 | 0 | 100% | Finished | 45000 | 45000
11 | adjust vans | 2017-01-06 08:00 | 2017-01-26 17:00 | 15d | Arb | 2880 | 0 | 0 | 0 | 2880 | 2017-01-11 14:00 | 12d 6h | 2448 | 0 | 0 | 0 | 0 | 2448 | 0 | 100% | Finished | 2880 | 2880
43 | Meeting | 2017-01-26 08:00 | 2017-05-03 17:00 | 70d |  |  | 2112 |  |  | 23452 |  | 63d 3h | [5 empty] | 22687 |  | 100% |  | 23452 | 23452
13 | Asking town for permission | 2017-01-26 08:00 | 2017-03-08 17:00 | 30d | Aankoop | 8160 | 0 | 0 | 0 | 8160 | 2017-01-20 16:00 | 38d 2h | 10404 | 0 | 0 | 0 | 0 | 10404 | 0 | 100% | Finished | 8160 | 8160
14 | Asking town for blue prints porwer network | 2017-03-09 08:00 | 2017-04-05 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 | 2017-03-16 09:00 | 23d 5h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | meeting with bike suppliers and contracting | 2017-03-09 08:00 | 2017-05-03 17:00 | 40d | Admin[0.50 #2] | 4160 | 0 | 0 | 0 | 4160 | 2017-03-16 09:00 | 25d 1h | 2613 | 0 | 0 | 0 | 0 | 2613 | 0 | 100% | Finished | 4160 | 4160
16 | meeting with docking stations and tower suppliers and contracting | 2017-03-09 08:00 | 2017-04-26 17:00 | 35d | Aankoop[0.50 #2] | 4760 | 0 | 0 | 0 | 4760 | 2017-03-16 09:00 | 24d 2h | 3298 | 0 | 0 | 0 | 0 | 3298 | 0 | 100% | Finished | 4760 | 4760
17 | meeting with duct suppliers & cable supliers & contracting | 2017-03-09 08:00 | 2017-03-29 17:00 | 15d | Engineer[0.50 #2];Admin[0.50 #2] | 4260 | 0 | 0 | 0 | 4260 | 2017-03-16 09:00 | 15d | 4260 | 0 | 0 | 0 | 0 | 4260 | 0 | 100% | Finished | 4260 | 4260
18 | meeting concrete suppliers | 2017-03-09 08:00 | 2017-03-22 17:00 | 10d |  | 0 | 2112 | 0 | 0 | 2112 | 2017-03-16 09:00 | 10d | 2112 | 0 | 0 | 0 | 0 | 2112 | 0 | 100% | Finished | 2112 | 2112
44 | Ict | 2017-03-09 08:00 | 2017-07-07 17:00 | 87d |  |  | 168000 |  |  | 175560 |  | 48d 7h | [5 empty] | 10920 |  | 4.306% |  | 7560 | 7560
20 | ICT contracter search | 2017-03-09 08:00 | 2017-04-03 17:00 | 18d | Admin[0.50 #2];Aankoop[0.50 #2];Engineer[0.50 #5] | 7560 | 0 | 0 | 0 | 7560 | 2017-03-16 09:00 | 26d | 10920 | 0 | 0 | 0 | 0 | 10920 | 0 | 100% | Finished | 7560 | 7560
21 | Developing app | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 22d 7h | 0 | 0 | 5d 5h | 0 | 0 | 0 | 0 | 80.26% | Started | 0 | 0
22 | developing pay system | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 22d 7h | 0 | 0 | 59d 2h | 0 | 0 | 0 | 0 | 27.85% | Started | 0 | 0
23 | Testing & approve app | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 |  | 0 | 0 | 84000 | 12d | 0 | 0 | 0 | 84000 | 0% | Not Started | 0 | 0
24 | Testing & approve pay system | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 |  | 0 | 0 | 84000 | 12d | 0 | 0 | 0 | 84000 | 0% | Not Started | 0 | 0
45 | Repair place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d |  |  | 0 |  |  | 17664 |  | 27d 7h | [5 empty] | 21408 |  | 100% |  | 17664 | 17664
26 | construct bike repearing place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d | Arb[4.00 #4] | 17664 | 0 | 0 | 0 | 17664 | 2017-01-30 11:00 | 27d 7h | 21408 | 0 | 0 | 0 | 0 | 21408 | 0 | 100% | Finished | 17664 | 17664
46 | Delivery | 2017-03-30 08:00 | 2017-07-12 17:00 | 75d |  |  | 460000 |  |  | 460000 |  | 33d 7h | [5 empty] | 460000 |  | 100% |  | 460000 | 460000
28 | Delivery bikes parts | 2017-05-04 08:00 | 2017-07-12 17:00 | 50d |  | 0 | 150000 | 0 | 0 | 150000 | 2017-04-20 10:00 | 23d 6h | 150000 | 0 | 45d 1h | 0 | 0 | 150000 | 0 | 34.48% | Started | 150000 | 150000
29 | delivery docking station & power tower | 2017-04-27 08:00 | 2017-06-07 17:00 | 30d |  | 0 | 250000 | 0 | 0 | 250000 | 2017-04-19 11:00 | 24d 5h | 250000 | 0 | 2h | 0 | 0 | 250000 | 0 | 98.99% | Started | 250000 | 250000
30 | delivery ducts | 2017-03-30 08:00 | 2017-04-24 17:00 | 18d |  | 0 | 60000 | 0 | 0 | 60000 | 2017-04-06 09:00 | 13d 5h | 60000 | 0 | 0 | 0 | 0 | 60000 | 0 | 100% | Finished | 60000 | 60000
47 | Assembly | 2017-04-25 08:00 | 2017-08-31 17:00 | 93d |  |  | 0 |  |  | 72575.9999 |  | 20d 2h | [5 empty] | 13857 |  | 18.45% |  | 13392 | 13392
32 | assembly docking station & power tower | 2017-06-08 08:00 | 2017-08-09 17:00 | 45d | Engineer[0.88 #2];Arb[2.00 #4] | 31535.9999 | 0 | 0 | 0 | 31535.9999 |  | 0 | 0 | 31535.9999 | 45d | 0 | 0 | 0 | 31535.9999 | 0% | Not Started | 0 | 0
33 | assembly bikes & Testing | 2017-07-13 08:00 | 2017-08-31 17:00 | 36d | Arb[4.00 #4] | 27648 | 0 | 0 | 0 | 27648 |  | 0 | 0 | 27648 | 36d | 0 | 0 | 0 | 27648 | 0% | Not Started | 0 | 0
34 | assembly ducts | 2017-04-25 08:00 | 2017-05-18 17:00 | 18d | Engineer;Arb[2.00 #4] | 13392 | 0 | 0 | 0 | 13392 | 2017-04-25 15:00 | 18d 5h | 13857 | 0 | 0 | 0 | 0 | 13857 | 0 | 100% | Finished | 13392 | 13392
48 | Construction total | 2017-04-06 08:00 | 2017-10-02 17:00 | 128d |  |  | 770922 |  |  | 770922 |  | 25d 2h | [5 empty] | 587706 |  | 76.23% |  | 587706 | 587706
36 | Construction 1 | 2017-04-06 08:00 | 2017-07-04 17:00 | 64d |  | 0 | 587706 | 0 | 0 | 587706 | 2017-04-18 15:00 | 25d 2h | 587706 | 0 | 24d 3h | 0 | 0 | 587706 | 0 | 50.88% | Started | 587706 | 587706
37 | Construction 2 | 2017-08-10 08:00 | 2017-10-02 17:00 | 38d |  | 0 | 183216 | 0 | 0 | 183216 |  | 0 | 0 | 183216 | 38d | 0 | 0 | 0 | 183216 | 0% | Not Started | 0 | 0
49 | Final phase | 2017-10-03 08:00 | 2017-11-28 17:00 | 41d |  |  | 0 |  |  | 11520 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | Placing bikes | 2017-10-03 08:00 | 2017-10-23 17:00 | 15d | Arb[4.00 #4] | 11520 | 0 | 0 | 0 | 11520 |  | 0 | 0 | 11520 | 15d | 0 | 0 | 0 | 11520 | 0% | Not Started | 0 | 0
40 | Final testing the total system | 2017-10-24 08:00 | 2017-11-28 17:00 | 26d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 26d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
50 | Project buffer | 2017-11-29 08:00 | 2018-03-20 17:00 | 80d |  | 0 | 100000 | 0 | 0 | 100000 |  | 0 | 0 | 100000 | 80d | 0 | 0 | 0 | 100000 | 0% | Not Started | 0 | 0

## TP10
| TP Status Date | 2017-06-13 17:00 |  | TP Name | 13/06/2017 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | projectKopie | 2016-11-16 08:00 | 2018-03-20 17:00 | 350d |  |  | 1546034 |  |  | 1703349.9999 |  | 150d | [5 empty] | 1282667.8 |  | 74.86% |  | 1275095.5796 | 1184233.2
41 | Onderzoek | 2016-11-16 08:00 | 2017-01-25 17:00 | 51d |  |  | 0 |  |  | 23776 |  | 47d 7h | [5 empty] | 24305 |  | 100% |  | 23776 | 23776
2 | Analysis of bikes and bikes usage in gent by students | 2016-11-16 08:00 | 2016-12-05 17:00 | 14d | Engineer[2.00 #2] | 10080 | 0 | 0 | 0 | 10080 | 2016-11-16 08:00 | 19d 3h | 13950 | 0 | 0 | 0 | 0 | 13950 | 0 | 100% | Finished | 10080 | 10080
3 | Properties of the bike | 2016-12-06 08:00 | 2016-12-09 17:00 | 4d | Engineer | 1440 | 0 | 0 | 0 | 1440 | 2016-12-13 11:00 | 2d 3h | 855 | 0 | 0 | 0 | 0 | 855 | 0 | 100% | Finished | 1440 | 1440
4 | Determine amount of bikes needed and hot spots | 2016-12-06 08:00 | 2016-12-12 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2016-12-13 11:00 | 4d 1h | 1485 | 0 | 0 | 0 | 0 | 1485 | 0 | 100% | Finished | 1800 | 1800
5 | research for possibledocking stations | 2016-12-13 08:00 | 2017-01-09 17:00 | 20d | Engineer | 7200 | 0 | 0 | 0 | 7200 | 2016-12-19 13:00 | 13d 4h | 4860 | 0 | 0 | 0 | 0 | 4860 | 0 | 100% | Finished | 7200 | 7200
6 | Resarch amount of staff needed (extra contractors) | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2017-01-06 08:00 | 5d 7h | 2115 | 0 | 0 | 0 | 0 | 2115 | 0 | 100% | Finished | 1800 | 1800
7 | feasibility study | 2017-01-17 08:00 | 2017-01-25 17:00 | 7d | Admin | 1456 | 0 | 0 | 0 | 1456 | 2017-01-13 16:00 | 5d | 1040 | 0 | 0 | 0 | 0 | 1040 | 0 | 100% | Finished | 1456 | 1456
42 | Vans | 2016-12-13 08:00 | 2017-01-26 17:00 | 33d |  |  | 45000 |  |  | 47880 |  | 29d 7h | [5 empty] | 47448 |  | 100% |  | 47880 | 47880
9 | determine type and amound of vans | 2016-12-13 08:00 | 2016-12-15 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 2016-12-19 13:00 | 3d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
10 | buy vans | 2016-12-16 08:00 | 2017-01-05 17:00 | 15d |  | 0 | 45000 | 0 | 0 | 45000 | 2016-12-22 13:00 | 14d 1h | 45000 | 0 | 0 | 0 | 0 | 45000 | 0 | 100% | Finished | 45000 | 45000
11 | adjust vans | 2017-01-06 08:00 | 2017-01-26 17:00 | 15d | Arb | 2880 | 0 | 0 | 0 | 2880 | 2017-01-11 14:00 | 12d 6h | 2448 | 0 | 0 | 0 | 0 | 2448 | 0 | 100% | Finished | 2880 | 2880
43 | Meeting | 2017-01-26 08:00 | 2017-05-03 17:00 | 70d |  |  | 2112 |  |  | 23452 |  | 63d 3h | [5 empty] | 22687 |  | 100% |  | 23452 | 23452
13 | Asking town for permission | 2017-01-26 08:00 | 2017-03-08 17:00 | 30d | Aankoop | 8160 | 0 | 0 | 0 | 8160 | 2017-01-20 16:00 | 38d 2h | 10404 | 0 | 0 | 0 | 0 | 10404 | 0 | 100% | Finished | 8160 | 8160
14 | Asking town for blue prints porwer network | 2017-03-09 08:00 | 2017-04-05 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 | 2017-03-16 09:00 | 23d 5h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | meeting with bike suppliers and contracting | 2017-03-09 08:00 | 2017-05-03 17:00 | 40d | Admin[0.50 #2] | 4160 | 0 | 0 | 0 | 4160 | 2017-03-16 09:00 | 25d 1h | 2613 | 0 | 0 | 0 | 0 | 2613 | 0 | 100% | Finished | 4160 | 4160
16 | meeting with docking stations and tower suppliers and contracting | 2017-03-09 08:00 | 2017-04-26 17:00 | 35d | Aankoop[0.50 #2] | 4760 | 0 | 0 | 0 | 4760 | 2017-03-16 09:00 | 24d 2h | 3298 | 0 | 0 | 0 | 0 | 3298 | 0 | 100% | Finished | 4760 | 4760
17 | meeting with duct suppliers & cable supliers & contracting | 2017-03-09 08:00 | 2017-03-29 17:00 | 15d | Engineer[0.50 #2];Admin[0.50 #2] | 4260 | 0 | 0 | 0 | 4260 | 2017-03-16 09:00 | 15d | 4260 | 0 | 0 | 0 | 0 | 4260 | 0 | 100% | Finished | 4260 | 4260
18 | meeting concrete suppliers | 2017-03-09 08:00 | 2017-03-22 17:00 | 10d |  | 0 | 2112 | 0 | 0 | 2112 | 2017-03-16 09:00 | 10d | 2112 | 0 | 0 | 0 | 0 | 2112 | 0 | 100% | Finished | 2112 | 2112
44 | Ict | 2017-03-09 08:00 | 2017-07-07 17:00 | 87d |  |  | 168000 |  |  | 175560 |  | 63d 7h | [5 empty] | 94920 |  | 52.15% |  | 91560 | 7560
20 | ICT contracter search | 2017-03-09 08:00 | 2017-04-03 17:00 | 18d | Admin[0.50 #2];Aankoop[0.50 #2];Engineer[0.50 #5] | 7560 | 0 | 0 | 0 | 7560 | 2017-03-16 09:00 | 26d | 10920 | 0 | 0 | 0 | 0 | 10920 | 0 | 100% | Finished | 7560 | 7560
21 | Developing app | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 28d 4h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
22 | developing pay system | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 37d 7h | 0 | 0 | 44d 2h | 0 | 0 | 0 | 0 | 46.12% | Started | 0 | 0
23 | Testing & approve app | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 2017-05-31 14:00 | 9d 3h | 84000 | 0 | 2d 5h | 0 | 0 | 84000 | 0 | 78.12% | Started | 84000 | 0
24 | Testing & approve pay system | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 |  | 0 | 0 | 84000 | 12d | 0 | 0 | 0 | 84000 | 0% | Not Started | 0 | 0
45 | Repair place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d |  |  | 0 |  |  | 17664 |  | 27d 7h | [5 empty] | 21408 |  | 100% |  | 17664 | 17664
26 | construct bike repearing place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d | Arb[4.00 #4] | 17664 | 0 | 0 | 0 | 17664 | 2017-01-30 11:00 | 27d 7h | 21408 | 0 | 0 | 0 | 0 | 21408 | 0 | 100% | Finished | 17664 | 17664
46 | Delivery | 2017-03-30 08:00 | 2017-07-12 17:00 | 75d |  |  | 460000 |  |  | 460000 |  | 48d 7h | [5 empty] | 460000 |  | 100% |  | 460000 | 460000
28 | Delivery bikes parts | 2017-05-04 08:00 | 2017-07-12 17:00 | 50d |  | 0 | 150000 | 0 | 0 | 150000 | 2017-04-20 10:00 | 38d 6h | 150000 | 0 | 30d 1h | 0 | 0 | 150000 | 0 | 56.26% | Started | 150000 | 150000
29 | delivery docking station & power tower | 2017-04-27 08:00 | 2017-06-07 17:00 | 30d |  | 0 | 250000 | 0 | 0 | 250000 | 2017-04-19 11:00 | 24d 7h | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | 100% | Finished | 250000 | 250000
30 | delivery ducts | 2017-03-30 08:00 | 2017-04-24 17:00 | 18d |  | 0 | 60000 | 0 | 0 | 60000 | 2017-04-06 09:00 | 13d 5h | 60000 | 0 | 0 | 0 | 0 | 60000 | 0 | 100% | Finished | 60000 | 60000
47 | Assembly | 2017-04-25 08:00 | 2017-08-31 17:00 | 93d |  |  | 0 |  |  | 72575.9999 |  | 35d 2h | [5 empty] | 24193.8 |  | 31.77% |  | 23057.5796 | 16195.2
32 | assembly docking station & power tower | 2017-06-08 08:00 | 2017-08-09 17:00 | 45d | Engineer[0.88 #2];Arb[2.00 #4] | 31535.9999 | 0 | 0 | 0 | 31535.9999 | 2017-05-24 10:00 | 14d 6h | 10336.8 | 23389.1999 | 33d 3h | 0 | 0 | 10336.8 | 23389.1999 | 30.65% | Started | 9665.5796 | 2803.2
33 | assembly bikes & Testing | 2017-07-13 08:00 | 2017-08-31 17:00 | 36d | Arb[4.00 #4] | 27648 | 0 | 0 | 0 | 27648 |  | 0 | 0 | 27648 | 36d | 0 | 0 | 0 | 27648 | 0% | Not Started | 0 | 0
34 | assembly ducts | 2017-04-25 08:00 | 2017-05-18 17:00 | 18d | Engineer;Arb[2.00 #4] | 13392 | 0 | 0 | 0 | 13392 | 2017-04-25 15:00 | 18d 5h | 13857 | 0 | 0 | 0 | 0 | 13857 | 0 | 100% | Finished | 13392 | 13392
48 | Construction total | 2017-04-06 08:00 | 2017-10-02 17:00 | 128d |  |  | 770922 |  |  | 770922 |  | 40d 2h | [5 empty] | 587706 |  | 76.23% |  | 587706 | 587706
36 | Construction 1 | 2017-04-06 08:00 | 2017-07-04 17:00 | 64d |  | 0 | 587706 | 0 | 0 | 587706 | 2017-04-18 15:00 | 40d 2h | 587706 | 0 | 9d 3h | 0 | 0 | 587706 | 0 | 81.11% | Started | 587706 | 587706
37 | Construction 2 | 2017-08-10 08:00 | 2017-10-02 17:00 | 38d |  | 0 | 183216 | 0 | 0 | 183216 |  | 0 | 0 | 183216 | 38d | 0 | 0 | 0 | 183216 | 0% | Not Started | 0 | 0
49 | Final phase | 2017-10-03 08:00 | 2017-11-28 17:00 | 41d |  |  | 0 |  |  | 11520 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | Placing bikes | 2017-10-03 08:00 | 2017-10-23 17:00 | 15d | Arb[4.00 #4] | 11520 | 0 | 0 | 0 | 11520 |  | 0 | 0 | 11520 | 15d | 0 | 0 | 0 | 11520 | 0% | Not Started | 0 | 0
40 | Final testing the total system | 2017-10-24 08:00 | 2017-11-28 17:00 | 26d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 26d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
50 | Project buffer | 2017-11-29 08:00 | 2018-03-20 17:00 | 80d |  | 0 | 100000 | 0 | 0 | 100000 |  | 0 | 0 | 100000 | 80d | 0 | 0 | 0 | 100000 | 0% | Not Started | 0 | 0

## TP11
| TP Status Date | 2017-07-04 17:00 |  | TP Name | 4/07/2017 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | projectKopie | 2016-11-16 08:00 | 2018-03-20 17:00 | 350d |  |  | 1546034 |  |  | 1703349.9999 |  | 165d | [5 empty] | 1293179.7999 |  | 75.44% |  | 1284924.982 | 1362745.2
41 | Onderzoek | 2016-11-16 08:00 | 2017-01-25 17:00 | 51d |  |  | 0 |  |  | 23776 |  | 47d 7h | [5 empty] | 24305 |  | 100% |  | 23776 | 23776
2 | Analysis of bikes and bikes usage in gent by students | 2016-11-16 08:00 | 2016-12-05 17:00 | 14d | Engineer[2.00 #2] | 10080 | 0 | 0 | 0 | 10080 | 2016-11-16 08:00 | 19d 3h | 13950 | 0 | 0 | 0 | 0 | 13950 | 0 | 100% | Finished | 10080 | 10080
3 | Properties of the bike | 2016-12-06 08:00 | 2016-12-09 17:00 | 4d | Engineer | 1440 | 0 | 0 | 0 | 1440 | 2016-12-13 11:00 | 2d 3h | 855 | 0 | 0 | 0 | 0 | 855 | 0 | 100% | Finished | 1440 | 1440
4 | Determine amount of bikes needed and hot spots | 2016-12-06 08:00 | 2016-12-12 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2016-12-13 11:00 | 4d 1h | 1485 | 0 | 0 | 0 | 0 | 1485 | 0 | 100% | Finished | 1800 | 1800
5 | research for possibledocking stations | 2016-12-13 08:00 | 2017-01-09 17:00 | 20d | Engineer | 7200 | 0 | 0 | 0 | 7200 | 2016-12-19 13:00 | 13d 4h | 4860 | 0 | 0 | 0 | 0 | 4860 | 0 | 100% | Finished | 7200 | 7200
6 | Resarch amount of staff needed (extra contractors) | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2017-01-06 08:00 | 5d 7h | 2115 | 0 | 0 | 0 | 0 | 2115 | 0 | 100% | Finished | 1800 | 1800
7 | feasibility study | 2017-01-17 08:00 | 2017-01-25 17:00 | 7d | Admin | 1456 | 0 | 0 | 0 | 1456 | 2017-01-13 16:00 | 5d | 1040 | 0 | 0 | 0 | 0 | 1040 | 0 | 100% | Finished | 1456 | 1456
42 | Vans | 2016-12-13 08:00 | 2017-01-26 17:00 | 33d |  |  | 45000 |  |  | 47880 |  | 29d 7h | [5 empty] | 47448 |  | 100% |  | 47880 | 47880
9 | determine type and amound of vans | 2016-12-13 08:00 | 2016-12-15 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 2016-12-19 13:00 | 3d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
10 | buy vans | 2016-12-16 08:00 | 2017-01-05 17:00 | 15d |  | 0 | 45000 | 0 | 0 | 45000 | 2016-12-22 13:00 | 14d 1h | 45000 | 0 | 0 | 0 | 0 | 45000 | 0 | 100% | Finished | 45000 | 45000
11 | adjust vans | 2017-01-06 08:00 | 2017-01-26 17:00 | 15d | Arb | 2880 | 0 | 0 | 0 | 2880 | 2017-01-11 14:00 | 12d 6h | 2448 | 0 | 0 | 0 | 0 | 2448 | 0 | 100% | Finished | 2880 | 2880
43 | Meeting | 2017-01-26 08:00 | 2017-05-03 17:00 | 70d |  |  | 2112 |  |  | 23452 |  | 63d 3h | [5 empty] | 22687 |  | 100% |  | 23452 | 23452
13 | Asking town for permission | 2017-01-26 08:00 | 2017-03-08 17:00 | 30d | Aankoop | 8160 | 0 | 0 | 0 | 8160 | 2017-01-20 16:00 | 38d 2h | 10404 | 0 | 0 | 0 | 0 | 10404 | 0 | 100% | Finished | 8160 | 8160
14 | Asking town for blue prints porwer network | 2017-03-09 08:00 | 2017-04-05 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 | 2017-03-16 09:00 | 23d 5h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | meeting with bike suppliers and contracting | 2017-03-09 08:00 | 2017-05-03 17:00 | 40d | Admin[0.50 #2] | 4160 | 0 | 0 | 0 | 4160 | 2017-03-16 09:00 | 25d 1h | 2613 | 0 | 0 | 0 | 0 | 2613 | 0 | 100% | Finished | 4160 | 4160
16 | meeting with docking stations and tower suppliers and contracting | 2017-03-09 08:00 | 2017-04-26 17:00 | 35d | Aankoop[0.50 #2] | 4760 | 0 | 0 | 0 | 4760 | 2017-03-16 09:00 | 24d 2h | 3298 | 0 | 0 | 0 | 0 | 3298 | 0 | 100% | Finished | 4760 | 4760
17 | meeting with duct suppliers & cable supliers & contracting | 2017-03-09 08:00 | 2017-03-29 17:00 | 15d | Engineer[0.50 #2];Admin[0.50 #2] | 4260 | 0 | 0 | 0 | 4260 | 2017-03-16 09:00 | 15d | 4260 | 0 | 0 | 0 | 0 | 4260 | 0 | 100% | Finished | 4260 | 4260
18 | meeting concrete suppliers | 2017-03-09 08:00 | 2017-03-22 17:00 | 10d |  | 0 | 2112 | 0 | 0 | 2112 | 2017-03-16 09:00 | 10d | 2112 | 0 | 0 | 0 | 0 | 2112 | 0 | 100% | Finished | 2112 | 2112
44 | Ict | 2017-03-09 08:00 | 2017-07-07 17:00 | 87d |  |  | 168000 |  |  | 175560 |  | 78d 7h | [5 empty] | 94920 |  | 52.15% |  | 91560 | 175560
20 | ICT contracter search | 2017-03-09 08:00 | 2017-04-03 17:00 | 18d | Admin[0.50 #2];Aankoop[0.50 #2];Engineer[0.50 #5] | 7560 | 0 | 0 | 0 | 7560 | 2017-03-16 09:00 | 26d | 10920 | 0 | 0 | 0 | 0 | 10920 | 0 | 100% | Finished | 7560 | 7560
21 | Developing app | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 28d 4h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
22 | developing pay system | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 52d 7h | 0 | 0 | 29d 2h | 0 | 0 | 0 | 0 | 64.38% | Started | 0 | 0
23 | Testing & approve app | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 2017-05-31 14:00 | 12d | 84000 | 0 | 0 | 0 | 0 | 84000 | 0 | 100% | Finished | 84000 | 84000
24 | Testing & approve pay system | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 |  | 0 | 0 | 84000 | 12d | 0 | 0 | 0 | 84000 | 0% | Not Started | 0 | 84000
45 | Repair place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d |  |  | 0 |  |  | 17664 |  | 27d 7h | [5 empty] | 21408 |  | 100% |  | 17664 | 17664
26 | construct bike repearing place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d | Arb[4.00 #4] | 17664 | 0 | 0 | 0 | 17664 | 2017-01-30 11:00 | 27d 7h | 21408 | 0 | 0 | 0 | 0 | 21408 | 0 | 100% | Finished | 17664 | 17664
46 | Delivery | 2017-03-30 08:00 | 2017-07-12 17:00 | 75d |  |  | 460000 |  |  | 460000 |  | 63d 7h | [5 empty] | 460000 |  | 100% |  | 460000 | 460000
28 | Delivery bikes parts | 2017-05-04 08:00 | 2017-07-12 17:00 | 50d |  | 0 | 150000 | 0 | 0 | 150000 | 2017-04-20 10:00 | 53d 6h | 150000 | 0 | 15d 1h | 0 | 0 | 150000 | 0 | 78.04% | Started | 150000 | 150000
29 | delivery docking station & power tower | 2017-04-27 08:00 | 2017-06-07 17:00 | 30d |  | 0 | 250000 | 0 | 0 | 250000 | 2017-04-19 11:00 | 24d 7h | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | 100% | Finished | 250000 | 250000
30 | delivery ducts | 2017-03-30 08:00 | 2017-04-24 17:00 | 18d |  | 0 | 60000 | 0 | 0 | 60000 | 2017-04-06 09:00 | 13d 5h | 60000 | 0 | 0 | 0 | 0 | 60000 | 0 | 100% | Finished | 60000 | 60000
47 | Assembly | 2017-04-25 08:00 | 2017-08-31 17:00 | 93d |  |  | 0 |  |  | 72575.9999 |  | 50d 2h | [5 empty] | 34705.7999 |  | 45.31% |  | 32886.982 | 26707.2
32 | assembly docking station & power tower | 2017-06-08 08:00 | 2017-08-09 17:00 | 45d | Engineer[0.88 #2];Arb[2.00 #4] | 31535.9999 | 0 | 0 | 0 | 31535.9999 | 2017-05-24 10:00 | 29d 6h | 20848.7999 | 12877.2 | 18d 3h | 0 | 0 | 20848.7999 | 12877.2 | 61.82% | Started | 19494.982 | 13315.2
33 | assembly bikes & Testing | 2017-07-13 08:00 | 2017-08-31 17:00 | 36d | Arb[4.00 #4] | 27648 | 0 | 0 | 0 | 27648 |  | 0 | 0 | 27648 | 36d | 0 | 0 | 0 | 27648 | 0% | Not Started | 0 | 0
34 | assembly ducts | 2017-04-25 08:00 | 2017-05-18 17:00 | 18d | Engineer;Arb[2.00 #4] | 13392 | 0 | 0 | 0 | 13392 | 2017-04-25 15:00 | 18d 5h | 13857 | 0 | 0 | 0 | 0 | 13857 | 0 | 100% | Finished | 13392 | 13392
48 | Construction total | 2017-04-06 08:00 | 2017-10-02 17:00 | 128d |  |  | 770922 |  |  | 770922 |  | 55d 2h | [5 empty] | 587706 |  | 76.23% |  | 587706 | 587706
36 | Construction 1 | 2017-04-06 08:00 | 2017-07-04 17:00 | 64d |  | 0 | 587706 | 0 | 0 | 587706 | 2017-04-18 15:00 | 49d 5h | 587706 | 0 | 0 | 0 | 0 | 587706 | 0 | 100% | Finished | 587706 | 587706
37 | Construction 2 | 2017-08-10 08:00 | 2017-10-02 17:00 | 38d |  | 0 | 183216 | 0 | 0 | 183216 |  | 0 | 0 | 183216 | 38d | 0 | 0 | 0 | 183216 | 0% | Not Started | 0 | 0
49 | Final phase | 2017-10-03 08:00 | 2017-11-28 17:00 | 41d |  |  | 0 |  |  | 11520 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | Placing bikes | 2017-10-03 08:00 | 2017-10-23 17:00 | 15d | Arb[4.00 #4] | 11520 | 0 | 0 | 0 | 11520 |  | 0 | 0 | 11520 | 15d | 0 | 0 | 0 | 11520 | 0% | Not Started | 0 | 0
40 | Final testing the total system | 2017-10-24 08:00 | 2017-11-28 17:00 | 26d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 26d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
50 | Project buffer | 2017-11-29 08:00 | 2018-03-20 17:00 | 80d |  | 0 | 100000 | 0 | 0 | 100000 |  | 0 | 0 | 100000 | 80d | 0 | 0 | 0 | 100000 | 0% | Not Started | 0 | 0

## TP12
| TP Status Date | 2017-07-25 17:00 |  | TP Name | 25/07/2017 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | projectKopie | 2016-11-16 08:00 | 2018-03-20 17:00 | 350d |  |  | 1546034 |  |  | 1703349.9999 |  | 180d | [5 empty] | 1303691.7999 |  | 76.01% |  | 1294754.3843 | 1380169.1999
41 | Onderzoek | 2016-11-16 08:00 | 2017-01-25 17:00 | 51d |  |  | 0 |  |  | 23776 |  | 47d 7h | [5 empty] | 24305 |  | 100% |  | 23776 | 23776
2 | Analysis of bikes and bikes usage in gent by students | 2016-11-16 08:00 | 2016-12-05 17:00 | 14d | Engineer[2.00 #2] | 10080 | 0 | 0 | 0 | 10080 | 2016-11-16 08:00 | 19d 3h | 13950 | 0 | 0 | 0 | 0 | 13950 | 0 | 100% | Finished | 10080 | 10080
3 | Properties of the bike | 2016-12-06 08:00 | 2016-12-09 17:00 | 4d | Engineer | 1440 | 0 | 0 | 0 | 1440 | 2016-12-13 11:00 | 2d 3h | 855 | 0 | 0 | 0 | 0 | 855 | 0 | 100% | Finished | 1440 | 1440
4 | Determine amount of bikes needed and hot spots | 2016-12-06 08:00 | 2016-12-12 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2016-12-13 11:00 | 4d 1h | 1485 | 0 | 0 | 0 | 0 | 1485 | 0 | 100% | Finished | 1800 | 1800
5 | research for possibledocking stations | 2016-12-13 08:00 | 2017-01-09 17:00 | 20d | Engineer | 7200 | 0 | 0 | 0 | 7200 | 2016-12-19 13:00 | 13d 4h | 4860 | 0 | 0 | 0 | 0 | 4860 | 0 | 100% | Finished | 7200 | 7200
6 | Resarch amount of staff needed (extra contractors) | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2017-01-06 08:00 | 5d 7h | 2115 | 0 | 0 | 0 | 0 | 2115 | 0 | 100% | Finished | 1800 | 1800
7 | feasibility study | 2017-01-17 08:00 | 2017-01-25 17:00 | 7d | Admin | 1456 | 0 | 0 | 0 | 1456 | 2017-01-13 16:00 | 5d | 1040 | 0 | 0 | 0 | 0 | 1040 | 0 | 100% | Finished | 1456 | 1456
42 | Vans | 2016-12-13 08:00 | 2017-01-26 17:00 | 33d |  |  | 45000 |  |  | 47880 |  | 29d 7h | [5 empty] | 47448 |  | 100% |  | 47880 | 47880
9 | determine type and amound of vans | 2016-12-13 08:00 | 2016-12-15 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 2016-12-19 13:00 | 3d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
10 | buy vans | 2016-12-16 08:00 | 2017-01-05 17:00 | 15d |  | 0 | 45000 | 0 | 0 | 45000 | 2016-12-22 13:00 | 14d 1h | 45000 | 0 | 0 | 0 | 0 | 45000 | 0 | 100% | Finished | 45000 | 45000
11 | adjust vans | 2017-01-06 08:00 | 2017-01-26 17:00 | 15d | Arb | 2880 | 0 | 0 | 0 | 2880 | 2017-01-11 14:00 | 12d 6h | 2448 | 0 | 0 | 0 | 0 | 2448 | 0 | 100% | Finished | 2880 | 2880
43 | Meeting | 2017-01-26 08:00 | 2017-05-03 17:00 | 70d |  |  | 2112 |  |  | 23452 |  | 63d 3h | [5 empty] | 22687 |  | 100% |  | 23452 | 23452
13 | Asking town for permission | 2017-01-26 08:00 | 2017-03-08 17:00 | 30d | Aankoop | 8160 | 0 | 0 | 0 | 8160 | 2017-01-20 16:00 | 38d 2h | 10404 | 0 | 0 | 0 | 0 | 10404 | 0 | 100% | Finished | 8160 | 8160
14 | Asking town for blue prints porwer network | 2017-03-09 08:00 | 2017-04-05 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 | 2017-03-16 09:00 | 23d 5h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | meeting with bike suppliers and contracting | 2017-03-09 08:00 | 2017-05-03 17:00 | 40d | Admin[0.50 #2] | 4160 | 0 | 0 | 0 | 4160 | 2017-03-16 09:00 | 25d 1h | 2613 | 0 | 0 | 0 | 0 | 2613 | 0 | 100% | Finished | 4160 | 4160
16 | meeting with docking stations and tower suppliers and contracting | 2017-03-09 08:00 | 2017-04-26 17:00 | 35d | Aankoop[0.50 #2] | 4760 | 0 | 0 | 0 | 4760 | 2017-03-16 09:00 | 24d 2h | 3298 | 0 | 0 | 0 | 0 | 3298 | 0 | 100% | Finished | 4760 | 4760
17 | meeting with duct suppliers & cable supliers & contracting | 2017-03-09 08:00 | 2017-03-29 17:00 | 15d | Engineer[0.50 #2];Admin[0.50 #2] | 4260 | 0 | 0 | 0 | 4260 | 2017-03-16 09:00 | 15d | 4260 | 0 | 0 | 0 | 0 | 4260 | 0 | 100% | Finished | 4260 | 4260
18 | meeting concrete suppliers | 2017-03-09 08:00 | 2017-03-22 17:00 | 10d |  | 0 | 2112 | 0 | 0 | 2112 | 2017-03-16 09:00 | 10d | 2112 | 0 | 0 | 0 | 0 | 2112 | 0 | 100% | Finished | 2112 | 2112
44 | Ict | 2017-03-09 08:00 | 2017-07-07 17:00 | 87d |  |  | 168000 |  |  | 175560 |  | 93d 7h | [5 empty] | 94920 |  | 52.15% |  | 91560 | 175560
20 | ICT contracter search | 2017-03-09 08:00 | 2017-04-03 17:00 | 18d | Admin[0.50 #2];Aankoop[0.50 #2];Engineer[0.50 #5] | 7560 | 0 | 0 | 0 | 7560 | 2017-03-16 09:00 | 26d | 10920 | 0 | 0 | 0 | 0 | 10920 | 0 | 100% | Finished | 7560 | 7560
21 | Developing app | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 28d 4h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
22 | developing pay system | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 67d 7h | 0 | 0 | 14d 2h | 0 | 0 | 0 | 0 | 82.65% | Started | 0 | 0
23 | Testing & approve app | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 2017-05-31 14:00 | 12d | 84000 | 0 | 0 | 0 | 0 | 84000 | 0 | 100% | Finished | 84000 | 84000
24 | Testing & approve pay system | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 |  | 0 | 0 | 84000 | 12d | 0 | 0 | 0 | 84000 | 0% | Not Started | 0 | 84000
45 | Repair place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d |  |  | 0 |  |  | 17664 |  | 27d 7h | [5 empty] | 21408 |  | 100% |  | 17664 | 17664
26 | construct bike repearing place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d | Arb[4.00 #4] | 17664 | 0 | 0 | 0 | 17664 | 2017-01-30 11:00 | 27d 7h | 21408 | 0 | 0 | 0 | 0 | 21408 | 0 | 100% | Finished | 17664 | 17664
46 | Delivery | 2017-03-30 08:00 | 2017-07-12 17:00 | 75d |  |  | 460000 |  |  | 460000 |  | 78d 7h | [5 empty] | 460000 |  | 100% |  | 460000 | 460000
28 | Delivery bikes parts | 2017-05-04 08:00 | 2017-07-12 17:00 | 50d |  | 0 | 150000 | 0 | 0 | 150000 | 2017-04-20 10:00 | 68d 6h | 150000 | 0 | 1h | 0 | 0 | 150000 | 0 | 99.82% | Started | 150000 | 150000
29 | delivery docking station & power tower | 2017-04-27 08:00 | 2017-06-07 17:00 | 30d |  | 0 | 250000 | 0 | 0 | 250000 | 2017-04-19 11:00 | 24d 7h | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | 100% | Finished | 250000 | 250000
30 | delivery ducts | 2017-03-30 08:00 | 2017-04-24 17:00 | 18d |  | 0 | 60000 | 0 | 0 | 60000 | 2017-04-06 09:00 | 13d 5h | 60000 | 0 | 0 | 0 | 0 | 60000 | 0 | 100% | Finished | 60000 | 60000
47 | Assembly | 2017-04-25 08:00 | 2017-08-31 17:00 | 93d |  |  | 0 |  |  | 72575.9999 |  | 65d 2h | [5 empty] | 45217.7999 |  | 58.86% |  | 42716.3843 | 44131.1999
32 | assembly docking station & power tower | 2017-06-08 08:00 | 2017-08-09 17:00 | 45d | Engineer[0.88 #2];Arb[2.00 #4] | 31535.9999 | 0 | 0 | 0 | 31535.9999 | 2017-05-24 10:00 | 44d 6h | 31360.7999 | 2365.2 | 3d 3h | 0 | 0 | 31360.7999 | 2365.2 | 92.99% | Started | 29324.3843 | 23827.1999
33 | assembly bikes & Testing | 2017-07-13 08:00 | 2017-08-31 17:00 | 36d | Arb[4.00 #4] | 27648 | 0 | 0 | 0 | 27648 |  | 0 | 0 | 27648 | 36d | 0 | 0 | 0 | 27648 | 0% | Not Started | 0 | 6912
34 | assembly ducts | 2017-04-25 08:00 | 2017-05-18 17:00 | 18d | Engineer;Arb[2.00 #4] | 13392 | 0 | 0 | 0 | 13392 | 2017-04-25 15:00 | 18d 5h | 13857 | 0 | 0 | 0 | 0 | 13857 | 0 | 100% | Finished | 13392 | 13392
48 | Construction total | 2017-04-06 08:00 | 2017-10-02 17:00 | 128d |  |  | 770922 |  |  | 770922 |  | 70d 2h | [5 empty] | 587706 |  | 76.23% |  | 587706 | 587706
36 | Construction 1 | 2017-04-06 08:00 | 2017-07-04 17:00 | 64d |  | 0 | 587706 | 0 | 0 | 587706 | 2017-04-18 15:00 | 49d 5h | 587706 | 0 | 0 | 0 | 0 | 587706 | 0 | 100% | Finished | 587706 | 587706
37 | Construction 2 | 2017-08-10 08:00 | 2017-10-02 17:00 | 38d |  | 0 | 183216 | 0 | 0 | 183216 |  | 0 | 0 | 183216 | 38d | 0 | 0 | 0 | 183216 | 0% | Not Started | 0 | 0
49 | Final phase | 2017-10-03 08:00 | 2017-11-28 17:00 | 41d |  |  | 0 |  |  | 11520 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | Placing bikes | 2017-10-03 08:00 | 2017-10-23 17:00 | 15d | Arb[4.00 #4] | 11520 | 0 | 0 | 0 | 11520 |  | 0 | 0 | 11520 | 15d | 0 | 0 | 0 | 11520 | 0% | Not Started | 0 | 0
40 | Final testing the total system | 2017-10-24 08:00 | 2017-11-28 17:00 | 26d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 26d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
50 | Project buffer | 2017-11-29 08:00 | 2018-03-20 17:00 | 80d |  | 0 | 100000 | 0 | 0 | 100000 |  | 0 | 0 | 100000 | 80d | 0 | 0 | 0 | 100000 | 0% | Not Started | 0 | 0

## TP13
| TP Status Date | 2017-08-15 17:00 |  | TP Name | 15/08/2017 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | projectKopie | 2016-11-16 08:00 | 2018-03-20 17:00 | 350d |  |  | 1546034 |  |  | 1703349.9999 |  | 195d | [5 empty] | 1584696.9999 |  | 92.38% |  | 1573636.3447 | 1582613.9999
41 | Onderzoek | 2016-11-16 08:00 | 2017-01-25 17:00 | 51d |  |  | 0 |  |  | 23776 |  | 47d 7h | [5 empty] | 24305 |  | 100% |  | 23776 | 23776
2 | Analysis of bikes and bikes usage in gent by students | 2016-11-16 08:00 | 2016-12-05 17:00 | 14d | Engineer[2.00 #2] | 10080 | 0 | 0 | 0 | 10080 | 2016-11-16 08:00 | 19d 3h | 13950 | 0 | 0 | 0 | 0 | 13950 | 0 | 100% | Finished | 10080 | 10080
3 | Properties of the bike | 2016-12-06 08:00 | 2016-12-09 17:00 | 4d | Engineer | 1440 | 0 | 0 | 0 | 1440 | 2016-12-13 11:00 | 2d 3h | 855 | 0 | 0 | 0 | 0 | 855 | 0 | 100% | Finished | 1440 | 1440
4 | Determine amount of bikes needed and hot spots | 2016-12-06 08:00 | 2016-12-12 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2016-12-13 11:00 | 4d 1h | 1485 | 0 | 0 | 0 | 0 | 1485 | 0 | 100% | Finished | 1800 | 1800
5 | research for possibledocking stations | 2016-12-13 08:00 | 2017-01-09 17:00 | 20d | Engineer | 7200 | 0 | 0 | 0 | 7200 | 2016-12-19 13:00 | 13d 4h | 4860 | 0 | 0 | 0 | 0 | 4860 | 0 | 100% | Finished | 7200 | 7200
6 | Resarch amount of staff needed (extra contractors) | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2017-01-06 08:00 | 5d 7h | 2115 | 0 | 0 | 0 | 0 | 2115 | 0 | 100% | Finished | 1800 | 1800
7 | feasibility study | 2017-01-17 08:00 | 2017-01-25 17:00 | 7d | Admin | 1456 | 0 | 0 | 0 | 1456 | 2017-01-13 16:00 | 5d | 1040 | 0 | 0 | 0 | 0 | 1040 | 0 | 100% | Finished | 1456 | 1456
42 | Vans | 2016-12-13 08:00 | 2017-01-26 17:00 | 33d |  |  | 45000 |  |  | 47880 |  | 29d 7h | [5 empty] | 47448 |  | 100% |  | 47880 | 47880
9 | determine type and amound of vans | 2016-12-13 08:00 | 2016-12-15 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 2016-12-19 13:00 | 3d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
10 | buy vans | 2016-12-16 08:00 | 2017-01-05 17:00 | 15d |  | 0 | 45000 | 0 | 0 | 45000 | 2016-12-22 13:00 | 14d 1h | 45000 | 0 | 0 | 0 | 0 | 45000 | 0 | 100% | Finished | 45000 | 45000
11 | adjust vans | 2017-01-06 08:00 | 2017-01-26 17:00 | 15d | Arb | 2880 | 0 | 0 | 0 | 2880 | 2017-01-11 14:00 | 12d 6h | 2448 | 0 | 0 | 0 | 0 | 2448 | 0 | 100% | Finished | 2880 | 2880
43 | Meeting | 2017-01-26 08:00 | 2017-05-03 17:00 | 70d |  |  | 2112 |  |  | 23452 |  | 63d 3h | [5 empty] | 22687 |  | 100% |  | 23452 | 23452
13 | Asking town for permission | 2017-01-26 08:00 | 2017-03-08 17:00 | 30d | Aankoop | 8160 | 0 | 0 | 0 | 8160 | 2017-01-20 16:00 | 38d 2h | 10404 | 0 | 0 | 0 | 0 | 10404 | 0 | 100% | Finished | 8160 | 8160
14 | Asking town for blue prints porwer network | 2017-03-09 08:00 | 2017-04-05 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 | 2017-03-16 09:00 | 23d 5h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | meeting with bike suppliers and contracting | 2017-03-09 08:00 | 2017-05-03 17:00 | 40d | Admin[0.50 #2] | 4160 | 0 | 0 | 0 | 4160 | 2017-03-16 09:00 | 25d 1h | 2613 | 0 | 0 | 0 | 0 | 2613 | 0 | 100% | Finished | 4160 | 4160
16 | meeting with docking stations and tower suppliers and contracting | 2017-03-09 08:00 | 2017-04-26 17:00 | 35d | Aankoop[0.50 #2] | 4760 | 0 | 0 | 0 | 4760 | 2017-03-16 09:00 | 24d 2h | 3298 | 0 | 0 | 0 | 0 | 3298 | 0 | 100% | Finished | 4760 | 4760
17 | meeting with duct suppliers & cable supliers & contracting | 2017-03-09 08:00 | 2017-03-29 17:00 | 15d | Engineer[0.50 #2];Admin[0.50 #2] | 4260 | 0 | 0 | 0 | 4260 | 2017-03-16 09:00 | 15d | 4260 | 0 | 0 | 0 | 0 | 4260 | 0 | 100% | Finished | 4260 | 4260
18 | meeting concrete suppliers | 2017-03-09 08:00 | 2017-03-22 17:00 | 10d |  | 0 | 2112 | 0 | 0 | 2112 | 2017-03-16 09:00 | 10d | 2112 | 0 | 0 | 0 | 0 | 2112 | 0 | 100% | Finished | 2112 | 2112
44 | Ict | 2017-03-09 08:00 | 2017-07-07 17:00 | 87d |  |  | 168000 |  |  | 175560 |  | 108d 7h | [5 empty] | 178920 |  | 100% |  | 175560 | 175560
20 | ICT contracter search | 2017-03-09 08:00 | 2017-04-03 17:00 | 18d | Admin[0.50 #2];Aankoop[0.50 #2];Engineer[0.50 #5] | 7560 | 0 | 0 | 0 | 7560 | 2017-03-16 09:00 | 26d | 10920 | 0 | 0 | 0 | 0 | 10920 | 0 | 100% | Finished | 7560 | 7560
21 | Developing app | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 28d 4h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
22 | developing pay system | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 82d 1h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
23 | Testing & approve app | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 2017-05-31 14:00 | 12d | 84000 | 0 | 0 | 0 | 0 | 84000 | 0 | 100% | Finished | 84000 | 84000
24 | Testing & approve pay system | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 2017-08-15 10:00 | 6h | 84000 | 0 | 16d 7h | 0 | 0 | 84000 | 0 | 4.255% | Started | 84000 | 84000
45 | Repair place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d |  |  | 0 |  |  | 17664 |  | 27d 7h | [5 empty] | 21408 |  | 100% |  | 17664 | 17664
26 | construct bike repearing place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d | Arb[4.00 #4] | 17664 | 0 | 0 | 0 | 17664 | 2017-01-30 11:00 | 27d 7h | 21408 | 0 | 0 | 0 | 0 | 21408 | 0 | 100% | Finished | 17664 | 17664
46 | Delivery | 2017-03-30 08:00 | 2017-07-12 17:00 | 75d |  |  | 460000 |  |  | 460000 |  | 79d | [5 empty] | 460000 |  | 100% |  | 460000 | 460000
28 | Delivery bikes parts | 2017-05-04 08:00 | 2017-07-12 17:00 | 50d |  | 0 | 150000 | 0 | 0 | 150000 | 2017-04-20 10:00 | 68d 7h | 150000 | 0 | 0 | 0 | 0 | 150000 | 0 | 100% | Finished | 150000 | 150000
29 | delivery docking station & power tower | 2017-04-27 08:00 | 2017-06-07 17:00 | 30d |  | 0 | 250000 | 0 | 0 | 250000 | 2017-04-19 11:00 | 24d 7h | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | 100% | Finished | 250000 | 250000
30 | delivery ducts | 2017-03-30 08:00 | 2017-04-24 17:00 | 18d |  | 0 | 60000 | 0 | 0 | 60000 | 2017-04-06 09:00 | 13d 5h | 60000 | 0 | 0 | 0 | 0 | 60000 | 0 | 100% | Finished | 60000 | 60000
47 | Assembly | 2017-04-25 08:00 | 2017-08-31 17:00 | 93d |  |  | 0 |  |  | 72575.9999 |  | 80d 2h | [5 empty] | 59006.9999 |  | 74.93% |  | 54382.3447 | 63359.9999
32 | assembly docking station & power tower | 2017-06-08 08:00 | 2017-08-09 17:00 | 45d | Engineer[0.88 #2];Arb[2.00 #4] | 31535.9999 | 0 | 0 | 0 | 31535.9999 | 2017-05-24 10:00 | 48d 1h | 33725.9999 | 0 | 0 | 0 | 0 | 33725.9999 | 0 | 100% | Finished | 31535.9999 | 31535.9999
33 | assembly bikes & Testing | 2017-07-13 08:00 | 2017-08-31 17:00 | 36d | Arb[4.00 #4] | 27648 | 0 | 0 | 0 | 27648 | 2017-07-26 09:00 | 14d 7h | 11424 | 21984 | 28d 5h | 0 | 0 | 11424 | 21984 | 34.2% | Started | 9454.3448 | 18432
34 | assembly ducts | 2017-04-25 08:00 | 2017-05-18 17:00 | 18d | Engineer;Arb[2.00 #4] | 13392 | 0 | 0 | 0 | 13392 | 2017-04-25 15:00 | 18d 5h | 13857 | 0 | 0 | 0 | 0 | 13857 | 0 | 100% | Finished | 13392 | 13392
48 | Construction total | 2017-04-06 08:00 | 2017-10-02 17:00 | 128d |  |  | 770922 |  |  | 770922 |  | 85d 2h | [5 empty] | 770922 |  | 100% |  | 770922 | 770922
36 | Construction 1 | 2017-04-06 08:00 | 2017-07-04 17:00 | 64d |  | 0 | 587706 | 0 | 0 | 587706 | 2017-04-18 15:00 | 49d 5h | 587706 | 0 | 0 | 0 | 0 | 587706 | 0 | 100% | Finished | 587706 | 587706
37 | Construction 2 | 2017-08-10 08:00 | 2017-10-02 17:00 | 38d |  | 0 | 183216 | 0 | 0 | 183216 | 2017-07-31 11:00 | 11d 5h | 183216 | 0 | 9d 1h | 0 | 0 | 183216 | 0 | 56.02% | Started | 183216 | 183216
49 | Final phase | 2017-10-03 08:00 | 2017-11-28 17:00 | 41d |  |  | 0 |  |  | 11520 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | Placing bikes | 2017-10-03 08:00 | 2017-10-23 17:00 | 15d | Arb[4.00 #4] | 11520 | 0 | 0 | 0 | 11520 |  | 0 | 0 | 11520 | 15d | 0 | 0 | 0 | 11520 | 0% | Not Started | 0 | 0
40 | Final testing the total system | 2017-10-24 08:00 | 2017-11-28 17:00 | 26d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 26d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
50 | Project buffer | 2017-11-29 08:00 | 2018-03-20 17:00 | 80d |  | 0 | 100000 | 0 | 0 | 100000 |  | 0 | 0 | 100000 | 80d | 0 | 0 | 0 | 100000 | 0% | Not Started | 0 | 0

## TP14
| TP Status Date | 2017-09-05 17:00 |  | TP Name | 5/09/2017 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | projectKopie | 2016-11-16 08:00 | 2018-03-20 17:00 | 350d |  |  | 1546034 |  |  | 1703349.9999 |  | 210d | [5 empty] | 1600728.9999 |  | 93.31% |  | 1589393.5851 | 1591829.9999
41 | Onderzoek | 2016-11-16 08:00 | 2017-01-25 17:00 | 51d |  |  | 0 |  |  | 23776 |  | 47d 7h | [5 empty] | 24305 |  | 100% |  | 23776 | 23776
2 | Analysis of bikes and bikes usage in gent by students | 2016-11-16 08:00 | 2016-12-05 17:00 | 14d | Engineer[2.00 #2] | 10080 | 0 | 0 | 0 | 10080 | 2016-11-16 08:00 | 19d 3h | 13950 | 0 | 0 | 0 | 0 | 13950 | 0 | 100% | Finished | 10080 | 10080
3 | Properties of the bike | 2016-12-06 08:00 | 2016-12-09 17:00 | 4d | Engineer | 1440 | 0 | 0 | 0 | 1440 | 2016-12-13 11:00 | 2d 3h | 855 | 0 | 0 | 0 | 0 | 855 | 0 | 100% | Finished | 1440 | 1440
4 | Determine amount of bikes needed and hot spots | 2016-12-06 08:00 | 2016-12-12 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2016-12-13 11:00 | 4d 1h | 1485 | 0 | 0 | 0 | 0 | 1485 | 0 | 100% | Finished | 1800 | 1800
5 | research for possibledocking stations | 2016-12-13 08:00 | 2017-01-09 17:00 | 20d | Engineer | 7200 | 0 | 0 | 0 | 7200 | 2016-12-19 13:00 | 13d 4h | 4860 | 0 | 0 | 0 | 0 | 4860 | 0 | 100% | Finished | 7200 | 7200
6 | Resarch amount of staff needed (extra contractors) | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2017-01-06 08:00 | 5d 7h | 2115 | 0 | 0 | 0 | 0 | 2115 | 0 | 100% | Finished | 1800 | 1800
7 | feasibility study | 2017-01-17 08:00 | 2017-01-25 17:00 | 7d | Admin | 1456 | 0 | 0 | 0 | 1456 | 2017-01-13 16:00 | 5d | 1040 | 0 | 0 | 0 | 0 | 1040 | 0 | 100% | Finished | 1456 | 1456
42 | Vans | 2016-12-13 08:00 | 2017-01-26 17:00 | 33d |  |  | 45000 |  |  | 47880 |  | 29d 7h | [5 empty] | 47448 |  | 100% |  | 47880 | 47880
9 | determine type and amound of vans | 2016-12-13 08:00 | 2016-12-15 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 2016-12-19 13:00 | 3d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
10 | buy vans | 2016-12-16 08:00 | 2017-01-05 17:00 | 15d |  | 0 | 45000 | 0 | 0 | 45000 | 2016-12-22 13:00 | 14d 1h | 45000 | 0 | 0 | 0 | 0 | 45000 | 0 | 100% | Finished | 45000 | 45000
11 | adjust vans | 2017-01-06 08:00 | 2017-01-26 17:00 | 15d | Arb | 2880 | 0 | 0 | 0 | 2880 | 2017-01-11 14:00 | 12d 6h | 2448 | 0 | 0 | 0 | 0 | 2448 | 0 | 100% | Finished | 2880 | 2880
43 | Meeting | 2017-01-26 08:00 | 2017-05-03 17:00 | 70d |  |  | 2112 |  |  | 23452 |  | 63d 3h | [5 empty] | 22687 |  | 100% |  | 23452 | 23452
13 | Asking town for permission | 2017-01-26 08:00 | 2017-03-08 17:00 | 30d | Aankoop | 8160 | 0 | 0 | 0 | 8160 | 2017-01-20 16:00 | 38d 2h | 10404 | 0 | 0 | 0 | 0 | 10404 | 0 | 100% | Finished | 8160 | 8160
14 | Asking town for blue prints porwer network | 2017-03-09 08:00 | 2017-04-05 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 | 2017-03-16 09:00 | 23d 5h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | meeting with bike suppliers and contracting | 2017-03-09 08:00 | 2017-05-03 17:00 | 40d | Admin[0.50 #2] | 4160 | 0 | 0 | 0 | 4160 | 2017-03-16 09:00 | 25d 1h | 2613 | 0 | 0 | 0 | 0 | 2613 | 0 | 100% | Finished | 4160 | 4160
16 | meeting with docking stations and tower suppliers and contracting | 2017-03-09 08:00 | 2017-04-26 17:00 | 35d | Aankoop[0.50 #2] | 4760 | 0 | 0 | 0 | 4760 | 2017-03-16 09:00 | 24d 2h | 3298 | 0 | 0 | 0 | 0 | 3298 | 0 | 100% | Finished | 4760 | 4760
17 | meeting with duct suppliers & cable supliers & contracting | 2017-03-09 08:00 | 2017-03-29 17:00 | 15d | Engineer[0.50 #2];Admin[0.50 #2] | 4260 | 0 | 0 | 0 | 4260 | 2017-03-16 09:00 | 15d | 4260 | 0 | 0 | 0 | 0 | 4260 | 0 | 100% | Finished | 4260 | 4260
18 | meeting concrete suppliers | 2017-03-09 08:00 | 2017-03-22 17:00 | 10d |  | 0 | 2112 | 0 | 0 | 2112 | 2017-03-16 09:00 | 10d | 2112 | 0 | 0 | 0 | 0 | 2112 | 0 | 100% | Finished | 2112 | 2112
44 | Ict | 2017-03-09 08:00 | 2017-07-07 17:00 | 87d |  |  | 168000 |  |  | 175560 |  | 123d 7h | [5 empty] | 178920 |  | 100% |  | 175560 | 175560
20 | ICT contracter search | 2017-03-09 08:00 | 2017-04-03 17:00 | 18d | Admin[0.50 #2];Aankoop[0.50 #2];Engineer[0.50 #5] | 7560 | 0 | 0 | 0 | 7560 | 2017-03-16 09:00 | 26d | 10920 | 0 | 0 | 0 | 0 | 10920 | 0 | 100% | Finished | 7560 | 7560
21 | Developing app | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 28d 4h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
22 | developing pay system | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 82d 1h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
23 | Testing & approve app | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 2017-05-31 14:00 | 12d | 84000 | 0 | 0 | 0 | 0 | 84000 | 0 | 100% | Finished | 84000 | 84000
24 | Testing & approve pay system | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 2017-08-15 10:00 | 15d 6h | 84000 | 0 | 1d 7h | 0 | 0 | 84000 | 0 | 89.36% | Started | 84000 | 84000
45 | Repair place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d |  |  | 0 |  |  | 17664 |  | 27d 7h | [5 empty] | 21408 |  | 100% |  | 17664 | 17664
26 | construct bike repearing place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d | Arb[4.00 #4] | 17664 | 0 | 0 | 0 | 17664 | 2017-01-30 11:00 | 27d 7h | 21408 | 0 | 0 | 0 | 0 | 21408 | 0 | 100% | Finished | 17664 | 17664
46 | Delivery | 2017-03-30 08:00 | 2017-07-12 17:00 | 75d |  |  | 460000 |  |  | 460000 |  | 79d | [5 empty] | 460000 |  | 100% |  | 460000 | 460000
28 | Delivery bikes parts | 2017-05-04 08:00 | 2017-07-12 17:00 | 50d |  | 0 | 150000 | 0 | 0 | 150000 | 2017-04-20 10:00 | 68d 7h | 150000 | 0 | 0 | 0 | 0 | 150000 | 0 | 100% | Finished | 150000 | 150000
29 | delivery docking station & power tower | 2017-04-27 08:00 | 2017-06-07 17:00 | 30d |  | 0 | 250000 | 0 | 0 | 250000 | 2017-04-19 11:00 | 24d 7h | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | 100% | Finished | 250000 | 250000
30 | delivery ducts | 2017-03-30 08:00 | 2017-04-24 17:00 | 18d |  | 0 | 60000 | 0 | 0 | 60000 | 2017-04-06 09:00 | 13d 5h | 60000 | 0 | 0 | 0 | 0 | 60000 | 0 | 100% | Finished | 60000 | 60000
47 | Assembly | 2017-04-25 08:00 | 2017-08-31 17:00 | 93d |  |  | 0 |  |  | 72575.9999 |  | 95d 2h | [5 empty] | 70526.9999 |  | 88.07% |  | 63916.1372 | 72575.9999
32 | assembly docking station & power tower | 2017-06-08 08:00 | 2017-08-09 17:00 | 45d | Engineer[0.88 #2];Arb[2.00 #4] | 31535.9999 | 0 | 0 | 0 | 31535.9999 | 2017-05-24 10:00 | 48d 1h | 33725.9999 | 0 | 0 | 0 | 0 | 33725.9999 | 0 | 100% | Finished | 31535.9999 | 31535.9999
33 | assembly bikes & Testing | 2017-07-13 08:00 | 2017-08-31 17:00 | 36d | Arb[4.00 #4] | 27648 | 0 | 0 | 0 | 27648 | 2017-07-26 09:00 | 29d 7h | 22944 | 10464 | 13d 5h | 0 | 0 | 22944 | 10464 | 68.68% | Started | 18988.1373 | 27648
34 | assembly ducts | 2017-04-25 08:00 | 2017-05-18 17:00 | 18d | Engineer;Arb[2.00 #4] | 13392 | 0 | 0 | 0 | 13392 | 2017-04-25 15:00 | 18d 5h | 13857 | 0 | 0 | 0 | 0 | 13857 | 0 | 100% | Finished | 13392 | 13392
48 | Construction total | 2017-04-06 08:00 | 2017-10-02 17:00 | 128d |  |  | 770922 |  |  | 770922 |  | 94d 3h | [5 empty] | 770922 |  | 100% |  | 770922 | 770922
36 | Construction 1 | 2017-04-06 08:00 | 2017-07-04 17:00 | 64d |  | 0 | 587706 | 0 | 0 | 587706 | 2017-04-18 15:00 | 49d 5h | 587706 | 0 | 0 | 0 | 0 | 587706 | 0 | 100% | Finished | 587706 | 587706
37 | Construction 2 | 2017-08-10 08:00 | 2017-10-02 17:00 | 38d |  | 0 | 183216 | 0 | 0 | 183216 | 2017-07-31 11:00 | 20d 6h | 183216 | 0 | 0 | 0 | 0 | 183216 | 0 | 100% | Finished | 183216 | 183216
49 | Final phase | 2017-10-03 08:00 | 2017-11-28 17:00 | 41d |  |  | 0 |  |  | 11520 |  | 5d 7h | [5 empty] | 4512 |  | 54.02% |  | 6223.448 | 0
39 | Placing bikes | 2017-10-03 08:00 | 2017-10-23 17:00 | 15d | Arb[4.00 #4] | 11520 | 0 | 0 | 0 | 11520 | 2017-08-29 09:00 | 5d 7h | 4512 | 3840 | 5d | 0 | 0 | 4512 | 3840 | 54.02% | Started | 6223.448 | 0
40 | Final testing the total system | 2017-10-24 08:00 | 2017-11-28 17:00 | 26d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 26d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
50 | Project buffer | 2017-11-29 08:00 | 2018-03-20 17:00 | 80d |  | 0 | 100000 | 0 | 0 | 100000 |  | 0 | 0 | 100000 | 80d | 0 | 0 | 0 | 100000 | 0% | Not Started | 0 | 0

## TP15
| TP Status Date | 2017-09-26 17:00 |  | TP Name | 26/09/2017 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | projectKopie | 2016-11-16 08:00 | 2018-03-20 17:00 | 350d |  |  | 1546034 |  |  | 1703349.9999 |  | 225d | [5 empty] | 1615032.9999 |  | 94.13% |  | 1603349.9999 | 1591829.9999
41 | Onderzoek | 2016-11-16 08:00 | 2017-01-25 17:00 | 51d |  |  | 0 |  |  | 23776 |  | 47d 7h | [5 empty] | 24305 |  | 100% |  | 23776 | 23776
2 | Analysis of bikes and bikes usage in gent by students | 2016-11-16 08:00 | 2016-12-05 17:00 | 14d | Engineer[2.00 #2] | 10080 | 0 | 0 | 0 | 10080 | 2016-11-16 08:00 | 19d 3h | 13950 | 0 | 0 | 0 | 0 | 13950 | 0 | 100% | Finished | 10080 | 10080
3 | Properties of the bike | 2016-12-06 08:00 | 2016-12-09 17:00 | 4d | Engineer | 1440 | 0 | 0 | 0 | 1440 | 2016-12-13 11:00 | 2d 3h | 855 | 0 | 0 | 0 | 0 | 855 | 0 | 100% | Finished | 1440 | 1440
4 | Determine amount of bikes needed and hot spots | 2016-12-06 08:00 | 2016-12-12 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2016-12-13 11:00 | 4d 1h | 1485 | 0 | 0 | 0 | 0 | 1485 | 0 | 100% | Finished | 1800 | 1800
5 | research for possibledocking stations | 2016-12-13 08:00 | 2017-01-09 17:00 | 20d | Engineer | 7200 | 0 | 0 | 0 | 7200 | 2016-12-19 13:00 | 13d 4h | 4860 | 0 | 0 | 0 | 0 | 4860 | 0 | 100% | Finished | 7200 | 7200
6 | Resarch amount of staff needed (extra contractors) | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2017-01-06 08:00 | 5d 7h | 2115 | 0 | 0 | 0 | 0 | 2115 | 0 | 100% | Finished | 1800 | 1800
7 | feasibility study | 2017-01-17 08:00 | 2017-01-25 17:00 | 7d | Admin | 1456 | 0 | 0 | 0 | 1456 | 2017-01-13 16:00 | 5d | 1040 | 0 | 0 | 0 | 0 | 1040 | 0 | 100% | Finished | 1456 | 1456
42 | Vans | 2016-12-13 08:00 | 2017-01-26 17:00 | 33d |  |  | 45000 |  |  | 47880 |  | 29d 7h | [5 empty] | 47448 |  | 100% |  | 47880 | 47880
9 | determine type and amound of vans | 2016-12-13 08:00 | 2016-12-15 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 2016-12-19 13:00 | 3d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
10 | buy vans | 2016-12-16 08:00 | 2017-01-05 17:00 | 15d |  | 0 | 45000 | 0 | 0 | 45000 | 2016-12-22 13:00 | 14d 1h | 45000 | 0 | 0 | 0 | 0 | 45000 | 0 | 100% | Finished | 45000 | 45000
11 | adjust vans | 2017-01-06 08:00 | 2017-01-26 17:00 | 15d | Arb | 2880 | 0 | 0 | 0 | 2880 | 2017-01-11 14:00 | 12d 6h | 2448 | 0 | 0 | 0 | 0 | 2448 | 0 | 100% | Finished | 2880 | 2880
43 | Meeting | 2017-01-26 08:00 | 2017-05-03 17:00 | 70d |  |  | 2112 |  |  | 23452 |  | 63d 3h | [5 empty] | 22687 |  | 100% |  | 23452 | 23452
13 | Asking town for permission | 2017-01-26 08:00 | 2017-03-08 17:00 | 30d | Aankoop | 8160 | 0 | 0 | 0 | 8160 | 2017-01-20 16:00 | 38d 2h | 10404 | 0 | 0 | 0 | 0 | 10404 | 0 | 100% | Finished | 8160 | 8160
14 | Asking town for blue prints porwer network | 2017-03-09 08:00 | 2017-04-05 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 | 2017-03-16 09:00 | 23d 5h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | meeting with bike suppliers and contracting | 2017-03-09 08:00 | 2017-05-03 17:00 | 40d | Admin[0.50 #2] | 4160 | 0 | 0 | 0 | 4160 | 2017-03-16 09:00 | 25d 1h | 2613 | 0 | 0 | 0 | 0 | 2613 | 0 | 100% | Finished | 4160 | 4160
16 | meeting with docking stations and tower suppliers and contracting | 2017-03-09 08:00 | 2017-04-26 17:00 | 35d | Aankoop[0.50 #2] | 4760 | 0 | 0 | 0 | 4760 | 2017-03-16 09:00 | 24d 2h | 3298 | 0 | 0 | 0 | 0 | 3298 | 0 | 100% | Finished | 4760 | 4760
17 | meeting with duct suppliers & cable supliers & contracting | 2017-03-09 08:00 | 2017-03-29 17:00 | 15d | Engineer[0.50 #2];Admin[0.50 #2] | 4260 | 0 | 0 | 0 | 4260 | 2017-03-16 09:00 | 15d | 4260 | 0 | 0 | 0 | 0 | 4260 | 0 | 100% | Finished | 4260 | 4260
18 | meeting concrete suppliers | 2017-03-09 08:00 | 2017-03-22 17:00 | 10d |  | 0 | 2112 | 0 | 0 | 2112 | 2017-03-16 09:00 | 10d | 2112 | 0 | 0 | 0 | 0 | 2112 | 0 | 100% | Finished | 2112 | 2112
44 | Ict | 2017-03-09 08:00 | 2017-07-07 17:00 | 87d |  |  | 168000 |  |  | 175560 |  | 125d 6h | [5 empty] | 178920 |  | 100% |  | 175560 | 175560
20 | ICT contracter search | 2017-03-09 08:00 | 2017-04-03 17:00 | 18d | Admin[0.50 #2];Aankoop[0.50 #2];Engineer[0.50 #5] | 7560 | 0 | 0 | 0 | 7560 | 2017-03-16 09:00 | 26d | 10920 | 0 | 0 | 0 | 0 | 10920 | 0 | 100% | Finished | 7560 | 7560
21 | Developing app | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 28d 4h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
22 | developing pay system | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 82d 1h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
23 | Testing & approve app | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 2017-05-31 14:00 | 12d | 84000 | 0 | 0 | 0 | 0 | 84000 | 0 | 100% | Finished | 84000 | 84000
24 | Testing & approve pay system | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 2017-08-15 10:00 | 17d 5h | 84000 | 0 | 0 | 0 | 0 | 84000 | 0 | 100% | Finished | 84000 | 84000
45 | Repair place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d |  |  | 0 |  |  | 17664 |  | 27d 7h | [5 empty] | 21408 |  | 100% |  | 17664 | 17664
26 | construct bike repearing place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d | Arb[4.00 #4] | 17664 | 0 | 0 | 0 | 17664 | 2017-01-30 11:00 | 27d 7h | 21408 | 0 | 0 | 0 | 0 | 21408 | 0 | 100% | Finished | 17664 | 17664
46 | Delivery | 2017-03-30 08:00 | 2017-07-12 17:00 | 75d |  |  | 460000 |  |  | 460000 |  | 79d | [5 empty] | 460000 |  | 100% |  | 460000 | 460000
28 | Delivery bikes parts | 2017-05-04 08:00 | 2017-07-12 17:00 | 50d |  | 0 | 150000 | 0 | 0 | 150000 | 2017-04-20 10:00 | 68d 7h | 150000 | 0 | 0 | 0 | 0 | 150000 | 0 | 100% | Finished | 150000 | 150000
29 | delivery docking station & power tower | 2017-04-27 08:00 | 2017-06-07 17:00 | 30d |  | 0 | 250000 | 0 | 0 | 250000 | 2017-04-19 11:00 | 24d 7h | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | 100% | Finished | 250000 | 250000
30 | delivery ducts | 2017-03-30 08:00 | 2017-04-24 17:00 | 18d |  | 0 | 60000 | 0 | 0 | 60000 | 2017-04-06 09:00 | 13d 5h | 60000 | 0 | 0 | 0 | 0 | 60000 | 0 | 100% | Finished | 60000 | 60000
47 | Assembly | 2017-04-25 08:00 | 2017-08-31 17:00 | 93d |  |  | 0 |  |  | 72575.9999 |  | 108d 7h | [5 empty] | 80990.9999 |  | 100% |  | 72575.9999 | 72575.9999
32 | assembly docking station & power tower | 2017-06-08 08:00 | 2017-08-09 17:00 | 45d | Engineer[0.88 #2];Arb[2.00 #4] | 31535.9999 | 0 | 0 | 0 | 31535.9999 | 2017-05-24 10:00 | 48d 1h | 33725.9999 | 0 | 0 | 0 | 0 | 33725.9999 | 0 | 100% | Finished | 31535.9999 | 31535.9999
33 | assembly bikes & Testing | 2017-07-13 08:00 | 2017-08-31 17:00 | 36d | Arb[4.00 #4] | 27648 | 0 | 0 | 0 | 27648 | 2017-07-26 09:00 | 43d 4h | 33408 | 0 | 0 | 0 | 0 | 33408 | 0 | 100% | Finished | 27648 | 27648
34 | assembly ducts | 2017-04-25 08:00 | 2017-05-18 17:00 | 18d | Engineer;Arb[2.00 #4] | 13392 | 0 | 0 | 0 | 13392 | 2017-04-25 15:00 | 18d 5h | 13857 | 0 | 0 | 0 | 0 | 13857 | 0 | 100% | Finished | 13392 | 13392
48 | Construction total | 2017-04-06 08:00 | 2017-10-02 17:00 | 128d |  |  | 770922 |  |  | 770922 |  | 94d 3h | [5 empty] | 770922 |  | 100% |  | 770922 | 770922
36 | Construction 1 | 2017-04-06 08:00 | 2017-07-04 17:00 | 64d |  | 0 | 587706 | 0 | 0 | 587706 | 2017-04-18 15:00 | 49d 5h | 587706 | 0 | 0 | 0 | 0 | 587706 | 0 | 100% | Finished | 587706 | 587706
37 | Construction 2 | 2017-08-10 08:00 | 2017-10-02 17:00 | 38d |  | 0 | 183216 | 0 | 0 | 183216 | 2017-07-31 11:00 | 20d 6h | 183216 | 0 | 0 | 0 | 0 | 183216 | 0 | 100% | Finished | 183216 | 183216
49 | Final phase | 2017-10-03 08:00 | 2017-11-28 17:00 | 41d |  |  | 0 |  |  | 11520 |  | 20d 7h | [5 empty] | 8352 |  | 100% |  | 11520 | 0
39 | Placing bikes | 2017-10-03 08:00 | 2017-10-23 17:00 | 15d | Arb[4.00 #4] | 11520 | 0 | 0 | 0 | 11520 | 2017-08-29 09:00 | 10d 7h | 8352 | 0 | 0 | 0 | 0 | 8352 | 0 | 100% | Finished | 11520 | 0
40 | Final testing the total system | 2017-10-24 08:00 | 2017-11-28 17:00 | 26d |  | 0 | 0 | 0 | 0 | 0 | 2017-09-13 08:00 | 10d | 0 | 0 | 13d 4h | 0 | 0 | 0 | 0 | 42.55% | Started | 0 | 0
50 | Project buffer | 2017-11-29 08:00 | 2018-03-20 17:00 | 80d |  | 0 | 100000 | 0 | 0 | 100000 |  | 0 | 0 | 100000 | 80d | 0 | 0 | 0 | 100000 | 0% | Not Started | 0 | 0

## TP16
| TP Status Date | 2017-10-17 17:00 |  | TP Name | 17/10/2017 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | projectKopie | 2016-11-16 08:00 | 2018-03-20 17:00 | 350d |  |  | 1546034 |  |  | 1703349.9999 |  | 240d | [5 empty] | 1715032.9999 |  | 100% |  | 1703349.9999 | 1600277.9999
41 | Onderzoek | 2016-11-16 08:00 | 2017-01-25 17:00 | 51d |  |  | 0 |  |  | 23776 |  | 47d 7h | [5 empty] | 24305 |  | 100% |  | 23776 | 23776
2 | Analysis of bikes and bikes usage in gent by students | 2016-11-16 08:00 | 2016-12-05 17:00 | 14d | Engineer[2.00 #2] | 10080 | 0 | 0 | 0 | 10080 | 2016-11-16 08:00 | 19d 3h | 13950 | 0 | 0 | 0 | 0 | 13950 | 0 | 100% | Finished | 10080 | 10080
3 | Properties of the bike | 2016-12-06 08:00 | 2016-12-09 17:00 | 4d | Engineer | 1440 | 0 | 0 | 0 | 1440 | 2016-12-13 11:00 | 2d 3h | 855 | 0 | 0 | 0 | 0 | 855 | 0 | 100% | Finished | 1440 | 1440
4 | Determine amount of bikes needed and hot spots | 2016-12-06 08:00 | 2016-12-12 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2016-12-13 11:00 | 4d 1h | 1485 | 0 | 0 | 0 | 0 | 1485 | 0 | 100% | Finished | 1800 | 1800
5 | research for possibledocking stations | 2016-12-13 08:00 | 2017-01-09 17:00 | 20d | Engineer | 7200 | 0 | 0 | 0 | 7200 | 2016-12-19 13:00 | 13d 4h | 4860 | 0 | 0 | 0 | 0 | 4860 | 0 | 100% | Finished | 7200 | 7200
6 | Resarch amount of staff needed (extra contractors) | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2017-01-06 08:00 | 5d 7h | 2115 | 0 | 0 | 0 | 0 | 2115 | 0 | 100% | Finished | 1800 | 1800
7 | feasibility study | 2017-01-17 08:00 | 2017-01-25 17:00 | 7d | Admin | 1456 | 0 | 0 | 0 | 1456 | 2017-01-13 16:00 | 5d | 1040 | 0 | 0 | 0 | 0 | 1040 | 0 | 100% | Finished | 1456 | 1456
42 | Vans | 2016-12-13 08:00 | 2017-01-26 17:00 | 33d |  |  | 45000 |  |  | 47880 |  | 29d 7h | [5 empty] | 47448 |  | 100% |  | 47880 | 47880
9 | determine type and amound of vans | 2016-12-13 08:00 | 2016-12-15 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 2016-12-19 13:00 | 3d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
10 | buy vans | 2016-12-16 08:00 | 2017-01-05 17:00 | 15d |  | 0 | 45000 | 0 | 0 | 45000 | 2016-12-22 13:00 | 14d 1h | 45000 | 0 | 0 | 0 | 0 | 45000 | 0 | 100% | Finished | 45000 | 45000
11 | adjust vans | 2017-01-06 08:00 | 2017-01-26 17:00 | 15d | Arb | 2880 | 0 | 0 | 0 | 2880 | 2017-01-11 14:00 | 12d 6h | 2448 | 0 | 0 | 0 | 0 | 2448 | 0 | 100% | Finished | 2880 | 2880
43 | Meeting | 2017-01-26 08:00 | 2017-05-03 17:00 | 70d |  |  | 2112 |  |  | 23452 |  | 63d 3h | [5 empty] | 22687 |  | 100% |  | 23452 | 23452
13 | Asking town for permission | 2017-01-26 08:00 | 2017-03-08 17:00 | 30d | Aankoop | 8160 | 0 | 0 | 0 | 8160 | 2017-01-20 16:00 | 38d 2h | 10404 | 0 | 0 | 0 | 0 | 10404 | 0 | 100% | Finished | 8160 | 8160
14 | Asking town for blue prints porwer network | 2017-03-09 08:00 | 2017-04-05 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 | 2017-03-16 09:00 | 23d 5h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | meeting with bike suppliers and contracting | 2017-03-09 08:00 | 2017-05-03 17:00 | 40d | Admin[0.50 #2] | 4160 | 0 | 0 | 0 | 4160 | 2017-03-16 09:00 | 25d 1h | 2613 | 0 | 0 | 0 | 0 | 2613 | 0 | 100% | Finished | 4160 | 4160
16 | meeting with docking stations and tower suppliers and contracting | 2017-03-09 08:00 | 2017-04-26 17:00 | 35d | Aankoop[0.50 #2] | 4760 | 0 | 0 | 0 | 4760 | 2017-03-16 09:00 | 24d 2h | 3298 | 0 | 0 | 0 | 0 | 3298 | 0 | 100% | Finished | 4760 | 4760
17 | meeting with duct suppliers & cable supliers & contracting | 2017-03-09 08:00 | 2017-03-29 17:00 | 15d | Engineer[0.50 #2];Admin[0.50 #2] | 4260 | 0 | 0 | 0 | 4260 | 2017-03-16 09:00 | 15d | 4260 | 0 | 0 | 0 | 0 | 4260 | 0 | 100% | Finished | 4260 | 4260
18 | meeting concrete suppliers | 2017-03-09 08:00 | 2017-03-22 17:00 | 10d |  | 0 | 2112 | 0 | 0 | 2112 | 2017-03-16 09:00 | 10d | 2112 | 0 | 0 | 0 | 0 | 2112 | 0 | 100% | Finished | 2112 | 2112
44 | Ict | 2017-03-09 08:00 | 2017-07-07 17:00 | 87d |  |  | 168000 |  |  | 175560 |  | 125d 6h | [5 empty] | 178920 |  | 100% |  | 175560 | 175560
20 | ICT contracter search | 2017-03-09 08:00 | 2017-04-03 17:00 | 18d | Admin[0.50 #2];Aankoop[0.50 #2];Engineer[0.50 #5] | 7560 | 0 | 0 | 0 | 7560 | 2017-03-16 09:00 | 26d | 10920 | 0 | 0 | 0 | 0 | 10920 | 0 | 100% | Finished | 7560 | 7560
21 | Developing app | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 28d 4h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
22 | developing pay system | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 82d 1h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
23 | Testing & approve app | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 2017-05-31 14:00 | 12d | 84000 | 0 | 0 | 0 | 0 | 84000 | 0 | 100% | Finished | 84000 | 84000
24 | Testing & approve pay system | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 2017-08-15 10:00 | 17d 5h | 84000 | 0 | 0 | 0 | 0 | 84000 | 0 | 100% | Finished | 84000 | 84000
45 | Repair place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d |  |  | 0 |  |  | 17664 |  | 27d 7h | [5 empty] | 21408 |  | 100% |  | 17664 | 17664
26 | construct bike repearing place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d | Arb[4.00 #4] | 17664 | 0 | 0 | 0 | 17664 | 2017-01-30 11:00 | 27d 7h | 21408 | 0 | 0 | 0 | 0 | 21408 | 0 | 100% | Finished | 17664 | 17664
46 | Delivery | 2017-03-30 08:00 | 2017-07-12 17:00 | 75d |  |  | 460000 |  |  | 460000 |  | 79d | [5 empty] | 460000 |  | 100% |  | 460000 | 460000
28 | Delivery bikes parts | 2017-05-04 08:00 | 2017-07-12 17:00 | 50d |  | 0 | 150000 | 0 | 0 | 150000 | 2017-04-20 10:00 | 68d 7h | 150000 | 0 | 0 | 0 | 0 | 150000 | 0 | 100% | Finished | 150000 | 150000
29 | delivery docking station & power tower | 2017-04-27 08:00 | 2017-06-07 17:00 | 30d |  | 0 | 250000 | 0 | 0 | 250000 | 2017-04-19 11:00 | 24d 7h | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | 100% | Finished | 250000 | 250000
30 | delivery ducts | 2017-03-30 08:00 | 2017-04-24 17:00 | 18d |  | 0 | 60000 | 0 | 0 | 60000 | 2017-04-06 09:00 | 13d 5h | 60000 | 0 | 0 | 0 | 0 | 60000 | 0 | 100% | Finished | 60000 | 60000
47 | Assembly | 2017-04-25 08:00 | 2017-08-31 17:00 | 93d |  |  | 0 |  |  | 72575.9999 |  | 108d 7h | [5 empty] | 80990.9999 |  | 100% |  | 72575.9999 | 72575.9999
32 | assembly docking station & power tower | 2017-06-08 08:00 | 2017-08-09 17:00 | 45d | Engineer[0.88 #2];Arb[2.00 #4] | 31535.9999 | 0 | 0 | 0 | 31535.9999 | 2017-05-24 10:00 | 48d 1h | 33725.9999 | 0 | 0 | 0 | 0 | 33725.9999 | 0 | 100% | Finished | 31535.9999 | 31535.9999
33 | assembly bikes & Testing | 2017-07-13 08:00 | 2017-08-31 17:00 | 36d | Arb[4.00 #4] | 27648 | 0 | 0 | 0 | 27648 | 2017-07-26 09:00 | 43d 4h | 33408 | 0 | 0 | 0 | 0 | 33408 | 0 | 100% | Finished | 27648 | 27648
34 | assembly ducts | 2017-04-25 08:00 | 2017-05-18 17:00 | 18d | Engineer;Arb[2.00 #4] | 13392 | 0 | 0 | 0 | 13392 | 2017-04-25 15:00 | 18d 5h | 13857 | 0 | 0 | 0 | 0 | 13857 | 0 | 100% | Finished | 13392 | 13392
48 | Construction total | 2017-04-06 08:00 | 2017-10-02 17:00 | 128d |  |  | 770922 |  |  | 770922 |  | 94d 3h | [5 empty] | 770922 |  | 100% |  | 770922 | 770922
36 | Construction 1 | 2017-04-06 08:00 | 2017-07-04 17:00 | 64d |  | 0 | 587706 | 0 | 0 | 587706 | 2017-04-18 15:00 | 49d 5h | 587706 | 0 | 0 | 0 | 0 | 587706 | 0 | 100% | Finished | 587706 | 587706
37 | Construction 2 | 2017-08-10 08:00 | 2017-10-02 17:00 | 38d |  | 0 | 183216 | 0 | 0 | 183216 | 2017-07-31 11:00 | 20d 6h | 183216 | 0 | 0 | 0 | 0 | 183216 | 0 | 100% | Finished | 183216 | 183216
49 | Final phase | 2017-10-03 08:00 | 2017-11-28 17:00 | 41d |  |  | 0 |  |  | 11520 |  | 34d 3h | [5 empty] | 8352 |  | 100% |  | 11520 | 8448
39 | Placing bikes | 2017-10-03 08:00 | 2017-10-23 17:00 | 15d | Arb[4.00 #4] | 11520 | 0 | 0 | 0 | 11520 | 2017-08-29 09:00 | 10d 7h | 8352 | 0 | 0 | 0 | 0 | 8352 | 0 | 100% | Finished | 11520 | 8448
40 | Final testing the total system | 2017-10-24 08:00 | 2017-11-28 17:00 | 26d |  | 0 | 0 | 0 | 0 | 0 | 2017-09-13 08:00 | 23d 4h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
50 | Project buffer | 2017-11-29 08:00 | 2018-03-20 17:00 | 80d |  | 0 | 100000 | 0 | 0 | 100000 | 2017-10-16 13:00 | 1d 4h | 100000 | 0 | 98d 5h | 0 | 0 | 100000 | 0 | 1.498% | Started | 100000 | 0

## TP17
| TP Status Date | 2017-11-07 17:00 |  | TP Name | 7/11/2017 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | projectKopie | 2016-11-16 08:00 | 2018-03-20 17:00 | 350d |  |  | 1546034 |  |  | 1703349.9999 |  | 255d | [5 empty] | 1715032.9999 |  | 100% |  | 1703349.9999 | 1603349.9999
41 | Onderzoek | 2016-11-16 08:00 | 2017-01-25 17:00 | 51d |  |  | 0 |  |  | 23776 |  | 47d 7h | [5 empty] | 24305 |  | 100% |  | 23776 | 23776
2 | Analysis of bikes and bikes usage in gent by students | 2016-11-16 08:00 | 2016-12-05 17:00 | 14d | Engineer[2.00 #2] | 10080 | 0 | 0 | 0 | 10080 | 2016-11-16 08:00 | 19d 3h | 13950 | 0 | 0 | 0 | 0 | 13950 | 0 | 100% | Finished | 10080 | 10080
3 | Properties of the bike | 2016-12-06 08:00 | 2016-12-09 17:00 | 4d | Engineer | 1440 | 0 | 0 | 0 | 1440 | 2016-12-13 11:00 | 2d 3h | 855 | 0 | 0 | 0 | 0 | 855 | 0 | 100% | Finished | 1440 | 1440
4 | Determine amount of bikes needed and hot spots | 2016-12-06 08:00 | 2016-12-12 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2016-12-13 11:00 | 4d 1h | 1485 | 0 | 0 | 0 | 0 | 1485 | 0 | 100% | Finished | 1800 | 1800
5 | research for possibledocking stations | 2016-12-13 08:00 | 2017-01-09 17:00 | 20d | Engineer | 7200 | 0 | 0 | 0 | 7200 | 2016-12-19 13:00 | 13d 4h | 4860 | 0 | 0 | 0 | 0 | 4860 | 0 | 100% | Finished | 7200 | 7200
6 | Resarch amount of staff needed (extra contractors) | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2017-01-06 08:00 | 5d 7h | 2115 | 0 | 0 | 0 | 0 | 2115 | 0 | 100% | Finished | 1800 | 1800
7 | feasibility study | 2017-01-17 08:00 | 2017-01-25 17:00 | 7d | Admin | 1456 | 0 | 0 | 0 | 1456 | 2017-01-13 16:00 | 5d | 1040 | 0 | 0 | 0 | 0 | 1040 | 0 | 100% | Finished | 1456 | 1456
42 | Vans | 2016-12-13 08:00 | 2017-01-26 17:00 | 33d |  |  | 45000 |  |  | 47880 |  | 29d 7h | [5 empty] | 47448 |  | 100% |  | 47880 | 47880
9 | determine type and amound of vans | 2016-12-13 08:00 | 2016-12-15 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 2016-12-19 13:00 | 3d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
10 | buy vans | 2016-12-16 08:00 | 2017-01-05 17:00 | 15d |  | 0 | 45000 | 0 | 0 | 45000 | 2016-12-22 13:00 | 14d 1h | 45000 | 0 | 0 | 0 | 0 | 45000 | 0 | 100% | Finished | 45000 | 45000
11 | adjust vans | 2017-01-06 08:00 | 2017-01-26 17:00 | 15d | Arb | 2880 | 0 | 0 | 0 | 2880 | 2017-01-11 14:00 | 12d 6h | 2448 | 0 | 0 | 0 | 0 | 2448 | 0 | 100% | Finished | 2880 | 2880
43 | Meeting | 2017-01-26 08:00 | 2017-05-03 17:00 | 70d |  |  | 2112 |  |  | 23452 |  | 63d 3h | [5 empty] | 22687 |  | 100% |  | 23452 | 23452
13 | Asking town for permission | 2017-01-26 08:00 | 2017-03-08 17:00 | 30d | Aankoop | 8160 | 0 | 0 | 0 | 8160 | 2017-01-20 16:00 | 38d 2h | 10404 | 0 | 0 | 0 | 0 | 10404 | 0 | 100% | Finished | 8160 | 8160
14 | Asking town for blue prints porwer network | 2017-03-09 08:00 | 2017-04-05 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 | 2017-03-16 09:00 | 23d 5h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | meeting with bike suppliers and contracting | 2017-03-09 08:00 | 2017-05-03 17:00 | 40d | Admin[0.50 #2] | 4160 | 0 | 0 | 0 | 4160 | 2017-03-16 09:00 | 25d 1h | 2613 | 0 | 0 | 0 | 0 | 2613 | 0 | 100% | Finished | 4160 | 4160
16 | meeting with docking stations and tower suppliers and contracting | 2017-03-09 08:00 | 2017-04-26 17:00 | 35d | Aankoop[0.50 #2] | 4760 | 0 | 0 | 0 | 4760 | 2017-03-16 09:00 | 24d 2h | 3298 | 0 | 0 | 0 | 0 | 3298 | 0 | 100% | Finished | 4760 | 4760
17 | meeting with duct suppliers & cable supliers & contracting | 2017-03-09 08:00 | 2017-03-29 17:00 | 15d | Engineer[0.50 #2];Admin[0.50 #2] | 4260 | 0 | 0 | 0 | 4260 | 2017-03-16 09:00 | 15d | 4260 | 0 | 0 | 0 | 0 | 4260 | 0 | 100% | Finished | 4260 | 4260
18 | meeting concrete suppliers | 2017-03-09 08:00 | 2017-03-22 17:00 | 10d |  | 0 | 2112 | 0 | 0 | 2112 | 2017-03-16 09:00 | 10d | 2112 | 0 | 0 | 0 | 0 | 2112 | 0 | 100% | Finished | 2112 | 2112
44 | Ict | 2017-03-09 08:00 | 2017-07-07 17:00 | 87d |  |  | 168000 |  |  | 175560 |  | 125d 6h | [5 empty] | 178920 |  | 100% |  | 175560 | 175560
20 | ICT contracter search | 2017-03-09 08:00 | 2017-04-03 17:00 | 18d | Admin[0.50 #2];Aankoop[0.50 #2];Engineer[0.50 #5] | 7560 | 0 | 0 | 0 | 7560 | 2017-03-16 09:00 | 26d | 10920 | 0 | 0 | 0 | 0 | 10920 | 0 | 100% | Finished | 7560 | 7560
21 | Developing app | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 28d 4h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
22 | developing pay system | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 82d 1h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
23 | Testing & approve app | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 2017-05-31 14:00 | 12d | 84000 | 0 | 0 | 0 | 0 | 84000 | 0 | 100% | Finished | 84000 | 84000
24 | Testing & approve pay system | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 2017-08-15 10:00 | 17d 5h | 84000 | 0 | 0 | 0 | 0 | 84000 | 0 | 100% | Finished | 84000 | 84000
45 | Repair place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d |  |  | 0 |  |  | 17664 |  | 27d 7h | [5 empty] | 21408 |  | 100% |  | 17664 | 17664
26 | construct bike repearing place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d | Arb[4.00 #4] | 17664 | 0 | 0 | 0 | 17664 | 2017-01-30 11:00 | 27d 7h | 21408 | 0 | 0 | 0 | 0 | 21408 | 0 | 100% | Finished | 17664 | 17664
46 | Delivery | 2017-03-30 08:00 | 2017-07-12 17:00 | 75d |  |  | 460000 |  |  | 460000 |  | 79d | [5 empty] | 460000 |  | 100% |  | 460000 | 460000
28 | Delivery bikes parts | 2017-05-04 08:00 | 2017-07-12 17:00 | 50d |  | 0 | 150000 | 0 | 0 | 150000 | 2017-04-20 10:00 | 68d 7h | 150000 | 0 | 0 | 0 | 0 | 150000 | 0 | 100% | Finished | 150000 | 150000
29 | delivery docking station & power tower | 2017-04-27 08:00 | 2017-06-07 17:00 | 30d |  | 0 | 250000 | 0 | 0 | 250000 | 2017-04-19 11:00 | 24d 7h | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | 100% | Finished | 250000 | 250000
30 | delivery ducts | 2017-03-30 08:00 | 2017-04-24 17:00 | 18d |  | 0 | 60000 | 0 | 0 | 60000 | 2017-04-06 09:00 | 13d 5h | 60000 | 0 | 0 | 0 | 0 | 60000 | 0 | 100% | Finished | 60000 | 60000
47 | Assembly | 2017-04-25 08:00 | 2017-08-31 17:00 | 93d |  |  | 0 |  |  | 72575.9999 |  | 108d 7h | [5 empty] | 80990.9999 |  | 100% |  | 72575.9999 | 72575.9999
32 | assembly docking station & power tower | 2017-06-08 08:00 | 2017-08-09 17:00 | 45d | Engineer[0.88 #2];Arb[2.00 #4] | 31535.9999 | 0 | 0 | 0 | 31535.9999 | 2017-05-24 10:00 | 48d 1h | 33725.9999 | 0 | 0 | 0 | 0 | 33725.9999 | 0 | 100% | Finished | 31535.9999 | 31535.9999
33 | assembly bikes & Testing | 2017-07-13 08:00 | 2017-08-31 17:00 | 36d | Arb[4.00 #4] | 27648 | 0 | 0 | 0 | 27648 | 2017-07-26 09:00 | 43d 4h | 33408 | 0 | 0 | 0 | 0 | 33408 | 0 | 100% | Finished | 27648 | 27648
34 | assembly ducts | 2017-04-25 08:00 | 2017-05-18 17:00 | 18d | Engineer;Arb[2.00 #4] | 13392 | 0 | 0 | 0 | 13392 | 2017-04-25 15:00 | 18d 5h | 13857 | 0 | 0 | 0 | 0 | 13857 | 0 | 100% | Finished | 13392 | 13392
48 | Construction total | 2017-04-06 08:00 | 2017-10-02 17:00 | 128d |  |  | 770922 |  |  | 770922 |  | 94d 3h | [5 empty] | 770922 |  | 100% |  | 770922 | 770922
36 | Construction 1 | 2017-04-06 08:00 | 2017-07-04 17:00 | 64d |  | 0 | 587706 | 0 | 0 | 587706 | 2017-04-18 15:00 | 49d 5h | 587706 | 0 | 0 | 0 | 0 | 587706 | 0 | 100% | Finished | 587706 | 587706
37 | Construction 2 | 2017-08-10 08:00 | 2017-10-02 17:00 | 38d |  | 0 | 183216 | 0 | 0 | 183216 | 2017-07-31 11:00 | 20d 6h | 183216 | 0 | 0 | 0 | 0 | 183216 | 0 | 100% | Finished | 183216 | 183216
49 | Final phase | 2017-10-03 08:00 | 2017-11-28 17:00 | 41d |  |  | 0 |  |  | 11520 |  | 34d 3h | [5 empty] | 8352 |  | 100% |  | 11520 | 11520
39 | Placing bikes | 2017-10-03 08:00 | 2017-10-23 17:00 | 15d | Arb[4.00 #4] | 11520 | 0 | 0 | 0 | 11520 | 2017-08-29 09:00 | 10d 7h | 8352 | 0 | 0 | 0 | 0 | 8352 | 0 | 100% | Finished | 11520 | 11520
40 | Final testing the total system | 2017-10-24 08:00 | 2017-11-28 17:00 | 26d |  | 0 | 0 | 0 | 0 | 0 | 2017-09-13 08:00 | 23d 4h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
50 | Project buffer | 2017-11-29 08:00 | 2018-03-20 17:00 | 80d |  | 0 | 100000 | 0 | 0 | 100000 | 2017-10-16 13:00 | 16d 4h | 100000 | 0 | 83d 5h | 0 | 0 | 100000 | 0 | 16.48% | Started | 100000 | 0

## TP18
| TP Status Date | 2017-11-28 17:00 |  | TP Name | 28/11/2017 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | projectKopie | 2016-11-16 08:00 | 2018-03-20 17:00 | 350d |  |  | 1546034 |  |  | 1703349.9999 |  | 270d | [5 empty] | 1715032.9999 |  | 100% |  | 1703349.9999 | 1603349.9999
41 | Onderzoek | 2016-11-16 08:00 | 2017-01-25 17:00 | 51d |  |  | 0 |  |  | 23776 |  | 47d 7h | [5 empty] | 24305 |  | 100% |  | 23776 | 23776
2 | Analysis of bikes and bikes usage in gent by students | 2016-11-16 08:00 | 2016-12-05 17:00 | 14d | Engineer[2.00 #2] | 10080 | 0 | 0 | 0 | 10080 | 2016-11-16 08:00 | 19d 3h | 13950 | 0 | 0 | 0 | 0 | 13950 | 0 | 100% | Finished | 10080 | 10080
3 | Properties of the bike | 2016-12-06 08:00 | 2016-12-09 17:00 | 4d | Engineer | 1440 | 0 | 0 | 0 | 1440 | 2016-12-13 11:00 | 2d 3h | 855 | 0 | 0 | 0 | 0 | 855 | 0 | 100% | Finished | 1440 | 1440
4 | Determine amount of bikes needed and hot spots | 2016-12-06 08:00 | 2016-12-12 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2016-12-13 11:00 | 4d 1h | 1485 | 0 | 0 | 0 | 0 | 1485 | 0 | 100% | Finished | 1800 | 1800
5 | research for possibledocking stations | 2016-12-13 08:00 | 2017-01-09 17:00 | 20d | Engineer | 7200 | 0 | 0 | 0 | 7200 | 2016-12-19 13:00 | 13d 4h | 4860 | 0 | 0 | 0 | 0 | 4860 | 0 | 100% | Finished | 7200 | 7200
6 | Resarch amount of staff needed (extra contractors) | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2017-01-06 08:00 | 5d 7h | 2115 | 0 | 0 | 0 | 0 | 2115 | 0 | 100% | Finished | 1800 | 1800
7 | feasibility study | 2017-01-17 08:00 | 2017-01-25 17:00 | 7d | Admin | 1456 | 0 | 0 | 0 | 1456 | 2017-01-13 16:00 | 5d | 1040 | 0 | 0 | 0 | 0 | 1040 | 0 | 100% | Finished | 1456 | 1456
42 | Vans | 2016-12-13 08:00 | 2017-01-26 17:00 | 33d |  |  | 45000 |  |  | 47880 |  | 29d 7h | [5 empty] | 47448 |  | 100% |  | 47880 | 47880
9 | determine type and amound of vans | 2016-12-13 08:00 | 2016-12-15 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 2016-12-19 13:00 | 3d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
10 | buy vans | 2016-12-16 08:00 | 2017-01-05 17:00 | 15d |  | 0 | 45000 | 0 | 0 | 45000 | 2016-12-22 13:00 | 14d 1h | 45000 | 0 | 0 | 0 | 0 | 45000 | 0 | 100% | Finished | 45000 | 45000
11 | adjust vans | 2017-01-06 08:00 | 2017-01-26 17:00 | 15d | Arb | 2880 | 0 | 0 | 0 | 2880 | 2017-01-11 14:00 | 12d 6h | 2448 | 0 | 0 | 0 | 0 | 2448 | 0 | 100% | Finished | 2880 | 2880
43 | Meeting | 2017-01-26 08:00 | 2017-05-03 17:00 | 70d |  |  | 2112 |  |  | 23452 |  | 63d 3h | [5 empty] | 22687 |  | 100% |  | 23452 | 23452
13 | Asking town for permission | 2017-01-26 08:00 | 2017-03-08 17:00 | 30d | Aankoop | 8160 | 0 | 0 | 0 | 8160 | 2017-01-20 16:00 | 38d 2h | 10404 | 0 | 0 | 0 | 0 | 10404 | 0 | 100% | Finished | 8160 | 8160
14 | Asking town for blue prints porwer network | 2017-03-09 08:00 | 2017-04-05 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 | 2017-03-16 09:00 | 23d 5h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | meeting with bike suppliers and contracting | 2017-03-09 08:00 | 2017-05-03 17:00 | 40d | Admin[0.50 #2] | 4160 | 0 | 0 | 0 | 4160 | 2017-03-16 09:00 | 25d 1h | 2613 | 0 | 0 | 0 | 0 | 2613 | 0 | 100% | Finished | 4160 | 4160
16 | meeting with docking stations and tower suppliers and contracting | 2017-03-09 08:00 | 2017-04-26 17:00 | 35d | Aankoop[0.50 #2] | 4760 | 0 | 0 | 0 | 4760 | 2017-03-16 09:00 | 24d 2h | 3298 | 0 | 0 | 0 | 0 | 3298 | 0 | 100% | Finished | 4760 | 4760
17 | meeting with duct suppliers & cable supliers & contracting | 2017-03-09 08:00 | 2017-03-29 17:00 | 15d | Engineer[0.50 #2];Admin[0.50 #2] | 4260 | 0 | 0 | 0 | 4260 | 2017-03-16 09:00 | 15d | 4260 | 0 | 0 | 0 | 0 | 4260 | 0 | 100% | Finished | 4260 | 4260
18 | meeting concrete suppliers | 2017-03-09 08:00 | 2017-03-22 17:00 | 10d |  | 0 | 2112 | 0 | 0 | 2112 | 2017-03-16 09:00 | 10d | 2112 | 0 | 0 | 0 | 0 | 2112 | 0 | 100% | Finished | 2112 | 2112
44 | Ict | 2017-03-09 08:00 | 2017-07-07 17:00 | 87d |  |  | 168000 |  |  | 175560 |  | 125d 6h | [5 empty] | 178920 |  | 100% |  | 175560 | 175560
20 | ICT contracter search | 2017-03-09 08:00 | 2017-04-03 17:00 | 18d | Admin[0.50 #2];Aankoop[0.50 #2];Engineer[0.50 #5] | 7560 | 0 | 0 | 0 | 7560 | 2017-03-16 09:00 | 26d | 10920 | 0 | 0 | 0 | 0 | 10920 | 0 | 100% | Finished | 7560 | 7560
21 | Developing app | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 28d 4h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
22 | developing pay system | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 82d 1h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
23 | Testing & approve app | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 2017-05-31 14:00 | 12d | 84000 | 0 | 0 | 0 | 0 | 84000 | 0 | 100% | Finished | 84000 | 84000
24 | Testing & approve pay system | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 2017-08-15 10:00 | 17d 5h | 84000 | 0 | 0 | 0 | 0 | 84000 | 0 | 100% | Finished | 84000 | 84000
45 | Repair place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d |  |  | 0 |  |  | 17664 |  | 27d 7h | [5 empty] | 21408 |  | 100% |  | 17664 | 17664
26 | construct bike repearing place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d | Arb[4.00 #4] | 17664 | 0 | 0 | 0 | 17664 | 2017-01-30 11:00 | 27d 7h | 21408 | 0 | 0 | 0 | 0 | 21408 | 0 | 100% | Finished | 17664 | 17664
46 | Delivery | 2017-03-30 08:00 | 2017-07-12 17:00 | 75d |  |  | 460000 |  |  | 460000 |  | 79d | [5 empty] | 460000 |  | 100% |  | 460000 | 460000
28 | Delivery bikes parts | 2017-05-04 08:00 | 2017-07-12 17:00 | 50d |  | 0 | 150000 | 0 | 0 | 150000 | 2017-04-20 10:00 | 68d 7h | 150000 | 0 | 0 | 0 | 0 | 150000 | 0 | 100% | Finished | 150000 | 150000
29 | delivery docking station & power tower | 2017-04-27 08:00 | 2017-06-07 17:00 | 30d |  | 0 | 250000 | 0 | 0 | 250000 | 2017-04-19 11:00 | 24d 7h | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | 100% | Finished | 250000 | 250000
30 | delivery ducts | 2017-03-30 08:00 | 2017-04-24 17:00 | 18d |  | 0 | 60000 | 0 | 0 | 60000 | 2017-04-06 09:00 | 13d 5h | 60000 | 0 | 0 | 0 | 0 | 60000 | 0 | 100% | Finished | 60000 | 60000
47 | Assembly | 2017-04-25 08:00 | 2017-08-31 17:00 | 93d |  |  | 0 |  |  | 72575.9999 |  | 108d 7h | [5 empty] | 80990.9999 |  | 100% |  | 72575.9999 | 72575.9999
32 | assembly docking station & power tower | 2017-06-08 08:00 | 2017-08-09 17:00 | 45d | Engineer[0.88 #2];Arb[2.00 #4] | 31535.9999 | 0 | 0 | 0 | 31535.9999 | 2017-05-24 10:00 | 48d 1h | 33725.9999 | 0 | 0 | 0 | 0 | 33725.9999 | 0 | 100% | Finished | 31535.9999 | 31535.9999
33 | assembly bikes & Testing | 2017-07-13 08:00 | 2017-08-31 17:00 | 36d | Arb[4.00 #4] | 27648 | 0 | 0 | 0 | 27648 | 2017-07-26 09:00 | 43d 4h | 33408 | 0 | 0 | 0 | 0 | 33408 | 0 | 100% | Finished | 27648 | 27648
34 | assembly ducts | 2017-04-25 08:00 | 2017-05-18 17:00 | 18d | Engineer;Arb[2.00 #4] | 13392 | 0 | 0 | 0 | 13392 | 2017-04-25 15:00 | 18d 5h | 13857 | 0 | 0 | 0 | 0 | 13857 | 0 | 100% | Finished | 13392 | 13392
48 | Construction total | 2017-04-06 08:00 | 2017-10-02 17:00 | 128d |  |  | 770922 |  |  | 770922 |  | 94d 3h | [5 empty] | 770922 |  | 100% |  | 770922 | 770922
36 | Construction 1 | 2017-04-06 08:00 | 2017-07-04 17:00 | 64d |  | 0 | 587706 | 0 | 0 | 587706 | 2017-04-18 15:00 | 49d 5h | 587706 | 0 | 0 | 0 | 0 | 587706 | 0 | 100% | Finished | 587706 | 587706
37 | Construction 2 | 2017-08-10 08:00 | 2017-10-02 17:00 | 38d |  | 0 | 183216 | 0 | 0 | 183216 | 2017-07-31 11:00 | 20d 6h | 183216 | 0 | 0 | 0 | 0 | 183216 | 0 | 100% | Finished | 183216 | 183216
49 | Final phase | 2017-10-03 08:00 | 2017-11-28 17:00 | 41d |  |  | 0 |  |  | 11520 |  | 34d 3h | [5 empty] | 8352 |  | 100% |  | 11520 | 11520
39 | Placing bikes | 2017-10-03 08:00 | 2017-10-23 17:00 | 15d | Arb[4.00 #4] | 11520 | 0 | 0 | 0 | 11520 | 2017-08-29 09:00 | 10d 7h | 8352 | 0 | 0 | 0 | 0 | 8352 | 0 | 100% | Finished | 11520 | 11520
40 | Final testing the total system | 2017-10-24 08:00 | 2017-11-28 17:00 | 26d |  | 0 | 0 | 0 | 0 | 0 | 2017-09-13 08:00 | 23d 4h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
50 | Project buffer | 2017-11-29 08:00 | 2018-03-20 17:00 | 80d |  | 0 | 100000 | 0 | 0 | 100000 | 2017-10-16 13:00 | 31d 4h | 100000 | 0 | 68d 5h | 0 | 0 | 100000 | 0 | 31.46% | Started | 100000 | 0

## TP19
| TP Status Date | 2017-12-19 17:00 |  | TP Name | 19/12/2017 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | projectKopie | 2016-11-16 08:00 | 2018-03-20 17:00 | 350d |  |  | 1546034 |  |  | 1703349.9999 |  | 285d | [5 empty] | 1715032.9999 |  | 100% |  | 1703349.9999 | 1703349.9999
41 | Onderzoek | 2016-11-16 08:00 | 2017-01-25 17:00 | 51d |  |  | 0 |  |  | 23776 |  | 47d 7h | [5 empty] | 24305 |  | 100% |  | 23776 | 23776
2 | Analysis of bikes and bikes usage in gent by students | 2016-11-16 08:00 | 2016-12-05 17:00 | 14d | Engineer[2.00 #2] | 10080 | 0 | 0 | 0 | 10080 | 2016-11-16 08:00 | 19d 3h | 13950 | 0 | 0 | 0 | 0 | 13950 | 0 | 100% | Finished | 10080 | 10080
3 | Properties of the bike | 2016-12-06 08:00 | 2016-12-09 17:00 | 4d | Engineer | 1440 | 0 | 0 | 0 | 1440 | 2016-12-13 11:00 | 2d 3h | 855 | 0 | 0 | 0 | 0 | 855 | 0 | 100% | Finished | 1440 | 1440
4 | Determine amount of bikes needed and hot spots | 2016-12-06 08:00 | 2016-12-12 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2016-12-13 11:00 | 4d 1h | 1485 | 0 | 0 | 0 | 0 | 1485 | 0 | 100% | Finished | 1800 | 1800
5 | research for possibledocking stations | 2016-12-13 08:00 | 2017-01-09 17:00 | 20d | Engineer | 7200 | 0 | 0 | 0 | 7200 | 2016-12-19 13:00 | 13d 4h | 4860 | 0 | 0 | 0 | 0 | 4860 | 0 | 100% | Finished | 7200 | 7200
6 | Resarch amount of staff needed (extra contractors) | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2017-01-06 08:00 | 5d 7h | 2115 | 0 | 0 | 0 | 0 | 2115 | 0 | 100% | Finished | 1800 | 1800
7 | feasibility study | 2017-01-17 08:00 | 2017-01-25 17:00 | 7d | Admin | 1456 | 0 | 0 | 0 | 1456 | 2017-01-13 16:00 | 5d | 1040 | 0 | 0 | 0 | 0 | 1040 | 0 | 100% | Finished | 1456 | 1456
42 | Vans | 2016-12-13 08:00 | 2017-01-26 17:00 | 33d |  |  | 45000 |  |  | 47880 |  | 29d 7h | [5 empty] | 47448 |  | 100% |  | 47880 | 47880
9 | determine type and amound of vans | 2016-12-13 08:00 | 2016-12-15 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 2016-12-19 13:00 | 3d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
10 | buy vans | 2016-12-16 08:00 | 2017-01-05 17:00 | 15d |  | 0 | 45000 | 0 | 0 | 45000 | 2016-12-22 13:00 | 14d 1h | 45000 | 0 | 0 | 0 | 0 | 45000 | 0 | 100% | Finished | 45000 | 45000
11 | adjust vans | 2017-01-06 08:00 | 2017-01-26 17:00 | 15d | Arb | 2880 | 0 | 0 | 0 | 2880 | 2017-01-11 14:00 | 12d 6h | 2448 | 0 | 0 | 0 | 0 | 2448 | 0 | 100% | Finished | 2880 | 2880
43 | Meeting | 2017-01-26 08:00 | 2017-05-03 17:00 | 70d |  |  | 2112 |  |  | 23452 |  | 63d 3h | [5 empty] | 22687 |  | 100% |  | 23452 | 23452
13 | Asking town for permission | 2017-01-26 08:00 | 2017-03-08 17:00 | 30d | Aankoop | 8160 | 0 | 0 | 0 | 8160 | 2017-01-20 16:00 | 38d 2h | 10404 | 0 | 0 | 0 | 0 | 10404 | 0 | 100% | Finished | 8160 | 8160
14 | Asking town for blue prints porwer network | 2017-03-09 08:00 | 2017-04-05 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 | 2017-03-16 09:00 | 23d 5h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | meeting with bike suppliers and contracting | 2017-03-09 08:00 | 2017-05-03 17:00 | 40d | Admin[0.50 #2] | 4160 | 0 | 0 | 0 | 4160 | 2017-03-16 09:00 | 25d 1h | 2613 | 0 | 0 | 0 | 0 | 2613 | 0 | 100% | Finished | 4160 | 4160
16 | meeting with docking stations and tower suppliers and contracting | 2017-03-09 08:00 | 2017-04-26 17:00 | 35d | Aankoop[0.50 #2] | 4760 | 0 | 0 | 0 | 4760 | 2017-03-16 09:00 | 24d 2h | 3298 | 0 | 0 | 0 | 0 | 3298 | 0 | 100% | Finished | 4760 | 4760
17 | meeting with duct suppliers & cable supliers & contracting | 2017-03-09 08:00 | 2017-03-29 17:00 | 15d | Engineer[0.50 #2];Admin[0.50 #2] | 4260 | 0 | 0 | 0 | 4260 | 2017-03-16 09:00 | 15d | 4260 | 0 | 0 | 0 | 0 | 4260 | 0 | 100% | Finished | 4260 | 4260
18 | meeting concrete suppliers | 2017-03-09 08:00 | 2017-03-22 17:00 | 10d |  | 0 | 2112 | 0 | 0 | 2112 | 2017-03-16 09:00 | 10d | 2112 | 0 | 0 | 0 | 0 | 2112 | 0 | 100% | Finished | 2112 | 2112
44 | Ict | 2017-03-09 08:00 | 2017-07-07 17:00 | 87d |  |  | 168000 |  |  | 175560 |  | 125d 6h | [5 empty] | 178920 |  | 100% |  | 175560 | 175560
20 | ICT contracter search | 2017-03-09 08:00 | 2017-04-03 17:00 | 18d | Admin[0.50 #2];Aankoop[0.50 #2];Engineer[0.50 #5] | 7560 | 0 | 0 | 0 | 7560 | 2017-03-16 09:00 | 26d | 10920 | 0 | 0 | 0 | 0 | 10920 | 0 | 100% | Finished | 7560 | 7560
21 | Developing app | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 28d 4h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
22 | developing pay system | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 82d 1h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
23 | Testing & approve app | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 2017-05-31 14:00 | 12d | 84000 | 0 | 0 | 0 | 0 | 84000 | 0 | 100% | Finished | 84000 | 84000
24 | Testing & approve pay system | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 2017-08-15 10:00 | 17d 5h | 84000 | 0 | 0 | 0 | 0 | 84000 | 0 | 100% | Finished | 84000 | 84000
45 | Repair place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d |  |  | 0 |  |  | 17664 |  | 27d 7h | [5 empty] | 21408 |  | 100% |  | 17664 | 17664
26 | construct bike repearing place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d | Arb[4.00 #4] | 17664 | 0 | 0 | 0 | 17664 | 2017-01-30 11:00 | 27d 7h | 21408 | 0 | 0 | 0 | 0 | 21408 | 0 | 100% | Finished | 17664 | 17664
46 | Delivery | 2017-03-30 08:00 | 2017-07-12 17:00 | 75d |  |  | 460000 |  |  | 460000 |  | 79d | [5 empty] | 460000 |  | 100% |  | 460000 | 460000
28 | Delivery bikes parts | 2017-05-04 08:00 | 2017-07-12 17:00 | 50d |  | 0 | 150000 | 0 | 0 | 150000 | 2017-04-20 10:00 | 68d 7h | 150000 | 0 | 0 | 0 | 0 | 150000 | 0 | 100% | Finished | 150000 | 150000
29 | delivery docking station & power tower | 2017-04-27 08:00 | 2017-06-07 17:00 | 30d |  | 0 | 250000 | 0 | 0 | 250000 | 2017-04-19 11:00 | 24d 7h | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | 100% | Finished | 250000 | 250000
30 | delivery ducts | 2017-03-30 08:00 | 2017-04-24 17:00 | 18d |  | 0 | 60000 | 0 | 0 | 60000 | 2017-04-06 09:00 | 13d 5h | 60000 | 0 | 0 | 0 | 0 | 60000 | 0 | 100% | Finished | 60000 | 60000
47 | Assembly | 2017-04-25 08:00 | 2017-08-31 17:00 | 93d |  |  | 0 |  |  | 72575.9999 |  | 108d 7h | [5 empty] | 80990.9999 |  | 100% |  | 72575.9999 | 72575.9999
32 | assembly docking station & power tower | 2017-06-08 08:00 | 2017-08-09 17:00 | 45d | Engineer[0.88 #2];Arb[2.00 #4] | 31535.9999 | 0 | 0 | 0 | 31535.9999 | 2017-05-24 10:00 | 48d 1h | 33725.9999 | 0 | 0 | 0 | 0 | 33725.9999 | 0 | 100% | Finished | 31535.9999 | 31535.9999
33 | assembly bikes & Testing | 2017-07-13 08:00 | 2017-08-31 17:00 | 36d | Arb[4.00 #4] | 27648 | 0 | 0 | 0 | 27648 | 2017-07-26 09:00 | 43d 4h | 33408 | 0 | 0 | 0 | 0 | 33408 | 0 | 100% | Finished | 27648 | 27648
34 | assembly ducts | 2017-04-25 08:00 | 2017-05-18 17:00 | 18d | Engineer;Arb[2.00 #4] | 13392 | 0 | 0 | 0 | 13392 | 2017-04-25 15:00 | 18d 5h | 13857 | 0 | 0 | 0 | 0 | 13857 | 0 | 100% | Finished | 13392 | 13392
48 | Construction total | 2017-04-06 08:00 | 2017-10-02 17:00 | 128d |  |  | 770922 |  |  | 770922 |  | 94d 3h | [5 empty] | 770922 |  | 100% |  | 770922 | 770922
36 | Construction 1 | 2017-04-06 08:00 | 2017-07-04 17:00 | 64d |  | 0 | 587706 | 0 | 0 | 587706 | 2017-04-18 15:00 | 49d 5h | 587706 | 0 | 0 | 0 | 0 | 587706 | 0 | 100% | Finished | 587706 | 587706
37 | Construction 2 | 2017-08-10 08:00 | 2017-10-02 17:00 | 38d |  | 0 | 183216 | 0 | 0 | 183216 | 2017-07-31 11:00 | 20d 6h | 183216 | 0 | 0 | 0 | 0 | 183216 | 0 | 100% | Finished | 183216 | 183216
49 | Final phase | 2017-10-03 08:00 | 2017-11-28 17:00 | 41d |  |  | 0 |  |  | 11520 |  | 34d 3h | [5 empty] | 8352 |  | 100% |  | 11520 | 11520
39 | Placing bikes | 2017-10-03 08:00 | 2017-10-23 17:00 | 15d | Arb[4.00 #4] | 11520 | 0 | 0 | 0 | 11520 | 2017-08-29 09:00 | 10d 7h | 8352 | 0 | 0 | 0 | 0 | 8352 | 0 | 100% | Finished | 11520 | 11520
40 | Final testing the total system | 2017-10-24 08:00 | 2017-11-28 17:00 | 26d |  | 0 | 0 | 0 | 0 | 0 | 2017-09-13 08:00 | 23d 4h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
50 | Project buffer | 2017-11-29 08:00 | 2018-03-20 17:00 | 80d |  | 0 | 100000 | 0 | 0 | 100000 | 2017-10-16 13:00 | 46d 4h | 100000 | 0 | 53d 5h | 0 | 0 | 100000 | 0 | 46.44% | Started | 100000 | 100000

## TP20
| TP Status Date | 2018-01-09 17:00 |  | TP Name | 9/01/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | projectKopie | 2016-11-16 08:00 | 2018-03-20 17:00 | 350d |  |  | 1546034 |  |  | 1703349.9999 |  | 300d | [5 empty] | 1715032.9999 |  | 100% |  | 1703349.9999 | 1703349.9999
41 | Onderzoek | 2016-11-16 08:00 | 2017-01-25 17:00 | 51d |  |  | 0 |  |  | 23776 |  | 47d 7h | [5 empty] | 24305 |  | 100% |  | 23776 | 23776
2 | Analysis of bikes and bikes usage in gent by students | 2016-11-16 08:00 | 2016-12-05 17:00 | 14d | Engineer[2.00 #2] | 10080 | 0 | 0 | 0 | 10080 | 2016-11-16 08:00 | 19d 3h | 13950 | 0 | 0 | 0 | 0 | 13950 | 0 | 100% | Finished | 10080 | 10080
3 | Properties of the bike | 2016-12-06 08:00 | 2016-12-09 17:00 | 4d | Engineer | 1440 | 0 | 0 | 0 | 1440 | 2016-12-13 11:00 | 2d 3h | 855 | 0 | 0 | 0 | 0 | 855 | 0 | 100% | Finished | 1440 | 1440
4 | Determine amount of bikes needed and hot spots | 2016-12-06 08:00 | 2016-12-12 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2016-12-13 11:00 | 4d 1h | 1485 | 0 | 0 | 0 | 0 | 1485 | 0 | 100% | Finished | 1800 | 1800
5 | research for possibledocking stations | 2016-12-13 08:00 | 2017-01-09 17:00 | 20d | Engineer | 7200 | 0 | 0 | 0 | 7200 | 2016-12-19 13:00 | 13d 4h | 4860 | 0 | 0 | 0 | 0 | 4860 | 0 | 100% | Finished | 7200 | 7200
6 | Resarch amount of staff needed (extra contractors) | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2017-01-06 08:00 | 5d 7h | 2115 | 0 | 0 | 0 | 0 | 2115 | 0 | 100% | Finished | 1800 | 1800
7 | feasibility study | 2017-01-17 08:00 | 2017-01-25 17:00 | 7d | Admin | 1456 | 0 | 0 | 0 | 1456 | 2017-01-13 16:00 | 5d | 1040 | 0 | 0 | 0 | 0 | 1040 | 0 | 100% | Finished | 1456 | 1456
42 | Vans | 2016-12-13 08:00 | 2017-01-26 17:00 | 33d |  |  | 45000 |  |  | 47880 |  | 29d 7h | [5 empty] | 47448 |  | 100% |  | 47880 | 47880
9 | determine type and amound of vans | 2016-12-13 08:00 | 2016-12-15 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 2016-12-19 13:00 | 3d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
10 | buy vans | 2016-12-16 08:00 | 2017-01-05 17:00 | 15d |  | 0 | 45000 | 0 | 0 | 45000 | 2016-12-22 13:00 | 14d 1h | 45000 | 0 | 0 | 0 | 0 | 45000 | 0 | 100% | Finished | 45000 | 45000
11 | adjust vans | 2017-01-06 08:00 | 2017-01-26 17:00 | 15d | Arb | 2880 | 0 | 0 | 0 | 2880 | 2017-01-11 14:00 | 12d 6h | 2448 | 0 | 0 | 0 | 0 | 2448 | 0 | 100% | Finished | 2880 | 2880
43 | Meeting | 2017-01-26 08:00 | 2017-05-03 17:00 | 70d |  |  | 2112 |  |  | 23452 |  | 63d 3h | [5 empty] | 22687 |  | 100% |  | 23452 | 23452
13 | Asking town for permission | 2017-01-26 08:00 | 2017-03-08 17:00 | 30d | Aankoop | 8160 | 0 | 0 | 0 | 8160 | 2017-01-20 16:00 | 38d 2h | 10404 | 0 | 0 | 0 | 0 | 10404 | 0 | 100% | Finished | 8160 | 8160
14 | Asking town for blue prints porwer network | 2017-03-09 08:00 | 2017-04-05 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 | 2017-03-16 09:00 | 23d 5h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | meeting with bike suppliers and contracting | 2017-03-09 08:00 | 2017-05-03 17:00 | 40d | Admin[0.50 #2] | 4160 | 0 | 0 | 0 | 4160 | 2017-03-16 09:00 | 25d 1h | 2613 | 0 | 0 | 0 | 0 | 2613 | 0 | 100% | Finished | 4160 | 4160
16 | meeting with docking stations and tower suppliers and contracting | 2017-03-09 08:00 | 2017-04-26 17:00 | 35d | Aankoop[0.50 #2] | 4760 | 0 | 0 | 0 | 4760 | 2017-03-16 09:00 | 24d 2h | 3298 | 0 | 0 | 0 | 0 | 3298 | 0 | 100% | Finished | 4760 | 4760
17 | meeting with duct suppliers & cable supliers & contracting | 2017-03-09 08:00 | 2017-03-29 17:00 | 15d | Engineer[0.50 #2];Admin[0.50 #2] | 4260 | 0 | 0 | 0 | 4260 | 2017-03-16 09:00 | 15d | 4260 | 0 | 0 | 0 | 0 | 4260 | 0 | 100% | Finished | 4260 | 4260
18 | meeting concrete suppliers | 2017-03-09 08:00 | 2017-03-22 17:00 | 10d |  | 0 | 2112 | 0 | 0 | 2112 | 2017-03-16 09:00 | 10d | 2112 | 0 | 0 | 0 | 0 | 2112 | 0 | 100% | Finished | 2112 | 2112
44 | Ict | 2017-03-09 08:00 | 2017-07-07 17:00 | 87d |  |  | 168000 |  |  | 175560 |  | 125d 6h | [5 empty] | 178920 |  | 100% |  | 175560 | 175560
20 | ICT contracter search | 2017-03-09 08:00 | 2017-04-03 17:00 | 18d | Admin[0.50 #2];Aankoop[0.50 #2];Engineer[0.50 #5] | 7560 | 0 | 0 | 0 | 7560 | 2017-03-16 09:00 | 26d | 10920 | 0 | 0 | 0 | 0 | 10920 | 0 | 100% | Finished | 7560 | 7560
21 | Developing app | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 28d 4h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
22 | developing pay system | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 82d 1h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
23 | Testing & approve app | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 2017-05-31 14:00 | 12d | 84000 | 0 | 0 | 0 | 0 | 84000 | 0 | 100% | Finished | 84000 | 84000
24 | Testing & approve pay system | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 2017-08-15 10:00 | 17d 5h | 84000 | 0 | 0 | 0 | 0 | 84000 | 0 | 100% | Finished | 84000 | 84000
45 | Repair place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d |  |  | 0 |  |  | 17664 |  | 27d 7h | [5 empty] | 21408 |  | 100% |  | 17664 | 17664
26 | construct bike repearing place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d | Arb[4.00 #4] | 17664 | 0 | 0 | 0 | 17664 | 2017-01-30 11:00 | 27d 7h | 21408 | 0 | 0 | 0 | 0 | 21408 | 0 | 100% | Finished | 17664 | 17664
46 | Delivery | 2017-03-30 08:00 | 2017-07-12 17:00 | 75d |  |  | 460000 |  |  | 460000 |  | 79d | [5 empty] | 460000 |  | 100% |  | 460000 | 460000
28 | Delivery bikes parts | 2017-05-04 08:00 | 2017-07-12 17:00 | 50d |  | 0 | 150000 | 0 | 0 | 150000 | 2017-04-20 10:00 | 68d 7h | 150000 | 0 | 0 | 0 | 0 | 150000 | 0 | 100% | Finished | 150000 | 150000
29 | delivery docking station & power tower | 2017-04-27 08:00 | 2017-06-07 17:00 | 30d |  | 0 | 250000 | 0 | 0 | 250000 | 2017-04-19 11:00 | 24d 7h | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | 100% | Finished | 250000 | 250000
30 | delivery ducts | 2017-03-30 08:00 | 2017-04-24 17:00 | 18d |  | 0 | 60000 | 0 | 0 | 60000 | 2017-04-06 09:00 | 13d 5h | 60000 | 0 | 0 | 0 | 0 | 60000 | 0 | 100% | Finished | 60000 | 60000
47 | Assembly | 2017-04-25 08:00 | 2017-08-31 17:00 | 93d |  |  | 0 |  |  | 72575.9999 |  | 108d 7h | [5 empty] | 80990.9999 |  | 100% |  | 72575.9999 | 72575.9999
32 | assembly docking station & power tower | 2017-06-08 08:00 | 2017-08-09 17:00 | 45d | Engineer[0.88 #2];Arb[2.00 #4] | 31535.9999 | 0 | 0 | 0 | 31535.9999 | 2017-05-24 10:00 | 48d 1h | 33725.9999 | 0 | 0 | 0 | 0 | 33725.9999 | 0 | 100% | Finished | 31535.9999 | 31535.9999
33 | assembly bikes & Testing | 2017-07-13 08:00 | 2017-08-31 17:00 | 36d | Arb[4.00 #4] | 27648 | 0 | 0 | 0 | 27648 | 2017-07-26 09:00 | 43d 4h | 33408 | 0 | 0 | 0 | 0 | 33408 | 0 | 100% | Finished | 27648 | 27648
34 | assembly ducts | 2017-04-25 08:00 | 2017-05-18 17:00 | 18d | Engineer;Arb[2.00 #4] | 13392 | 0 | 0 | 0 | 13392 | 2017-04-25 15:00 | 18d 5h | 13857 | 0 | 0 | 0 | 0 | 13857 | 0 | 100% | Finished | 13392 | 13392
48 | Construction total | 2017-04-06 08:00 | 2017-10-02 17:00 | 128d |  |  | 770922 |  |  | 770922 |  | 94d 3h | [5 empty] | 770922 |  | 100% |  | 770922 | 770922
36 | Construction 1 | 2017-04-06 08:00 | 2017-07-04 17:00 | 64d |  | 0 | 587706 | 0 | 0 | 587706 | 2017-04-18 15:00 | 49d 5h | 587706 | 0 | 0 | 0 | 0 | 587706 | 0 | 100% | Finished | 587706 | 587706
37 | Construction 2 | 2017-08-10 08:00 | 2017-10-02 17:00 | 38d |  | 0 | 183216 | 0 | 0 | 183216 | 2017-07-31 11:00 | 20d 6h | 183216 | 0 | 0 | 0 | 0 | 183216 | 0 | 100% | Finished | 183216 | 183216
49 | Final phase | 2017-10-03 08:00 | 2017-11-28 17:00 | 41d |  |  | 0 |  |  | 11520 |  | 34d 3h | [5 empty] | 8352 |  | 100% |  | 11520 | 11520
39 | Placing bikes | 2017-10-03 08:00 | 2017-10-23 17:00 | 15d | Arb[4.00 #4] | 11520 | 0 | 0 | 0 | 11520 | 2017-08-29 09:00 | 10d 7h | 8352 | 0 | 0 | 0 | 0 | 8352 | 0 | 100% | Finished | 11520 | 11520
40 | Final testing the total system | 2017-10-24 08:00 | 2017-11-28 17:00 | 26d |  | 0 | 0 | 0 | 0 | 0 | 2017-09-13 08:00 | 23d 4h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
50 | Project buffer | 2017-11-29 08:00 | 2018-03-20 17:00 | 80d |  | 0 | 100000 | 0 | 0 | 100000 | 2017-10-16 13:00 | 61d 4h | 100000 | 0 | 38d 5h | 0 | 0 | 100000 | 0 | 61.42% | Started | 100000 | 100000

## TP21
| TP Status Date | 2018-01-30 17:00 |  | TP Name | 30/01/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | projectKopie | 2016-11-16 08:00 | 2018-03-20 17:00 | 350d |  |  | 1546034 |  |  | 1703349.9999 |  | 315d | [5 empty] | 1715032.9999 |  | 100% |  | 1703349.9999 | 1703349.9999
41 | Onderzoek | 2016-11-16 08:00 | 2017-01-25 17:00 | 51d |  |  | 0 |  |  | 23776 |  | 47d 7h | [5 empty] | 24305 |  | 100% |  | 23776 | 23776
2 | Analysis of bikes and bikes usage in gent by students | 2016-11-16 08:00 | 2016-12-05 17:00 | 14d | Engineer[2.00 #2] | 10080 | 0 | 0 | 0 | 10080 | 2016-11-16 08:00 | 19d 3h | 13950 | 0 | 0 | 0 | 0 | 13950 | 0 | 100% | Finished | 10080 | 10080
3 | Properties of the bike | 2016-12-06 08:00 | 2016-12-09 17:00 | 4d | Engineer | 1440 | 0 | 0 | 0 | 1440 | 2016-12-13 11:00 | 2d 3h | 855 | 0 | 0 | 0 | 0 | 855 | 0 | 100% | Finished | 1440 | 1440
4 | Determine amount of bikes needed and hot spots | 2016-12-06 08:00 | 2016-12-12 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2016-12-13 11:00 | 4d 1h | 1485 | 0 | 0 | 0 | 0 | 1485 | 0 | 100% | Finished | 1800 | 1800
5 | research for possibledocking stations | 2016-12-13 08:00 | 2017-01-09 17:00 | 20d | Engineer | 7200 | 0 | 0 | 0 | 7200 | 2016-12-19 13:00 | 13d 4h | 4860 | 0 | 0 | 0 | 0 | 4860 | 0 | 100% | Finished | 7200 | 7200
6 | Resarch amount of staff needed (extra contractors) | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2017-01-06 08:00 | 5d 7h | 2115 | 0 | 0 | 0 | 0 | 2115 | 0 | 100% | Finished | 1800 | 1800
7 | feasibility study | 2017-01-17 08:00 | 2017-01-25 17:00 | 7d | Admin | 1456 | 0 | 0 | 0 | 1456 | 2017-01-13 16:00 | 5d | 1040 | 0 | 0 | 0 | 0 | 1040 | 0 | 100% | Finished | 1456 | 1456
42 | Vans | 2016-12-13 08:00 | 2017-01-26 17:00 | 33d |  |  | 45000 |  |  | 47880 |  | 29d 7h | [5 empty] | 47448 |  | 100% |  | 47880 | 47880
9 | determine type and amound of vans | 2016-12-13 08:00 | 2016-12-15 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 2016-12-19 13:00 | 3d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
10 | buy vans | 2016-12-16 08:00 | 2017-01-05 17:00 | 15d |  | 0 | 45000 | 0 | 0 | 45000 | 2016-12-22 13:00 | 14d 1h | 45000 | 0 | 0 | 0 | 0 | 45000 | 0 | 100% | Finished | 45000 | 45000
11 | adjust vans | 2017-01-06 08:00 | 2017-01-26 17:00 | 15d | Arb | 2880 | 0 | 0 | 0 | 2880 | 2017-01-11 14:00 | 12d 6h | 2448 | 0 | 0 | 0 | 0 | 2448 | 0 | 100% | Finished | 2880 | 2880
43 | Meeting | 2017-01-26 08:00 | 2017-05-03 17:00 | 70d |  |  | 2112 |  |  | 23452 |  | 63d 3h | [5 empty] | 22687 |  | 100% |  | 23452 | 23452
13 | Asking town for permission | 2017-01-26 08:00 | 2017-03-08 17:00 | 30d | Aankoop | 8160 | 0 | 0 | 0 | 8160 | 2017-01-20 16:00 | 38d 2h | 10404 | 0 | 0 | 0 | 0 | 10404 | 0 | 100% | Finished | 8160 | 8160
14 | Asking town for blue prints porwer network | 2017-03-09 08:00 | 2017-04-05 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 | 2017-03-16 09:00 | 23d 5h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | meeting with bike suppliers and contracting | 2017-03-09 08:00 | 2017-05-03 17:00 | 40d | Admin[0.50 #2] | 4160 | 0 | 0 | 0 | 4160 | 2017-03-16 09:00 | 25d 1h | 2613 | 0 | 0 | 0 | 0 | 2613 | 0 | 100% | Finished | 4160 | 4160
16 | meeting with docking stations and tower suppliers and contracting | 2017-03-09 08:00 | 2017-04-26 17:00 | 35d | Aankoop[0.50 #2] | 4760 | 0 | 0 | 0 | 4760 | 2017-03-16 09:00 | 24d 2h | 3298 | 0 | 0 | 0 | 0 | 3298 | 0 | 100% | Finished | 4760 | 4760
17 | meeting with duct suppliers & cable supliers & contracting | 2017-03-09 08:00 | 2017-03-29 17:00 | 15d | Engineer[0.50 #2];Admin[0.50 #2] | 4260 | 0 | 0 | 0 | 4260 | 2017-03-16 09:00 | 15d | 4260 | 0 | 0 | 0 | 0 | 4260 | 0 | 100% | Finished | 4260 | 4260
18 | meeting concrete suppliers | 2017-03-09 08:00 | 2017-03-22 17:00 | 10d |  | 0 | 2112 | 0 | 0 | 2112 | 2017-03-16 09:00 | 10d | 2112 | 0 | 0 | 0 | 0 | 2112 | 0 | 100% | Finished | 2112 | 2112
44 | Ict | 2017-03-09 08:00 | 2017-07-07 17:00 | 87d |  |  | 168000 |  |  | 175560 |  | 125d 6h | [5 empty] | 178920 |  | 100% |  | 175560 | 175560
20 | ICT contracter search | 2017-03-09 08:00 | 2017-04-03 17:00 | 18d | Admin[0.50 #2];Aankoop[0.50 #2];Engineer[0.50 #5] | 7560 | 0 | 0 | 0 | 7560 | 2017-03-16 09:00 | 26d | 10920 | 0 | 0 | 0 | 0 | 10920 | 0 | 100% | Finished | 7560 | 7560
21 | Developing app | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 28d 4h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
22 | developing pay system | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 82d 1h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
23 | Testing & approve app | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 2017-05-31 14:00 | 12d | 84000 | 0 | 0 | 0 | 0 | 84000 | 0 | 100% | Finished | 84000 | 84000
24 | Testing & approve pay system | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 2017-08-15 10:00 | 17d 5h | 84000 | 0 | 0 | 0 | 0 | 84000 | 0 | 100% | Finished | 84000 | 84000
45 | Repair place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d |  |  | 0 |  |  | 17664 |  | 27d 7h | [5 empty] | 21408 |  | 100% |  | 17664 | 17664
26 | construct bike repearing place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d | Arb[4.00 #4] | 17664 | 0 | 0 | 0 | 17664 | 2017-01-30 11:00 | 27d 7h | 21408 | 0 | 0 | 0 | 0 | 21408 | 0 | 100% | Finished | 17664 | 17664
46 | Delivery | 2017-03-30 08:00 | 2017-07-12 17:00 | 75d |  |  | 460000 |  |  | 460000 |  | 79d | [5 empty] | 460000 |  | 100% |  | 460000 | 460000
28 | Delivery bikes parts | 2017-05-04 08:00 | 2017-07-12 17:00 | 50d |  | 0 | 150000 | 0 | 0 | 150000 | 2017-04-20 10:00 | 68d 7h | 150000 | 0 | 0 | 0 | 0 | 150000 | 0 | 100% | Finished | 150000 | 150000
29 | delivery docking station & power tower | 2017-04-27 08:00 | 2017-06-07 17:00 | 30d |  | 0 | 250000 | 0 | 0 | 250000 | 2017-04-19 11:00 | 24d 7h | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | 100% | Finished | 250000 | 250000
30 | delivery ducts | 2017-03-30 08:00 | 2017-04-24 17:00 | 18d |  | 0 | 60000 | 0 | 0 | 60000 | 2017-04-06 09:00 | 13d 5h | 60000 | 0 | 0 | 0 | 0 | 60000 | 0 | 100% | Finished | 60000 | 60000
47 | Assembly | 2017-04-25 08:00 | 2017-08-31 17:00 | 93d |  |  | 0 |  |  | 72575.9999 |  | 108d 7h | [5 empty] | 80990.9999 |  | 100% |  | 72575.9999 | 72575.9999
32 | assembly docking station & power tower | 2017-06-08 08:00 | 2017-08-09 17:00 | 45d | Engineer[0.88 #2];Arb[2.00 #4] | 31535.9999 | 0 | 0 | 0 | 31535.9999 | 2017-05-24 10:00 | 48d 1h | 33725.9999 | 0 | 0 | 0 | 0 | 33725.9999 | 0 | 100% | Finished | 31535.9999 | 31535.9999
33 | assembly bikes & Testing | 2017-07-13 08:00 | 2017-08-31 17:00 | 36d | Arb[4.00 #4] | 27648 | 0 | 0 | 0 | 27648 | 2017-07-26 09:00 | 43d 4h | 33408 | 0 | 0 | 0 | 0 | 33408 | 0 | 100% | Finished | 27648 | 27648
34 | assembly ducts | 2017-04-25 08:00 | 2017-05-18 17:00 | 18d | Engineer;Arb[2.00 #4] | 13392 | 0 | 0 | 0 | 13392 | 2017-04-25 15:00 | 18d 5h | 13857 | 0 | 0 | 0 | 0 | 13857 | 0 | 100% | Finished | 13392 | 13392
48 | Construction total | 2017-04-06 08:00 | 2017-10-02 17:00 | 128d |  |  | 770922 |  |  | 770922 |  | 94d 3h | [5 empty] | 770922 |  | 100% |  | 770922 | 770922
36 | Construction 1 | 2017-04-06 08:00 | 2017-07-04 17:00 | 64d |  | 0 | 587706 | 0 | 0 | 587706 | 2017-04-18 15:00 | 49d 5h | 587706 | 0 | 0 | 0 | 0 | 587706 | 0 | 100% | Finished | 587706 | 587706
37 | Construction 2 | 2017-08-10 08:00 | 2017-10-02 17:00 | 38d |  | 0 | 183216 | 0 | 0 | 183216 | 2017-07-31 11:00 | 20d 6h | 183216 | 0 | 0 | 0 | 0 | 183216 | 0 | 100% | Finished | 183216 | 183216
49 | Final phase | 2017-10-03 08:00 | 2017-11-28 17:00 | 41d |  |  | 0 |  |  | 11520 |  | 34d 3h | [5 empty] | 8352 |  | 100% |  | 11520 | 11520
39 | Placing bikes | 2017-10-03 08:00 | 2017-10-23 17:00 | 15d | Arb[4.00 #4] | 11520 | 0 | 0 | 0 | 11520 | 2017-08-29 09:00 | 10d 7h | 8352 | 0 | 0 | 0 | 0 | 8352 | 0 | 100% | Finished | 11520 | 11520
40 | Final testing the total system | 2017-10-24 08:00 | 2017-11-28 17:00 | 26d |  | 0 | 0 | 0 | 0 | 0 | 2017-09-13 08:00 | 23d 4h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
50 | Project buffer | 2017-11-29 08:00 | 2018-03-20 17:00 | 80d |  | 0 | 100000 | 0 | 0 | 100000 | 2017-10-16 13:00 | 76d 4h | 100000 | 0 | 23d 5h | 0 | 0 | 100000 | 0 | 76.4% | Started | 100000 | 100000

## TP22
| TP Status Date | 2018-02-20 17:00 |  | TP Name | 20/02/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | projectKopie | 2016-11-16 08:00 | 2018-03-20 17:00 | 350d |  |  | 1546034 |  |  | 1703349.9999 |  | 330d | [5 empty] | 1715032.9999 |  | 100% |  | 1703349.9999 | 1703349.9999
41 | Onderzoek | 2016-11-16 08:00 | 2017-01-25 17:00 | 51d |  |  | 0 |  |  | 23776 |  | 47d 7h | [5 empty] | 24305 |  | 100% |  | 23776 | 23776
2 | Analysis of bikes and bikes usage in gent by students | 2016-11-16 08:00 | 2016-12-05 17:00 | 14d | Engineer[2.00 #2] | 10080 | 0 | 0 | 0 | 10080 | 2016-11-16 08:00 | 19d 3h | 13950 | 0 | 0 | 0 | 0 | 13950 | 0 | 100% | Finished | 10080 | 10080
3 | Properties of the bike | 2016-12-06 08:00 | 2016-12-09 17:00 | 4d | Engineer | 1440 | 0 | 0 | 0 | 1440 | 2016-12-13 11:00 | 2d 3h | 855 | 0 | 0 | 0 | 0 | 855 | 0 | 100% | Finished | 1440 | 1440
4 | Determine amount of bikes needed and hot spots | 2016-12-06 08:00 | 2016-12-12 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2016-12-13 11:00 | 4d 1h | 1485 | 0 | 0 | 0 | 0 | 1485 | 0 | 100% | Finished | 1800 | 1800
5 | research for possibledocking stations | 2016-12-13 08:00 | 2017-01-09 17:00 | 20d | Engineer | 7200 | 0 | 0 | 0 | 7200 | 2016-12-19 13:00 | 13d 4h | 4860 | 0 | 0 | 0 | 0 | 4860 | 0 | 100% | Finished | 7200 | 7200
6 | Resarch amount of staff needed (extra contractors) | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2017-01-06 08:00 | 5d 7h | 2115 | 0 | 0 | 0 | 0 | 2115 | 0 | 100% | Finished | 1800 | 1800
7 | feasibility study | 2017-01-17 08:00 | 2017-01-25 17:00 | 7d | Admin | 1456 | 0 | 0 | 0 | 1456 | 2017-01-13 16:00 | 5d | 1040 | 0 | 0 | 0 | 0 | 1040 | 0 | 100% | Finished | 1456 | 1456
42 | Vans | 2016-12-13 08:00 | 2017-01-26 17:00 | 33d |  |  | 45000 |  |  | 47880 |  | 29d 7h | [5 empty] | 47448 |  | 100% |  | 47880 | 47880
9 | determine type and amound of vans | 2016-12-13 08:00 | 2016-12-15 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 2016-12-19 13:00 | 3d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
10 | buy vans | 2016-12-16 08:00 | 2017-01-05 17:00 | 15d |  | 0 | 45000 | 0 | 0 | 45000 | 2016-12-22 13:00 | 14d 1h | 45000 | 0 | 0 | 0 | 0 | 45000 | 0 | 100% | Finished | 45000 | 45000
11 | adjust vans | 2017-01-06 08:00 | 2017-01-26 17:00 | 15d | Arb | 2880 | 0 | 0 | 0 | 2880 | 2017-01-11 14:00 | 12d 6h | 2448 | 0 | 0 | 0 | 0 | 2448 | 0 | 100% | Finished | 2880 | 2880
43 | Meeting | 2017-01-26 08:00 | 2017-05-03 17:00 | 70d |  |  | 2112 |  |  | 23452 |  | 63d 3h | [5 empty] | 22687 |  | 100% |  | 23452 | 23452
13 | Asking town for permission | 2017-01-26 08:00 | 2017-03-08 17:00 | 30d | Aankoop | 8160 | 0 | 0 | 0 | 8160 | 2017-01-20 16:00 | 38d 2h | 10404 | 0 | 0 | 0 | 0 | 10404 | 0 | 100% | Finished | 8160 | 8160
14 | Asking town for blue prints porwer network | 2017-03-09 08:00 | 2017-04-05 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 | 2017-03-16 09:00 | 23d 5h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | meeting with bike suppliers and contracting | 2017-03-09 08:00 | 2017-05-03 17:00 | 40d | Admin[0.50 #2] | 4160 | 0 | 0 | 0 | 4160 | 2017-03-16 09:00 | 25d 1h | 2613 | 0 | 0 | 0 | 0 | 2613 | 0 | 100% | Finished | 4160 | 4160
16 | meeting with docking stations and tower suppliers and contracting | 2017-03-09 08:00 | 2017-04-26 17:00 | 35d | Aankoop[0.50 #2] | 4760 | 0 | 0 | 0 | 4760 | 2017-03-16 09:00 | 24d 2h | 3298 | 0 | 0 | 0 | 0 | 3298 | 0 | 100% | Finished | 4760 | 4760
17 | meeting with duct suppliers & cable supliers & contracting | 2017-03-09 08:00 | 2017-03-29 17:00 | 15d | Engineer[0.50 #2];Admin[0.50 #2] | 4260 | 0 | 0 | 0 | 4260 | 2017-03-16 09:00 | 15d | 4260 | 0 | 0 | 0 | 0 | 4260 | 0 | 100% | Finished | 4260 | 4260
18 | meeting concrete suppliers | 2017-03-09 08:00 | 2017-03-22 17:00 | 10d |  | 0 | 2112 | 0 | 0 | 2112 | 2017-03-16 09:00 | 10d | 2112 | 0 | 0 | 0 | 0 | 2112 | 0 | 100% | Finished | 2112 | 2112
44 | Ict | 2017-03-09 08:00 | 2017-07-07 17:00 | 87d |  |  | 168000 |  |  | 175560 |  | 125d 6h | [5 empty] | 178920 |  | 100% |  | 175560 | 175560
20 | ICT contracter search | 2017-03-09 08:00 | 2017-04-03 17:00 | 18d | Admin[0.50 #2];Aankoop[0.50 #2];Engineer[0.50 #5] | 7560 | 0 | 0 | 0 | 7560 | 2017-03-16 09:00 | 26d | 10920 | 0 | 0 | 0 | 0 | 10920 | 0 | 100% | Finished | 7560 | 7560
21 | Developing app | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 28d 4h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
22 | developing pay system | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 82d 1h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
23 | Testing & approve app | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 2017-05-31 14:00 | 12d | 84000 | 0 | 0 | 0 | 0 | 84000 | 0 | 100% | Finished | 84000 | 84000
24 | Testing & approve pay system | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 2017-08-15 10:00 | 17d 5h | 84000 | 0 | 0 | 0 | 0 | 84000 | 0 | 100% | Finished | 84000 | 84000
45 | Repair place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d |  |  | 0 |  |  | 17664 |  | 27d 7h | [5 empty] | 21408 |  | 100% |  | 17664 | 17664
26 | construct bike repearing place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d | Arb[4.00 #4] | 17664 | 0 | 0 | 0 | 17664 | 2017-01-30 11:00 | 27d 7h | 21408 | 0 | 0 | 0 | 0 | 21408 | 0 | 100% | Finished | 17664 | 17664
46 | Delivery | 2017-03-30 08:00 | 2017-07-12 17:00 | 75d |  |  | 460000 |  |  | 460000 |  | 79d | [5 empty] | 460000 |  | 100% |  | 460000 | 460000
28 | Delivery bikes parts | 2017-05-04 08:00 | 2017-07-12 17:00 | 50d |  | 0 | 150000 | 0 | 0 | 150000 | 2017-04-20 10:00 | 68d 7h | 150000 | 0 | 0 | 0 | 0 | 150000 | 0 | 100% | Finished | 150000 | 150000
29 | delivery docking station & power tower | 2017-04-27 08:00 | 2017-06-07 17:00 | 30d |  | 0 | 250000 | 0 | 0 | 250000 | 2017-04-19 11:00 | 24d 7h | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | 100% | Finished | 250000 | 250000
30 | delivery ducts | 2017-03-30 08:00 | 2017-04-24 17:00 | 18d |  | 0 | 60000 | 0 | 0 | 60000 | 2017-04-06 09:00 | 13d 5h | 60000 | 0 | 0 | 0 | 0 | 60000 | 0 | 100% | Finished | 60000 | 60000
47 | Assembly | 2017-04-25 08:00 | 2017-08-31 17:00 | 93d |  |  | 0 |  |  | 72575.9999 |  | 108d 7h | [5 empty] | 80990.9999 |  | 100% |  | 72575.9999 | 72575.9999
32 | assembly docking station & power tower | 2017-06-08 08:00 | 2017-08-09 17:00 | 45d | Engineer[0.88 #2];Arb[2.00 #4] | 31535.9999 | 0 | 0 | 0 | 31535.9999 | 2017-05-24 10:00 | 48d 1h | 33725.9999 | 0 | 0 | 0 | 0 | 33725.9999 | 0 | 100% | Finished | 31535.9999 | 31535.9999
33 | assembly bikes & Testing | 2017-07-13 08:00 | 2017-08-31 17:00 | 36d | Arb[4.00 #4] | 27648 | 0 | 0 | 0 | 27648 | 2017-07-26 09:00 | 43d 4h | 33408 | 0 | 0 | 0 | 0 | 33408 | 0 | 100% | Finished | 27648 | 27648
34 | assembly ducts | 2017-04-25 08:00 | 2017-05-18 17:00 | 18d | Engineer;Arb[2.00 #4] | 13392 | 0 | 0 | 0 | 13392 | 2017-04-25 15:00 | 18d 5h | 13857 | 0 | 0 | 0 | 0 | 13857 | 0 | 100% | Finished | 13392 | 13392
48 | Construction total | 2017-04-06 08:00 | 2017-10-02 17:00 | 128d |  |  | 770922 |  |  | 770922 |  | 94d 3h | [5 empty] | 770922 |  | 100% |  | 770922 | 770922
36 | Construction 1 | 2017-04-06 08:00 | 2017-07-04 17:00 | 64d |  | 0 | 587706 | 0 | 0 | 587706 | 2017-04-18 15:00 | 49d 5h | 587706 | 0 | 0 | 0 | 0 | 587706 | 0 | 100% | Finished | 587706 | 587706
37 | Construction 2 | 2017-08-10 08:00 | 2017-10-02 17:00 | 38d |  | 0 | 183216 | 0 | 0 | 183216 | 2017-07-31 11:00 | 20d 6h | 183216 | 0 | 0 | 0 | 0 | 183216 | 0 | 100% | Finished | 183216 | 183216
49 | Final phase | 2017-10-03 08:00 | 2017-11-28 17:00 | 41d |  |  | 0 |  |  | 11520 |  | 34d 3h | [5 empty] | 8352 |  | 100% |  | 11520 | 11520
39 | Placing bikes | 2017-10-03 08:00 | 2017-10-23 17:00 | 15d | Arb[4.00 #4] | 11520 | 0 | 0 | 0 | 11520 | 2017-08-29 09:00 | 10d 7h | 8352 | 0 | 0 | 0 | 0 | 8352 | 0 | 100% | Finished | 11520 | 11520
40 | Final testing the total system | 2017-10-24 08:00 | 2017-11-28 17:00 | 26d |  | 0 | 0 | 0 | 0 | 0 | 2017-09-13 08:00 | 23d 4h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
50 | Project buffer | 2017-11-29 08:00 | 2018-03-20 17:00 | 80d |  | 0 | 100000 | 0 | 0 | 100000 | 2017-10-16 13:00 | 91d 4h | 100000 | 0 | 8d 5h | 0 | 0 | 100000 | 0 | 91.39% | Started | 100000 | 100000

## TP23
| TP Status Date | 2018-03-13 17:00 |  | TP Name | 13/03/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | projectKopie | 2016-11-16 08:00 | 2018-03-20 17:00 | 350d |  |  | 1546034 |  |  | 1703349.9999 |  | 338d 5h | [5 empty] | 1715032.9999 |  | 100% |  | 1703349.9999 | 1703349.9999
41 | Onderzoek | 2016-11-16 08:00 | 2017-01-25 17:00 | 51d |  |  | 0 |  |  | 23776 |  | 47d 7h | [5 empty] | 24305 |  | 100% |  | 23776 | 23776
2 | Analysis of bikes and bikes usage in gent by students | 2016-11-16 08:00 | 2016-12-05 17:00 | 14d | Engineer[2.00 #2] | 10080 | 0 | 0 | 0 | 10080 | 2016-11-16 08:00 | 19d 3h | 13950 | 0 | 0 | 0 | 0 | 13950 | 0 | 100% | Finished | 10080 | 10080
3 | Properties of the bike | 2016-12-06 08:00 | 2016-12-09 17:00 | 4d | Engineer | 1440 | 0 | 0 | 0 | 1440 | 2016-12-13 11:00 | 2d 3h | 855 | 0 | 0 | 0 | 0 | 855 | 0 | 100% | Finished | 1440 | 1440
4 | Determine amount of bikes needed and hot spots | 2016-12-06 08:00 | 2016-12-12 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2016-12-13 11:00 | 4d 1h | 1485 | 0 | 0 | 0 | 0 | 1485 | 0 | 100% | Finished | 1800 | 1800
5 | research for possibledocking stations | 2016-12-13 08:00 | 2017-01-09 17:00 | 20d | Engineer | 7200 | 0 | 0 | 0 | 7200 | 2016-12-19 13:00 | 13d 4h | 4860 | 0 | 0 | 0 | 0 | 4860 | 0 | 100% | Finished | 7200 | 7200
6 | Resarch amount of staff needed (extra contractors) | 2017-01-10 08:00 | 2017-01-16 17:00 | 5d | Engineer | 1800 | 0 | 0 | 0 | 1800 | 2017-01-06 08:00 | 5d 7h | 2115 | 0 | 0 | 0 | 0 | 2115 | 0 | 100% | Finished | 1800 | 1800
7 | feasibility study | 2017-01-17 08:00 | 2017-01-25 17:00 | 7d | Admin | 1456 | 0 | 0 | 0 | 1456 | 2017-01-13 16:00 | 5d | 1040 | 0 | 0 | 0 | 0 | 1040 | 0 | 100% | Finished | 1456 | 1456
42 | Vans | 2016-12-13 08:00 | 2017-01-26 17:00 | 33d |  |  | 45000 |  |  | 47880 |  | 29d 7h | [5 empty] | 47448 |  | 100% |  | 47880 | 47880
9 | determine type and amound of vans | 2016-12-13 08:00 | 2016-12-15 17:00 | 3d |  | 0 | 0 | 0 | 0 | 0 | 2016-12-19 13:00 | 3d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
10 | buy vans | 2016-12-16 08:00 | 2017-01-05 17:00 | 15d |  | 0 | 45000 | 0 | 0 | 45000 | 2016-12-22 13:00 | 14d 1h | 45000 | 0 | 0 | 0 | 0 | 45000 | 0 | 100% | Finished | 45000 | 45000
11 | adjust vans | 2017-01-06 08:00 | 2017-01-26 17:00 | 15d | Arb | 2880 | 0 | 0 | 0 | 2880 | 2017-01-11 14:00 | 12d 6h | 2448 | 0 | 0 | 0 | 0 | 2448 | 0 | 100% | Finished | 2880 | 2880
43 | Meeting | 2017-01-26 08:00 | 2017-05-03 17:00 | 70d |  |  | 2112 |  |  | 23452 |  | 63d 3h | [5 empty] | 22687 |  | 100% |  | 23452 | 23452
13 | Asking town for permission | 2017-01-26 08:00 | 2017-03-08 17:00 | 30d | Aankoop | 8160 | 0 | 0 | 0 | 8160 | 2017-01-20 16:00 | 38d 2h | 10404 | 0 | 0 | 0 | 0 | 10404 | 0 | 100% | Finished | 8160 | 8160
14 | Asking town for blue prints porwer network | 2017-03-09 08:00 | 2017-04-05 17:00 | 20d |  | 0 | 0 | 0 | 0 | 0 | 2017-03-16 09:00 | 23d 5h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | meeting with bike suppliers and contracting | 2017-03-09 08:00 | 2017-05-03 17:00 | 40d | Admin[0.50 #2] | 4160 | 0 | 0 | 0 | 4160 | 2017-03-16 09:00 | 25d 1h | 2613 | 0 | 0 | 0 | 0 | 2613 | 0 | 100% | Finished | 4160 | 4160
16 | meeting with docking stations and tower suppliers and contracting | 2017-03-09 08:00 | 2017-04-26 17:00 | 35d | Aankoop[0.50 #2] | 4760 | 0 | 0 | 0 | 4760 | 2017-03-16 09:00 | 24d 2h | 3298 | 0 | 0 | 0 | 0 | 3298 | 0 | 100% | Finished | 4760 | 4760
17 | meeting with duct suppliers & cable supliers & contracting | 2017-03-09 08:00 | 2017-03-29 17:00 | 15d | Engineer[0.50 #2];Admin[0.50 #2] | 4260 | 0 | 0 | 0 | 4260 | 2017-03-16 09:00 | 15d | 4260 | 0 | 0 | 0 | 0 | 4260 | 0 | 100% | Finished | 4260 | 4260
18 | meeting concrete suppliers | 2017-03-09 08:00 | 2017-03-22 17:00 | 10d |  | 0 | 2112 | 0 | 0 | 2112 | 2017-03-16 09:00 | 10d | 2112 | 0 | 0 | 0 | 0 | 2112 | 0 | 100% | Finished | 2112 | 2112
44 | Ict | 2017-03-09 08:00 | 2017-07-07 17:00 | 87d |  |  | 168000 |  |  | 175560 |  | 125d 6h | [5 empty] | 178920 |  | 100% |  | 175560 | 175560
20 | ICT contracter search | 2017-03-09 08:00 | 2017-04-03 17:00 | 18d | Admin[0.50 #2];Aankoop[0.50 #2];Engineer[0.50 #5] | 7560 | 0 | 0 | 0 | 7560 | 2017-03-16 09:00 | 26d | 10920 | 0 | 0 | 0 | 0 | 10920 | 0 | 100% | Finished | 7560 | 7560
21 | Developing app | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 28d 4h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
22 | developing pay system | 2017-04-04 08:00 | 2017-06-21 17:00 | 57d |  | 0 | 0 | 0 | 0 | 0 | 2017-04-21 09:00 | 82d 1h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
23 | Testing & approve app | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 2017-05-31 14:00 | 12d | 84000 | 0 | 0 | 0 | 0 | 84000 | 0 | 100% | Finished | 84000 | 84000
24 | Testing & approve pay system | 2017-06-22 08:00 | 2017-07-07 17:00 | 12d |  | 0 | 84000 | 0 | 0 | 84000 | 2017-08-15 10:00 | 17d 5h | 84000 | 0 | 0 | 0 | 0 | 84000 | 0 | 100% | Finished | 84000 | 84000
45 | Repair place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d |  |  | 0 |  |  | 17664 |  | 27d 7h | [5 empty] | 21408 |  | 100% |  | 17664 | 17664
26 | construct bike repearing place | 2017-01-27 08:00 | 2017-02-28 17:00 | 23d | Arb[4.00 #4] | 17664 | 0 | 0 | 0 | 17664 | 2017-01-30 11:00 | 27d 7h | 21408 | 0 | 0 | 0 | 0 | 21408 | 0 | 100% | Finished | 17664 | 17664
46 | Delivery | 2017-03-30 08:00 | 2017-07-12 17:00 | 75d |  |  | 460000 |  |  | 460000 |  | 79d | [5 empty] | 460000 |  | 100% |  | 460000 | 460000
28 | Delivery bikes parts | 2017-05-04 08:00 | 2017-07-12 17:00 | 50d |  | 0 | 150000 | 0 | 0 | 150000 | 2017-04-20 10:00 | 68d 7h | 150000 | 0 | 0 | 0 | 0 | 150000 | 0 | 100% | Finished | 150000 | 150000
29 | delivery docking station & power tower | 2017-04-27 08:00 | 2017-06-07 17:00 | 30d |  | 0 | 250000 | 0 | 0 | 250000 | 2017-04-19 11:00 | 24d 7h | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | 100% | Finished | 250000 | 250000
30 | delivery ducts | 2017-03-30 08:00 | 2017-04-24 17:00 | 18d |  | 0 | 60000 | 0 | 0 | 60000 | 2017-04-06 09:00 | 13d 5h | 60000 | 0 | 0 | 0 | 0 | 60000 | 0 | 100% | Finished | 60000 | 60000
47 | Assembly | 2017-04-25 08:00 | 2017-08-31 17:00 | 93d |  |  | 0 |  |  | 72575.9999 |  | 108d 7h | [5 empty] | 80990.9999 |  | 100% |  | 72575.9999 | 72575.9999
32 | assembly docking station & power tower | 2017-06-08 08:00 | 2017-08-09 17:00 | 45d | Engineer[0.88 #2];Arb[2.00 #4] | 31535.9999 | 0 | 0 | 0 | 31535.9999 | 2017-05-24 10:00 | 48d 1h | 33725.9999 | 0 | 0 | 0 | 0 | 33725.9999 | 0 | 100% | Finished | 31535.9999 | 31535.9999
33 | assembly bikes & Testing | 2017-07-13 08:00 | 2017-08-31 17:00 | 36d | Arb[4.00 #4] | 27648 | 0 | 0 | 0 | 27648 | 2017-07-26 09:00 | 43d 4h | 33408 | 0 | 0 | 0 | 0 | 33408 | 0 | 100% | Finished | 27648 | 27648
34 | assembly ducts | 2017-04-25 08:00 | 2017-05-18 17:00 | 18d | Engineer;Arb[2.00 #4] | 13392 | 0 | 0 | 0 | 13392 | 2017-04-25 15:00 | 18d 5h | 13857 | 0 | 0 | 0 | 0 | 13857 | 0 | 100% | Finished | 13392 | 13392
48 | Construction total | 2017-04-06 08:00 | 2017-10-02 17:00 | 128d |  |  | 770922 |  |  | 770922 |  | 94d 3h | [5 empty] | 770922 |  | 100% |  | 770922 | 770922
36 | Construction 1 | 2017-04-06 08:00 | 2017-07-04 17:00 | 64d |  | 0 | 587706 | 0 | 0 | 587706 | 2017-04-18 15:00 | 49d 5h | 587706 | 0 | 0 | 0 | 0 | 587706 | 0 | 100% | Finished | 587706 | 587706
37 | Construction 2 | 2017-08-10 08:00 | 2017-10-02 17:00 | 38d |  | 0 | 183216 | 0 | 0 | 183216 | 2017-07-31 11:00 | 20d 6h | 183216 | 0 | 0 | 0 | 0 | 183216 | 0 | 100% | Finished | 183216 | 183216
49 | Final phase | 2017-10-03 08:00 | 2017-11-28 17:00 | 41d |  |  | 0 |  |  | 11520 |  | 34d 3h | [5 empty] | 8352 |  | 100% |  | 11520 | 11520
39 | Placing bikes | 2017-10-03 08:00 | 2017-10-23 17:00 | 15d | Arb[4.00 #4] | 11520 | 0 | 0 | 0 | 11520 | 2017-08-29 09:00 | 10d 7h | 8352 | 0 | 0 | 0 | 0 | 8352 | 0 | 100% | Finished | 11520 | 11520
40 | Final testing the total system | 2017-10-24 08:00 | 2017-11-28 17:00 | 26d |  | 0 | 0 | 0 | 0 | 0 | 2017-09-13 08:00 | 23d 4h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
50 | Project buffer | 2017-11-29 08:00 | 2018-03-20 17:00 | 80d |  | 0 | 100000 | 0 | 0 | 100000 | 2017-10-16 13:00 | 100d 1h | 100000 | 0 | 0 | 0 | 0 | 100000 | 0 | 100% | Finished | 100000 | 100000

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI threshold | SPI(t) threshold
6/12/2016 17:00 | 2016-11-16 08:00 | 2016-12-06 17:00 | 10800 | 7803.8707 | 10800 | 2016-11-30 15:00 | -2996.1293 | 72.26% | -2996.1293 | 72.26% | -4d 2h | 71.67% | 100% | 2018-03-21 14:00 | 2018-09-25 11:00 | 2019-06-12 11:00 | 2018-03-27 09:00 | 2018-09-25 11:00 | 2019-06-04 14:00 | 2018-03-27 10:00 | 2018-10-01 11:00 | 2019-06-12 09:00 | 1706346.1292 | 2357314.8023 | 2357314.8023 | 2376678.3198 | 3258208.9749 | 3285006.7009 | 2357314.8023 | 2361162.1073 | 0.71667 | 0.72258 | 0.72258 | 1 | -4.25 | 1 | 1
27/12/2016 17:00 | 2016-12-06 17:00 | 2016-12-27 17:00 | 62280 | 61786.6667 | 63630 | 2016-12-26 14:00 | -493.3333 | 99.21% | -1843.3333 | 97.1% | -1d 3h | 95.42% | 100% | 2018-03-21 09:00 | 2018-03-23 15:00 | 2018-04-09 11:00 | 2018-03-21 10:00 | 2018-03-23 15:00 | 2018-04-06 11:00 | 2018-03-22 11:00 | 2018-04-12 15:00 | 2018-04-26 16:00 | 1705193.3332 | 1754167.4637 | 1718300.3322 | 1784045.7204 | 1767665.4948 | 1835372.32 | 1746870.1797 | 1760059.8029 | 0.95417 | 0.97103 | 0.99208 | 1 | -1.375 | 1 | 1
17/01/2017 17:00 | 2016-12-27 17:00 | 2017-01-17 17:00 | 69064 | 68927.0353 | 69547 | 2017-01-17 14:00 | -136.9647 | 99.8% | -619.9647 | 99.11% | -3h | 99.17% | 99.31% | 2018-03-20 17:00 | 2018-03-21 15:00 | 2018-03-26 16:00 | 2018-03-21 09:00 | 2018-03-21 15:00 | 2018-03-26 12:00 | 2018-03-21 11:00 | 2018-03-23 17:00 | 2018-03-28 15:00 | 1703969.9646 | 1718670.7924 | 1707217.7205 | 1717704.6113 | 1721947.7603 | 1732528.9756 | 1716367.3804 | 1718477.4656 | 0.99167 | 0.99109 | 0.99802 | 0.9931 | -3 | 1 | 1
7/02/2017 17:00 | 2017-01-17 17:00 | 2017-02-07 17:00 | 80248 | 78440.8371 | 80139 | 2017-02-06 10:00 | -1807.1629 | 97.75% | -1698.1629 | 97.88% | -1d 6h | 97.08% | 99.23% | 2018-03-21 11:00 | 2018-04-02 09:00 | 2018-04-11 16:00 | 2018-03-22 11:00 | 2018-04-02 09:00 | 2018-04-10 12:00 | 2018-03-22 15:00 | 2018-04-04 12:00 | 2018-04-12 17:00 | 1705048.1628 | 1740225.7642 | 1742483.7093 | 1753865.1763 | 1778471.7515 | 1790099.6155 | 1740676.8624 | 1742935.8337 | 0.97083 | 0.97881 | 0.97748 | 0.99233 | -1.75 | 1 | 1
28/02/2017 17:00 | 2017-02-07 17:00 | 2017-02-28 17:00 | 95848 | 91146.1281 | 95739 | 2017-02-22 11:00 | -4701.8719 | 95.09% | -4592.8719 | 95.2% | -4d 5h | 93.83% | 99.55% | 2018-03-21 17:00 | 2018-04-13 17:00 | 2018-05-10 14:00 | 2018-03-26 14:00 | 2018-04-13 17:00 | 2018-05-04 16:00 | 2018-03-27 14:00 | 2018-04-20 17:00 | 2018-05-11 17:00 | 1707942.8719 | 1789182.1532 | 1791110.1585 | 1813895.8794 | 1876540.2564 | 1900474.1544 | 1789567.4034 | 1794067.8577 | 0.93833 | 0.95203 | 0.95094 | 0.99551 | -4.625 | 1 | 1
21/03/2017 17:00 | 2017-02-28 17:00 | 2017-03-21 17:00 | 108088 | 103221.4413 | 109335 | 2017-03-14 15:00 | -4866.5587 | 95.5% | -6113.5587 | 94.41% | -5d 2h | 94.17% | 99.57% | 2018-03-21 17:00 | 2018-04-12 12:00 | 2018-05-14 10:00 | 2018-03-26 17:00 | 2018-04-12 12:00 | 2018-05-04 16:00 | 2018-03-28 10:00 | 2018-04-19 14:00 | 2018-05-14 11:00 | 1709463.5586 | 1804235.3399 | 1784904.4695 | 1808586.5667 | 1884144.4352 | 1909229.1663 | 1800333.5651 | 1805103.8016 | 0.94167 | 0.94408 | 0.95498 | 0.99565 | -5.25 | 1 | 1
11/04/2017 17:00 | 2017-03-21 17:00 | 2017-04-11 17:00 | 764878 | 176170.3921 | 182394.5 | 2017-04-05 15:00 | -588707.6079 | 23.03% | -6224.1079 | 96.59% | -4d 2h | 95.95% | 98.82% | 2018-09-05 17:00 | 2022-09-13 14:00 | 2022-11-28 10:00 | 2018-07-11 16:00 | 2022-09-13 14:00 | 2022-11-22 14:00 | 2018-03-27 10:00 | 2018-04-10 15:00 | 2018-04-23 17:00 | 1709574.1079 | 1763529.4327 | 6812941.6111 | 1773996.0764 | 7047199.1414 | 1830227.4324 | 2047616.9009 | 1765611.7341 | 0.95952 | 0.96588 | 0.23032 | 0.98824 | -4.25 | 1 | 1
2/05/2017 17:00 | 2017-04-11 17:00 | 2017-05-02 17:00 | 1022398 | 1171812.9261 | 1178380 | 2017-05-04 09:00 | 149414.9261 | 114.6% | -6567.0739 | 99.44% | 1d 1h | 100.9% | 99.87% | 2018-02-06 10:00 | 2018-01-17 11:00 | 2018-01-19 09:00 | 2018-02-23 12:00 | 2018-01-17 11:00 | 2018-01-18 11:00 | 2018-03-19 16:00 | 2018-03-15 15:00 | 2018-03-16 17:00 | 1709917.0739 | 1712895.9139 | 1642142.1152 | 1704980.197 | 1644741.1308 | 1707931.3698 | 1697069.1667 | 1711293.7897 | 1.0094 | 0.99443 | 1.1461 | 0.9987 | 1.125 | 1 | 1
23/05/2017 17:00 | 2017-05-02 17:00 | 2017-05-23 17:00 | 1181430 | 1181430 | 1188331 | 2017-05-23 17:00 | 0 | 100% | -6901 | 99.42% | 0 | 100% | 100% | 2018-03-20 17:00 | 2018-03-20 17:00 | 2018-03-22 17:00 | 2018-03-20 17:00 | 2018-03-20 17:00 | 2018-03-22 10:00 | 2018-03-20 17:00 | 2018-03-20 17:00 | 2018-03-22 10:00 | 1710250.9999 | 1713299.6528 | 1710250.9999 | 1710250.9999 | 1713299.6528 | 1713299.6528 | 1712687.0763 | 1712687.0763 | 1 | 0.99419 | 1 | 1 | 0 | 1 | 1
13/06/2017 17:00 | 2017-05-23 17:00 | 2017-06-13 17:00 | 1184233.2 | 1275095.5796 | 1282667.8 | 2017-06-22 09:00 | 90862.3797 | 107.7% | -7572.2203 | 99.41% | 6d 1h | 104.1% | 93.81% | 2018-02-22 11:00 | 2018-02-13 17:00 | 2018-02-15 17:00 | 2018-03-05 12:00 | 2018-02-13 17:00 | 2018-02-15 09:00 | 2018-03-12 16:00 | 2018-03-01 10:00 | 2018-03-02 11:00 | 1710922.2203 | 1713465.431 | 1680405.1231 | 1694121.2062 | 1682767.1065 | 1696564.6433 | 1706420.8785 | 1709452.4285 | 1.0408 | 0.9941 | 1.0767 | 0.93808 | 6.125 | 1 | 1
4/07/2017 17:00 | 2017-06-13 17:00 | 2017-07-04 17:00 | 1362745.2 | 1284924.982 | 1293179.7999 | 2017-06-21 17:00 | -77820.218 | 94.29% | -8254.818 | 99.36% | -9d | 94.55% | 100% | 2018-04-11 17:00 | 2018-04-19 10:00 | 2018-04-23 14:00 | 2018-04-03 11:00 | 2018-04-19 10:00 | 2018-04-20 12:00 | 2018-04-02 17:00 | 2018-04-18 10:00 | 2018-04-19 12:00 | 1711604.8179 | 1714292.93 | 1736946.3176 | 1735744.7228 | 1739797.2326 | 1738587.9182 | 1718636.6734 | 1718415.2918 | 0.94545 | 0.99362 | 0.94289 | 1 | -9 | 1 | 1
25/07/2017 17:00 | 2017-07-04 17:00 | 2017-07-25 17:00 | 1380169.1999 | 1294754.3843 | 1303691.7999 | 2017-06-21 17:00 | -85414.8156 | 93.81% | -8937.4156 | 99.31% | -24d | 86.67% | 100% | 2018-04-13 12:00 | 2018-04-23 09:00 | 2018-04-25 14:00 | 2018-04-05 09:00 | 2018-04-23 09:00 | 2018-04-24 11:00 | 2018-04-23 17:00 | 2018-06-04 16:00 | 2018-06-06 11:00 | 1712287.4155 | 1715107.8646 | 1739242.4269 | 1775148.2795 | 1742248.9408 | 1778402.6438 | 1719718.4056 | 1725860.5809 | 0.86667 | 0.99314 | 0.93811 | 1 | -24 | 1 | 1
15/08/2017 17:00 | 2017-07-25 17:00 | 2017-08-15 17:00 | 1582613.9999 | 1573636.3447 | 1584696.9999 | 2017-08-09 17:00 | -8977.6552 | 99.43% | -11060.6552 | 99.3% | -4d | 97.95% | 99.58% | 2018-03-22 16:00 | 2018-03-22 17:00 | 2018-03-27 12:00 | 2018-03-22 09:00 | 2018-03-22 17:00 | 2018-03-26 09:00 | 2018-03-26 17:00 | 2018-03-30 11:00 | 2018-04-02 12:00 | 1714410.6551 | 1715322.3766 | 1715150.6764 | 1717127.1714 | 1716067.5993 | 1718057.9865 | 1715288.0004 | 1715679.3894 | 0.97949 | 0.99302 | 0.99433 | 0.99577 | -4 | 1 | 1
5/09/2017 17:00 | 2017-08-15 17:00 | 2017-09-05 17:00 | 1591829.9999 | 1589393.5851 | 1600728.9999 | 2017-08-28 15:00 | -2436.4148 | 99.85% | -11335.4148 | 99.29% | -6d 2h | 97.02% | 99.61% | 2018-03-21 12:00 | 2018-03-21 12:00 | 2018-03-23 17:00 | 2018-03-21 11:00 | 2018-03-21 12:00 | 2018-03-22 12:00 | 2018-03-29 10:00 | 2018-04-04 15:00 | 2018-04-05 15:00 | 1714685.4147 | 1715498.1418 | 1714860.1009 | 1718181.0102 | 1715674.0738 | 1719018.6676 | 1715369.9635 | 1716024.8652 | 0.97024 | 0.99292 | 0.99847 | 0.99612 | -6.25 | 1 | 1
26/09/2017 17:00 | 2017-09-05 17:00 | 2017-09-26 17:00 | 1591829.9999 | 1603349.9999 | 1615032.9999 | 2017-10-23 17:00 | 11520 | 100.7% | -11683 | 99.28% | 19d | 108.4% | 100% | 2018-03-16 14:00 | 2018-03-16 12:00 | 2018-03-20 17:00 | 2018-03-19 11:00 | 2018-03-16 12:00 | 2018-03-19 11:00 | 2018-02-21 17:00 | 2018-02-09 15:00 | 2018-02-12 12:00 | 1715032.9999 | 1715761.6618 | 1714314.5043 | 1707246.1147 | 1715037.9307 | 1707918.0365 | 1715468.865 | 1713935.0132 | 1.0844 | 0.99277 | 1.0072 | 1 | 19 | 1 | 1
17/10/2017 17:00 | 2017-09-26 17:00 | 2017-10-17 17:00 | 1600277.9999 | 1703349.9999 | 1715032.9999 | 2017-11-29 09:00 | 103072 | 106.4% | -11683 | 99.32% | 30d 1h | 112.6% | 100% | 2018-02-19 16:00 | 2018-02-19 16:00 | 2018-02-22 09:00 | 2018-02-27 12:00 | 2018-02-19 16:00 | 2018-02-20 11:00 | 2018-02-06 16:00 | 2018-01-24 17:00 | 2018-01-25 12:00 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1.1255 | 0.99319 | 1.0644 | 1 | 30.125 | 1 | 1
7/11/2017 17:00 | 2017-10-17 17:00 | 2017-11-07 17:00 | 1603349.9999 | 1703349.9999 | 1715032.9999 | 2017-11-29 09:00 | 100000 | 106.2% | -11683 | 99.32% | 15d 1h | 105.9% | 100% | 2018-02-20 12:00 | 2018-02-20 12:00 | 2018-02-22 15:00 | 2018-02-27 09:00 | 2018-02-20 12:00 | 2018-02-20 17:00 | 2018-02-27 16:00 | 2018-02-21 11:00 | 2018-02-21 16:00 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1.0593 | 0.99319 | 1.0624 | 1 | 15.125 | 1 | 1
28/11/2017 17:00 | 2017-11-07 17:00 | 2017-11-28 17:00 | 1603349.9999 | 1703349.9999 | 1715032.9999 | 2017-11-29 09:00 | 100000 | 106.2% | -11683 | 99.32% | 1h | 100% | 100% | 2018-02-20 12:00 | 2018-02-20 12:00 | 2018-02-22 15:00 | 2018-02-26 09:00 | 2018-02-20 12:00 | 2018-02-20 16:00 | 2018-03-20 16:00 | 2018-03-20 16:00 | 2018-03-21 11:00 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1.0005 | 0.99319 | 1.0624 | 1 | 0.125 | 1 | 1
19/12/2017 17:00 | 2017-11-28 17:00 | 2017-12-19 17:00 | 1703349.9999 | 1703349.9999 | 1715032.9999 | 2017-12-19 17:00 | 0 | 100% | -11683 | 99.32% | 0 | 100% | 100% | 2018-03-20 17:00 | 2018-03-20 17:00 | 2018-03-23 11:00 | 2018-03-20 17:00 | 2018-03-20 17:00 | 2018-03-21 12:00 | 2018-03-20 17:00 | 2018-03-20 17:00 | 2018-03-21 12:00 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1 | 0.99319 | 1 | 1 | 0 | 1 | 1
9/01/2018 17:00 | 2017-12-19 17:00 | 2018-01-09 17:00 | 1703349.9999 | 1703349.9999 | 1715032.9999 | 2018-01-09 17:00 | 0 | 100% | -11683 | 99.32% | 0 | 100% | 100% | 2018-03-20 17:00 | 2018-03-20 17:00 | 2018-03-23 11:00 | 2018-03-20 17:00 | 2018-03-20 17:00 | 2018-03-21 11:00 | 2018-03-20 17:00 | 2018-03-20 17:00 | 2018-03-21 11:00 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1 | 0.99319 | 1 | 1 | 0 | 1 | 1
30/01/2018 17:00 | 2018-01-09 17:00 | 2018-01-30 17:00 | 1703349.9999 | 1703349.9999 | 1715032.9999 | 2018-01-30 17:00 | 0 | 100% | -11683 | 99.32% | 0 | 100% | 100% | 2018-03-20 17:00 | 2018-03-20 17:00 | 2018-03-23 11:00 | 2018-03-20 17:00 | 2018-03-20 17:00 | 2018-03-21 10:00 | 2018-03-20 17:00 | 2018-03-20 17:00 | 2018-03-21 10:00 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1 | 0.99319 | 1 | 1 | 0 | 1 | 1
20/02/2018 17:00 | 2018-01-30 17:00 | 2018-02-20 17:00 | 1703349.9999 | 1703349.9999 | 1715032.9999 | 2018-02-20 17:00 | 0 | 100% | -11683 | 99.32% | 0 | 100% | 100% | 2018-03-20 17:00 | 2018-03-20 17:00 | 2018-03-23 11:00 | 2018-03-20 17:00 | 2018-03-20 17:00 | 2018-03-21 09:00 | 2018-03-20 17:00 | 2018-03-20 17:00 | 2018-03-21 09:00 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1 | 0.99319 | 1 | 1 | 0 | 1 | 1
13/03/2018 17:00 | 2018-02-20 17:00 | 2018-03-13 17:00 | 1703349.9999 | 1703349.9999 | 1715032.9999 | 2018-03-13 17:00 | 0 | 100% | -11683 | 99.32% | 0 | 100% | 100% | 2018-03-20 17:00 | 2018-03-20 17:00 | 2018-03-23 11:00 | 2018-03-20 17:00 | 2018-03-20 17:00 | 2018-03-20 17:00 | 2018-03-20 17:00 | 2018-03-20 17:00 | 2018-03-20 17:00 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1715032.9999 | 1 | 0.99319 | 1 | 1 | 0 | 1 | 1

## SV(t)
S