## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | Job Fair in Ghent | 1 |  |  | 2018-04-02 08:00 | 2019-01-18 17:00 | 210d |  |  | 0 |  |  | 34720
1 | Job Fair Date Planning | 1.1 |  | FS2;FS4;FS6 | 2018-04-02 08:00 | 2018-04-02 17:00 | 1d | Maria Cunha Patricija Oreski | 80 | 0 | 0 | 0 | 80
2 | Estimate the Budget | 1.2 | 1FS | FS3;FS5 | 2018-04-03 08:00 | 2018-04-16 17:00 | 10d | Maria Cunha Patricija Oreski | 800 | 0 | 0 | 0 | 800
3 | Sponsorship Deals to be Prepared & Offered | 1.3 | 2FS | FS7;FS12 | 2018-04-17 08:00 | 2018-05-07 17:00 | 15d | Maria Cunha Patricija Oreski | 1200 | 0 | 0 | 0 | 1200
4 | Preparing the Company List to be Pursued | 1.4 | 1FS |  | 2018-04-03 08:00 | 2018-04-16 17:00 | 10d | Madalena Malcata | 600 | 0 | 0 | 0 | 600
5 | Job Fair Program Plan | 1.5 | 2FS |  | 2018-04-17 08:00 | 2018-04-23 17:00 | 5d | Maria Cunha Patricija Oreski | 400 | 0 | 0 | 0 | 400
6 | Authorisation & Decision Mechanism to be decided | 1.6 | 1FS |  | 2018-04-03 08:00 | 2018-04-03 17:00 | 1d | Maria Cunha Patricija Oreski | 80 | 0 | 0 | 0 | 80
7 | Make the contracts with sponsors | 1.7 | 3FS | FS8;FS24;FS19 | 2018-05-08 08:00 | 2018-05-21 17:00 | 10d | Maria Cunha Patricija Oreski | 800 | 0 | 0 | 0 | 800
8 | Project Income/Expense Management | 1.8 | 7FS | FS14 | 2018-09-18 08:00 | 2019-01-11 17:00 | 84d | Francisco Agostinho | 6720 | 0 | 0 | 0 | 6720
12 | Invoice Management | 1.9 | 3FS | FS14 | 2018-05-08 08:00 | 2018-09-17 17:00 | 95d | Francisco Agostinho | 7600 | 0 | 0 | 0 | 7600
14 | Prepare the Final Financial Statement | 1.10 | 8FS;12FS |  | 2019-01-14 08:00 | 2019-01-18 17:00 | 5d | Francisco Agostinho | 400 | 0 | 0 | 0 | 400
15 | Booth Advertisement for companies | 1.11 | 19FS | FS21 | 2018-09-04 08:00 | 2018-09-17 17:00 | 10d | Madalena Malcata | 600 | 0 | 0 | 0 | 600
16 | Prepare Advertisement Brochures | 1.12 | 19FS |  | 2018-07-03 08:00 | 2018-07-23 17:00 | 15d | Madalena Malcata | 900 | 0 | 0 | 0 | 900
17 | Prepare Billboard Advertisement | 1.13 | 19FS |  | 2018-07-24 08:00 | 2018-09-03 17:00 | 30d | Madalena Malcata | 1800 | 0 | 0 | 0 | 1800
18 | Prepare Social Media Advertisements | 1.14 | 19FS |  | 2018-09-18 08:00 | 2018-10-01 17:00 | 10d | Madalena Malcata | 600 | 0 | 0 | 0 | 600
19 | Prepare the website | 1.15 | 7FS | FS20;FS18;FS17;FS16;FS15 | 2018-05-22 08:00 | 2018-06-25 17:00 | 25d | Pieter Claeys | 3000 | 0 | 0 | 0 | 3000
20 | Prepare the Registration System | 1.16 | 19FS | FS26 | 2018-07-03 08:00 | 2018-08-01 17:00 | 22d | Pieter Claeys | 2640 | 0 | 0 | 0 | 2640
21 | Prepare the Digital Advertisements | 1.17 | 15FS | FS22 | 2018-09-18 08:00 | 2018-10-08 17:00 | 15d | Kevin Vendelman | 1800 | 0 | 0 | 0 | 1800
22 | Contacting Companies | 1.18 | 21FS | FS23 | 2018-10-09 08:00 | 2018-10-22 17:00 | 10d | Madalena Malcata | 600 | 0 | 0 | 0 | 600
23 | Renting the booths to companies | 1.19 | 22FS | FS28 | 2018-10-23 08:00 | 2018-11-12 17:00 | 15d | Madalena Malcata | 900 | 0 | 0 | 0 | 900
24 | RFQ to the Convention Centers | 1.20 | 7FS | FS25 | 2018-05-22 08:00 | 2018-06-04 17:00 | 10d | Burak Simsek | 600 | 0 | 0 | 0 | 600
25 | Deciding on the Convention Center | 1.21 | 24FS | FS27;FS28 | 2018-06-05 08:00 | 2018-06-18 17:00 | 10d | Burak Simsek | 600 | 0 | 0 | 0 | 600
26 | Amount of food & beverages to be determined | 1.22 | 20FS |  | 2018-09-17 08:00 | 2018-09-19 17:00 | 3d | Burak Simsek | 180 | 0 | 0 | 0 | 180
27 | Layout of the Convention Center to be done | 1.23 | 25FS |  | 2018-06-19 08:00 | 2018-07-09 17:00 | 15d | Maria Cunha Patricija Oreski | 1200 | 0 | 0 | 0 | 1200
28 | Company/Booth Matching according to the Layout | 1.24 | 23FS;25FS | FS29 | 2018-11-13 08:00 | 2018-11-16 17:00 | 4d | Maria Cunha Patricija Oreski | 320 | 0 | 0 | 0 | 320
29 | Maps,coupons and name tags for the participants to be printed | 1.25 | 28FS |  | 2018-11-19 08:00 | 2018-11-23 17:00 | 5d | Burak Simsek | 300 | 0 | 0 | 0 | 300

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Maria Cunha Patricija Oreski | Renewable | 2 project managers | 0 | 10 | 1;2;3;5;6;7;27;28; | 4880
2 | Burak Simsek | Renewable | 1 purchasing | 0 | 7.5 | 24;25;26;29; | 1680
3 | Madalena Malcata | Renewable | 1 marketing | 0 | 7.5 | 4;15;16;17;18;22;23; | 6000
4 | Francisco Agostinho | Renewable | 1 finance | 0 | 10 | 8;12;14; | 14720
5 | Kevin Vendelman | Renewable | 1 it | 0 | 15 | 21; | 1800
6 | Pieter Claeys | Renewable | 1 it | 0 | 15 | 19;20; | 5640

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | Job Fair in Ghent | 1680h
1 | Job Fair Date Planning | 8h | standard - symmetric | 80 | 100 | 120
2 | Estimate the Budget | 80h | standard - symmetric | 80 | 100 | 120
3 | Sponsorship Deals to be Prepared & Offered | 120h | standard - symmetric | 80 | 100 | 120
4 | Preparing the Company List to be Pursued | 80h | standard - symmetric | 80 | 100 | 120
5 | Job Fair Program Plan | 40h | standard - symmetric | 80 | 100 | 120
6 | Authorisation & Decision Mechanism to be decided | 8h | standard - symmetric | 80 | 100 | 120
7 | Make the contracts with sponsors | 80h | standard - symmetric | 80 | 100 | 120
8 | Project Income/Expense Management | 672h | standard - symmetric | 80 | 100 | 120
12 | Invoice Management | 760h | standard - symmetric | 80 | 100 | 120
14 | Prepare the Final Financial Statement | 40h | standard - symmetric | 80 | 100 | 120
15 | Booth Advertisement for companies | 80h | standard - symmetric | 80 | 100 | 120
16 | Prepare Advertisement Brochures | 120h | standard - symmetric | 80 | 100 | 120
17 | Prepare Billboard Advertisement | 240h | standard - symmetric | 80 | 100 | 120
18 | Prepare Social Media Advertisements | 80h | standard - symmetric | 80 | 100 | 120
19 | Prepare the website | 200h | standard - symmetric | 80 | 100 | 120
20 | Prepare the Registration System | 176h | standard - symmetric | 80 | 100 | 120
21 | Prepare the Digital Advertisements | 120h | standard - symmetric | 80 | 100 | 120
22 | Contacting Companies | 80h | standard - symmetric | 80 | 100 | 120
23 | Renting the booths to companies | 120h | standard - symmetric | 80 | 100 | 120
24 | RFQ to the Convention Centers | 80h | standard - symmetric | 80 | 100 | 120
25 | Deciding on the Convention Center | 80h | standard - symmetric | 80 | 100 | 120
26 | Amount of food & beverages to be determined | 24h | standard - symmetric | 80 | 100 | 120
27 | Layout of the Convention Center to be done | 120h | standard - symmetric | 80 | 100 | 120
28 | Company/Booth Matching according to the Layout | 32h | standard - symmetric | 80 | 100 | 120
29 | Maps,coupons and name tags for the participants to be printed | 40h | standard - symmetric | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t))