## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Landing Gear Project | 1 |  |  | 2018-07-17 08:00 | 2019-10-07 17:00 | 320d |  |  | 0 |  |  | 11562500 | 447.375
31 | Feasibilty Study | 1.1 |  |  | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d |  |  | 0 |  |  | 1805000 | 62.375
1 | Feasiblity Study | 1.1.1 |  | FS3 | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d | Consultant | 1805000 | 0 | 0 | 0 | 1805000 | 62.375
26 | Market Research | 1.2 |  |  | 2018-09-18 08:00 | 2018-10-29 17:00 | 30d |  |  | 0 |  |  | 2057500 | 41.375
3 | Specifying the size of Single and Twin engined light aircrafts replacement in the market | 1.2.1 | 1FS | FS4;FS5 | 2018-09-18 08:00 | 2018-10-01 17:00 | 10d | Consultant;Engineers | 532500 | 0 | 0 | 0 | 532500 | 13.375
4 | Calculation of the potential annual demand volumes for landing gear struts according to each of the different retail prices | 1.2.2 | 3FS | FS6 | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Consultant;Engineers | 792500 | 0 | 0 | 0 | 792500 | 20.375
5 | Calculation of the annual sales volumes actually achievable, taking into account the maximum capacity of the factory set by the directors | 1.2.3 | 3FS | FS7 | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Engineers | 187500 | 0 | 0 | 0 | 187500 | 20.375
6 | Calculation of the total annual trade sales revenues and fixed/variable/total costs for each retail | 1.2.4 | 4FS | FS9 | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 6.375
7 | Calculation of the-trade price at which the company should sell at to generate the maximum profit | 1.2.5 | 5FS | FS9 | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 6.375
27 | Business Plan, Financial Analysis, and Team Selection | 1.3 |  |  | 2018-10-30 08:00 | 2019-01-07 17:00 | 50d |  |  | 0 |  |  | 2615000 | 69.375
9 | Preparation of Business Plan | 1.3.1 | 7FS;6FS | FS10;FS11 | 2018-10-30 08:00 | 2018-12-10 17:00 | 30d | Consultant | 1205000 | 0 | 0 | 0 | 1205000 | 41.375
10 | Financial Analysis | 1.3.2 | 9FS | FS13 | 2018-12-18 08:00 | 2019-01-07 17:00 | 15d | Consultant | 605000 | 0 | 0 | 0 | 605000 | 20.375
11 | Team Selection (Recruitment of Management Team and Staff) | 1.3.3 | 9FS | FS13 | 2018-12-11 08:00 | 2019-01-07 17:00 | 20d | Consultant | 805000 | 0 | 0 | 0 | 805000 | 27.375
28 | Process Analysis | 1.4 |  |  | 2019-01-08 08:00 | 2019-04-08 17:00 | 65d |  |  | 0 |  |  | 2159500 | 90.375
13 | Preparation of Bill of Materials (BOM) file | 1.4.1 | 11FS;10FS | FS14;FS15;FS16 | 2019-01-08 08:00 | 2019-03-11 17:00 | 45d | Engineers;Workers | 917500 | 0 | 0 | 0 | 917500 | 62.375
14 | Calculation of Machine Requirements | 1.4.2 | 13FS | FS18 | 2019-03-19 08:00 | 2019-04-08 17:00 | 15d | Engineers;Workers[0.40 #1] | 239500 | 0 | 0 | 0 | 239500 | 20.375
15 | Calculation of Labour Requirements | 1.4.3 | 13FS | FS18 | 2019-03-26 08:00 | 2019-04-08 17:00 | 10d | Engineers;Workers[0.40 #1] | 163500 | 0 | 0 | 0 | 163500 | 13.375
16 | Calculation of Factory Capacity | 1.4.4 | 13FS | FS18 | 2019-03-12 08:00 | 2019-04-08 17:00 | 20d | Workers[0.20 #1];Consultant | 839000 | 0 | 0 | 0 | 839000 | 27.375
29 | Productivity Analysis | 1.5 |  |  | 2019-04-09 08:00 | 2019-06-10 17:00 | 45d |  |  | 0 |  |  | 850000 | 62.375
18 | Creation the Line of Balance for the Landing Gear System and its Level 1 Sub-Assemblies | 1.5.1 | 16FS;15FS;14FS | FS19 | 2019-04-09 08:00 | 2019-05-06 17:00 | 20d | Workers[0.20 #1];The Graduates | 439000 | 0 | 0 | 0 | 439000 | 27.375
19 | Defining implication of this MPS on the capacity of the factory | 1.5.2 | 18FS | FS20 | 2019-05-07 08:00 | 2019-05-20 17:00 | 10d | Workers[0.60 #1] | 54000 | 0 | 0 | 0 | 54000 | 13.375
20 | Assisting of line of balance in solution providing for problems | 1.5.3 | 19FS | FS22;FS23 | 2019-05-21 08:00 | 2019-06-10 17:00 | 15d | Workers[0.40 #1];The Graduates | 357000 | 0 | 0 | 0 | 357000 | 20.375
30 | Start to Production | 1.6 |  |  | 2019-06-11 08:00 | 2019-10-07 17:00 | 85d |  |  | 0 |  |  | 2075500 | 118.375
22 | Identifying Production Site | 1.6.1 | 20FS | FS24 | 2019-06-11 08:00 | 2019-07-15 17:00 | 25d | Consultant;Workers[0.40 #1] | 1089000 | 0 | 0 | 0 | 1089000 | 34.375
23 | Supplier Selection | 1.6.2 | 20FS | FS24 | 2019-07-02 08:00 | 2019-07-15 17:00 | 10d | Engineers;Workers[0.60 #1] | 181500 | 0 | 0 | 0 | 181500 | 13.375
24 | Ordering Machines and Raw Materials | 1.6.3 | 22FS;23FS | FS25 | 2019-07-16 08:00 | 2019-09-16 17:00 | 45d | Workers | 370000 | 0 | 0 | 0 | 370000 | 62.375
25 | Manufacturing Trials | 1.6.4 | 24FS | FS33 | 2019-09-17 08:00 | 2019-10-07 17:00 | 15d | Workers;The Graduates | 435000 | 0 | 0 | 0 | 435000 | 20.375
33 | Finish | 1.7 | 25FS |  | 2019-10-07 17:00 | 2019-10-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Consultant | Renewable | 1 | 5000 | 5000 | 1;3;4;6;7;9;10;11;16;22; | 7650000
2 | Engineers | Renewable | 1 | 7500 | 1500 | 3;4;5;6;7;13;14;15;23; | 1627500
3 | Workers | Renewable | 1 | 10000 | 1000 | 13;14[0.40 Workers];15[0.40 Workers];16[0.20 Workers];18[0.20 Workers];19[0.60 Workers];20[0.40 Workers];22[0.40 Workers];23[0.60 Workers];24;25; | 1270000
4 | The Graduates | Renewable | 1 | 5000 | 2500 | 18;20;25; | 1015000

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Landing Gear Project | 2560h |  |  |  |  | 99 | 100 | 101
31 | Feasibilty Study | 360h |  |  |  |  | 99 | 100 | 101
1 | Feasiblity Study | 360h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Market Research | 240h |  |  |  |  | 99 | 100 | 101
3 | Specifying the size of Single and Twin engined light aircrafts replacement in the market | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Calculation of the potential annual demand volumes for landing gear struts according to each of the different retail prices | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Calculation of the annual sales volumes actually achievable, taking into account the maximum capacity of the factory set by the directors | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Calculation of the total annual trade sales revenues and fixed/variable/total costs for each retail | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Calculation of the-trade price at which the company should sell at to generate the maximum profit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Business Plan, Financial Analysis, and Team Selection | 400h |  |  |  |  | 99 | 100 | 101
9 | Preparation of Business Plan | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Financial Analysis | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Team Selection (Recruitment of Management Team and Staff) | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Process Analysis | 520h |  |  |  |  | 99 | 100 | 101
13 | Preparation of Bill of Materials (BOM) file | 360h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Calculation of Machine Requirements | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Calculation of Labour Requirements | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Calculation of Factory Capacity | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Productivity Analysis | 360h |  |  |  |  | 99 | 100 | 101
18 | Creation the Line of Balance for the Landing Gear System and its Level 1 Sub-Assemblies | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Defining implication of this MPS on the capacity of the factory | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Assisting of line of balance in solution providing for problems | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | Start to Production | 680h |  |  |  |  | 99 | 100 | 101
22 | Identifying Production Site | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Supplier Selection | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Ordering Machines and Raw Materials | 360h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Manufacturing Trials | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | Finish | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2018-08-06 17:00 |  | TP Name | 6.08.2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Landing Gear Project | 2018-07-17 08:00 | 2019-10-07 17:00 | 320d |  |  | 0 |  |  | 11562500 |  | 15d | [5 empty] | 605000 |  | 6.397% |  | 739693.9027 | 605000
31 | Feasibilty Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d |  |  | 0 |  |  | 1805000 |  | 15d | [5 empty] | 605000 |  | 40.98% |  | 739693.9027 | 605000
1 | Feasiblity Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d | Consultant | 1805000 | 0 | 0 | 0 | 1805000 | 2018-07-17 08:00 | 15d | 605000 | 870000 | 21d 6h | 0 | 0 | 605000 | 870000 | 40.82% | Started | 739693.9027 | 605000
26 | Market Research | 2018-09-18 08:00 | 2018-10-29 17:00 | 30d |  |  | 0 |  |  | 2057500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Specifying the size of Single and Twin engined light aircrafts replacement in the market | 2018-09-18 08:00 | 2018-10-01 17:00 | 10d | Consultant;Engineers | 532500 | 0 | 0 | 0 | 532500 |  | 0 | 0 | 532500 | 10d | 0 | 0 | 0 | 532500 | 0% | Not Started | 0 | 0
4 | Calculation of the potential annual demand volumes for landing gear struts according to each of the different retail prices | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Consultant;Engineers | 792500 | 0 | 0 | 0 | 792500 |  | 0 | 0 | 792500 | 15d | 0 | 0 | 0 | 792500 | 0% | Not Started | 0 | 0
5 | Calculation of the annual sales volumes actually achievable, taking into account the maximum capacity of the factory set by the directors | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Engineers | 187500 | 0 | 0 | 0 | 187500 |  | 0 | 0 | 187500 | 15d | 0 | 0 | 0 | 187500 | 0% | Not Started | 0 | 0
6 | Calculation of the total annual trade sales revenues and fixed/variable/total costs for each retail | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 |  | 0 | 0 | 272500 | 5d | 0 | 0 | 0 | 272500 | 0% | Not Started | 0 | 0
7 | Calculation of the-trade price at which the company should sell at to generate the maximum profit | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 |  | 0 | 0 | 272500 | 5d | 0 | 0 | 0 | 272500 | 0% | Not Started | 0 | 0
27 | Business Plan, Financial Analysis, and Team Selection | 2018-10-30 08:00 | 2019-01-07 17:00 | 50d |  |  | 0 |  |  | 2615000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
9 | Preparation of Business Plan | 2018-10-30 08:00 | 2018-12-10 17:00 | 30d | Consultant | 1205000 | 0 | 0 | 0 | 1205000 |  | 0 | 0 | 1205000 | 30d | 0 | 0 | 0 | 1205000 | 0% | Not Started | 0 | 0
10 | Financial Analysis | 2018-12-18 08:00 | 2019-01-07 17:00 | 15d | Consultant | 605000 | 0 | 0 | 0 | 605000 |  | 0 | 0 | 605000 | 15d | 0 | 0 | 0 | 605000 | 0% | Not Started | 0 | 0
11 | Team Selection (Recruitment of Management Team and Staff) | 2018-12-11 08:00 | 2019-01-07 17:00 | 20d | Consultant | 805000 | 0 | 0 | 0 | 805000 |  | 0 | 0 | 805000 | 20d | 0 | 0 | 0 | 805000 | 0% | Not Started | 0 | 0
28 | Process Analysis | 2019-01-08 08:00 | 2019-04-08 17:00 | 65d |  |  | 0 |  |  | 2159500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
13 | Preparation of Bill of Materials (BOM) file | 2019-01-08 08:00 | 2019-03-11 17:00 | 45d | Engineers;Workers | 917500 | 0 | 0 | 0 | 917500 |  | 0 | 0 | 917500 | 45d | 0 | 0 | 0 | 917500 | 0% | Not Started | 0 | 0
14 | Calculation of Machine Requirements | 2019-03-19 08:00 | 2019-04-08 17:00 | 15d | Engineers;Workers[0.40 #1] | 239500 | 0 | 0 | 0 | 239500 |  | 0 | 0 | 239500 | 15d | 0 | 0 | 0 | 239500 | 0% | Not Started | 0 | 0
15 | Calculation of Labour Requirements | 2019-03-26 08:00 | 2019-04-08 17:00 | 10d | Engineers;Workers[0.40 #1] | 163500 | 0 | 0 | 0 | 163500 |  | 0 | 0 | 163500 | 10d | 0 | 0 | 0 | 163500 | 0% | Not Started | 0 | 0
16 | Calculation of Factory Capacity | 2019-03-12 08:00 | 2019-04-08 17:00 | 20d | Workers[0.20 #1];Consultant | 839000 | 0 | 0 | 0 | 839000 |  | 0 | 0 | 839000 | 20d | 0 | 0 | 0 | 839000 | 0% | Not Started | 0 | 0
29 | Productivity Analysis | 2019-04-09 08:00 | 2019-06-10 17:00 | 45d |  |  | 0 |  |  | 850000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | Creation the Line of Balance for the Landing Gear System and its Level 1 Sub-Assemblies | 2019-04-09 08:00 | 2019-05-06 17:00 | 20d | Workers[0.20 #1];The Graduates | 439000 | 0 | 0 | 0 | 439000 |  | 0 | 0 | 439000 | 20d | 0 | 0 | 0 | 439000 | 0% | Not Started | 0 | 0
19 | Defining implication of this MPS on the capacity of the factory | 2019-05-07 08:00 | 2019-05-20 17:00 | 10d | Workers[0.60 #1] | 54000 | 0 | 0 | 0 | 54000 |  | 0 | 0 | 54000 | 10d | 0 | 0 | 0 | 54000 | 0% | Not Started | 0 | 0
20 | Assisting of line of balance in solution providing for problems | 2019-05-21 08:00 | 2019-06-10 17:00 | 15d | Workers[0.40 #1];The Graduates | 357000 | 0 | 0 | 0 | 357000 |  | 0 | 0 | 357000 | 15d | 0 | 0 | 0 | 357000 | 0% | Not Started | 0 | 0
30 | Start to Production | 2019-06-11 08:00 | 2019-10-07 17:00 | 85d |  |  | 0 |  |  | 2075500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Identifying Production Site | 2019-06-11 08:00 | 2019-07-15 17:00 | 25d | Consultant;Workers[0.40 #1] | 1089000 | 0 | 0 | 0 | 1089000 |  | 0 | 0 | 1089000 | 25d | 0 | 0 | 0 | 1089000 | 0% | Not Started | 0 | 0
23 | Supplier Selection | 2019-07-02 08:00 | 2019-07-15 17:00 | 10d | Engineers;Workers[0.60 #1] | 181500 | 0 | 0 | 0 | 181500 |  | 0 | 0 | 181500 | 10d | 0 | 0 | 0 | 181500 | 0% | Not Started | 0 | 0
24 | Ordering Machines and Raw Materials | 2019-07-16 08:00 | 2019-09-16 17:00 | 45d | Workers | 370000 | 0 | 0 | 0 | 370000 |  | 0 | 0 | 370000 | 45d | 0 | 0 | 0 | 370000 | 0% | Not Started | 0 | 0
25 | Manufacturing Trials | 2019-09-17 08:00 | 2019-10-07 17:00 | 15d | Workers;The Graduates | 435000 | 0 | 0 | 0 | 435000 |  | 0 | 0 | 435000 | 15d | 0 | 0 | 0 | 435000 | 0% | Not Started | 0 | 0
33 | Finish | 2019-10-07 17:00 | 2019-10-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP2
| TP Status Date | 2018-08-27 17:00 |  | TP Name | 27.08.2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Landing Gear Project | 2018-07-17 08:00 | 2019-10-07 17:00 | 320d |  |  | 0 |  |  | 11562500 |  | 30d | [5 empty] | 1205000 |  | 12.75% |  | 1474387.8055 | 1205000
31 | Feasibilty Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d |  |  | 0 |  |  | 1805000 |  | 30d | [5 empty] | 1205000 |  | 81.68% |  | 1474387.8055 | 1205000
1 | Feasiblity Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d | Consultant | 1805000 | 0 | 0 | 0 | 1805000 | 2018-07-17 08:00 | 30d | 1205000 | 270000 | 6d 6h | 0 | 0 | 1205000 | 270000 | 81.63% | Started | 1474387.8055 | 1205000
26 | Market Research | 2018-09-18 08:00 | 2018-10-29 17:00 | 30d |  |  | 0 |  |  | 2057500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
3 | Specifying the size of Single and Twin engined light aircrafts replacement in the market | 2018-09-18 08:00 | 2018-10-01 17:00 | 10d | Consultant;Engineers | 532500 | 0 | 0 | 0 | 532500 |  | 0 | 0 | 532500 | 10d | 0 | 0 | 0 | 532500 | 0% | Not Started | 0 | 0
4 | Calculation of the potential annual demand volumes for landing gear struts according to each of the different retail prices | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Consultant;Engineers | 792500 | 0 | 0 | 0 | 792500 |  | 0 | 0 | 792500 | 15d | 0 | 0 | 0 | 792500 | 0% | Not Started | 0 | 0
5 | Calculation of the annual sales volumes actually achievable, taking into account the maximum capacity of the factory set by the directors | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Engineers | 187500 | 0 | 0 | 0 | 187500 |  | 0 | 0 | 187500 | 15d | 0 | 0 | 0 | 187500 | 0% | Not Started | 0 | 0
6 | Calculation of the total annual trade sales revenues and fixed/variable/total costs for each retail | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 |  | 0 | 0 | 272500 | 5d | 0 | 0 | 0 | 272500 | 0% | Not Started | 0 | 0
7 | Calculation of the-trade price at which the company should sell at to generate the maximum profit | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 |  | 0 | 0 | 272500 | 5d | 0 | 0 | 0 | 272500 | 0% | Not Started | 0 | 0
27 | Business Plan, Financial Analysis, and Team Selection | 2018-10-30 08:00 | 2019-01-07 17:00 | 50d |  |  | 0 |  |  | 2615000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
9 | Preparation of Business Plan | 2018-10-30 08:00 | 2018-12-10 17:00 | 30d | Consultant | 1205000 | 0 | 0 | 0 | 1205000 |  | 0 | 0 | 1205000 | 30d | 0 | 0 | 0 | 1205000 | 0% | Not Started | 0 | 0
10 | Financial Analysis | 2018-12-18 08:00 | 2019-01-07 17:00 | 15d | Consultant | 605000 | 0 | 0 | 0 | 605000 |  | 0 | 0 | 605000 | 15d | 0 | 0 | 0 | 605000 | 0% | Not Started | 0 | 0
11 | Team Selection (Recruitment of Management Team and Staff) | 2018-12-11 08:00 | 2019-01-07 17:00 | 20d | Consultant | 805000 | 0 | 0 | 0 | 805000 |  | 0 | 0 | 805000 | 20d | 0 | 0 | 0 | 805000 | 0% | Not Started | 0 | 0
28 | Process Analysis | 2019-01-08 08:00 | 2019-04-08 17:00 | 65d |  |  | 0 |  |  | 2159500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
13 | Preparation of Bill of Materials (BOM) file | 2019-01-08 08:00 | 2019-03-11 17:00 | 45d | Engineers;Workers | 917500 | 0 | 0 | 0 | 917500 |  | 0 | 0 | 917500 | 45d | 0 | 0 | 0 | 917500 | 0% | Not Started | 0 | 0
14 | Calculation of Machine Requirements | 2019-03-19 08:00 | 2019-04-08 17:00 | 15d | Engineers;Workers[0.40 #1] | 239500 | 0 | 0 | 0 | 239500 |  | 0 | 0 | 239500 | 15d | 0 | 0 | 0 | 239500 | 0% | Not Started | 0 | 0
15 | Calculation of Labour Requirements | 2019-03-26 08:00 | 2019-04-08 17:00 | 10d | Engineers;Workers[0.40 #1] | 163500 | 0 | 0 | 0 | 163500 |  | 0 | 0 | 163500 | 10d | 0 | 0 | 0 | 163500 | 0% | Not Started | 0 | 0
16 | Calculation of Factory Capacity | 2019-03-12 08:00 | 2019-04-08 17:00 | 20d | Workers[0.20 #1];Consultant | 839000 | 0 | 0 | 0 | 839000 |  | 0 | 0 | 839000 | 20d | 0 | 0 | 0 | 839000 | 0% | Not Started | 0 | 0
29 | Productivity Analysis | 2019-04-09 08:00 | 2019-06-10 17:00 | 45d |  |  | 0 |  |  | 850000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | Creation the Line of Balance for the Landing Gear System and its Level 1 Sub-Assemblies | 2019-04-09 08:00 | 2019-05-06 17:00 | 20d | Workers[0.20 #1];The Graduates | 439000 | 0 | 0 | 0 | 439000 |  | 0 | 0 | 439000 | 20d | 0 | 0 | 0 | 439000 | 0% | Not Started | 0 | 0
19 | Defining implication of this MPS on the capacity of the factory | 2019-05-07 08:00 | 2019-05-20 17:00 | 10d | Workers[0.60 #1] | 54000 | 0 | 0 | 0 | 54000 |  | 0 | 0 | 54000 | 10d | 0 | 0 | 0 | 54000 | 0% | Not Started | 0 | 0
20 | Assisting of line of balance in solution providing for problems | 2019-05-21 08:00 | 2019-06-10 17:00 | 15d | Workers[0.40 #1];The Graduates | 357000 | 0 | 0 | 0 | 357000 |  | 0 | 0 | 357000 | 15d | 0 | 0 | 0 | 357000 | 0% | Not Started | 0 | 0
30 | Start to Production | 2019-06-11 08:00 | 2019-10-07 17:00 | 85d |  |  | 0 |  |  | 2075500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Identifying Production Site | 2019-06-11 08:00 | 2019-07-15 17:00 | 25d | Consultant;Workers[0.40 #1] | 1089000 | 0 | 0 | 0 | 1089000 |  | 0 | 0 | 1089000 | 25d | 0 | 0 | 0 | 1089000 | 0% | Not Started | 0 | 0
23 | Supplier Selection | 2019-07-02 08:00 | 2019-07-15 17:00 | 10d | Engineers;Workers[0.60 #1] | 181500 | 0 | 0 | 0 | 181500 |  | 0 | 0 | 181500 | 10d | 0 | 0 | 0 | 181500 | 0% | Not Started | 0 | 0
24 | Ordering Machines and Raw Materials | 2019-07-16 08:00 | 2019-09-16 17:00 | 45d | Workers | 370000 | 0 | 0 | 0 | 370000 |  | 0 | 0 | 370000 | 45d | 0 | 0 | 0 | 370000 | 0% | Not Started | 0 | 0
25 | Manufacturing Trials | 2019-09-17 08:00 | 2019-10-07 17:00 | 15d | Workers;The Graduates | 435000 | 0 | 0 | 0 | 435000 |  | 0 | 0 | 435000 | 15d | 0 | 0 | 0 | 435000 | 0% | Not Started | 0 | 0
33 | Finish | 2019-10-07 17:00 | 2019-10-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP3
| TP Status Date | 2018-09-17 17:00 |  | TP Name | 17.09.2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Landing Gear Project | 2018-07-17 08:00 | 2019-10-07 17:00 | 320d |  |  | 0 |  |  | 11562500 |  | 45d | [5 empty] | 1916500 |  | 18.26% |  | 2110833.3468 | 1805000
31 | Feasibilty Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d |  |  | 0 |  |  | 1805000 |  | 36d 6h | [5 empty] | 1475000 |  | 100% |  | 1805000 | 1805000
1 | Feasiblity Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d | Consultant | 1805000 | 0 | 0 | 0 | 1805000 | 2018-07-17 08:00 | 36d 6h | 1475000 | 0 | 0 | 0 | 0 | 1475000 | 0 | 100% | Finished | 1805000 | 1805000
26 | Market Research | 2018-09-18 08:00 | 2018-10-29 17:00 | 30d |  |  | 0 |  |  | 2057500 |  | 8d 2h | [5 empty] | 441500 |  | 14.86% |  | 305833.3468 | 0
3 | Specifying the size of Single and Twin engined light aircrafts replacement in the market | 2018-09-18 08:00 | 2018-10-01 17:00 | 10d | Consultant;Engineers | 532500 | 0 | 0 | 0 | 532500 | 2018-09-05 15:00 | 8d 2h | 441500 | 331500 | 6d 3h | 0 | 0 | 441500 | 331500 | 56.41% | Started | 305833.3468 | 0
4 | Calculation of the potential annual demand volumes for landing gear struts according to each of the different retail prices | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Consultant;Engineers | 792500 | 0 | 0 | 0 | 792500 |  | 0 | 0 | 792500 | 15d | 0 | 0 | 0 | 792500 | 0% | Not Started | 0 | 0
5 | Calculation of the annual sales volumes actually achievable, taking into account the maximum capacity of the factory set by the directors | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Engineers | 187500 | 0 | 0 | 0 | 187500 |  | 0 | 0 | 187500 | 15d | 0 | 0 | 0 | 187500 | 0% | Not Started | 0 | 0
6 | Calculation of the total annual trade sales revenues and fixed/variable/total costs for each retail | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 |  | 0 | 0 | 272500 | 5d | 0 | 0 | 0 | 272500 | 0% | Not Started | 0 | 0
7 | Calculation of the-trade price at which the company should sell at to generate the maximum profit | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 |  | 0 | 0 | 272500 | 5d | 0 | 0 | 0 | 272500 | 0% | Not Started | 0 | 0
27 | Business Plan, Financial Analysis, and Team Selection | 2018-10-30 08:00 | 2019-01-07 17:00 | 50d |  |  | 0 |  |  | 2615000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
9 | Preparation of Business Plan | 2018-10-30 08:00 | 2018-12-10 17:00 | 30d | Consultant | 1205000 | 0 | 0 | 0 | 1205000 |  | 0 | 0 | 1205000 | 30d | 0 | 0 | 0 | 1205000 | 0% | Not Started | 0 | 0
10 | Financial Analysis | 2018-12-18 08:00 | 2019-01-07 17:00 | 15d | Consultant | 605000 | 0 | 0 | 0 | 605000 |  | 0 | 0 | 605000 | 15d | 0 | 0 | 0 | 605000 | 0% | Not Started | 0 | 0
11 | Team Selection (Recruitment of Management Team and Staff) | 2018-12-11 08:00 | 2019-01-07 17:00 | 20d | Consultant | 805000 | 0 | 0 | 0 | 805000 |  | 0 | 0 | 805000 | 20d | 0 | 0 | 0 | 805000 | 0% | Not Started | 0 | 0
28 | Process Analysis | 2019-01-08 08:00 | 2019-04-08 17:00 | 65d |  |  | 0 |  |  | 2159500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
13 | Preparation of Bill of Materials (BOM) file | 2019-01-08 08:00 | 2019-03-11 17:00 | 45d | Engineers;Workers | 917500 | 0 | 0 | 0 | 917500 |  | 0 | 0 | 917500 | 45d | 0 | 0 | 0 | 917500 | 0% | Not Started | 0 | 0
14 | Calculation of Machine Requirements | 2019-03-19 08:00 | 2019-04-08 17:00 | 15d | Engineers;Workers[0.40 #1] | 239500 | 0 | 0 | 0 | 239500 |  | 0 | 0 | 239500 | 15d | 0 | 0 | 0 | 239500 | 0% | Not Started | 0 | 0
15 | Calculation of Labour Requirements | 2019-03-26 08:00 | 2019-04-08 17:00 | 10d | Engineers;Workers[0.40 #1] | 163500 | 0 | 0 | 0 | 163500 |  | 0 | 0 | 163500 | 10d | 0 | 0 | 0 | 163500 | 0% | Not Started | 0 | 0
16 | Calculation of Factory Capacity | 2019-03-12 08:00 | 2019-04-08 17:00 | 20d | Workers[0.20 #1];Consultant | 839000 | 0 | 0 | 0 | 839000 |  | 0 | 0 | 839000 | 20d | 0 | 0 | 0 | 839000 | 0% | Not Started | 0 | 0
29 | Productivity Analysis | 2019-04-09 08:00 | 2019-06-10 17:00 | 45d |  |  | 0 |  |  | 850000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | Creation the Line of Balance for the Landing Gear System and its Level 1 Sub-Assemblies | 2019-04-09 08:00 | 2019-05-06 17:00 | 20d | Workers[0.20 #1];The Graduates | 439000 | 0 | 0 | 0 | 439000 |  | 0 | 0 | 439000 | 20d | 0 | 0 | 0 | 439000 | 0% | Not Started | 0 | 0
19 | Defining implication of this MPS on the capacity of the factory | 2019-05-07 08:00 | 2019-05-20 17:00 | 10d | Workers[0.60 #1] | 54000 | 0 | 0 | 0 | 54000 |  | 0 | 0 | 54000 | 10d | 0 | 0 | 0 | 54000 | 0% | Not Started | 0 | 0
20 | Assisting of line of balance in solution providing for problems | 2019-05-21 08:00 | 2019-06-10 17:00 | 15d | Workers[0.40 #1];The Graduates | 357000 | 0 | 0 | 0 | 357000 |  | 0 | 0 | 357000 | 15d | 0 | 0 | 0 | 357000 | 0% | Not Started | 0 | 0
30 | Start to Production | 2019-06-11 08:00 | 2019-10-07 17:00 | 85d |  |  | 0 |  |  | 2075500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Identifying Production Site | 2019-06-11 08:00 | 2019-07-15 17:00 | 25d | Consultant;Workers[0.40 #1] | 1089000 | 0 | 0 | 0 | 1089000 |  | 0 | 0 | 1089000 | 25d | 0 | 0 | 0 | 1089000 | 0% | Not Started | 0 | 0
23 | Supplier Selection | 2019-07-02 08:00 | 2019-07-15 17:00 | 10d | Engineers;Workers[0.60 #1] | 181500 | 0 | 0 | 0 | 181500 |  | 0 | 0 | 181500 | 10d | 0 | 0 | 0 | 181500 | 0% | Not Started | 0 | 0
24 | Ordering Machines and Raw Materials | 2019-07-16 08:00 | 2019-09-16 17:00 | 45d | Workers | 370000 | 0 | 0 | 0 | 370000 |  | 0 | 0 | 370000 | 45d | 0 | 0 | 0 | 370000 | 0% | Not Started | 0 | 0
25 | Manufacturing Trials | 2019-09-17 08:00 | 2019-10-07 17:00 | 15d | Workers;The Graduates | 435000 | 0 | 0 | 0 | 435000 |  | 0 | 0 | 435000 | 15d | 0 | 0 | 0 | 435000 | 0% | Not Started | 0 | 0
33 | Finish | 2019-10-07 17:00 | 2019-10-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP4
| TP Status Date | 2018-10-08 17:00 |  | TP Name | 8.10.2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Landing Gear Project | 2018-07-17 08:00 | 2019-10-07 17:00 | 320d |  |  | 0 |  |  | 11562500 |  | 60d | [5 empty] | 2837500 |  | 27.82% |  | 3216341.4422 | 2677500
31 | Feasibilty Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d |  |  | 0 |  |  | 1805000 |  | 36d 6h | [5 empty] | 1475000 |  | 100% |  | 1805000 | 1805000
1 | Feasiblity Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d | Consultant | 1805000 | 0 | 0 | 0 | 1805000 | 2018-07-17 08:00 | 36d 6h | 1475000 | 0 | 0 | 0 | 0 | 1475000 | 0 | 100% | Finished | 1805000 | 1805000
26 | Market Research | 2018-09-18 08:00 | 2018-10-29 17:00 | 30d |  |  | 0 |  |  | 2057500 |  | 23d 2h | [5 empty] | 1362500 |  | 68.59% |  | 1411341.4422 | 872500
3 | Specifying the size of Single and Twin engined light aircrafts replacement in the market | 2018-09-18 08:00 | 2018-10-01 17:00 | 10d | Consultant;Engineers | 532500 | 0 | 0 | 0 | 532500 | 2018-09-05 15:00 | 14d 5h | 773000 | 0 | 0 | 0 | 0 | 773000 | 0 | 100% | Finished | 532500 | 532500
4 | Calculation of the potential annual demand volumes for landing gear struts according to each of the different retail prices | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Consultant;Engineers | 792500 | 0 | 0 | 0 | 792500 | 2018-09-26 11:00 | 8d 5h | 461000 | 84500 | 1d 5h | 0 | 0 | 461000 | 84500 | 84.15% | Started | 668841.4419 | 272500
5 | Calculation of the annual sales volumes actually achievable, taking into account the maximum capacity of the factory set by the directors | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Engineers | 187500 | 0 | 0 | 0 | 187500 | 2018-09-26 11:00 | 8d 4h | 109500 | 0 | 0 | 0 | 0 | 109500 | 0 | 100% | Finished | 187500 | 67500
6 | Calculation of the total annual trade sales revenues and fixed/variable/total costs for each retail | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 |  | 0 | 0 | 272500 | 5d | 0 | 0 | 0 | 272500 | 0% | Not Started | 0 | 0
7 | Calculation of the-trade price at which the company should sell at to generate the maximum profit | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-08 16:00 | 1h | 19000 | 162500 | 3d 1h | 0 | 0 | 19000 | 162500 | 3.846% | Started | 22500.0004 | 0
27 | Business Plan, Financial Analysis, and Team Selection | 2018-10-30 08:00 | 2019-01-07 17:00 | 50d |  |  | 0 |  |  | 2615000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
9 | Preparation of Business Plan | 2018-10-30 08:00 | 2018-12-10 17:00 | 30d | Consultant | 1205000 | 0 | 0 | 0 | 1205000 |  | 0 | 0 | 1205000 | 30d | 0 | 0 | 0 | 1205000 | 0% | Not Started | 0 | 0
10 | Financial Analysis | 2018-12-18 08:00 | 2019-01-07 17:00 | 15d | Consultant | 605000 | 0 | 0 | 0 | 605000 |  | 0 | 0 | 605000 | 15d | 0 | 0 | 0 | 605000 | 0% | Not Started | 0 | 0
11 | Team Selection (Recruitment of Management Team and Staff) | 2018-12-11 08:00 | 2019-01-07 17:00 | 20d | Consultant | 805000 | 0 | 0 | 0 | 805000 |  | 0 | 0 | 805000 | 20d | 0 | 0 | 0 | 805000 | 0% | Not Started | 0 | 0
28 | Process Analysis | 2019-01-08 08:00 | 2019-04-08 17:00 | 65d |  |  | 0 |  |  | 2159500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
13 | Preparation of Bill of Materials (BOM) file | 2019-01-08 08:00 | 2019-03-11 17:00 | 45d | Engineers;Workers | 917500 | 0 | 0 | 0 | 917500 |  | 0 | 0 | 917500 | 45d | 0 | 0 | 0 | 917500 | 0% | Not Started | 0 | 0
14 | Calculation of Machine Requirements | 2019-03-19 08:00 | 2019-04-08 17:00 | 15d | Engineers;Workers[0.40 #1] | 239500 | 0 | 0 | 0 | 239500 |  | 0 | 0 | 239500 | 15d | 0 | 0 | 0 | 239500 | 0% | Not Started | 0 | 0
15 | Calculation of Labour Requirements | 2019-03-26 08:00 | 2019-04-08 17:00 | 10d | Engineers;Workers[0.40 #1] | 163500 | 0 | 0 | 0 | 163500 |  | 0 | 0 | 163500 | 10d | 0 | 0 | 0 | 163500 | 0% | Not Started | 0 | 0
16 | Calculation of Factory Capacity | 2019-03-12 08:00 | 2019-04-08 17:00 | 20d | Workers[0.20 #1];Consultant | 839000 | 0 | 0 | 0 | 839000 |  | 0 | 0 | 839000 | 20d | 0 | 0 | 0 | 839000 | 0% | Not Started | 0 | 0
29 | Productivity Analysis | 2019-04-09 08:00 | 2019-06-10 17:00 | 45d |  |  | 0 |  |  | 850000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | Creation the Line of Balance for the Landing Gear System and its Level 1 Sub-Assemblies | 2019-04-09 08:00 | 2019-05-06 17:00 | 20d | Workers[0.20 #1];The Graduates | 439000 | 0 | 0 | 0 | 439000 |  | 0 | 0 | 439000 | 20d | 0 | 0 | 0 | 439000 | 0% | Not Started | 0 | 0
19 | Defining implication of this MPS on the capacity of the factory | 2019-05-07 08:00 | 2019-05-20 17:00 | 10d | Workers[0.60 #1] | 54000 | 0 | 0 | 0 | 54000 |  | 0 | 0 | 54000 | 10d | 0 | 0 | 0 | 54000 | 0% | Not Started | 0 | 0
20 | Assisting of line of balance in solution providing for problems | 2019-05-21 08:00 | 2019-06-10 17:00 | 15d | Workers[0.40 #1];The Graduates | 357000 | 0 | 0 | 0 | 357000 |  | 0 | 0 | 357000 | 15d | 0 | 0 | 0 | 357000 | 0% | Not Started | 0 | 0
30 | Start to Production | 2019-06-11 08:00 | 2019-10-07 17:00 | 85d |  |  | 0 |  |  | 2075500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Identifying Production Site | 2019-06-11 08:00 | 2019-07-15 17:00 | 25d | Consultant;Workers[0.40 #1] | 1089000 | 0 | 0 | 0 | 1089000 |  | 0 | 0 | 1089000 | 25d | 0 | 0 | 0 | 1089000 | 0% | Not Started | 0 | 0
23 | Supplier Selection | 2019-07-02 08:00 | 2019-07-15 17:00 | 10d | Engineers;Workers[0.60 #1] | 181500 | 0 | 0 | 0 | 181500 |  | 0 | 0 | 181500 | 10d | 0 | 0 | 0 | 181500 | 0% | Not Started | 0 | 0
24 | Ordering Machines and Raw Materials | 2019-07-16 08:00 | 2019-09-16 17:00 | 45d | Workers | 370000 | 0 | 0 | 0 | 370000 |  | 0 | 0 | 370000 | 45d | 0 | 0 | 0 | 370000 | 0% | Not Started | 0 | 0
25 | Manufacturing Trials | 2019-09-17 08:00 | 2019-10-07 17:00 | 15d | Workers;The Graduates | 435000 | 0 | 0 | 0 | 435000 |  | 0 | 0 | 435000 | 15d | 0 | 0 | 0 | 435000 | 0% | Not Started | 0 | 0
33 | Finish | 2019-10-07 17:00 | 2019-10-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP5
| TP Status Date | 2018-10-29 17:00 |  | TP Name | 29.10.2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Landing Gear Project | 2018-07-17 08:00 | 2019-10-07 17:00 | 320d |  |  | 0 |  |  | 11562500 |  | 75d | [5 empty] | 3689500 |  | 36.29% |  | 4196017.1032 | 3862500
31 | Feasibilty Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d |  |  | 0 |  |  | 1805000 |  | 36d 6h | [5 empty] | 1475000 |  | 100% |  | 1805000 | 1805000
1 | Feasiblity Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d | Consultant | 1805000 | 0 | 0 | 0 | 1805000 | 2018-07-17 08:00 | 36d 6h | 1475000 | 0 | 0 | 0 | 0 | 1475000 | 0 | 100% | Finished | 1805000 | 1805000
26 | Market Research | 2018-09-18 08:00 | 2018-10-29 17:00 | 30d |  |  | 0 |  |  | 2057500 |  | 29d 2h | [5 empty] | 1849500 |  | 100% |  | 2057500 | 2057500
3 | Specifying the size of Single and Twin engined light aircrafts replacement in the market | 2018-09-18 08:00 | 2018-10-01 17:00 | 10d | Consultant;Engineers | 532500 | 0 | 0 | 0 | 532500 | 2018-09-05 15:00 | 14d 5h | 773000 | 0 | 0 | 0 | 0 | 773000 | 0 | 100% | Finished | 532500 | 532500
4 | Calculation of the potential annual demand volumes for landing gear struts according to each of the different retail prices | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Consultant;Engineers | 792500 | 0 | 0 | 0 | 792500 | 2018-09-26 11:00 | 10d 2h | 545500 | 0 | 0 | 0 | 0 | 545500 | 0 | 100% | Finished | 792500 | 792500
5 | Calculation of the annual sales volumes actually achievable, taking into account the maximum capacity of the factory set by the directors | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Engineers | 187500 | 0 | 0 | 0 | 187500 | 2018-09-26 11:00 | 8d 4h | 109500 | 0 | 0 | 0 | 0 | 109500 | 0 | 100% | Finished | 187500 | 187500
6 | Calculation of the total annual trade sales revenues and fixed/variable/total costs for each retail | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-10 14:00 | 4d 3h | 240000 | 0 | 0 | 0 | 0 | 240000 | 0 | 100% | Finished | 272500 | 272500
7 | Calculation of the-trade price at which the company should sell at to generate the maximum profit | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-08 16:00 | 3d 2h | 181500 | 0 | 0 | 0 | 0 | 181500 | 0 | 100% | Finished | 272500 | 272500
27 | Business Plan, Financial Analysis, and Team Selection | 2018-10-30 08:00 | 2019-01-07 17:00 | 50d |  |  | 0 |  |  | 2615000 |  | 9d | [5 empty] | 365000 |  | 12.75% |  | 333517.1032 | 0
9 | Preparation of Business Plan | 2018-10-30 08:00 | 2018-12-10 17:00 | 30d | Consultant | 1205000 | 0 | 0 | 0 | 1205000 | 2018-10-17 08:00 | 9d | 365000 | 955000 | 23d 7h | 0 | 0 | 365000 | 955000 | 27.38% | Started | 333517.1032 | 0
10 | Financial Analysis | 2018-12-18 08:00 | 2019-01-07 17:00 | 15d | Consultant | 605000 | 0 | 0 | 0 | 605000 |  | 0 | 0 | 605000 | 15d | 0 | 0 | 0 | 605000 | 0% | Not Started | 0 | 0
11 | Team Selection (Recruitment of Management Team and Staff) | 2018-12-11 08:00 | 2019-01-07 17:00 | 20d | Consultant | 805000 | 0 | 0 | 0 | 805000 |  | 0 | 0 | 805000 | 20d | 0 | 0 | 0 | 805000 | 0% | Not Started | 0 | 0
28 | Process Analysis | 2019-01-08 08:00 | 2019-04-08 17:00 | 65d |  |  | 0 |  |  | 2159500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
13 | Preparation of Bill of Materials (BOM) file | 2019-01-08 08:00 | 2019-03-11 17:00 | 45d | Engineers;Workers | 917500 | 0 | 0 | 0 | 917500 |  | 0 | 0 | 917500 | 45d | 0 | 0 | 0 | 917500 | 0% | Not Started | 0 | 0
14 | Calculation of Machine Requirements | 2019-03-19 08:00 | 2019-04-08 17:00 | 15d | Engineers;Workers[0.40 #1] | 239500 | 0 | 0 | 0 | 239500 |  | 0 | 0 | 239500 | 15d | 0 | 0 | 0 | 239500 | 0% | Not Started | 0 | 0
15 | Calculation of Labour Requirements | 2019-03-26 08:00 | 2019-04-08 17:00 | 10d | Engineers;Workers[0.40 #1] | 163500 | 0 | 0 | 0 | 163500 |  | 0 | 0 | 163500 | 10d | 0 | 0 | 0 | 163500 | 0% | Not Started | 0 | 0
16 | Calculation of Factory Capacity | 2019-03-12 08:00 | 2019-04-08 17:00 | 20d | Workers[0.20 #1];Consultant | 839000 | 0 | 0 | 0 | 839000 |  | 0 | 0 | 839000 | 20d | 0 | 0 | 0 | 839000 | 0% | Not Started | 0 | 0
29 | Productivity Analysis | 2019-04-09 08:00 | 2019-06-10 17:00 | 45d |  |  | 0 |  |  | 850000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | Creation the Line of Balance for the Landing Gear System and its Level 1 Sub-Assemblies | 2019-04-09 08:00 | 2019-05-06 17:00 | 20d | Workers[0.20 #1];The Graduates | 439000 | 0 | 0 | 0 | 439000 |  | 0 | 0 | 439000 | 20d | 0 | 0 | 0 | 439000 | 0% | Not Started | 0 | 0
19 | Defining implication of this MPS on the capacity of the factory | 2019-05-07 08:00 | 2019-05-20 17:00 | 10d | Workers[0.60 #1] | 54000 | 0 | 0 | 0 | 54000 |  | 0 | 0 | 54000 | 10d | 0 | 0 | 0 | 54000 | 0% | Not Started | 0 | 0
20 | Assisting of line of balance in solution providing for problems | 2019-05-21 08:00 | 2019-06-10 17:00 | 15d | Workers[0.40 #1];The Graduates | 357000 | 0 | 0 | 0 | 357000 |  | 0 | 0 | 357000 | 15d | 0 | 0 | 0 | 357000 | 0% | Not Started | 0 | 0
30 | Start to Production | 2019-06-11 08:00 | 2019-10-07 17:00 | 85d |  |  | 0 |  |  | 2075500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Identifying Production Site | 2019-06-11 08:00 | 2019-07-15 17:00 | 25d | Consultant;Workers[0.40 #1] | 1089000 | 0 | 0 | 0 | 1089000 |  | 0 | 0 | 1089000 | 25d | 0 | 0 | 0 | 1089000 | 0% | Not Started | 0 | 0
23 | Supplier Selection | 2019-07-02 08:00 | 2019-07-15 17:00 | 10d | Engineers;Workers[0.60 #1] | 181500 | 0 | 0 | 0 | 181500 |  | 0 | 0 | 181500 | 10d | 0 | 0 | 0 | 181500 | 0% | Not Started | 0 | 0
24 | Ordering Machines and Raw Materials | 2019-07-16 08:00 | 2019-09-16 17:00 | 45d | Workers | 370000 | 0 | 0 | 0 | 370000 |  | 0 | 0 | 370000 | 45d | 0 | 0 | 0 | 370000 | 0% | Not Started | 0 | 0
25 | Manufacturing Trials | 2019-09-17 08:00 | 2019-10-07 17:00 | 15d | Workers;The Graduates | 435000 | 0 | 0 | 0 | 435000 |  | 0 | 0 | 435000 | 15d | 0 | 0 | 0 | 435000 | 0% | Not Started | 0 | 0
33 | Finish | 2019-10-07 17:00 | 2019-10-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP6
| TP Status Date | 2018-11-19 17:00 |  | TP Name | 19.11.2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Landing Gear Project | 2018-07-17 08:00 | 2019-10-07 17:00 | 320d |  |  | 0 |  |  | 11562500 |  | 90d | [5 empty] | 4289500 |  | 41.03% |  | 4743545.6562 | 4467500
31 | Feasibilty Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d |  |  | 0 |  |  | 1805000 |  | 36d 6h | [5 empty] | 1475000 |  | 100% |  | 1805000 | 1805000
1 | Feasiblity Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d | Consultant | 1805000 | 0 | 0 | 0 | 1805000 | 2018-07-17 08:00 | 36d 6h | 1475000 | 0 | 0 | 0 | 0 | 1475000 | 0 | 100% | Finished | 1805000 | 1805000
26 | Market Research | 2018-09-18 08:00 | 2018-10-29 17:00 | 30d |  |  | 0 |  |  | 2057500 |  | 29d 2h | [5 empty] | 1849500 |  | 100% |  | 2057500 | 2057500
3 | Specifying the size of Single and Twin engined light aircrafts replacement in the market | 2018-09-18 08:00 | 2018-10-01 17:00 | 10d | Consultant;Engineers | 532500 | 0 | 0 | 0 | 532500 | 2018-09-05 15:00 | 14d 5h | 773000 | 0 | 0 | 0 | 0 | 773000 | 0 | 100% | Finished | 532500 | 532500
4 | Calculation of the potential annual demand volumes for landing gear struts according to each of the different retail prices | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Consultant;Engineers | 792500 | 0 | 0 | 0 | 792500 | 2018-09-26 11:00 | 10d 2h | 545500 | 0 | 0 | 0 | 0 | 545500 | 0 | 100% | Finished | 792500 | 792500
5 | Calculation of the annual sales volumes actually achievable, taking into account the maximum capacity of the factory set by the directors | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Engineers | 187500 | 0 | 0 | 0 | 187500 | 2018-09-26 11:00 | 8d 4h | 109500 | 0 | 0 | 0 | 0 | 109500 | 0 | 100% | Finished | 187500 | 187500
6 | Calculation of the total annual trade sales revenues and fixed/variable/total costs for each retail | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-10 14:00 | 4d 3h | 240000 | 0 | 0 | 0 | 0 | 240000 | 0 | 100% | Finished | 272500 | 272500
7 | Calculation of the-trade price at which the company should sell at to generate the maximum profit | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-08 16:00 | 3d 2h | 181500 | 0 | 0 | 0 | 0 | 181500 | 0 | 100% | Finished | 272500 | 272500
27 | Business Plan, Financial Analysis, and Team Selection | 2018-10-30 08:00 | 2019-01-07 17:00 | 50d |  |  | 0 |  |  | 2615000 |  | 24d | [5 empty] | 965000 |  | 33.69% |  | 881045.6562 | 605000
9 | Preparation of Business Plan | 2018-10-30 08:00 | 2018-12-10 17:00 | 30d | Consultant | 1205000 | 0 | 0 | 0 | 1205000 | 2018-10-17 08:00 | 24d | 965000 | 355000 | 8d 7h | 0 | 0 | 965000 | 355000 | 73% | Started | 881045.6562 | 605000
10 | Financial Analysis | 2018-12-18 08:00 | 2019-01-07 17:00 | 15d | Consultant | 605000 | 0 | 0 | 0 | 605000 |  | 0 | 0 | 605000 | 15d | 0 | 0 | 0 | 605000 | 0% | Not Started | 0 | 0
11 | Team Selection (Recruitment of Management Team and Staff) | 2018-12-11 08:00 | 2019-01-07 17:00 | 20d | Consultant | 805000 | 0 | 0 | 0 | 805000 |  | 0 | 0 | 805000 | 20d | 0 | 0 | 0 | 805000 | 0% | Not Started | 0 | 0
28 | Process Analysis | 2019-01-08 08:00 | 2019-04-08 17:00 | 65d |  |  | 0 |  |  | 2159500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
13 | Preparation of Bill of Materials (BOM) file | 2019-01-08 08:00 | 2019-03-11 17:00 | 45d | Engineers;Workers | 917500 | 0 | 0 | 0 | 917500 |  | 0 | 0 | 917500 | 45d | 0 | 0 | 0 | 917500 | 0% | Not Started | 0 | 0
14 | Calculation of Machine Requirements | 2019-03-19 08:00 | 2019-04-08 17:00 | 15d | Engineers;Workers[0.40 #1] | 239500 | 0 | 0 | 0 | 239500 |  | 0 | 0 | 239500 | 15d | 0 | 0 | 0 | 239500 | 0% | Not Started | 0 | 0
15 | Calculation of Labour Requirements | 2019-03-26 08:00 | 2019-04-08 17:00 | 10d | Engineers;Workers[0.40 #1] | 163500 | 0 | 0 | 0 | 163500 |  | 0 | 0 | 163500 | 10d | 0 | 0 | 0 | 163500 | 0% | Not Started | 0 | 0
16 | Calculation of Factory Capacity | 2019-03-12 08:00 | 2019-04-08 17:00 | 20d | Workers[0.20 #1];Consultant | 839000 | 0 | 0 | 0 | 839000 |  | 0 | 0 | 839000 | 20d | 0 | 0 | 0 | 839000 | 0% | Not Started | 0 | 0
29 | Productivity Analysis | 2019-04-09 08:00 | 2019-06-10 17:00 | 45d |  |  | 0 |  |  | 850000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | Creation the Line of Balance for the Landing Gear System and its Level 1 Sub-Assemblies | 2019-04-09 08:00 | 2019-05-06 17:00 | 20d | Workers[0.20 #1];The Graduates | 439000 | 0 | 0 | 0 | 439000 |  | 0 | 0 | 439000 | 20d | 0 | 0 | 0 | 439000 | 0% | Not Started | 0 | 0
19 | Defining implication of this MPS on the capacity of the factory | 2019-05-07 08:00 | 2019-05-20 17:00 | 10d | Workers[0.60 #1] | 54000 | 0 | 0 | 0 | 54000 |  | 0 | 0 | 54000 | 10d | 0 | 0 | 0 | 54000 | 0% | Not Started | 0 | 0
20 | Assisting of line of balance in solution providing for problems | 2019-05-21 08:00 | 2019-06-10 17:00 | 15d | Workers[0.40 #1];The Graduates | 357000 | 0 | 0 | 0 | 357000 |  | 0 | 0 | 357000 | 15d | 0 | 0 | 0 | 357000 | 0% | Not Started | 0 | 0
30 | Start to Production | 2019-06-11 08:00 | 2019-10-07 17:00 | 85d |  |  | 0 |  |  | 2075500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Identifying Production Site | 2019-06-11 08:00 | 2019-07-15 17:00 | 25d | Consultant;Workers[0.40 #1] | 1089000 | 0 | 0 | 0 | 1089000 |  | 0 | 0 | 1089000 | 25d | 0 | 0 | 0 | 1089000 | 0% | Not Started | 0 | 0
23 | Supplier Selection | 2019-07-02 08:00 | 2019-07-15 17:00 | 10d | Engineers;Workers[0.60 #1] | 181500 | 0 | 0 | 0 | 181500 |  | 0 | 0 | 181500 | 10d | 0 | 0 | 0 | 181500 | 0% | Not Started | 0 | 0
24 | Ordering Machines and Raw Materials | 2019-07-16 08:00 | 2019-09-16 17:00 | 45d | Workers | 370000 | 0 | 0 | 0 | 370000 |  | 0 | 0 | 370000 | 45d | 0 | 0 | 0 | 370000 | 0% | Not Started | 0 | 0
25 | Manufacturing Trials | 2019-09-17 08:00 | 2019-10-07 17:00 | 15d | Workers;The Graduates | 435000 | 0 | 0 | 0 | 435000 |  | 0 | 0 | 435000 | 15d | 0 | 0 | 0 | 435000 | 0% | Not Started | 0 | 0
33 | Finish | 2019-10-07 17:00 | 2019-10-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP7
| TP Status Date | 2018-12-10 17:00 |  | TP Name | 10.12.2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Landing Gear Project | 2018-07-17 08:00 | 2019-10-07 17:00 | 320d |  |  | 0 |  |  | 11562500 |  | 105d | [5 empty] | 5144500 |  | 48.89% |  | 5653464.8919 | 5067500
31 | Feasibilty Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d |  |  | 0 |  |  | 1805000 |  | 36d 6h | [5 empty] | 1475000 |  | 100% |  | 1805000 | 1805000
1 | Feasiblity Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d | Consultant | 1805000 | 0 | 0 | 0 | 1805000 | 2018-07-17 08:00 | 36d 6h | 1475000 | 0 | 0 | 0 | 0 | 1475000 | 0 | 100% | Finished | 1805000 | 1805000
26 | Market Research | 2018-09-18 08:00 | 2018-10-29 17:00 | 30d |  |  | 0 |  |  | 2057500 |  | 29d 2h | [5 empty] | 1849500 |  | 100% |  | 2057500 | 2057500
3 | Specifying the size of Single and Twin engined light aircrafts replacement in the market | 2018-09-18 08:00 | 2018-10-01 17:00 | 10d | Consultant;Engineers | 532500 | 0 | 0 | 0 | 532500 | 2018-09-05 15:00 | 14d 5h | 773000 | 0 | 0 | 0 | 0 | 773000 | 0 | 100% | Finished | 532500 | 532500
4 | Calculation of the potential annual demand volumes for landing gear struts according to each of the different retail prices | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Consultant;Engineers | 792500 | 0 | 0 | 0 | 792500 | 2018-09-26 11:00 | 10d 2h | 545500 | 0 | 0 | 0 | 0 | 545500 | 0 | 100% | Finished | 792500 | 792500
5 | Calculation of the annual sales volumes actually achievable, taking into account the maximum capacity of the factory set by the directors | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Engineers | 187500 | 0 | 0 | 0 | 187500 | 2018-09-26 11:00 | 8d 4h | 109500 | 0 | 0 | 0 | 0 | 109500 | 0 | 100% | Finished | 187500 | 187500
6 | Calculation of the total annual trade sales revenues and fixed/variable/total costs for each retail | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-10 14:00 | 4d 3h | 240000 | 0 | 0 | 0 | 0 | 240000 | 0 | 100% | Finished | 272500 | 272500
7 | Calculation of the-trade price at which the company should sell at to generate the maximum profit | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-08 16:00 | 3d 2h | 181500 | 0 | 0 | 0 | 0 | 181500 | 0 | 100% | Finished | 272500 | 272500
27 | Business Plan, Financial Analysis, and Team Selection | 2018-10-30 08:00 | 2019-01-07 17:00 | 50d |  |  | 0 |  |  | 2615000 |  | 39d | [5 empty] | 1820000 |  | 68.49% |  | 1790964.8919 | 1205000
9 | Preparation of Business Plan | 2018-10-30 08:00 | 2018-12-10 17:00 | 30d | Consultant | 1205000 | 0 | 0 | 0 | 1205000 | 2018-10-17 08:00 | 32d 7h | 1320000 | 0 | 0 | 0 | 0 | 1320000 | 0 | 100% | Finished | 1205000 | 1205000
10 | Financial Analysis | 2018-12-18 08:00 | 2019-01-07 17:00 | 15d | Consultant | 605000 | 0 | 0 | 0 | 605000 | 2018-11-30 16:00 | 6d 1h | 250000 | 655000 | 16d 3h | 0 | 0 | 250000 | 655000 | 27.22% | Started | 168333.3325 | 0
11 | Team Selection (Recruitment of Management Team and Staff) | 2018-12-11 08:00 | 2019-01-07 17:00 | 20d | Consultant | 805000 | 0 | 0 | 0 | 805000 | 2018-11-30 16:00 | 6d 1h | 250000 | 230000 | 5d 6h | 0 | 0 | 250000 | 230000 | 51.58% | Started | 417631.5594 | 0
28 | Process Analysis | 2019-01-08 08:00 | 2019-04-08 17:00 | 65d |  |  | 0 |  |  | 2159500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
13 | Preparation of Bill of Materials (BOM) file | 2019-01-08 08:00 | 2019-03-11 17:00 | 45d | Engineers;Workers | 917500 | 0 | 0 | 0 | 917500 |  | 0 | 0 | 917500 | 45d | 0 | 0 | 0 | 917500 | 0% | Not Started | 0 | 0
14 | Calculation of Machine Requirements | 2019-03-19 08:00 | 2019-04-08 17:00 | 15d | Engineers;Workers[0.40 #1] | 239500 | 0 | 0 | 0 | 239500 |  | 0 | 0 | 239500 | 15d | 0 | 0 | 0 | 239500 | 0% | Not Started | 0 | 0
15 | Calculation of Labour Requirements | 2019-03-26 08:00 | 2019-04-08 17:00 | 10d | Engineers;Workers[0.40 #1] | 163500 | 0 | 0 | 0 | 163500 |  | 0 | 0 | 163500 | 10d | 0 | 0 | 0 | 163500 | 0% | Not Started | 0 | 0
16 | Calculation of Factory Capacity | 2019-03-12 08:00 | 2019-04-08 17:00 | 20d | Workers[0.20 #1];Consultant | 839000 | 0 | 0 | 0 | 839000 |  | 0 | 0 | 839000 | 20d | 0 | 0 | 0 | 839000 | 0% | Not Started | 0 | 0
29 | Productivity Analysis | 2019-04-09 08:00 | 2019-06-10 17:00 | 45d |  |  | 0 |  |  | 850000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | Creation the Line of Balance for the Landing Gear System and its Level 1 Sub-Assemblies | 2019-04-09 08:00 | 2019-05-06 17:00 | 20d | Workers[0.20 #1];The Graduates | 439000 | 0 | 0 | 0 | 439000 |  | 0 | 0 | 439000 | 20d | 0 | 0 | 0 | 439000 | 0% | Not Started | 0 | 0
19 | Defining implication of this MPS on the capacity of the factory | 2019-05-07 08:00 | 2019-05-20 17:00 | 10d | Workers[0.60 #1] | 54000 | 0 | 0 | 0 | 54000 |  | 0 | 0 | 54000 | 10d | 0 | 0 | 0 | 54000 | 0% | Not Started | 0 | 0
20 | Assisting of line of balance in solution providing for problems | 2019-05-21 08:00 | 2019-06-10 17:00 | 15d | Workers[0.40 #1];The Graduates | 357000 | 0 | 0 | 0 | 357000 |  | 0 | 0 | 357000 | 15d | 0 | 0 | 0 | 357000 | 0% | Not Started | 0 | 0
30 | Start to Production | 2019-06-11 08:00 | 2019-10-07 17:00 | 85d |  |  | 0 |  |  | 2075500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Identifying Production Site | 2019-06-11 08:00 | 2019-07-15 17:00 | 25d | Consultant;Workers[0.40 #1] | 1089000 | 0 | 0 | 0 | 1089000 |  | 0 | 0 | 1089000 | 25d | 0 | 0 | 0 | 1089000 | 0% | Not Started | 0 | 0
23 | Supplier Selection | 2019-07-02 08:00 | 2019-07-15 17:00 | 10d | Engineers;Workers[0.60 #1] | 181500 | 0 | 0 | 0 | 181500 |  | 0 | 0 | 181500 | 10d | 0 | 0 | 0 | 181500 | 0% | Not Started | 0 | 0
24 | Ordering Machines and Raw Materials | 2019-07-16 08:00 | 2019-09-16 17:00 | 45d | Workers | 370000 | 0 | 0 | 0 | 370000 |  | 0 | 0 | 370000 | 45d | 0 | 0 | 0 | 370000 | 0% | Not Started | 0 | 0
25 | Manufacturing Trials | 2019-09-17 08:00 | 2019-10-07 17:00 | 15d | Workers;The Graduates | 435000 | 0 | 0 | 0 | 435000 |  | 0 | 0 | 435000 | 15d | 0 | 0 | 0 | 435000 | 0% | Not Started | 0 | 0
33 | Finish | 2019-10-07 17:00 | 2019-10-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP8
| TP Status Date | 2018-12-31 17:00 |  | TP Name | 31.12.2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Landing Gear Project | 2018-07-17 08:00 | 2019-10-07 17:00 | 320d |  |  | 0 |  |  | 11562500 |  | 120d | [5 empty] | 5974500 |  | 55.7% |  | 6440833.3445 | 6077500
31 | Feasibilty Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d |  |  | 0 |  |  | 1805000 |  | 36d 6h | [5 empty] | 1475000 |  | 100% |  | 1805000 | 1805000
1 | Feasiblity Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d | Consultant | 1805000 | 0 | 0 | 0 | 1805000 | 2018-07-17 08:00 | 36d 6h | 1475000 | 0 | 0 | 0 | 0 | 1475000 | 0 | 100% | Finished | 1805000 | 1805000
26 | Market Research | 2018-09-18 08:00 | 2018-10-29 17:00 | 30d |  |  | 0 |  |  | 2057500 |  | 29d 2h | [5 empty] | 1849500 |  | 100% |  | 2057500 | 2057500
3 | Specifying the size of Single and Twin engined light aircrafts replacement in the market | 2018-09-18 08:00 | 2018-10-01 17:00 | 10d | Consultant;Engineers | 532500 | 0 | 0 | 0 | 532500 | 2018-09-05 15:00 | 14d 5h | 773000 | 0 | 0 | 0 | 0 | 773000 | 0 | 100% | Finished | 532500 | 532500
4 | Calculation of the potential annual demand volumes for landing gear struts according to each of the different retail prices | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Consultant;Engineers | 792500 | 0 | 0 | 0 | 792500 | 2018-09-26 11:00 | 10d 2h | 545500 | 0 | 0 | 0 | 0 | 545500 | 0 | 100% | Finished | 792500 | 792500
5 | Calculation of the annual sales volumes actually achievable, taking into account the maximum capacity of the factory set by the directors | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Engineers | 187500 | 0 | 0 | 0 | 187500 | 2018-09-26 11:00 | 8d 4h | 109500 | 0 | 0 | 0 | 0 | 109500 | 0 | 100% | Finished | 187500 | 187500
6 | Calculation of the total annual trade sales revenues and fixed/variable/total costs for each retail | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-10 14:00 | 4d 3h | 240000 | 0 | 0 | 0 | 0 | 240000 | 0 | 100% | Finished | 272500 | 272500
7 | Calculation of the-trade price at which the company should sell at to generate the maximum profit | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-08 16:00 | 3d 2h | 181500 | 0 | 0 | 0 | 0 | 181500 | 0 | 100% | Finished | 272500 | 272500
27 | Business Plan, Financial Analysis, and Team Selection | 2018-10-30 08:00 | 2019-01-07 17:00 | 50d |  |  | 0 |  |  | 2615000 |  | 54d | [5 empty] | 2650000 |  | 98.6% |  | 2578333.3445 | 2215000
9 | Preparation of Business Plan | 2018-10-30 08:00 | 2018-12-10 17:00 | 30d | Consultant | 1205000 | 0 | 0 | 0 | 1205000 | 2018-10-17 08:00 | 32d 7h | 1320000 | 0 | 0 | 0 | 0 | 1320000 | 0 | 100% | Finished | 1205000 | 1205000
10 | Financial Analysis | 2018-12-18 08:00 | 2019-01-07 17:00 | 15d | Consultant | 605000 | 0 | 0 | 0 | 605000 | 2018-11-30 16:00 | 21d 1h | 850000 | 55000 | 1d 3h | 0 | 0 | 850000 | 55000 | 93.89% | Started | 568333.3445 | 405000
11 | Team Selection (Recruitment of Management Team and Staff) | 2018-12-11 08:00 | 2019-01-07 17:00 | 20d | Consultant | 805000 | 0 | 0 | 0 | 805000 | 2018-11-30 16:00 | 11d 7h | 480000 | 0 | 0 | 0 | 0 | 480000 | 0 | 100% | Finished | 805000 | 605000
28 | Process Analysis | 2019-01-08 08:00 | 2019-04-08 17:00 | 65d |  |  | 0 |  |  | 2159500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
13 | Preparation of Bill of Materials (BOM) file | 2019-01-08 08:00 | 2019-03-11 17:00 | 45d | Engineers;Workers | 917500 | 0 | 0 | 0 | 917500 |  | 0 | 0 | 917500 | 45d | 0 | 0 | 0 | 917500 | 0% | Not Started | 0 | 0
14 | Calculation of Machine Requirements | 2019-03-19 08:00 | 2019-04-08 17:00 | 15d | Engineers;Workers[0.40 #1] | 239500 | 0 | 0 | 0 | 239500 |  | 0 | 0 | 239500 | 15d | 0 | 0 | 0 | 239500 | 0% | Not Started | 0 | 0
15 | Calculation of Labour Requirements | 2019-03-26 08:00 | 2019-04-08 17:00 | 10d | Engineers;Workers[0.40 #1] | 163500 | 0 | 0 | 0 | 163500 |  | 0 | 0 | 163500 | 10d | 0 | 0 | 0 | 163500 | 0% | Not Started | 0 | 0
16 | Calculation of Factory Capacity | 2019-03-12 08:00 | 2019-04-08 17:00 | 20d | Workers[0.20 #1];Consultant | 839000 | 0 | 0 | 0 | 839000 |  | 0 | 0 | 839000 | 20d | 0 | 0 | 0 | 839000 | 0% | Not Started | 0 | 0
29 | Productivity Analysis | 2019-04-09 08:00 | 2019-06-10 17:00 | 45d |  |  | 0 |  |  | 850000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | Creation the Line of Balance for the Landing Gear System and its Level 1 Sub-Assemblies | 2019-04-09 08:00 | 2019-05-06 17:00 | 20d | Workers[0.20 #1];The Graduates | 439000 | 0 | 0 | 0 | 439000 |  | 0 | 0 | 439000 | 20d | 0 | 0 | 0 | 439000 | 0% | Not Started | 0 | 0
19 | Defining implication of this MPS on the capacity of the factory | 2019-05-07 08:00 | 2019-05-20 17:00 | 10d | Workers[0.60 #1] | 54000 | 0 | 0 | 0 | 54000 |  | 0 | 0 | 54000 | 10d | 0 | 0 | 0 | 54000 | 0% | Not Started | 0 | 0
20 | Assisting of line of balance in solution providing for problems | 2019-05-21 08:00 | 2019-06-10 17:00 | 15d | Workers[0.40 #1];The Graduates | 357000 | 0 | 0 | 0 | 357000 |  | 0 | 0 | 357000 | 15d | 0 | 0 | 0 | 357000 | 0% | Not Started | 0 | 0
30 | Start to Production | 2019-06-11 08:00 | 2019-10-07 17:00 | 85d |  |  | 0 |  |  | 2075500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Identifying Production Site | 2019-06-11 08:00 | 2019-07-15 17:00 | 25d | Consultant;Workers[0.40 #1] | 1089000 | 0 | 0 | 0 | 1089000 |  | 0 | 0 | 1089000 | 25d | 0 | 0 | 0 | 1089000 | 0% | Not Started | 0 | 0
23 | Supplier Selection | 2019-07-02 08:00 | 2019-07-15 17:00 | 10d | Engineers;Workers[0.60 #1] | 181500 | 0 | 0 | 0 | 181500 |  | 0 | 0 | 181500 | 10d | 0 | 0 | 0 | 181500 | 0% | Not Started | 0 | 0
24 | Ordering Machines and Raw Materials | 2019-07-16 08:00 | 2019-09-16 17:00 | 45d | Workers | 370000 | 0 | 0 | 0 | 370000 |  | 0 | 0 | 370000 | 45d | 0 | 0 | 0 | 370000 | 0% | Not Started | 0 | 0
25 | Manufacturing Trials | 2019-09-17 08:00 | 2019-10-07 17:00 | 15d | Workers;The Graduates | 435000 | 0 | 0 | 0 | 435000 |  | 0 | 0 | 435000 | 15d | 0 | 0 | 0 | 435000 | 0% | Not Started | 0 | 0
33 | Finish | 2019-10-07 17:00 | 2019-10-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP9
| TP Status Date | 2019-01-21 17:00 |  | TP Name | 21.01.2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Landing Gear Project | 2018-07-17 08:00 | 2019-10-07 17:00 | 320d |  |  | 0 |  |  | 11562500 |  | 135d | [5 empty] | 6319500 |  | 60.31% |  | 6973536.6118 | 6695000
31 | Feasibilty Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d |  |  | 0 |  |  | 1805000 |  | 36d 6h | [5 empty] | 1475000 |  | 100% |  | 1805000 | 1805000
1 | Feasiblity Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d | Consultant | 1805000 | 0 | 0 | 0 | 1805000 | 2018-07-17 08:00 | 36d 6h | 1475000 | 0 | 0 | 0 | 0 | 1475000 | 0 | 100% | Finished | 1805000 | 1805000
26 | Market Research | 2018-09-18 08:00 | 2018-10-29 17:00 | 30d |  |  | 0 |  |  | 2057500 |  | 29d 2h | [5 empty] | 1849500 |  | 100% |  | 2057500 | 2057500
3 | Specifying the size of Single and Twin engined light aircrafts replacement in the market | 2018-09-18 08:00 | 2018-10-01 17:00 | 10d | Consultant;Engineers | 532500 | 0 | 0 | 0 | 532500 | 2018-09-05 15:00 | 14d 5h | 773000 | 0 | 0 | 0 | 0 | 773000 | 0 | 100% | Finished | 532500 | 532500
4 | Calculation of the potential annual demand volumes for landing gear struts according to each of the different retail prices | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Consultant;Engineers | 792500 | 0 | 0 | 0 | 792500 | 2018-09-26 11:00 | 10d 2h | 545500 | 0 | 0 | 0 | 0 | 545500 | 0 | 100% | Finished | 792500 | 792500
5 | Calculation of the annual sales volumes actually achievable, taking into account the maximum capacity of the factory set by the directors | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Engineers | 187500 | 0 | 0 | 0 | 187500 | 2018-09-26 11:00 | 8d 4h | 109500 | 0 | 0 | 0 | 0 | 109500 | 0 | 100% | Finished | 187500 | 187500
6 | Calculation of the total annual trade sales revenues and fixed/variable/total costs for each retail | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-10 14:00 | 4d 3h | 240000 | 0 | 0 | 0 | 0 | 240000 | 0 | 100% | Finished | 272500 | 272500
7 | Calculation of the-trade price at which the company should sell at to generate the maximum profit | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-08 16:00 | 3d 2h | 181500 | 0 | 0 | 0 | 0 | 181500 | 0 | 100% | Finished | 272500 | 272500
27 | Business Plan, Financial Analysis, and Team Selection | 2018-10-30 08:00 | 2019-01-07 17:00 | 50d |  |  | 0 |  |  | 2615000 |  | 55d 3h | [5 empty] | 2705000 |  | 100% |  | 2615000 | 2615000
9 | Preparation of Business Plan | 2018-10-30 08:00 | 2018-12-10 17:00 | 30d | Consultant | 1205000 | 0 | 0 | 0 | 1205000 | 2018-10-17 08:00 | 32d 7h | 1320000 | 0 | 0 | 0 | 0 | 1320000 | 0 | 100% | Finished | 1205000 | 1205000
10 | Financial Analysis | 2018-12-18 08:00 | 2019-01-07 17:00 | 15d | Consultant | 605000 | 0 | 0 | 0 | 605000 | 2018-11-30 16:00 | 22d 4h | 905000 | 0 | 0 | 0 | 0 | 905000 | 0 | 100% | Finished | 605000 | 605000
11 | Team Selection (Recruitment of Management Team and Staff) | 2018-12-11 08:00 | 2019-01-07 17:00 | 20d | Consultant | 805000 | 0 | 0 | 0 | 805000 | 2018-11-30 16:00 | 11d 7h | 480000 | 0 | 0 | 0 | 0 | 480000 | 0 | 100% | Finished | 805000 | 805000
28 | Process Analysis | 2019-01-08 08:00 | 2019-04-08 17:00 | 65d |  |  | 0 |  |  | 2159500 |  | 13d 5h | [5 empty] | 290000 |  | 22.97% |  | 496036.6118 | 217500
13 | Preparation of Bill of Materials (BOM) file | 2019-01-08 08:00 | 2019-03-11 17:00 | 45d | Engineers;Workers | 917500 | 0 | 0 | 0 | 917500 | 2019-01-02 11:00 | 13d 5h | 290000 | 240000 | 12d | 0 | 0 | 290000 | 240000 | 53.17% | Started | 496036.6118 | 217500
14 | Calculation of Machine Requirements | 2019-03-19 08:00 | 2019-04-08 17:00 | 15d | Engineers;Workers[0.40 #1] | 239500 | 0 | 0 | 0 | 239500 |  | 0 | 0 | 239500 | 15d | 0 | 0 | 0 | 239500 | 0% | Not Started | 0 | 0
15 | Calculation of Labour Requirements | 2019-03-26 08:00 | 2019-04-08 17:00 | 10d | Engineers;Workers[0.40 #1] | 163500 | 0 | 0 | 0 | 163500 |  | 0 | 0 | 163500 | 10d | 0 | 0 | 0 | 163500 | 0% | Not Started | 0 | 0
16 | Calculation of Factory Capacity | 2019-03-12 08:00 | 2019-04-08 17:00 | 20d | Workers[0.20 #1];Consultant | 839000 | 0 | 0 | 0 | 839000 |  | 0 | 0 | 839000 | 20d | 0 | 0 | 0 | 839000 | 0% | Not Started | 0 | 0
29 | Productivity Analysis | 2019-04-09 08:00 | 2019-06-10 17:00 | 45d |  |  | 0 |  |  | 850000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | Creation the Line of Balance for the Landing Gear System and its Level 1 Sub-Assemblies | 2019-04-09 08:00 | 2019-05-06 17:00 | 20d | Workers[0.20 #1];The Graduates | 439000 | 0 | 0 | 0 | 439000 |  | 0 | 0 | 439000 | 20d | 0 | 0 | 0 | 439000 | 0% | Not Started | 0 | 0
19 | Defining implication of this MPS on the capacity of the factory | 2019-05-07 08:00 | 2019-05-20 17:00 | 10d | Workers[0.60 #1] | 54000 | 0 | 0 | 0 | 54000 |  | 0 | 0 | 54000 | 10d | 0 | 0 | 0 | 54000 | 0% | Not Started | 0 | 0
20 | Assisting of line of balance in solution providing for problems | 2019-05-21 08:00 | 2019-06-10 17:00 | 15d | Workers[0.40 #1];The Graduates | 357000 | 0 | 0 | 0 | 357000 |  | 0 | 0 | 357000 | 15d | 0 | 0 | 0 | 357000 | 0% | Not Started | 0 | 0
30 | Start to Production | 2019-06-11 08:00 | 2019-10-07 17:00 | 85d |  |  | 0 |  |  | 2075500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Identifying Production Site | 2019-06-11 08:00 | 2019-07-15 17:00 | 25d | Consultant;Workers[0.40 #1] | 1089000 | 0 | 0 | 0 | 1089000 |  | 0 | 0 | 1089000 | 25d | 0 | 0 | 0 | 1089000 | 0% | Not Started | 0 | 0
23 | Supplier Selection | 2019-07-02 08:00 | 2019-07-15 17:00 | 10d | Engineers;Workers[0.60 #1] | 181500 | 0 | 0 | 0 | 181500 |  | 0 | 0 | 181500 | 10d | 0 | 0 | 0 | 181500 | 0% | Not Started | 0 | 0
24 | Ordering Machines and Raw Materials | 2019-07-16 08:00 | 2019-09-16 17:00 | 45d | Workers | 370000 | 0 | 0 | 0 | 370000 |  | 0 | 0 | 370000 | 45d | 0 | 0 | 0 | 370000 | 0% | Not Started | 0 | 0
25 | Manufacturing Trials | 2019-09-17 08:00 | 2019-10-07 17:00 | 15d | Workers;The Graduates | 435000 | 0 | 0 | 0 | 435000 |  | 0 | 0 | 435000 | 15d | 0 | 0 | 0 | 435000 | 0% | Not Started | 0 | 0
33 | Finish | 2019-10-07 17:00 | 2019-10-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP10
| TP Status Date | 2019-02-11 17:00 |  | TP Name | 11.02.2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Landing Gear Project | 2018-07-17 08:00 | 2019-10-07 17:00 | 320d |  |  | 0 |  |  | 11562500 |  | 150d | [5 empty] | 6805500 |  | 66.62% |  | 7702875.6334 | 6995000
31 | Feasibilty Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d |  |  | 0 |  |  | 1805000 |  | 36d 6h | [5 empty] | 1475000 |  | 100% |  | 1805000 | 1805000
1 | Feasiblity Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d | Consultant | 1805000 | 0 | 0 | 0 | 1805000 | 2018-07-17 08:00 | 36d 6h | 1475000 | 0 | 0 | 0 | 0 | 1475000 | 0 | 100% | Finished | 1805000 | 1805000
26 | Market Research | 2018-09-18 08:00 | 2018-10-29 17:00 | 30d |  |  | 0 |  |  | 2057500 |  | 29d 2h | [5 empty] | 1849500 |  | 100% |  | 2057500 | 2057500
3 | Specifying the size of Single and Twin engined light aircrafts replacement in the market | 2018-09-18 08:00 | 2018-10-01 17:00 | 10d | Consultant;Engineers | 532500 | 0 | 0 | 0 | 532500 | 2018-09-05 15:00 | 14d 5h | 773000 | 0 | 0 | 0 | 0 | 773000 | 0 | 100% | Finished | 532500 | 532500
4 | Calculation of the potential annual demand volumes for landing gear struts according to each of the different retail prices | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Consultant;Engineers | 792500 | 0 | 0 | 0 | 792500 | 2018-09-26 11:00 | 10d 2h | 545500 | 0 | 0 | 0 | 0 | 545500 | 0 | 100% | Finished | 792500 | 792500
5 | Calculation of the annual sales volumes actually achievable, taking into account the maximum capacity of the factory set by the directors | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Engineers | 187500 | 0 | 0 | 0 | 187500 | 2018-09-26 11:00 | 8d 4h | 109500 | 0 | 0 | 0 | 0 | 109500 | 0 | 100% | Finished | 187500 | 187500
6 | Calculation of the total annual trade sales revenues and fixed/variable/total costs for each retail | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-10 14:00 | 4d 3h | 240000 | 0 | 0 | 0 | 0 | 240000 | 0 | 100% | Finished | 272500 | 272500
7 | Calculation of the-trade price at which the company should sell at to generate the maximum profit | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-08 16:00 | 3d 2h | 181500 | 0 | 0 | 0 | 0 | 181500 | 0 | 100% | Finished | 272500 | 272500
27 | Business Plan, Financial Analysis, and Team Selection | 2018-10-30 08:00 | 2019-01-07 17:00 | 50d |  |  | 0 |  |  | 2615000 |  | 55d 3h | [5 empty] | 2705000 |  | 100% |  | 2615000 | 2615000
9 | Preparation of Business Plan | 2018-10-30 08:00 | 2018-12-10 17:00 | 30d | Consultant | 1205000 | 0 | 0 | 0 | 1205000 | 2018-10-17 08:00 | 32d 7h | 1320000 | 0 | 0 | 0 | 0 | 1320000 | 0 | 100% | Finished | 1205000 | 1205000
10 | Financial Analysis | 2018-12-18 08:00 | 2019-01-07 17:00 | 15d | Consultant | 605000 | 0 | 0 | 0 | 605000 | 2018-11-30 16:00 | 22d 4h | 905000 | 0 | 0 | 0 | 0 | 905000 | 0 | 100% | Finished | 605000 | 605000
11 | Team Selection (Recruitment of Management Team and Staff) | 2018-12-11 08:00 | 2019-01-07 17:00 | 20d | Consultant | 805000 | 0 | 0 | 0 | 805000 | 2018-11-30 16:00 | 11d 7h | 480000 | 0 | 0 | 0 | 0 | 480000 | 0 | 100% | Finished | 805000 | 805000
28 | Process Analysis | 2019-01-08 08:00 | 2019-04-08 17:00 | 65d |  |  | 0 |  |  | 2159500 |  | 28d 5h | [5 empty] | 776000 |  | 56.74% |  | 1225375.6334 | 517500
13 | Preparation of Bill of Materials (BOM) file | 2019-01-08 08:00 | 2019-03-11 17:00 | 45d | Engineers;Workers | 917500 | 0 | 0 | 0 | 917500 | 2019-01-02 11:00 | 25d 5h | 530000 | 0 | 0 | 0 | 0 | 530000 | 0 | 100% | Finished | 917500 | 517500
14 | Calculation of Machine Requirements | 2019-03-19 08:00 | 2019-04-08 17:00 | 15d | Engineers;Workers[0.40 #1] | 239500 | 0 | 0 | 0 | 239500 | 2019-02-07 08:00 | 3d | 57100 | 125400 | 8d 2h | 0 | 0 | 57100 | 125400 | 26.67% | Started | 72300.0032 | 0
15 | Calculation of Labour Requirements | 2019-03-26 08:00 | 2019-04-08 17:00 | 10d | Engineers;Workers[0.40 #1] | 163500 | 0 | 0 | 0 | 163500 | 2019-02-07 08:00 | 3d | 57100 | 36100 | 2d 3h | 0 | 0 | 57100 | 36100 | 55.81% | Started | 96337.2135 | 0
16 | Calculation of Factory Capacity | 2019-03-12 08:00 | 2019-04-08 17:00 | 20d | Workers[0.20 #1];Consultant | 839000 | 0 | 0 | 0 | 839000 | 2019-02-07 08:00 | 3d | 131800 | 660400 | 15d 7h | 0 | 0 | 131800 | 660400 | 15.89% | Started | 139238.4167 | 0
29 | Productivity Analysis | 2019-04-09 08:00 | 2019-06-10 17:00 | 45d |  |  | 0 |  |  | 850000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | Creation the Line of Balance for the Landing Gear System and its Level 1 Sub-Assemblies | 2019-04-09 08:00 | 2019-05-06 17:00 | 20d | Workers[0.20 #1];The Graduates | 439000 | 0 | 0 | 0 | 439000 |  | 0 | 0 | 439000 | 20d | 0 | 0 | 0 | 439000 | 0% | Not Started | 0 | 0
19 | Defining implication of this MPS on the capacity of the factory | 2019-05-07 08:00 | 2019-05-20 17:00 | 10d | Workers[0.60 #1] | 54000 | 0 | 0 | 0 | 54000 |  | 0 | 0 | 54000 | 10d | 0 | 0 | 0 | 54000 | 0% | Not Started | 0 | 0
20 | Assisting of line of balance in solution providing for problems | 2019-05-21 08:00 | 2019-06-10 17:00 | 15d | Workers[0.40 #1];The Graduates | 357000 | 0 | 0 | 0 | 357000 |  | 0 | 0 | 357000 | 15d | 0 | 0 | 0 | 357000 | 0% | Not Started | 0 | 0
30 | Start to Production | 2019-06-11 08:00 | 2019-10-07 17:00 | 85d |  |  | 0 |  |  | 2075500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Identifying Production Site | 2019-06-11 08:00 | 2019-07-15 17:00 | 25d | Consultant;Workers[0.40 #1] | 1089000 | 0 | 0 | 0 | 1089000 |  | 0 | 0 | 1089000 | 25d | 0 | 0 | 0 | 1089000 | 0% | Not Started | 0 | 0
23 | Supplier Selection | 2019-07-02 08:00 | 2019-07-15 17:00 | 10d | Engineers;Workers[0.60 #1] | 181500 | 0 | 0 | 0 | 181500 |  | 0 | 0 | 181500 | 10d | 0 | 0 | 0 | 181500 | 0% | Not Started | 0 | 0
24 | Ordering Machines and Raw Materials | 2019-07-16 08:00 | 2019-09-16 17:00 | 45d | Workers | 370000 | 0 | 0 | 0 | 370000 |  | 0 | 0 | 370000 | 45d | 0 | 0 | 0 | 370000 | 0% | Not Started | 0 | 0
25 | Manufacturing Trials | 2019-09-17 08:00 | 2019-10-07 17:00 | 15d | Workers;The Graduates | 435000 | 0 | 0 | 0 | 435000 |  | 0 | 0 | 435000 | 15d | 0 | 0 | 0 | 435000 | 0% | Not Started | 0 | 0
33 | Finish | 2019-10-07 17:00 | 2019-10-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP11
| TP Status Date | 2019-03-04 17:00 |  | TP Name | 4.03.2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Landing Gear Project | 2018-07-17 08:00 | 2019-10-07 17:00 | 320d |  |  | 0 |  |  | 11562500 |  | 165d | [5 empty] | 7591000 |  | 74.36% |  | 8598430.4504 | 7295000
31 | Feasibilty Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d |  |  | 0 |  |  | 1805000 |  | 36d 6h | [5 empty] | 1475000 |  | 100% |  | 1805000 | 1805000
1 | Feasiblity Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d | Consultant | 1805000 | 0 | 0 | 0 | 1805000 | 2018-07-17 08:00 | 36d 6h | 1475000 | 0 | 0 | 0 | 0 | 1475000 | 0 | 100% | Finished | 1805000 | 1805000
26 | Market Research | 2018-09-18 08:00 | 2018-10-29 17:00 | 30d |  |  | 0 |  |  | 2057500 |  | 29d 2h | [5 empty] | 1849500 |  | 100% |  | 2057500 | 2057500
3 | Specifying the size of Single and Twin engined light aircrafts replacement in the market | 2018-09-18 08:00 | 2018-10-01 17:00 | 10d | Consultant;Engineers | 532500 | 0 | 0 | 0 | 532500 | 2018-09-05 15:00 | 14d 5h | 773000 | 0 | 0 | 0 | 0 | 773000 | 0 | 100% | Finished | 532500 | 532500
4 | Calculation of the potential annual demand volumes for landing gear struts according to each of the different retail prices | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Consultant;Engineers | 792500 | 0 | 0 | 0 | 792500 | 2018-09-26 11:00 | 10d 2h | 545500 | 0 | 0 | 0 | 0 | 545500 | 0 | 100% | Finished | 792500 | 792500
5 | Calculation of the annual sales volumes actually achievable, taking into account the maximum capacity of the factory set by the directors | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Engineers | 187500 | 0 | 0 | 0 | 187500 | 2018-09-26 11:00 | 8d 4h | 109500 | 0 | 0 | 0 | 0 | 109500 | 0 | 100% | Finished | 187500 | 187500
6 | Calculation of the total annual trade sales revenues and fixed/variable/total costs for each retail | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-10 14:00 | 4d 3h | 240000 | 0 | 0 | 0 | 0 | 240000 | 0 | 100% | Finished | 272500 | 272500
7 | Calculation of the-trade price at which the company should sell at to generate the maximum profit | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-08 16:00 | 3d 2h | 181500 | 0 | 0 | 0 | 0 | 181500 | 0 | 100% | Finished | 272500 | 272500
27 | Business Plan, Financial Analysis, and Team Selection | 2018-10-30 08:00 | 2019-01-07 17:00 | 50d |  |  | 0 |  |  | 2615000 |  | 55d 3h | [5 empty] | 2705000 |  | 100% |  | 2615000 | 2615000
9 | Preparation of Business Plan | 2018-10-30 08:00 | 2018-12-10 17:00 | 30d | Consultant | 1205000 | 0 | 0 | 0 | 1205000 | 2018-10-17 08:00 | 32d 7h | 1320000 | 0 | 0 | 0 | 0 | 1320000 | 0 | 100% | Finished | 1205000 | 1205000
10 | Financial Analysis | 2018-12-18 08:00 | 2019-01-07 17:00 | 15d | Consultant | 605000 | 0 | 0 | 0 | 605000 | 2018-11-30 16:00 | 22d 4h | 905000 | 0 | 0 | 0 | 0 | 905000 | 0 | 100% | Finished | 605000 | 605000
11 | Team Selection (Recruitment of Management Team and Staff) | 2018-12-11 08:00 | 2019-01-07 17:00 | 20d | Consultant | 805000 | 0 | 0 | 0 | 805000 | 2018-11-30 16:00 | 11d 7h | 480000 | 0 | 0 | 0 | 0 | 480000 | 0 | 100% | Finished | 805000 | 805000
28 | Process Analysis | 2019-01-08 08:00 | 2019-04-08 17:00 | 65d |  |  | 0 |  |  | 2159500 |  | 43d 5h | [5 empty] | 1561500 |  | 98.21% |  | 2120930.4504 | 817500
13 | Preparation of Bill of Materials (BOM) file | 2019-01-08 08:00 | 2019-03-11 17:00 | 45d | Engineers;Workers | 917500 | 0 | 0 | 0 | 917500 | 2019-01-02 11:00 | 25d 5h | 530000 | 0 | 0 | 0 | 0 | 530000 | 0 | 100% | Finished | 917500 | 817500
14 | Calculation of Machine Requirements | 2019-03-19 08:00 | 2019-04-08 17:00 | 15d | Engineers;Workers[0.40 #1] | 239500 | 0 | 0 | 0 | 239500 | 2019-02-07 08:00 | 11d 2h | 182500 | 0 | 0 | 0 | 0 | 182500 | 0 | 100% | Finished | 239500 | 0
15 | Calculation of Labour Requirements | 2019-03-26 08:00 | 2019-04-08 17:00 | 10d | Engineers;Workers[0.40 #1] | 163500 | 0 | 0 | 0 | 163500 | 2019-02-07 08:00 | 5d 3h | 93200 | 0 | 0 | 0 | 0 | 93200 | 0 | 100% | Finished | 163500 | 0
16 | Calculation of Factory Capacity | 2019-03-12 08:00 | 2019-04-08 17:00 | 20d | Workers[0.20 #1];Consultant | 839000 | 0 | 0 | 0 | 839000 | 2019-02-07 08:00 | 18d | 755800 | 36400 | 7h | 0 | 0 | 755800 | 36400 | 95.36% | Started | 800430.4504 | 0
29 | Productivity Analysis | 2019-04-09 08:00 | 2019-06-10 17:00 | 45d |  |  | 0 |  |  | 850000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | Creation the Line of Balance for the Landing Gear System and its Level 1 Sub-Assemblies | 2019-04-09 08:00 | 2019-05-06 17:00 | 20d | Workers[0.20 #1];The Graduates | 439000 | 0 | 0 | 0 | 439000 |  | 0 | 0 | 439000 | 20d | 0 | 0 | 0 | 439000 | 0% | Not Started | 0 | 0
19 | Defining implication of this MPS on the capacity of the factory | 2019-05-07 08:00 | 2019-05-20 17:00 | 10d | Workers[0.60 #1] | 54000 | 0 | 0 | 0 | 54000 |  | 0 | 0 | 54000 | 10d | 0 | 0 | 0 | 54000 | 0% | Not Started | 0 | 0
20 | Assisting of line of balance in solution providing for problems | 2019-05-21 08:00 | 2019-06-10 17:00 | 15d | Workers[0.40 #1];The Graduates | 357000 | 0 | 0 | 0 | 357000 |  | 0 | 0 | 357000 | 15d | 0 | 0 | 0 | 357000 | 0% | Not Started | 0 | 0
30 | Start to Production | 2019-06-11 08:00 | 2019-10-07 17:00 | 85d |  |  | 0 |  |  | 2075500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Identifying Production Site | 2019-06-11 08:00 | 2019-07-15 17:00 | 25d | Consultant;Workers[0.40 #1] | 1089000 | 0 | 0 | 0 | 1089000 |  | 0 | 0 | 1089000 | 25d | 0 | 0 | 0 | 1089000 | 0% | Not Started | 0 | 0
23 | Supplier Selection | 2019-07-02 08:00 | 2019-07-15 17:00 | 10d | Engineers;Workers[0.60 #1] | 181500 | 0 | 0 | 0 | 181500 |  | 0 | 0 | 181500 | 10d | 0 | 0 | 0 | 181500 | 0% | Not Started | 0 | 0
24 | Ordering Machines and Raw Materials | 2019-07-16 08:00 | 2019-09-16 17:00 | 45d | Workers | 370000 | 0 | 0 | 0 | 370000 |  | 0 | 0 | 370000 | 45d | 0 | 0 | 0 | 370000 | 0% | Not Started | 0 | 0
25 | Manufacturing Trials | 2019-09-17 08:00 | 2019-10-07 17:00 | 15d | Workers;The Graduates | 435000 | 0 | 0 | 0 | 435000 |  | 0 | 0 | 435000 | 15d | 0 | 0 | 0 | 435000 | 0% | Not Started | 0 | 0
33 | Finish | 2019-10-07 17:00 | 2019-10-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP12
| TP Status Date | 2019-03-25 17:00 |  | TP Name | 25.03.2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Landing Gear Project | 2018-07-17 08:00 | 2019-10-07 17:00 | 320d |  |  | 0 |  |  | 11562500 |  | 180d | [5 empty] | 7884600 |  | 78.76% |  | 9106857.1424 | 7905500
31 | Feasibilty Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d |  |  | 0 |  |  | 1805000 |  | 36d 6h | [5 empty] | 1475000 |  | 100% |  | 1805000 | 1805000
1 | Feasiblity Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d | Consultant | 1805000 | 0 | 0 | 0 | 1805000 | 2018-07-17 08:00 | 36d 6h | 1475000 | 0 | 0 | 0 | 0 | 1475000 | 0 | 100% | Finished | 1805000 | 1805000
26 | Market Research | 2018-09-18 08:00 | 2018-10-29 17:00 | 30d |  |  | 0 |  |  | 2057500 |  | 29d 2h | [5 empty] | 1849500 |  | 100% |  | 2057500 | 2057500
3 | Specifying the size of Single and Twin engined light aircrafts replacement in the market | 2018-09-18 08:00 | 2018-10-01 17:00 | 10d | Consultant;Engineers | 532500 | 0 | 0 | 0 | 532500 | 2018-09-05 15:00 | 14d 5h | 773000 | 0 | 0 | 0 | 0 | 773000 | 0 | 100% | Finished | 532500 | 532500
4 | Calculation of the potential annual demand volumes for landing gear struts according to each of the different retail prices | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Consultant;Engineers | 792500 | 0 | 0 | 0 | 792500 | 2018-09-26 11:00 | 10d 2h | 545500 | 0 | 0 | 0 | 0 | 545500 | 0 | 100% | Finished | 792500 | 792500
5 | Calculation of the annual sales volumes actually achievable, taking into account the maximum capacity of the factory set by the directors | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Engineers | 187500 | 0 | 0 | 0 | 187500 | 2018-09-26 11:00 | 8d 4h | 109500 | 0 | 0 | 0 | 0 | 109500 | 0 | 100% | Finished | 187500 | 187500
6 | Calculation of the total annual trade sales revenues and fixed/variable/total costs for each retail | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-10 14:00 | 4d 3h | 240000 | 0 | 0 | 0 | 0 | 240000 | 0 | 100% | Finished | 272500 | 272500
7 | Calculation of the-trade price at which the company should sell at to generate the maximum profit | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-08 16:00 | 3d 2h | 181500 | 0 | 0 | 0 | 0 | 181500 | 0 | 100% | Finished | 272500 | 272500
27 | Business Plan, Financial Analysis, and Team Selection | 2018-10-30 08:00 | 2019-01-07 17:00 | 50d |  |  | 0 |  |  | 2615000 |  | 55d 3h | [5 empty] | 2705000 |  | 100% |  | 2615000 | 2615000
9 | Preparation of Business Plan | 2018-10-30 08:00 | 2018-12-10 17:00 | 30d | Consultant | 1205000 | 0 | 0 | 0 | 1205000 | 2018-10-17 08:00 | 32d 7h | 1320000 | 0 | 0 | 0 | 0 | 1320000 | 0 | 100% | Finished | 1205000 | 1205000
10 | Financial Analysis | 2018-12-18 08:00 | 2019-01-07 17:00 | 15d | Consultant | 605000 | 0 | 0 | 0 | 605000 | 2018-11-30 16:00 | 22d 4h | 905000 | 0 | 0 | 0 | 0 | 905000 | 0 | 100% | Finished | 605000 | 605000
11 | Team Selection (Recruitment of Management Team and Staff) | 2018-12-11 08:00 | 2019-01-07 17:00 | 20d | Consultant | 805000 | 0 | 0 | 0 | 805000 | 2018-11-30 16:00 | 11d 7h | 480000 | 0 | 0 | 0 | 0 | 480000 | 0 | 100% | Finished | 805000 | 805000
28 | Process Analysis | 2019-01-08 08:00 | 2019-04-08 17:00 | 65d |  |  | 0 |  |  | 2159500 |  | 44d 4h | [5 empty] | 1597900 |  | 100% |  | 2159500 | 1428000
13 | Preparation of Bill of Materials (BOM) file | 2019-01-08 08:00 | 2019-03-11 17:00 | 45d | Engineers;Workers | 917500 | 0 | 0 | 0 | 917500 | 2019-01-02 11:00 | 25d 5h | 530000 | 0 | 0 | 0 | 0 | 530000 | 0 | 100% | Finished | 917500 | 917500
14 | Calculation of Machine Requirements | 2019-03-19 08:00 | 2019-04-08 17:00 | 15d | Engineers;Workers[0.40 #1] | 239500 | 0 | 0 | 0 | 239500 | 2019-02-07 08:00 | 11d 2h | 182500 | 0 | 0 | 0 | 0 | 182500 | 0 | 100% | Finished | 239500 | 87500
15 | Calculation of Labour Requirements | 2019-03-26 08:00 | 2019-04-08 17:00 | 10d | Engineers;Workers[0.40 #1] | 163500 | 0 | 0 | 0 | 163500 | 2019-02-07 08:00 | 5d 3h | 93200 | 0 | 0 | 0 | 0 | 93200 | 0 | 100% | Finished | 163500 | 0
16 | Calculation of Factory Capacity | 2019-03-12 08:00 | 2019-04-08 17:00 | 20d | Workers[0.20 #1];Consultant | 839000 | 0 | 0 | 0 | 839000 | 2019-02-07 08:00 | 18d 7h | 792200 | 0 | 0 | 0 | 0 | 792200 | 0 | 100% | Finished | 839000 | 423000
29 | Productivity Analysis | 2019-04-09 08:00 | 2019-06-10 17:00 | 45d |  |  | 0 |  |  | 850000 |  | 14d 1h | [5 empty] | 257200 |  | 55.28% |  | 469857.1424 | 0
18 | Creation the Line of Balance for the Landing Gear System and its Level 1 Sub-Assemblies | 2019-04-09 08:00 | 2019-05-06 17:00 | 20d | Workers[0.20 #1];The Graduates | 439000 | 0 | 0 | 0 | 439000 | 2019-03-05 16:00 | 10d 4h | 233800 | 0 | 0 | 0 | 0 | 233800 | 0 | 100% | Finished | 439000 | 0
19 | Defining implication of this MPS on the capacity of the factory | 2019-05-07 08:00 | 2019-05-20 17:00 | 10d | Workers[0.60 #1] | 54000 | 0 | 0 | 0 | 54000 | 2019-03-20 11:00 | 3d 5h | 23400 | 16200 | 3d 3h | 0 | 0 | 23400 | 16200 | 51.79% | Started | 30857.1424 | 0
20 | Assisting of line of balance in solution providing for problems | 2019-05-21 08:00 | 2019-06-10 17:00 | 15d | Workers[0.40 #1];The Graduates | 357000 | 0 | 0 | 0 | 357000 |  | 0 | 0 | 357000 | 15d | 0 | 0 | 0 | 357000 | 0% | Not Started | 0 | 0
30 | Start to Production | 2019-06-11 08:00 | 2019-10-07 17:00 | 85d |  |  | 0 |  |  | 2075500 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Identifying Production Site | 2019-06-11 08:00 | 2019-07-15 17:00 | 25d | Consultant;Workers[0.40 #1] | 1089000 | 0 | 0 | 0 | 1089000 |  | 0 | 0 | 1089000 | 25d | 0 | 0 | 0 | 1089000 | 0% | Not Started | 0 | 0
23 | Supplier Selection | 2019-07-02 08:00 | 2019-07-15 17:00 | 10d | Engineers;Workers[0.60 #1] | 181500 | 0 | 0 | 0 | 181500 |  | 0 | 0 | 181500 | 10d | 0 | 0 | 0 | 181500 | 0% | Not Started | 0 | 0
24 | Ordering Machines and Raw Materials | 2019-07-16 08:00 | 2019-09-16 17:00 | 45d | Workers | 370000 | 0 | 0 | 0 | 370000 |  | 0 | 0 | 370000 | 45d | 0 | 0 | 0 | 370000 | 0% | Not Started | 0 | 0
25 | Manufacturing Trials | 2019-09-17 08:00 | 2019-10-07 17:00 | 15d | Workers;The Graduates | 435000 | 0 | 0 | 0 | 435000 |  | 0 | 0 | 435000 | 15d | 0 | 0 | 0 | 435000 | 0% | Not Started | 0 | 0
33 | Finish | 2019-10-07 17:00 | 2019-10-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP13
| TP Status Date | 2019-04-15 17:00 |  | TP Name | 15.04.2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Landing Gear Project | 2018-07-17 08:00 | 2019-10-07 17:00 | 320d |  |  | 0 |  |  | 11562500 |  | 195d | [5 empty] | 8317000 |  | 83.51% |  | 9655448.0643 | 8752000
31 | Feasibilty Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d |  |  | 0 |  |  | 1805000 |  | 36d 6h | [5 empty] | 1475000 |  | 100% |  | 1805000 | 1805000
1 | Feasiblity Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d | Consultant | 1805000 | 0 | 0 | 0 | 1805000 | 2018-07-17 08:00 | 36d 6h | 1475000 | 0 | 0 | 0 | 0 | 1475000 | 0 | 100% | Finished | 1805000 | 1805000
26 | Market Research | 2018-09-18 08:00 | 2018-10-29 17:00 | 30d |  |  | 0 |  |  | 2057500 |  | 29d 2h | [5 empty] | 1849500 |  | 100% |  | 2057500 | 2057500
3 | Specifying the size of Single and Twin engined light aircrafts replacement in the market | 2018-09-18 08:00 | 2018-10-01 17:00 | 10d | Consultant;Engineers | 532500 | 0 | 0 | 0 | 532500 | 2018-09-05 15:00 | 14d 5h | 773000 | 0 | 0 | 0 | 0 | 773000 | 0 | 100% | Finished | 532500 | 532500
4 | Calculation of the potential annual demand volumes for landing gear struts according to each of the different retail prices | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Consultant;Engineers | 792500 | 0 | 0 | 0 | 792500 | 2018-09-26 11:00 | 10d 2h | 545500 | 0 | 0 | 0 | 0 | 545500 | 0 | 100% | Finished | 792500 | 792500
5 | Calculation of the annual sales volumes actually achievable, taking into account the maximum capacity of the factory set by the directors | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Engineers | 187500 | 0 | 0 | 0 | 187500 | 2018-09-26 11:00 | 8d 4h | 109500 | 0 | 0 | 0 | 0 | 109500 | 0 | 100% | Finished | 187500 | 187500
6 | Calculation of the total annual trade sales revenues and fixed/variable/total costs for each retail | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-10 14:00 | 4d 3h | 240000 | 0 | 0 | 0 | 0 | 240000 | 0 | 100% | Finished | 272500 | 272500
7 | Calculation of the-trade price at which the company should sell at to generate the maximum profit | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-08 16:00 | 3d 2h | 181500 | 0 | 0 | 0 | 0 | 181500 | 0 | 100% | Finished | 272500 | 272500
27 | Business Plan, Financial Analysis, and Team Selection | 2018-10-30 08:00 | 2019-01-07 17:00 | 50d |  |  | 0 |  |  | 2615000 |  | 55d 3h | [5 empty] | 2705000 |  | 100% |  | 2615000 | 2615000
9 | Preparation of Business Plan | 2018-10-30 08:00 | 2018-12-10 17:00 | 30d | Consultant | 1205000 | 0 | 0 | 0 | 1205000 | 2018-10-17 08:00 | 32d 7h | 1320000 | 0 | 0 | 0 | 0 | 1320000 | 0 | 100% | Finished | 1205000 | 1205000
10 | Financial Analysis | 2018-12-18 08:00 | 2019-01-07 17:00 | 15d | Consultant | 605000 | 0 | 0 | 0 | 605000 | 2018-11-30 16:00 | 22d 4h | 905000 | 0 | 0 | 0 | 0 | 905000 | 0 | 100% | Finished | 605000 | 605000
11 | Team Selection (Recruitment of Management Team and Staff) | 2018-12-11 08:00 | 2019-01-07 17:00 | 20d | Consultant | 805000 | 0 | 0 | 0 | 805000 | 2018-11-30 16:00 | 11d 7h | 480000 | 0 | 0 | 0 | 0 | 480000 | 0 | 100% | Finished | 805000 | 805000
28 | Process Analysis | 2019-01-08 08:00 | 2019-04-08 17:00 | 65d |  |  | 0 |  |  | 2159500 |  | 44d 4h | [5 empty] | 1597900 |  | 100% |  | 2159500 | 2159500
13 | Preparation of Bill of Materials (BOM) file | 2019-01-08 08:00 | 2019-03-11 17:00 | 45d | Engineers;Workers | 917500 | 0 | 0 | 0 | 917500 | 2019-01-02 11:00 | 25d 5h | 530000 | 0 | 0 | 0 | 0 | 530000 | 0 | 100% | Finished | 917500 | 917500
14 | Calculation of Machine Requirements | 2019-03-19 08:00 | 2019-04-08 17:00 | 15d | Engineers;Workers[0.40 #1] | 239500 | 0 | 0 | 0 | 239500 | 2019-02-07 08:00 | 11d 2h | 182500 | 0 | 0 | 0 | 0 | 182500 | 0 | 100% | Finished | 239500 | 239500
15 | Calculation of Labour Requirements | 2019-03-26 08:00 | 2019-04-08 17:00 | 10d | Engineers;Workers[0.40 #1] | 163500 | 0 | 0 | 0 | 163500 | 2019-02-07 08:00 | 5d 3h | 93200 | 0 | 0 | 0 | 0 | 93200 | 0 | 100% | Finished | 163500 | 163500
16 | Calculation of Factory Capacity | 2019-03-12 08:00 | 2019-04-08 17:00 | 20d | Workers[0.20 #1];Consultant | 839000 | 0 | 0 | 0 | 839000 | 2019-02-07 08:00 | 18d 7h | 792200 | 0 | 0 | 0 | 0 | 792200 | 0 | 100% | Finished | 839000 | 839000
29 | Productivity Analysis | 2019-04-09 08:00 | 2019-06-10 17:00 | 45d |  |  | 0 |  |  | 850000 |  | 26d | [5 empty] | 479600 |  | 100% |  | 850000 | 115000
18 | Creation the Line of Balance for the Landing Gear System and its Level 1 Sub-Assemblies | 2019-04-09 08:00 | 2019-05-06 17:00 | 20d | Workers[0.20 #1];The Graduates | 439000 | 0 | 0 | 0 | 439000 | 2019-03-05 16:00 | 10d 4h | 233800 | 0 | 0 | 0 | 0 | 233800 | 0 | 100% | Finished | 439000 | 115000
19 | Defining implication of this MPS on the capacity of the factory | 2019-05-07 08:00 | 2019-05-20 17:00 | 10d | Workers[0.60 #1] | 54000 | 0 | 0 | 0 | 54000 | 2019-03-20 11:00 | 7d | 39600 | 0 | 0 | 0 | 0 | 39600 | 0 | 100% | Finished | 54000 | 0
20 | Assisting of line of balance in solution providing for problems | 2019-05-21 08:00 | 2019-06-10 17:00 | 15d | Workers[0.40 #1];The Graduates | 357000 | 0 | 0 | 0 | 357000 | 2019-03-29 11:00 | 8d 4h | 206200 | 0 | 0 | 0 | 0 | 206200 | 0 | 100% | Finished | 357000 | 0
30 | Start to Production | 2019-06-11 08:00 | 2019-10-07 17:00 | 85d |  |  | 0 |  |  | 2075500 |  | 3d 1h | [5 empty] | 210000 |  | 8.116% |  | 168448.0643 | 0
22 | Identifying Production Site | 2019-06-11 08:00 | 2019-07-15 17:00 | 25d | Consultant;Workers[0.40 #1] | 1089000 | 0 | 0 | 0 | 1089000 | 2019-04-10 16:00 | 3d 1h | 144000 | 1436400 | 33d 2h | 0 | 0 | 144000 | 1436400 | 8.591% | Started | 101783.508 | 0
23 | Supplier Selection | 2019-07-02 08:00 | 2019-07-15 17:00 | 10d | Engineers;Workers[0.60 #1] | 181500 | 0 | 0 | 0 | 181500 | 2019-04-10 16:00 | 3d 1h | 66000 | 113400 | 6d 6h | 0 | 0 | 66000 | 113400 | 31.65% | Started | 66664.5563 | 0
24 | Ordering Machines and Raw Materials | 2019-07-16 08:00 | 2019-09-16 17:00 | 45d | Workers | 370000 | 0 | 0 | 0 | 370000 |  | 0 | 0 | 370000 | 45d | 0 | 0 | 0 | 370000 | 0% | Not Started | 0 | 0
25 | Manufacturing Trials | 2019-09-17 08:00 | 2019-10-07 17:00 | 15d | Workers;The Graduates | 435000 | 0 | 0 | 0 | 435000 |  | 0 | 0 | 435000 | 15d | 0 | 0 | 0 | 435000 | 0% | Not Started | 0 | 0
33 | Finish | 2019-10-07 17:00 | 2019-10-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP14
| TP Status Date | 2019-05-06 17:00 |  | TP Name | 6.05.2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Landing Gear Project | 2018-07-17 08:00 | 2019-10-07 17:00 | 320d |  |  | 0 |  |  | 11562500 |  | 210d | [5 empty] | 9078400 |  | 88.35% |  | 10215644.3191 | 9076000
31 | Feasibilty Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d |  |  | 0 |  |  | 1805000 |  | 36d 6h | [5 empty] | 1475000 |  | 100% |  | 1805000 | 1805000
1 | Feasiblity Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d | Consultant | 1805000 | 0 | 0 | 0 | 1805000 | 2018-07-17 08:00 | 36d 6h | 1475000 | 0 | 0 | 0 | 0 | 1475000 | 0 | 100% | Finished | 1805000 | 1805000
26 | Market Research | 2018-09-18 08:00 | 2018-10-29 17:00 | 30d |  |  | 0 |  |  | 2057500 |  | 29d 2h | [5 empty] | 1849500 |  | 100% |  | 2057500 | 2057500
3 | Specifying the size of Single and Twin engined light aircrafts replacement in the market | 2018-09-18 08:00 | 2018-10-01 17:00 | 10d | Consultant;Engineers | 532500 | 0 | 0 | 0 | 532500 | 2018-09-05 15:00 | 14d 5h | 773000 | 0 | 0 | 0 | 0 | 773000 | 0 | 100% | Finished | 532500 | 532500
4 | Calculation of the potential annual demand volumes for landing gear struts according to each of the different retail prices | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Consultant;Engineers | 792500 | 0 | 0 | 0 | 792500 | 2018-09-26 11:00 | 10d 2h | 545500 | 0 | 0 | 0 | 0 | 545500 | 0 | 100% | Finished | 792500 | 792500
5 | Calculation of the annual sales volumes actually achievable, taking into account the maximum capacity of the factory set by the directors | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Engineers | 187500 | 0 | 0 | 0 | 187500 | 2018-09-26 11:00 | 8d 4h | 109500 | 0 | 0 | 0 | 0 | 109500 | 0 | 100% | Finished | 187500 | 187500
6 | Calculation of the total annual trade sales revenues and fixed/variable/total costs for each retail | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-10 14:00 | 4d 3h | 240000 | 0 | 0 | 0 | 0 | 240000 | 0 | 100% | Finished | 272500 | 272500
7 | Calculation of the-trade price at which the company should sell at to generate the maximum profit | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-08 16:00 | 3d 2h | 181500 | 0 | 0 | 0 | 0 | 181500 | 0 | 100% | Finished | 272500 | 272500
27 | Business Plan, Financial Analysis, and Team Selection | 2018-10-30 08:00 | 2019-01-07 17:00 | 50d |  |  | 0 |  |  | 2615000 |  | 55d 3h | [5 empty] | 2705000 |  | 100% |  | 2615000 | 2615000
9 | Preparation of Business Plan | 2018-10-30 08:00 | 2018-12-10 17:00 | 30d | Consultant | 1205000 | 0 | 0 | 0 | 1205000 | 2018-10-17 08:00 | 32d 7h | 1320000 | 0 | 0 | 0 | 0 | 1320000 | 0 | 100% | Finished | 1205000 | 1205000
10 | Financial Analysis | 2018-12-18 08:00 | 2019-01-07 17:00 | 15d | Consultant | 605000 | 0 | 0 | 0 | 605000 | 2018-11-30 16:00 | 22d 4h | 905000 | 0 | 0 | 0 | 0 | 905000 | 0 | 100% | Finished | 605000 | 605000
11 | Team Selection (Recruitment of Management Team and Staff) | 2018-12-11 08:00 | 2019-01-07 17:00 | 20d | Consultant | 805000 | 0 | 0 | 0 | 805000 | 2018-11-30 16:00 | 11d 7h | 480000 | 0 | 0 | 0 | 0 | 480000 | 0 | 100% | Finished | 805000 | 805000
28 | Process Analysis | 2019-01-08 08:00 | 2019-04-08 17:00 | 65d |  |  | 0 |  |  | 2159500 |  | 44d 4h | [5 empty] | 1597900 |  | 100% |  | 2159500 | 2159500
13 | Preparation of Bill of Materials (BOM) file | 2019-01-08 08:00 | 2019-03-11 17:00 | 45d | Engineers;Workers | 917500 | 0 | 0 | 0 | 917500 | 2019-01-02 11:00 | 25d 5h | 530000 | 0 | 0 | 0 | 0 | 530000 | 0 | 100% | Finished | 917500 | 917500
14 | Calculation of Machine Requirements | 2019-03-19 08:00 | 2019-04-08 17:00 | 15d | Engineers;Workers[0.40 #1] | 239500 | 0 | 0 | 0 | 239500 | 2019-02-07 08:00 | 11d 2h | 182500 | 0 | 0 | 0 | 0 | 182500 | 0 | 100% | Finished | 239500 | 239500
15 | Calculation of Labour Requirements | 2019-03-26 08:00 | 2019-04-08 17:00 | 10d | Engineers;Workers[0.40 #1] | 163500 | 0 | 0 | 0 | 163500 | 2019-02-07 08:00 | 5d 3h | 93200 | 0 | 0 | 0 | 0 | 93200 | 0 | 100% | Finished | 163500 | 163500
16 | Calculation of Factory Capacity | 2019-03-12 08:00 | 2019-04-08 17:00 | 20d | Workers[0.20 #1];Consultant | 839000 | 0 | 0 | 0 | 839000 | 2019-02-07 08:00 | 18d 7h | 792200 | 0 | 0 | 0 | 0 | 792200 | 0 | 100% | Finished | 839000 | 839000
29 | Productivity Analysis | 2019-04-09 08:00 | 2019-06-10 17:00 | 45d |  |  | 0 |  |  | 850000 |  | 26d | [5 empty] | 479600 |  | 100% |  | 850000 | 439000
18 | Creation the Line of Balance for the Landing Gear System and its Level 1 Sub-Assemblies | 2019-04-09 08:00 | 2019-05-06 17:00 | 20d | Workers[0.20 #1];The Graduates | 439000 | 0 | 0 | 0 | 439000 | 2019-03-05 16:00 | 10d 4h | 233800 | 0 | 0 | 0 | 0 | 233800 | 0 | 100% | Finished | 439000 | 439000
19 | Defining implication of this MPS on the capacity of the factory | 2019-05-07 08:00 | 2019-05-20 17:00 | 10d | Workers[0.60 #1] | 54000 | 0 | 0 | 0 | 54000 | 2019-03-20 11:00 | 7d | 39600 | 0 | 0 | 0 | 0 | 39600 | 0 | 100% | Finished | 54000 | 0
20 | Assisting of line of balance in solution providing for problems | 2019-05-21 08:00 | 2019-06-10 17:00 | 15d | Workers[0.40 #1];The Graduates | 357000 | 0 | 0 | 0 | 357000 | 2019-03-29 11:00 | 8d 4h | 206200 | 0 | 0 | 0 | 0 | 206200 | 0 | 100% | Finished | 357000 | 0
30 | Start to Production | 2019-06-11 08:00 | 2019-10-07 17:00 | 85d |  |  | 0 |  |  | 2075500 |  | 18d 1h | [5 empty] | 971400 |  | 35.11% |  | 728644.3191 | 0
22 | Identifying Production Site | 2019-06-11 08:00 | 2019-07-15 17:00 | 25d | Consultant;Workers[0.40 #1] | 1089000 | 0 | 0 | 0 | 1089000 | 2019-04-10 16:00 | 18d 1h | 792000 | 788400 | 18d 2h | 0 | 0 | 792000 | 788400 | 49.83% | Started | 547144.3191 | 0
23 | Supplier Selection | 2019-07-02 08:00 | 2019-07-15 17:00 | 10d | Engineers;Workers[0.60 #1] | 181500 | 0 | 0 | 0 | 181500 | 2019-04-10 16:00 | 9d 7h | 179400 | 0 | 0 | 0 | 0 | 179400 | 0 | 100% | Finished | 181500 | 0
24 | Ordering Machines and Raw Materials | 2019-07-16 08:00 | 2019-09-16 17:00 | 45d | Workers | 370000 | 0 | 0 | 0 | 370000 |  | 0 | 0 | 370000 | 45d | 0 | 0 | 0 | 370000 | 0% | Not Started | 0 | 0
25 | Manufacturing Trials | 2019-09-17 08:00 | 2019-10-07 17:00 | 15d | Workers;The Graduates | 435000 | 0 | 0 | 0 | 435000 |  | 0 | 0 | 435000 | 15d | 0 | 0 | 0 | 435000 | 0% | Not Started | 0 | 0
33 | Finish | 2019-10-07 17:00 | 2019-10-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP15
| TP Status Date | 2019-05-27 17:00 |  | TP Name | 27.05.2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Landing Gear Project | 2018-07-17 08:00 | 2019-10-07 17:00 | 320d |  |  | 0 |  |  | 11562500 |  | 225d | [5 empty] | 9726400 |  | 92.2% |  | 10661005.1703 | 9255000
31 | Feasibilty Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d |  |  | 0 |  |  | 1805000 |  | 36d 6h | [5 empty] | 1475000 |  | 100% |  | 1805000 | 1805000
1 | Feasiblity Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d | Consultant | 1805000 | 0 | 0 | 0 | 1805000 | 2018-07-17 08:00 | 36d 6h | 1475000 | 0 | 0 | 0 | 0 | 1475000 | 0 | 100% | Finished | 1805000 | 1805000
26 | Market Research | 2018-09-18 08:00 | 2018-10-29 17:00 | 30d |  |  | 0 |  |  | 2057500 |  | 29d 2h | [5 empty] | 1849500 |  | 100% |  | 2057500 | 2057500
3 | Specifying the size of Single and Twin engined light aircrafts replacement in the market | 2018-09-18 08:00 | 2018-10-01 17:00 | 10d | Consultant;Engineers | 532500 | 0 | 0 | 0 | 532500 | 2018-09-05 15:00 | 14d 5h | 773000 | 0 | 0 | 0 | 0 | 773000 | 0 | 100% | Finished | 532500 | 532500
4 | Calculation of the potential annual demand volumes for landing gear struts according to each of the different retail prices | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Consultant;Engineers | 792500 | 0 | 0 | 0 | 792500 | 2018-09-26 11:00 | 10d 2h | 545500 | 0 | 0 | 0 | 0 | 545500 | 0 | 100% | Finished | 792500 | 792500
5 | Calculation of the annual sales volumes actually achievable, taking into account the maximum capacity of the factory set by the directors | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Engineers | 187500 | 0 | 0 | 0 | 187500 | 2018-09-26 11:00 | 8d 4h | 109500 | 0 | 0 | 0 | 0 | 109500 | 0 | 100% | Finished | 187500 | 187500
6 | Calculation of the total annual trade sales revenues and fixed/variable/total costs for each retail | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-10 14:00 | 4d 3h | 240000 | 0 | 0 | 0 | 0 | 240000 | 0 | 100% | Finished | 272500 | 272500
7 | Calculation of the-trade price at which the company should sell at to generate the maximum profit | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-08 16:00 | 3d 2h | 181500 | 0 | 0 | 0 | 0 | 181500 | 0 | 100% | Finished | 272500 | 272500
27 | Business Plan, Financial Analysis, and Team Selection | 2018-10-30 08:00 | 2019-01-07 17:00 | 50d |  |  | 0 |  |  | 2615000 |  | 55d 3h | [5 empty] | 2705000 |  | 100% |  | 2615000 | 2615000
9 | Preparation of Business Plan | 2018-10-30 08:00 | 2018-12-10 17:00 | 30d | Consultant | 1205000 | 0 | 0 | 0 | 1205000 | 2018-10-17 08:00 | 32d 7h | 1320000 | 0 | 0 | 0 | 0 | 1320000 | 0 | 100% | Finished | 1205000 | 1205000
10 | Financial Analysis | 2018-12-18 08:00 | 2019-01-07 17:00 | 15d | Consultant | 605000 | 0 | 0 | 0 | 605000 | 2018-11-30 16:00 | 22d 4h | 905000 | 0 | 0 | 0 | 0 | 905000 | 0 | 100% | Finished | 605000 | 605000
11 | Team Selection (Recruitment of Management Team and Staff) | 2018-12-11 08:00 | 2019-01-07 17:00 | 20d | Consultant | 805000 | 0 | 0 | 0 | 805000 | 2018-11-30 16:00 | 11d 7h | 480000 | 0 | 0 | 0 | 0 | 480000 | 0 | 100% | Finished | 805000 | 805000
28 | Process Analysis | 2019-01-08 08:00 | 2019-04-08 17:00 | 65d |  |  | 0 |  |  | 2159500 |  | 44d 4h | [5 empty] | 1597900 |  | 100% |  | 2159500 | 2159500
13 | Preparation of Bill of Materials (BOM) file | 2019-01-08 08:00 | 2019-03-11 17:00 | 45d | Engineers;Workers | 917500 | 0 | 0 | 0 | 917500 | 2019-01-02 11:00 | 25d 5h | 530000 | 0 | 0 | 0 | 0 | 530000 | 0 | 100% | Finished | 917500 | 917500
14 | Calculation of Machine Requirements | 2019-03-19 08:00 | 2019-04-08 17:00 | 15d | Engineers;Workers[0.40 #1] | 239500 | 0 | 0 | 0 | 239500 | 2019-02-07 08:00 | 11d 2h | 182500 | 0 | 0 | 0 | 0 | 182500 | 0 | 100% | Finished | 239500 | 239500
15 | Calculation of Labour Requirements | 2019-03-26 08:00 | 2019-04-08 17:00 | 10d | Engineers;Workers[0.40 #1] | 163500 | 0 | 0 | 0 | 163500 | 2019-02-07 08:00 | 5d 3h | 93200 | 0 | 0 | 0 | 0 | 93200 | 0 | 100% | Finished | 163500 | 163500
16 | Calculation of Factory Capacity | 2019-03-12 08:00 | 2019-04-08 17:00 | 20d | Workers[0.20 #1];Consultant | 839000 | 0 | 0 | 0 | 839000 | 2019-02-07 08:00 | 18d 7h | 792200 | 0 | 0 | 0 | 0 | 792200 | 0 | 100% | Finished | 839000 | 839000
29 | Productivity Analysis | 2019-04-09 08:00 | 2019-06-10 17:00 | 45d |  |  | 0 |  |  | 850000 |  | 26d | [5 empty] | 479600 |  | 100% |  | 850000 | 618000
18 | Creation the Line of Balance for the Landing Gear System and its Level 1 Sub-Assemblies | 2019-04-09 08:00 | 2019-05-06 17:00 | 20d | Workers[0.20 #1];The Graduates | 439000 | 0 | 0 | 0 | 439000 | 2019-03-05 16:00 | 10d 4h | 233800 | 0 | 0 | 0 | 0 | 233800 | 0 | 100% | Finished | 439000 | 439000
19 | Defining implication of this MPS on the capacity of the factory | 2019-05-07 08:00 | 2019-05-20 17:00 | 10d | Workers[0.60 #1] | 54000 | 0 | 0 | 0 | 54000 | 2019-03-20 11:00 | 7d | 39600 | 0 | 0 | 0 | 0 | 39600 | 0 | 100% | Finished | 54000 | 54000
20 | Assisting of line of balance in solution providing for problems | 2019-05-21 08:00 | 2019-06-10 17:00 | 15d | Workers[0.40 #1];The Graduates | 357000 | 0 | 0 | 0 | 357000 | 2019-03-29 11:00 | 8d 4h | 206200 | 0 | 0 | 0 | 0 | 206200 | 0 | 100% | Finished | 357000 | 125000
30 | Start to Production | 2019-06-11 08:00 | 2019-10-07 17:00 | 85d |  |  | 0 |  |  | 2075500 |  | 33d 1h | [5 empty] | 1619400 |  | 56.56% |  | 1174005.1703 | 0
22 | Identifying Production Site | 2019-06-11 08:00 | 2019-07-15 17:00 | 25d | Consultant;Workers[0.40 #1] | 1089000 | 0 | 0 | 0 | 1089000 | 2019-04-10 16:00 | 33d 1h | 1440000 | 140400 | 3d 2h | 0 | 0 | 1440000 | 140400 | 91.07% | Started | 992505.1703 | 0
23 | Supplier Selection | 2019-07-02 08:00 | 2019-07-15 17:00 | 10d | Engineers;Workers[0.60 #1] | 181500 | 0 | 0 | 0 | 181500 | 2019-04-10 16:00 | 9d 7h | 179400 | 0 | 0 | 0 | 0 | 179400 | 0 | 100% | Finished | 181500 | 0
24 | Ordering Machines and Raw Materials | 2019-07-16 08:00 | 2019-09-16 17:00 | 45d | Workers | 370000 | 0 | 0 | 0 | 370000 |  | 0 | 0 | 370000 | 45d | 0 | 0 | 0 | 370000 | 0% | Not Started | 0 | 0
25 | Manufacturing Trials | 2019-09-17 08:00 | 2019-10-07 17:00 | 15d | Workers;The Graduates | 435000 | 0 | 0 | 0 | 435000 |  | 0 | 0 | 435000 | 15d | 0 | 0 | 0 | 435000 | 0% | Not Started | 0 | 0
33 | Finish | 2019-10-07 17:00 | 2019-10-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP16
| TP Status Date | 2019-06-17 17:00 |  | TP Name | 17.06.2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Landing Gear Project | 2018-07-17 08:00 | 2019-10-07 17:00 | 320d |  |  | 0 |  |  | 11562500 |  | 240d | [5 empty] | 9970800 |  | 94.63% |  | 10941932.9894 | 9712000
31 | Feasibilty Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d |  |  | 0 |  |  | 1805000 |  | 36d 6h | [5 empty] | 1475000 |  | 100% |  | 1805000 | 1805000
1 | Feasiblity Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d | Consultant | 1805000 | 0 | 0 | 0 | 1805000 | 2018-07-17 08:00 | 36d 6h | 1475000 | 0 | 0 | 0 | 0 | 1475000 | 0 | 100% | Finished | 1805000 | 1805000
26 | Market Research | 2018-09-18 08:00 | 2018-10-29 17:00 | 30d |  |  | 0 |  |  | 2057500 |  | 29d 2h | [5 empty] | 1849500 |  | 100% |  | 2057500 | 2057500
3 | Specifying the size of Single and Twin engined light aircrafts replacement in the market | 2018-09-18 08:00 | 2018-10-01 17:00 | 10d | Consultant;Engineers | 532500 | 0 | 0 | 0 | 532500 | 2018-09-05 15:00 | 14d 5h | 773000 | 0 | 0 | 0 | 0 | 773000 | 0 | 100% | Finished | 532500 | 532500
4 | Calculation of the potential annual demand volumes for landing gear struts according to each of the different retail prices | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Consultant;Engineers | 792500 | 0 | 0 | 0 | 792500 | 2018-09-26 11:00 | 10d 2h | 545500 | 0 | 0 | 0 | 0 | 545500 | 0 | 100% | Finished | 792500 | 792500
5 | Calculation of the annual sales volumes actually achievable, taking into account the maximum capacity of the factory set by the directors | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Engineers | 187500 | 0 | 0 | 0 | 187500 | 2018-09-26 11:00 | 8d 4h | 109500 | 0 | 0 | 0 | 0 | 109500 | 0 | 100% | Finished | 187500 | 187500
6 | Calculation of the total annual trade sales revenues and fixed/variable/total costs for each retail | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-10 14:00 | 4d 3h | 240000 | 0 | 0 | 0 | 0 | 240000 | 0 | 100% | Finished | 272500 | 272500
7 | Calculation of the-trade price at which the company should sell at to generate the maximum profit | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-08 16:00 | 3d 2h | 181500 | 0 | 0 | 0 | 0 | 181500 | 0 | 100% | Finished | 272500 | 272500
27 | Business Plan, Financial Analysis, and Team Selection | 2018-10-30 08:00 | 2019-01-07 17:00 | 50d |  |  | 0 |  |  | 2615000 |  | 55d 3h | [5 empty] | 2705000 |  | 100% |  | 2615000 | 2615000
9 | Preparation of Business Plan | 2018-10-30 08:00 | 2018-12-10 17:00 | 30d | Consultant | 1205000 | 0 | 0 | 0 | 1205000 | 2018-10-17 08:00 | 32d 7h | 1320000 | 0 | 0 | 0 | 0 | 1320000 | 0 | 100% | Finished | 1205000 | 1205000
10 | Financial Analysis | 2018-12-18 08:00 | 2019-01-07 17:00 | 15d | Consultant | 605000 | 0 | 0 | 0 | 605000 | 2018-11-30 16:00 | 22d 4h | 905000 | 0 | 0 | 0 | 0 | 905000 | 0 | 100% | Finished | 605000 | 605000
11 | Team Selection (Recruitment of Management Team and Staff) | 2018-12-11 08:00 | 2019-01-07 17:00 | 20d | Consultant | 805000 | 0 | 0 | 0 | 805000 | 2018-11-30 16:00 | 11d 7h | 480000 | 0 | 0 | 0 | 0 | 480000 | 0 | 100% | Finished | 805000 | 805000
28 | Process Analysis | 2019-01-08 08:00 | 2019-04-08 17:00 | 65d |  |  | 0 |  |  | 2159500 |  | 44d 4h | [5 empty] | 1597900 |  | 100% |  | 2159500 | 2159500
13 | Preparation of Bill of Materials (BOM) file | 2019-01-08 08:00 | 2019-03-11 17:00 | 45d | Engineers;Workers | 917500 | 0 | 0 | 0 | 917500 | 2019-01-02 11:00 | 25d 5h | 530000 | 0 | 0 | 0 | 0 | 530000 | 0 | 100% | Finished | 917500 | 917500
14 | Calculation of Machine Requirements | 2019-03-19 08:00 | 2019-04-08 17:00 | 15d | Engineers;Workers[0.40 #1] | 239500 | 0 | 0 | 0 | 239500 | 2019-02-07 08:00 | 11d 2h | 182500 | 0 | 0 | 0 | 0 | 182500 | 0 | 100% | Finished | 239500 | 239500
15 | Calculation of Labour Requirements | 2019-03-26 08:00 | 2019-04-08 17:00 | 10d | Engineers;Workers[0.40 #1] | 163500 | 0 | 0 | 0 | 163500 | 2019-02-07 08:00 | 5d 3h | 93200 | 0 | 0 | 0 | 0 | 93200 | 0 | 100% | Finished | 163500 | 163500
16 | Calculation of Factory Capacity | 2019-03-12 08:00 | 2019-04-08 17:00 | 20d | Workers[0.20 #1];Consultant | 839000 | 0 | 0 | 0 | 839000 | 2019-02-07 08:00 | 18d 7h | 792200 | 0 | 0 | 0 | 0 | 792200 | 0 | 100% | Finished | 839000 | 839000
29 | Productivity Analysis | 2019-04-09 08:00 | 2019-06-10 17:00 | 45d |  |  | 0 |  |  | 850000 |  | 26d | [5 empty] | 479600 |  | 100% |  | 850000 | 850000
18 | Creation the Line of Balance for the Landing Gear System and its Level 1 Sub-Assemblies | 2019-04-09 08:00 | 2019-05-06 17:00 | 20d | Workers[0.20 #1];The Graduates | 439000 | 0 | 0 | 0 | 439000 | 2019-03-05 16:00 | 10d 4h | 233800 | 0 | 0 | 0 | 0 | 233800 | 0 | 100% | Finished | 439000 | 439000
19 | Defining implication of this MPS on the capacity of the factory | 2019-05-07 08:00 | 2019-05-20 17:00 | 10d | Workers[0.60 #1] | 54000 | 0 | 0 | 0 | 54000 | 2019-03-20 11:00 | 7d | 39600 | 0 | 0 | 0 | 0 | 39600 | 0 | 100% | Finished | 54000 | 54000
20 | Assisting of line of balance in solution providing for problems | 2019-05-21 08:00 | 2019-06-10 17:00 | 15d | Workers[0.40 #1];The Graduates | 357000 | 0 | 0 | 0 | 357000 | 2019-03-29 11:00 | 8d 4h | 206200 | 0 | 0 | 0 | 0 | 206200 | 0 | 100% | Finished | 357000 | 357000
30 | Start to Production | 2019-06-11 08:00 | 2019-10-07 17:00 | 85d |  |  | 0 |  |  | 2075500 |  | 48d 1h | [5 empty] | 1863800 |  | 70.1% |  | 1454932.9894 | 225000
22 | Identifying Production Site | 2019-06-11 08:00 | 2019-07-15 17:00 | 25d | Consultant;Workers[0.40 #1] | 1089000 | 0 | 0 | 0 | 1089000 | 2019-04-10 16:00 | 36d 3h | 1580400 | 0 | 0 | 0 | 0 | 1580400 | 0 | 100% | Finished | 1089000 | 225000
23 | Supplier Selection | 2019-07-02 08:00 | 2019-07-15 17:00 | 10d | Engineers;Workers[0.60 #1] | 181500 | 0 | 0 | 0 | 181500 | 2019-04-10 16:00 | 9d 7h | 179400 | 0 | 0 | 0 | 0 | 179400 | 0 | 100% | Finished | 181500 | 0
24 | Ordering Machines and Raw Materials | 2019-07-16 08:00 | 2019-09-16 17:00 | 45d | Workers | 370000 | 0 | 0 | 0 | 370000 | 2019-05-31 10:00 | 11d 6h | 104000 | 100000 | 12d 4h | 0 | 0 | 104000 | 100000 | 48.45% | Started | 184432.9894 | 0
25 | Manufacturing Trials | 2019-09-17 08:00 | 2019-10-07 17:00 | 15d | Workers;The Graduates | 435000 | 0 | 0 | 0 | 435000 |  | 0 | 0 | 435000 | 15d | 0 | 0 | 0 | 435000 | 0% | Not Started | 0 | 0
33 | Finish | 2019-10-07 17:00 | 2019-10-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP17
| TP Status Date | 2019-07-08 17:00 |  | TP Name | 8.07.2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Landing Gear Project | 2018-07-17 08:00 | 2019-10-07 17:00 | 320d |  |  | 0 |  |  | 11562500 |  | 255d | [5 empty] | 10155800 |  | 96.79% |  | 11191337.2107 | 10457500
31 | Feasibilty Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d |  |  | 0 |  |  | 1805000 |  | 36d 6h | [5 empty] | 1475000 |  | 100% |  | 1805000 | 1805000
1 | Feasiblity Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d | Consultant | 1805000 | 0 | 0 | 0 | 1805000 | 2018-07-17 08:00 | 36d 6h | 1475000 | 0 | 0 | 0 | 0 | 1475000 | 0 | 100% | Finished | 1805000 | 1805000
26 | Market Research | 2018-09-18 08:00 | 2018-10-29 17:00 | 30d |  |  | 0 |  |  | 2057500 |  | 29d 2h | [5 empty] | 1849500 |  | 100% |  | 2057500 | 2057500
3 | Specifying the size of Single and Twin engined light aircrafts replacement in the market | 2018-09-18 08:00 | 2018-10-01 17:00 | 10d | Consultant;Engineers | 532500 | 0 | 0 | 0 | 532500 | 2018-09-05 15:00 | 14d 5h | 773000 | 0 | 0 | 0 | 0 | 773000 | 0 | 100% | Finished | 532500 | 532500
4 | Calculation of the potential annual demand volumes for landing gear struts according to each of the different retail prices | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Consultant;Engineers | 792500 | 0 | 0 | 0 | 792500 | 2018-09-26 11:00 | 10d 2h | 545500 | 0 | 0 | 0 | 0 | 545500 | 0 | 100% | Finished | 792500 | 792500
5 | Calculation of the annual sales volumes actually achievable, taking into account the maximum capacity of the factory set by the directors | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Engineers | 187500 | 0 | 0 | 0 | 187500 | 2018-09-26 11:00 | 8d 4h | 109500 | 0 | 0 | 0 | 0 | 109500 | 0 | 100% | Finished | 187500 | 187500
6 | Calculation of the total annual trade sales revenues and fixed/variable/total costs for each retail | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-10 14:00 | 4d 3h | 240000 | 0 | 0 | 0 | 0 | 240000 | 0 | 100% | Finished | 272500 | 272500
7 | Calculation of the-trade price at which the company should sell at to generate the maximum profit | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-08 16:00 | 3d 2h | 181500 | 0 | 0 | 0 | 0 | 181500 | 0 | 100% | Finished | 272500 | 272500
27 | Business Plan, Financial Analysis, and Team Selection | 2018-10-30 08:00 | 2019-01-07 17:00 | 50d |  |  | 0 |  |  | 2615000 |  | 55d 3h | [5 empty] | 2705000 |  | 100% |  | 2615000 | 2615000
9 | Preparation of Business Plan | 2018-10-30 08:00 | 2018-12-10 17:00 | 30d | Consultant | 1205000 | 0 | 0 | 0 | 1205000 | 2018-10-17 08:00 | 32d 7h | 1320000 | 0 | 0 | 0 | 0 | 1320000 | 0 | 100% | Finished | 1205000 | 1205000
10 | Financial Analysis | 2018-12-18 08:00 | 2019-01-07 17:00 | 15d | Consultant | 605000 | 0 | 0 | 0 | 605000 | 2018-11-30 16:00 | 22d 4h | 905000 | 0 | 0 | 0 | 0 | 905000 | 0 | 100% | Finished | 605000 | 605000
11 | Team Selection (Recruitment of Management Team and Staff) | 2018-12-11 08:00 | 2019-01-07 17:00 | 20d | Consultant | 805000 | 0 | 0 | 0 | 805000 | 2018-11-30 16:00 | 11d 7h | 480000 | 0 | 0 | 0 | 0 | 480000 | 0 | 100% | Finished | 805000 | 805000
28 | Process Analysis | 2019-01-08 08:00 | 2019-04-08 17:00 | 65d |  |  | 0 |  |  | 2159500 |  | 44d 4h | [5 empty] | 1597900 |  | 100% |  | 2159500 | 2159500
13 | Preparation of Bill of Materials (BOM) file | 2019-01-08 08:00 | 2019-03-11 17:00 | 45d | Engineers;Workers | 917500 | 0 | 0 | 0 | 917500 | 2019-01-02 11:00 | 25d 5h | 530000 | 0 | 0 | 0 | 0 | 530000 | 0 | 100% | Finished | 917500 | 917500
14 | Calculation of Machine Requirements | 2019-03-19 08:00 | 2019-04-08 17:00 | 15d | Engineers;Workers[0.40 #1] | 239500 | 0 | 0 | 0 | 239500 | 2019-02-07 08:00 | 11d 2h | 182500 | 0 | 0 | 0 | 0 | 182500 | 0 | 100% | Finished | 239500 | 239500
15 | Calculation of Labour Requirements | 2019-03-26 08:00 | 2019-04-08 17:00 | 10d | Engineers;Workers[0.40 #1] | 163500 | 0 | 0 | 0 | 163500 | 2019-02-07 08:00 | 5d 3h | 93200 | 0 | 0 | 0 | 0 | 93200 | 0 | 100% | Finished | 163500 | 163500
16 | Calculation of Factory Capacity | 2019-03-12 08:00 | 2019-04-08 17:00 | 20d | Workers[0.20 #1];Consultant | 839000 | 0 | 0 | 0 | 839000 | 2019-02-07 08:00 | 18d 7h | 792200 | 0 | 0 | 0 | 0 | 792200 | 0 | 100% | Finished | 839000 | 839000
29 | Productivity Analysis | 2019-04-09 08:00 | 2019-06-10 17:00 | 45d |  |  | 0 |  |  | 850000 |  | 26d | [5 empty] | 479600 |  | 100% |  | 850000 | 850000
18 | Creation the Line of Balance for the Landing Gear System and its Level 1 Sub-Assemblies | 2019-04-09 08:00 | 2019-05-06 17:00 | 20d | Workers[0.20 #1];The Graduates | 439000 | 0 | 0 | 0 | 439000 | 2019-03-05 16:00 | 10d 4h | 233800 | 0 | 0 | 0 | 0 | 233800 | 0 | 100% | Finished | 439000 | 439000
19 | Defining implication of this MPS on the capacity of the factory | 2019-05-07 08:00 | 2019-05-20 17:00 | 10d | Workers[0.60 #1] | 54000 | 0 | 0 | 0 | 54000 | 2019-03-20 11:00 | 7d | 39600 | 0 | 0 | 0 | 0 | 39600 | 0 | 100% | Finished | 54000 | 54000
20 | Assisting of line of balance in solution providing for problems | 2019-05-21 08:00 | 2019-06-10 17:00 | 15d | Workers[0.40 #1];The Graduates | 357000 | 0 | 0 | 0 | 357000 | 2019-03-29 11:00 | 8d 4h | 206200 | 0 | 0 | 0 | 0 | 206200 | 0 | 100% | Finished | 357000 | 357000
30 | Start to Production | 2019-06-11 08:00 | 2019-10-07 17:00 | 85d |  |  | 0 |  |  | 2075500 |  | 63d 1h | [5 empty] | 2048800 |  | 82.12% |  | 1704337.2107 | 970500
22 | Identifying Production Site | 2019-06-11 08:00 | 2019-07-15 17:00 | 25d | Consultant;Workers[0.40 #1] | 1089000 | 0 | 0 | 0 | 1089000 | 2019-04-10 16:00 | 36d 3h | 1580400 | 0 | 0 | 0 | 0 | 1580400 | 0 | 100% | Finished | 1089000 | 873000
23 | Supplier Selection | 2019-07-02 08:00 | 2019-07-15 17:00 | 10d | Engineers;Workers[0.60 #1] | 181500 | 0 | 0 | 0 | 181500 | 2019-04-10 16:00 | 9d 7h | 179400 | 0 | 0 | 0 | 0 | 179400 | 0 | 100% | Finished | 181500 | 97500
24 | Ordering Machines and Raw Materials | 2019-07-16 08:00 | 2019-09-16 17:00 | 45d | Workers | 370000 | 0 | 0 | 0 | 370000 | 2019-05-31 10:00 | 24d 2h | 204000 | 0 | 0 | 0 | 0 | 204000 | 0 | 100% | Finished | 370000 | 0
25 | Manufacturing Trials | 2019-09-17 08:00 | 2019-10-07 17:00 | 15d | Workers;The Graduates | 435000 | 0 | 0 | 0 | 435000 | 2019-07-04 13:00 | 2d 4h | 85000 | 532000 | 19d | 0 | 0 | 85000 | 532000 | 11.63% | Started | 63837.2107 | 0
33 | Finish | 2019-10-07 17:00 | 2019-10-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP18
| TP Status Date | 2019-07-29 17:00 |  | TP Name | 29.07.2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Landing Gear Project | 2018-07-17 08:00 | 2019-10-07 17:00 | 320d |  |  | 0 |  |  | 11562500 |  | 270d | [5 empty] | 10575800 |  | 99.32% |  | 11484360.4529 | 10847500
31 | Feasibilty Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d |  |  | 0 |  |  | 1805000 |  | 36d 6h | [5 empty] | 1475000 |  | 100% |  | 1805000 | 1805000
1 | Feasiblity Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d | Consultant | 1805000 | 0 | 0 | 0 | 1805000 | 2018-07-17 08:00 | 36d 6h | 1475000 | 0 | 0 | 0 | 0 | 1475000 | 0 | 100% | Finished | 1805000 | 1805000
26 | Market Research | 2018-09-18 08:00 | 2018-10-29 17:00 | 30d |  |  | 0 |  |  | 2057500 |  | 29d 2h | [5 empty] | 1849500 |  | 100% |  | 2057500 | 2057500
3 | Specifying the size of Single and Twin engined light aircrafts replacement in the market | 2018-09-18 08:00 | 2018-10-01 17:00 | 10d | Consultant;Engineers | 532500 | 0 | 0 | 0 | 532500 | 2018-09-05 15:00 | 14d 5h | 773000 | 0 | 0 | 0 | 0 | 773000 | 0 | 100% | Finished | 532500 | 532500
4 | Calculation of the potential annual demand volumes for landing gear struts according to each of the different retail prices | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Consultant;Engineers | 792500 | 0 | 0 | 0 | 792500 | 2018-09-26 11:00 | 10d 2h | 545500 | 0 | 0 | 0 | 0 | 545500 | 0 | 100% | Finished | 792500 | 792500
5 | Calculation of the annual sales volumes actually achievable, taking into account the maximum capacity of the factory set by the directors | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Engineers | 187500 | 0 | 0 | 0 | 187500 | 2018-09-26 11:00 | 8d 4h | 109500 | 0 | 0 | 0 | 0 | 109500 | 0 | 100% | Finished | 187500 | 187500
6 | Calculation of the total annual trade sales revenues and fixed/variable/total costs for each retail | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-10 14:00 | 4d 3h | 240000 | 0 | 0 | 0 | 0 | 240000 | 0 | 100% | Finished | 272500 | 272500
7 | Calculation of the-trade price at which the company should sell at to generate the maximum profit | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-08 16:00 | 3d 2h | 181500 | 0 | 0 | 0 | 0 | 181500 | 0 | 100% | Finished | 272500 | 272500
27 | Business Plan, Financial Analysis, and Team Selection | 2018-10-30 08:00 | 2019-01-07 17:00 | 50d |  |  | 0 |  |  | 2615000 |  | 55d 3h | [5 empty] | 2705000 |  | 100% |  | 2615000 | 2615000
9 | Preparation of Business Plan | 2018-10-30 08:00 | 2018-12-10 17:00 | 30d | Consultant | 1205000 | 0 | 0 | 0 | 1205000 | 2018-10-17 08:00 | 32d 7h | 1320000 | 0 | 0 | 0 | 0 | 1320000 | 0 | 100% | Finished | 1205000 | 1205000
10 | Financial Analysis | 2018-12-18 08:00 | 2019-01-07 17:00 | 15d | Consultant | 605000 | 0 | 0 | 0 | 605000 | 2018-11-30 16:00 | 22d 4h | 905000 | 0 | 0 | 0 | 0 | 905000 | 0 | 100% | Finished | 605000 | 605000
11 | Team Selection (Recruitment of Management Team and Staff) | 2018-12-11 08:00 | 2019-01-07 17:00 | 20d | Consultant | 805000 | 0 | 0 | 0 | 805000 | 2018-11-30 16:00 | 11d 7h | 480000 | 0 | 0 | 0 | 0 | 480000 | 0 | 100% | Finished | 805000 | 805000
28 | Process Analysis | 2019-01-08 08:00 | 2019-04-08 17:00 | 65d |  |  | 0 |  |  | 2159500 |  | 44d 4h | [5 empty] | 1597900 |  | 100% |  | 2159500 | 2159500
13 | Preparation of Bill of Materials (BOM) file | 2019-01-08 08:00 | 2019-03-11 17:00 | 45d | Engineers;Workers | 917500 | 0 | 0 | 0 | 917500 | 2019-01-02 11:00 | 25d 5h | 530000 | 0 | 0 | 0 | 0 | 530000 | 0 | 100% | Finished | 917500 | 917500
14 | Calculation of Machine Requirements | 2019-03-19 08:00 | 2019-04-08 17:00 | 15d | Engineers;Workers[0.40 #1] | 239500 | 0 | 0 | 0 | 239500 | 2019-02-07 08:00 | 11d 2h | 182500 | 0 | 0 | 0 | 0 | 182500 | 0 | 100% | Finished | 239500 | 239500
15 | Calculation of Labour Requirements | 2019-03-26 08:00 | 2019-04-08 17:00 | 10d | Engineers;Workers[0.40 #1] | 163500 | 0 | 0 | 0 | 163500 | 2019-02-07 08:00 | 5d 3h | 93200 | 0 | 0 | 0 | 0 | 93200 | 0 | 100% | Finished | 163500 | 163500
16 | Calculation of Factory Capacity | 2019-03-12 08:00 | 2019-04-08 17:00 | 20d | Workers[0.20 #1];Consultant | 839000 | 0 | 0 | 0 | 839000 | 2019-02-07 08:00 | 18d 7h | 792200 | 0 | 0 | 0 | 0 | 792200 | 0 | 100% | Finished | 839000 | 839000
29 | Productivity Analysis | 2019-04-09 08:00 | 2019-06-10 17:00 | 45d |  |  | 0 |  |  | 850000 |  | 26d | [5 empty] | 479600 |  | 100% |  | 850000 | 850000
18 | Creation the Line of Balance for the Landing Gear System and its Level 1 Sub-Assemblies | 2019-04-09 08:00 | 2019-05-06 17:00 | 20d | Workers[0.20 #1];The Graduates | 439000 | 0 | 0 | 0 | 439000 | 2019-03-05 16:00 | 10d 4h | 233800 | 0 | 0 | 0 | 0 | 233800 | 0 | 100% | Finished | 439000 | 439000
19 | Defining implication of this MPS on the capacity of the factory | 2019-05-07 08:00 | 2019-05-20 17:00 | 10d | Workers[0.60 #1] | 54000 | 0 | 0 | 0 | 54000 | 2019-03-20 11:00 | 7d | 39600 | 0 | 0 | 0 | 0 | 39600 | 0 | 100% | Finished | 54000 | 54000
20 | Assisting of line of balance in solution providing for problems | 2019-05-21 08:00 | 2019-06-10 17:00 | 15d | Workers[0.40 #1];The Graduates | 357000 | 0 | 0 | 0 | 357000 | 2019-03-29 11:00 | 8d 4h | 206200 | 0 | 0 | 0 | 0 | 206200 | 0 | 100% | Finished | 357000 | 357000
30 | Start to Production | 2019-06-11 08:00 | 2019-10-07 17:00 | 85d |  |  | 0 |  |  | 2075500 |  | 78d 1h | [5 empty] | 2468800 |  | 96.24% |  | 1997360.4529 | 1360500
22 | Identifying Production Site | 2019-06-11 08:00 | 2019-07-15 17:00 | 25d | Consultant;Workers[0.40 #1] | 1089000 | 0 | 0 | 0 | 1089000 | 2019-04-10 16:00 | 36d 3h | 1580400 | 0 | 0 | 0 | 0 | 1580400 | 0 | 100% | Finished | 1089000 | 1089000
23 | Supplier Selection | 2019-07-02 08:00 | 2019-07-15 17:00 | 10d | Engineers;Workers[0.60 #1] | 181500 | 0 | 0 | 0 | 181500 | 2019-04-10 16:00 | 9d 7h | 179400 | 0 | 0 | 0 | 0 | 179400 | 0 | 100% | Finished | 181500 | 181500
24 | Ordering Machines and Raw Materials | 2019-07-16 08:00 | 2019-09-16 17:00 | 45d | Workers | 370000 | 0 | 0 | 0 | 370000 | 2019-05-31 10:00 | 24d 2h | 204000 | 0 | 0 | 0 | 0 | 204000 | 0 | 100% | Finished | 370000 | 90000
25 | Manufacturing Trials | 2019-09-17 08:00 | 2019-10-07 17:00 | 15d | Workers;The Graduates | 435000 | 0 | 0 | 0 | 435000 | 2019-07-04 13:00 | 17d 4h | 505000 | 112000 | 4d | 0 | 0 | 505000 | 112000 | 81.4% | Started | 356860.4529 | 0
33 | Finish | 2019-10-07 17:00 | 2019-10-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP19
| TP Status Date | 2019-08-19 17:00 |  | TP Name | 19.08.2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Landing Gear Project | 2018-07-17 08:00 | 2019-10-07 17:00 | 320d |  |  | 0 |  |  | 11562500 |  | 274d | [5 empty] | 10687800 |  | 100% |  | 11562500 | 10967500
31 | Feasibilty Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d |  |  | 0 |  |  | 1805000 |  | 36d 6h | [5 empty] | 1475000 |  | 100% |  | 1805000 | 1805000
1 | Feasiblity Study | 2018-07-17 08:00 | 2018-09-17 17:00 | 45d | Consultant | 1805000 | 0 | 0 | 0 | 1805000 | 2018-07-17 08:00 | 36d 6h | 1475000 | 0 | 0 | 0 | 0 | 1475000 | 0 | 100% | Finished | 1805000 | 1805000
26 | Market Research | 2018-09-18 08:00 | 2018-10-29 17:00 | 30d |  |  | 0 |  |  | 2057500 |  | 29d 2h | [5 empty] | 1849500 |  | 100% |  | 2057500 | 2057500
3 | Specifying the size of Single and Twin engined light aircrafts replacement in the market | 2018-09-18 08:00 | 2018-10-01 17:00 | 10d | Consultant;Engineers | 532500 | 0 | 0 | 0 | 532500 | 2018-09-05 15:00 | 14d 5h | 773000 | 0 | 0 | 0 | 0 | 773000 | 0 | 100% | Finished | 532500 | 532500
4 | Calculation of the potential annual demand volumes for landing gear struts according to each of the different retail prices | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Consultant;Engineers | 792500 | 0 | 0 | 0 | 792500 | 2018-09-26 11:00 | 10d 2h | 545500 | 0 | 0 | 0 | 0 | 545500 | 0 | 100% | Finished | 792500 | 792500
5 | Calculation of the annual sales volumes actually achievable, taking into account the maximum capacity of the factory set by the directors | 2018-10-02 08:00 | 2018-10-22 17:00 | 15d | Engineers | 187500 | 0 | 0 | 0 | 187500 | 2018-09-26 11:00 | 8d 4h | 109500 | 0 | 0 | 0 | 0 | 109500 | 0 | 100% | Finished | 187500 | 187500
6 | Calculation of the total annual trade sales revenues and fixed/variable/total costs for each retail | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-10 14:00 | 4d 3h | 240000 | 0 | 0 | 0 | 0 | 240000 | 0 | 100% | Finished | 272500 | 272500
7 | Calculation of the-trade price at which the company should sell at to generate the maximum profit | 2018-10-23 08:00 | 2018-10-29 17:00 | 5d | Consultant;Engineers | 272500 | 0 | 0 | 0 | 272500 | 2018-10-08 16:00 | 3d 2h | 181500 | 0 | 0 | 0 | 0 | 181500 | 0 | 100% | Finished | 272500 | 272500
27 | Business Plan, Financial Analysis, and Team Selection | 2018-10-30 08:00 | 2019-01-07 17:00 | 50d |  |  | 0 |  |  | 2615000 |  | 55d 3h | [5 empty] | 2705000 |  | 100% |  | 2615000 | 2615000
9 | Preparation of Business Plan | 2018-10-30 08:00 | 2018-12-10 17:00 | 30d | Consultant | 1205000 | 0 | 0 | 0 | 1205000 | 2018-10-17 08:00 | 32d 7h | 1320000 | 0 | 0 | 0 | 0 | 1320000 | 0 | 100% | Finished | 1205000 | 1205000
10 | Financial Analysis | 2018-12-18 08:00 | 2019-01-07 17:00 | 15d | Consultant | 605000 | 0 | 0 | 0 | 605000 | 2018-11-30 16:00 | 22d 4h | 905000 | 0 | 0 | 0 | 0 | 905000 | 0 | 100% | Finished | 605000 | 605000
11 | Team Selection (Recruitment of Management Team and Staff) | 2018-12-11 08:00 | 2019-01-07 17:00 | 20d | Consultant | 805000 | 0 | 0 | 0 | 805000 | 2018-11-30 16:00 | 11d 7h | 480000 | 0 | 0 | 0 | 0 | 480000 | 0 | 100% | Finished | 805000 | 805000
28 | Process Analysis | 2019-01-08 08:00 | 2019-04-08 17:00 | 65d |  |  | 0 |  |  | 2159500 |  | 44d 4h | [5 empty] | 1597900 |  | 100% |  | 2159500 | 2159500
13 | Preparation of Bill of Materials (BOM) file | 2019-01-08 08:00 | 2019-03-11 17:00 | 45d | Engineers;Workers | 917500 | 0 | 0 | 0 | 917500 | 2019-01-02 11:00 | 25d 5h | 530000 | 0 | 0 | 0 | 0 | 530000 | 0 | 100% | Finished | 917500 | 917500
14 | Calculation of Machine Requirements | 2019-03-19 08:00 | 2019-04-08 17:00 | 15d | Engineers;Workers[0.40 #1] | 239500 | 0 | 0 | 0 | 239500 | 2019-02-07 08:00 | 11d 2h | 182500 | 0 | 0 | 0 | 0 | 182500 | 0 | 100% | Finished | 239500 | 239500
15 | Calculation of Labour Requirements | 2019-03-26 08:00 | 2019-04-08 17:00 | 10d | Engineers;Workers[0.40 #1] | 163500 | 0 | 0 | 0 | 163500 | 2019-02-07 08:00 | 5d 3h | 93200 | 0 | 0 | 0 | 0 | 93200 | 0 | 100% | Finished | 163500 | 163500
16 | Calculation of Factory Capacity | 2019-03-12 08:00 | 2019-04-08 17:00 | 20d | Workers[0.20 #1];Consultant | 839000 | 0 | 0 | 0 | 839000 | 2019-02-07 08:00 | 18d 7h | 792200 | 0 | 0 | 0 | 0 | 792200 | 0 | 100% | Finished | 839000 | 839000
29 | Productivity Analysis | 2019-04-09 08:00 | 2019-06-10 17:00 | 45d |  |  | 0 |  |  | 850000 |  | 26d | [5 empty] | 479600 |  | 100% |  | 850000 | 850000
18 | Creation the Line of Balance for the Landing Gear System and its Level 1 Sub-Assemblies | 2019-04-09 08:00 | 2019-05-06 17:00 | 20d | Workers[0.20 #1];The Graduates | 439000 | 0 | 0 | 0 | 439000 | 2019-03-05 16:00 | 10d 4h | 233800 | 0 | 0 | 0 | 0 | 233800 | 0 | 100% | Finished | 439000 | 439000
19 | Defining implication of this MPS on the capacity of the factory | 2019-05-07 08:00 | 2019-05-20 17:00 | 10d | Workers[0.60 #1] | 54000 | 0 | 0 | 0 | 54000 | 2019-03-20 11:00 | 7d | 39600 | 0 | 0 | 0 | 0 | 39600 | 0 | 100% | Finished | 54000 | 54000
20 | Assisting of line of balance in solution providing for problems | 2019-05-21 08:00 | 2019-06-10 17:00 | 15d | Workers[0.40 #1];The Graduates | 357000 | 0 | 0 | 0 | 357000 | 2019-03-29 11:00 | 8d 4h | 206200 | 0 | 0 | 0 | 0 | 206200 | 0 | 100% | Finished | 357000 | 357000
30 | Start to Production | 2019-06-11 08:00 | 2019-10-07 17:00 | 85d |  |  | 0 |  |  | 2075500 |  | 82d 1h | [5 empty] | 2580800 |  | 100% |  | 2075500 | 1480500
22 | Identifying Production Site | 2019-06-11 08:00 | 2019-07-15 17:00 | 25d | Consultant;Workers[0.40 #1] | 1089000 | 0 | 0 | 0 | 1089000 | 2019-04-10 16:00 | 36d 3h | 1580400 | 0 | 0 | 0 | 0 | 1580400 | 0 | 100% | Finished | 1089000 | 1089000
23 | Supplier Selection | 2019-07-02 08:00 | 2019-07-15 17:00 | 10d | Engineers;Workers[0.60 #1] | 181500 | 0 | 0 | 0 | 181500 | 2019-04-10 16:00 | 9d 7h | 179400 | 0 | 0 | 0 | 0 | 179400 | 0 | 100% | Finished | 181500 | 181500
24 | Ordering Machines and Raw Materials | 2019-07-16 08:00 | 2019-09-16 17:00 | 45d | Workers | 370000 | 0 | 0 | 0 | 370000 | 2019-05-31 10:00 | 24d 2h | 204000 | 0 | 0 | 0 | 0 | 204000 | 0 | 100% | Finished | 370000 | 210000
25 | Manufacturing Trials | 2019-09-17 08:00 | 2019-10-07 17:00 | 15d | Workers;The Graduates | 435000 | 0 | 0 | 0 | 435000 | 2019-07-04 13:00 | 21d 4h | 617000 | 0 | 0 | 0 | 0 | 617000 | 0 | 100% | Finished | 435000 | 0
33 | Finish | 2019-10-07 17:00 | 2019-10-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-08-05 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
6.08.2018 17:00 | 2018-07-17 08:00 | 2018-08-06 17:00 | 605000 | 739693.9027 | 605000 | 2018-08-10 11:00 | 134693.9027 | 122.3% | 134693.9027 | 122.3% | 3d 3h | 122.5% | 99.96% | 2019-10-02 10:00 | 2019-07-17 15:00 | 2019-05-13 09:00 | 2019-10-02 14:00 | 2019-07-17 15:00 | 2019-05-15 15:00 | 2019-10-02 14:00 | 2019-07-17 10:00 | 2019-05-15 11:00 | 11427806.0973 | 9457036.8556 | 9457036.8556 | 9439943.7529 | 7845133.0846 | 7831152.5352 | 9457036.8556 | 9453612.9459 | 1.225 | 1.2226 | 1.2226 | 0.99959 | 3.375 | 1.2226 | 1 | 1.225 | 1
27.08.2018 17:00 | 2018-08-06 17:00 | 2018-08-27 17:00 | 1205000 | 1474387.8055 | 1205000 | 2018-09-05 15:00 | 269387.8055 | 122.4% | 269387.8055 | 122.4% | 6d 6h | 122.5% | 99.96% | 2019-09-26 12:00 | 2019-07-17 12:00 | 2019-05-10 15:00 | 2019-09-27 10:00 | 2019-07-17 12:00 | 2019-05-20 10:00 | 2019-09-27 10:00 | 2019-07-17 10:00 | 2019-05-17 17:00 | 11293112.1945 | 9449896.7289 | 9449896.7289 | 9440193.6282 | 7943458.1733 | 7935527.942 | 9449896.7289 | 9447954.28 | 1.225 | 1.2236 | 1.2236 | 0.99958 | 6.75 | 1.2236 | 1 | 1.225 | 1
17.09.2018 17:00 | 2018-08-27 17:00 | 2018-09-17 17:00 | 1805000 | 2110833.3468 | 1916500 | 2018-09-25 15:00 | 305833.3468 | 116.9% | 194333.3468 | 110.1% | 5d 6h | 112.8% | 99.73% | 2019-09-25 12:00 | 2019-08-02 14:00 | 2019-06-28 12:00 | 2019-09-26 11:00 | 2019-08-02 14:00 | 2019-07-04 14:00 | 2019-09-30 10:00 | 2019-08-16 15:00 | 2019-07-17 15:00 | 11368166.6532 | 10498001.3146 | 9998738.3891 | 10297288.1654 | 9254649.1229 | 9525712.9883 | 10393274.4064 | 10457093.2441 | 1.1278 | 1.1014 | 1.1694 | 0.99732 | 5.75 | 1.1014 | 1 | 1.1278 | 1
8.10.2018 17:00 | 2018-09-17 17:00 | 2018-10-08 17:00 | 2677500 | 3216341.4422 | 2837500 | 2018-10-19 12:00 | 538841.4422 | 120.1% | 378841.4422 | 113.4% | 8d 4h | 114.2% | 98.58% | 2019-09-17 09:00 | 2019-07-24 11:00 | 2019-06-10 17:00 | 2019-09-19 16:00 | 2019-07-24 11:00 | 2019-06-20 09:00 | 2019-09-25 12:00 | 2019-08-13 10:00 | 2019-07-08 11:00 | 11183658.5578 | 10200594.1655 | 9785406.4769 | 10148003.8462 | 8967037.2342 | 9286925.5464 | 10113633.8358 | 10190015.6567 | 1.1417 | 1.1335 | 1.2012 | 0.98583 | 8.5 | 1.1335 | 1 | 1.1417 | 1
29.10.2018 17:00 | 2018-10-08 17:00 | 2018-10-29 17:00 | 3862500 | 4196017.1032 | 3689500 | 2018-11-09 10:00 | 333517.1032 | 108.6% | 506517.1032 | 113.7% | 8d 2h | 111% | 99.96% | 2019-09-24 15:00 | 2019-09-02 14:00 | 2019-07-12 17:00 | 2019-09-27 12:00 | 2019-09-02 14:00 | 2019-07-25 17:00 | 2019-09-25 15:00 | 2019-08-23 10:00 | 2019-07-18 12:00 | 11055982.8968 | 10166746.8699 | 10470463.8257 | 10325971.0782 | 9651908.0216 | 9524857.5405 | 10225294.0477 | 10197977.5397 | 1.11 | 1.1373 | 1.0863 | 0.99965 | 8.25 | 1.1373 | 1 | 1.11 | 1
19.11.2018 17:00 | 2018-10-29 17:00 | 2018-11-19 17:00 | 4467500 | 4743545.6562 | 4289500 | 2018-11-28 17:00 | 276045.6562 | 106.2% | 454045.6562 | 110.6% | 7d | 107.8% | 99.92% | 2019-09-26 11:00 | 2019-09-11 11:00 | 2019-08-01 12:00 | 2019-09-30 12:00 | 2019-09-11 11:00 | 2019-08-14 09:00 | 2019-09-26 17:00 | 2019-09-04 16:00 | 2019-08-08 09:00 | 11108454.3438 | 10455753.4268 | 10711632.4593 | 10616364.8551 | 10096914.7865 | 10010766.0661 | 10505284.9194 | 10487220.028 | 1.0778 | 1.1059 | 1.0618 | 0.99917 | 7 | 1.1059 | 1 | 1.0778 | 1
10.12.2018 17:00 | 2018-11-19 17:00 | 2018-12-10 17:00 | 5067500 | 5653464.8919 | 5144500 | 2018-12-24 15:00 | 585964.8919 | 111.6% | 508964.8919 | 109.9% | 9d 6h | 109.3% | 99.53% | 2019-09-13 15:00 | 2019-08-21 16:00 | 2019-07-16 17:00 | 2019-09-19 16:00 | 2019-08-21 16:00 | 2019-07-30 12:00 | 2019-09-24 10:00 | 2019-08-29 15:00 | 2019-08-06 16:00 | 11053535.1081 | 10521561.9779 | 10441081.1202 | 10551460.2296 | 9964245.4294 | 10064687.4307 | 10505270.7358 | 10527515.1469 | 1.0929 | 1.0989 | 1.1156 | 0.99529 | 9.75 | 1.0989 | 1 | 1.0929 | 1
31.12.2018 17:00 | 2018-12-10 17:00 | 2018-12-31 17:00 | 6077500 | 6440833.3445 | 5974500 | 2019-01-07 14:00 | 363333.3445 | 106% | 466333.3445 | 107.8% | 4d 5h | 103.9% | 99.66% | 2019-09-23 17:00 | 2019-09-11 17:00 | 2019-08-13 09:00 | 2019-09-26 16:00 | 2019-09-11 17:00 | 2019-08-23 15:00 | 2019-10-01 11:00 | 2019-09-20 09:00 | 2019-09-02 12:00 | 11096166.6555 | 10725344.4633 | 10807248.7197 | 10906094.7736 | 10457344.949 | 10549034.2876 | 10741502.4642 | 10760426.7352 | 1.0385 | 1.0781 | 1.0598 | 0.99664 | 4.625 | 1.0781 | 1 | 1.0385 | 1
21.01.2019 17:00 | 2018-12-31 17:00 | 2019-01-21 17:00 | 6695000 | 6973536.6118 | 6319500 | 2019-02-08 17:00 | 278536.6118 | 104.2% | 654036.6118 | 110.3% | 14d | 110.4% | 99.98% | 2019-09-26 10:00 | 2019-09-19 10:00 | 2019-08-09 11:00 | 2019-09-30 11:00 | 2019-09-19 10:00 | 2019-08-28 09:00 | 2019-09-17 17:00 | 2019-08-26 16:00 | 2019-08-06 11:00 | 10908463.3882 | 10478072.0053 | 10725171.2676 | 10477285.6202 | 10311970.5534 | 10087333.6961 | 10525249.2674 | 10477914.7045 | 1.1037 | 1.1035 | 1.0416 | 0.99979 | 14 | 1.1035 | 1 | 1.1037 | 1
11.02.2019 17:00 | 2019-01-21 17:00 | 2019-02-11 17:00 | 6995000 | 7702875.6334 | 6805500 | 2019-03-20 12:00 | 707875.6334 | 110.1% | 897375.6334 | 113.2% | 26d 4h | 117.7% | 98.21% | 2019-09-10 11:00 | 2019-08-27 14:00 | 2019-07-10 15:00 | 2019-09-16 16:00 | 2019-08-27 14:00 | 2019-08-05 10:00 | 2019-08-30 12:00 | 2019-07-31 17:00 | 2019-07-11 15:00 | 10665124.3666 | 10215482.8269 | 10310434.2258 | 10085634.0226 | 9902113.6556 | 9703502.4024 | 10234059.2954 | 10188697.0862 | 1.1767 | 1.1319 | 1.1012 | 0.98207 | 26.5 | 1.1319 | 1 | 1.1767 | 1
4.03.2019 17:00 | 2019-02-11 17:00 | 2019-03-04 17:00 | 7295000 | 8598430.4504 | 7591000 | 2019-04-08 12:00 | 1303430.4504 | 117.9% | 1007430.4504 | 113.3% | 24d 4h | 114.8% | 99.79% | 2019-08-16 16:00 | 2019-07-31 12:00 | 2019-06-17 14:00 | 2019-08-27 12:00 | 2019-07-31 12:00 | 2019-07-12 17:00 | 2019-09-03 12:00 | 2019-08-09 14:00 | 2019-07-23 11:00 | 10555069.5496 | 10207785.9449 | 10105748.1844 | 10171852.1144 | 9811109.0743 | 9869467.9731 | 10186721.2841 | 10200519.3506 | 1.1485 | 1.1327 | 1.1787 | 0.99793 | 24.5 | 1.1327 | 1 | 1.1485 | 1
25.03.2019 17:00 | 2019-03-04 17:00 | 2019-03-25 17:00 | 7905500 | 9106857.1424 | 7884600 | 2019-05-14 10:00 | 1201357.1424 | 115.2% | 1222257.1424 | 115.5% | 35d 2h | 119.6% | 100% | 2019-08-21 15:00 | 2019-08-08 15:00 | 2019-06-18 12:00 | 2019-08-29 14:00 | 2019-08-08 15:00 | 2019-07-22 14:00 | 2019-08-19 15:00 | 2019-07-25 14:00 | 2019-07-09 16:00 | 10340242.8576 | 10010664.0605 | 10016299.6969 | 9938099.2537 | 9730198.2308 | 9662493.291 | 10011788.8027 | 9995743.7011 | 1.1958 | 1.155 | 1.152 | 0.99996 | 35.25 | 1.155 | 1 | 1.1958 | 1
15.04.2019 17:00 | 2019-03-25 17:00 | 2019-04-15 17:00 | 8752000 | 9655448.0643 | 8317000 | 2019-06-14 15:00 | 903448.0643 | 110.3% | 1338448.0643 | 116.1% | 43d 6h | 122.4% | 99.28% | 2019-09-02 17:00 | 2019-08-26 17:00 | 2019-07-01 16:00 | 2019-09-09 16:00 | 2019-08-26 17:00 | 2019-08-07 16:00 | 2019-08-07 10:00 | 2019-07-17 11:00 | 2019-07-04 09:00 | 10224051.9357 | 9959694.4502 | 10045611.4979 | 9874592.1569 | 9805989.608 | 9658677.1426 | 9976187.7471 | 9941938.0746 | 1.2244 | 1.1609 | 1.1032 | 0.99283 | 43.75 | 1.1609 | 1 | 1.2244 | 1
6.05.2019 17:00 | 2019-04-15 17:00 | 2019-05-06 17:00 | 9076000 | 10215644.3191 | 9078400 | 2019-07-02 17:00 | 1139644.3191 | 112.6% | 1137244.3191 | 112.5% | 41d | 119.5% | 98.5% | 2019-08-23 12:00 | 2019-08-19 10:00 | 2019-07-04 14:00 | 2019-08-30 14:00 | 2019-08-19 10:00 | 2019-08-06 17:00 | 2019-08-09 17:00 | 2019-07-25 15:00 | 2019-07-17 10:00 | 10425255.6809 | 10275318.5919 | 10275002.17 | 10205251.3665 | 10141791.8724 | 10079805.9932 | 10275255.2941 | 10260616.6283 | 1.1952 | 1.1253 | 1.1256 | 0.98502 | 41 | 1.1253 | 1 | 1.1952 | 1
27.05.2019 17:00 | 2019-05-06 17:00 | 2019-05-27 17:00 | 9255000 | 10661005.1703 | 9726400 | 2019-07-12 12:00 | 1406005.1703 | 115.2% | 934605.1703 | 109.6% | 33d 4h | 114.9% | 99.7% | 2019-08-14 09:00 | 2019-08-08 15:00 | 2019-07-05 12:00 | 2019-08-20 16:00 | 2019-08-08 15:00 | 2019-08-02 09:00 | 2019-08-21 12:00 | 2019-08-09 12:00 | 2019-08-02 16:00 | 10627894.8297 | 10548864.5961 | 10509003.0018 | 10511066.6796 | 10440395.5112 | 10442278.2751 | 10540570.6994 | 10541016.4725 | 1.1489 | 1.0961 | 1.1519 | 0.99703 | 33.4 | 1.0961 | 1 | 1.1489 | 1
17.06.2019 17:00 | 2019-05-27 17:00 | 2019-06-17 17:00 | 9712000 | 10941932.9894 | 9970800 | 2019-08-14 16:00 | 1229932.9894 | 112.7% | 971132.9894 | 109.7% | 41d 7h | 117.4% | 99.99% | 2019-08-20 17:00 | 2019-08-16 17:00 | 2019-07-12 16:00 | 2019-08-26 14:00 | 2019-08-16 17:00 | 2019-08-13 09:00 | 2019-08-09 09:00 | 2019-08-01 12:00 | 2019-07-29 14:00 | 10591367.0106 | 10536289.622 | 10521611.8916 | 10499176.3461 | 10472725.502 | 10452281.1859 | 10533291.8278 | 10528455.6498 | 1.1745 | 1.0974 | 1.1266 | 0.99995 | 41.875 | 1.0974 | 1 | 1.1745 | 1
8.07.2019 17:00 | 2019-06-17 17:00 | 2019-07-08 17:00 | 10457500 | 11191337.2107 | 10155800 | 2019-09-18 15:00 | 733837.2107 | 107% | 1035537.2107 | 110.2% | 51d 6h | 120.3% | 100% | 2019-09-09 15:00 | 2019-09-06 17:00 | 2019-07-31 11:00 | 2019-09-12 09:00 | 2019-09-06 17:00 | 2019-09-02 17:00 | 2019-07-26 10:00 | 2019-07-23 17:00 | 2019-07-22 17:00 | 10526962.7893 | 10492619.0043 | 10502624.9411 | 10464346.084 | 10470533.1432 | 10435796.2383 | 10494573.736 | 10486557.3642 | 1.2029 | 1.102 | 1.0702 | 0.99999 | 51.75 | 1.102 | 1 | 1.2029 | 1
29.07.2019 17:00 | 2019-07-08 17:00 | 2019-07-29 17:00 | 10847500 | 11484360.4529 | 10575800 | 2019-10-03 10:00 | 636860.4529 | 105.9% | 908560.4529 | 108.6% | 47d 2h | 117.5% | 99.99% | 2019-09-12 11:00 | 2019-09-12 10:00 | 2019-08-09 11:00 | 2019-09-16 09:00 | 2019-09-12 10:00 | 2019-09-09 15:00 | 2019-08-01 15:00 | 2019-08-01 11:00 | 2019-08-01 09:00 | 10653939.5471 | 10647757.7051 | 10649606.3509 | 10642301.7422 | 10643767.3203 | 10637040.6001 | 10648119.9884 | 10646596.0494 | 1.175 | 1.0859 | 1.0587 | 0.9999 | 47.25 | 1.0859 | 1 | 1.175 | 1
19.08.2019 17:00 | 2019-07-29 17:00 | 2019-08-19 17:00 | 10967500 | 11562500 | 10687800 | 2019-10-07 17:00 | 595000 | 105.4% | 874700 | 108.2% | 35d | 112.3% | 100% | 2019-09-13 12:00 | 2019-09-13 12:00 | 2019-08-13 14:00 | 2019-09-16 12:00 | 2019-09-13 12:00 | 2019-09-12 09:00 | 2019-08-19 17:00 | 2019-08-19 17:00 | 2019-08-19 17:00 | 10687800 | 10687800 | 10687800 | 10687800 | 10687800 | 10687800 | 10687800 | 10687800 | 1.1228 | 1.0818 | 1.0543 | 1 | 35 | 1.0818 | 1 | 1.1228 | 1