## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | Project 22 ProTrack | 1 |  |  | 2018-01-01 08:00 | 2018-01-31 17:00 | 23d |  |  | 19100 |  |  | 37980
17 | Draw up a technical file | 1.1 |  | FS18 | 2018-01-01 08:00 | 2018-01-02 17:00 | 2d | Resource1[3.00 #5] | 2400 | 0 | 0 | 0 | 2400
18 | Kick-off meeting | 1.2 | 17FS | FS3 | 2018-01-03 08:00 | 2018-01-03 17:00 | 1d | Resource1[5.00 #5] | 4000 | 0 | 0 | 0 | 4000
3 | Coordination meeting and working session | 1.3 | 18FS | FS4;FS7 | 2018-01-04 08:00 | 2018-01-08 17:00 | 3d | Resource1[5.00 #5] | 4000 | 0 | 0 | 0 | 4000
4 | Drilling holes | 1.4 | 3FS | FS5 | 2018-01-09 08:00 | 2018-01-11 17:00 | 3d | Resource 2[2.00 #4] | 640 | 0 | 0 | 0 | 640
5 | Construction cable ways | 1.5 | 4FS | FS6 | 2018-01-16 08:00 | 2018-01-18 17:00 | 3d | Resource 2[2.00 #4] | 640 | 1500 | 0 | 0 | 2140
6 | Cabling | 1.6 | 5FS | FS14 | 2018-01-19 08:00 | 2018-01-23 17:00 | 3d | Resource 2[2.00 #4] | 640 | 3600 | 0 | 0 | 4240
7 | Cabinet delivery and installation | 1.7 | 3FS | FS8;FS9 | 2018-01-09 08:00 | 2018-01-09 17:00 | 1d | Resource 2[2.00 #4] | 640 | 1000 | 0 | 0 | 1640
8 | Connecting the cabinet to the data network of Infrabel via fibre optics | 1.8 | 7FS | FS15 | 2018-01-12 08:00 | 2018-01-15 17:00 | 2d | Resource 2[3.00 #4] | 960 | 1500 | 0 | 0 | 2460
9 | Equipping the cabinet with patch panels and switches | 1.9 | 7FS | FS10;FS12 | 2018-01-10 08:00 | 2018-01-10 17:00 | 1d | Resource 2[2.00 #4] | 640 | 2000 | 0 | 0 | 2640
10 | Connecting the camera cables to the patch panel in the cabinet | 1.10 | 9FS | FS11 | 2018-01-11 08:00 | 2018-01-11 17:00 | 1d | Resource 2[2.00 #4] | 640 | 0 | 0 | 0 | 640
11 | Measurements of the cables | 1.11 | 10FS | FS15 | 2018-01-12 08:00 | 2018-01-12 17:00 | 1d | Resource 2 | 320 | 0 | 0 | 0 | 320
12 | Delivery and unpacking the cameras | 1.12 | 9FS | FS13 | 2018-01-16 08:00 | 2018-01-18 17:00 | 3d | Resource 2[2.00 #4] | 640 | 9000 | 0 | 0 | 9640
13 | Inspection of the cameras | 1.13 | 12FS | FS14 | 2018-01-19 08:00 | 2018-01-22 17:00 | 2d | Resource 2[2.00 #4] | 640 | 0 | 0 | 0 | 640
14 | Inserting and connecting the camera | 1.14 | 6FS;13FS | FS15 | 2018-01-24 08:00 | 2018-01-25 17:00 | 2d | Resource 2[2.00 #4] | 640 | 500 | 0 | 0 | 1140
15 | Camera programming and testing | 1.15 | 11FS;8FS;14FS | FS16 | 2018-01-26 08:00 | 2018-01-29 17:00 | 2d | Resource 2 | 320 | 0 | 0 | 0 | 320
16 | Drawing an as-built plan of the installation and the delivery of the project | 1.16 | 15FS |  | 2018-01-30 08:00 | 2018-01-31 17:00 | 2d | Resource 2;Resource1 | 1120 | 0 | 0 | 0 | 1120

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Resource1 | Renewable | 5 | 800 | 0 | 17[3.00 Resource1];18[5.00 Resource1];3[5.00 Resource1];16; | 11200
2 | Resource 2 | Renewable | 4 | 320 | 0 | 4[2.00 Resource 2];5[2.00 Resource 2];6[2.00 Resource 2];7[2.00 Resource 2];8[3.00 Resource 2];9[2.00 Resource 2];10[2.00 Resource 2];11;12[2.00 Resource 2];13[2.00 Resource 2];14[2.00 Resource 2];15;16; | 7680

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | Project 22 ProTrack | 184h
17 | Draw up a technical file | 16h | standard - symmetric | 80 | 100 | 120
18 | Kick-off meeting | 8h | standard - symmetric | 80 | 100 | 120
3 | Coordination meeting and working session | 24h | standard - symmetric | 80 | 100 | 120
4 | Drilling holes | 24h | standard - symmetric | 80 | 100 | 120
5 | Construction cable ways | 24h | standard - symmetric | 80 | 100 | 120
6 | Cabling | 24h | standard - symmetric | 80 | 100 | 120
7 | Cabinet delivery and installation | 8h | standard - symmetric | 80 | 100 | 120
8 | Connecting the cabinet to the data network of Infrabel via fibre optics | 16h | standard - symmetric | 80 | 100 | 120
9 | Equipping the cabinet with patch panels and switches | 8h | standard - symmetric | 80 | 100 | 120
10 | Connecting the camera cables to the patch panel in the cabinet | 8h | standard - symmetric | 80 | 100 | 120
11 | Measurements of the cables | 8h | standard - symmetric | 80 | 100 | 120
12 | Delivery and unpacking the cameras | 24h | standard - symmetric | 80 | 100 | 120
13 | Inspection of the cameras | 16h | standard - symmetric | 80 | 100 | 120
14 | Inserting and connecting the camera | 16h | standard - symmetric | 80 | 100 | 120
15 | Camera programming and testing | 16h | standard - symmetric | 80 | 100 | 120
16 | Drawing an as-built plan of the installation and the delivery of the project | 16h | standard - symmetric | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t))