## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | Project | 1 |  |  | 2019-01-01 08:00 | 2019-10-25 17:00 | 214d |  |  | 379794 |  |  | 439234
1 | Total | 1.1 |  |  | 2019-01-01 08:00 | 2019-10-25 17:00 | 214d |  |  | 379794 |  |  | 439234
2 | Research for possible docking stations | 1.1.1 |  |  | 2019-01-01 08:00 | 2019-03-05 17:00 | 46d |  |  | 0 |  |  | 15680
3 | 1. Analysis of car usage in general, link to car sharing, environment, cost of parking | 1.1.1.1 |  | FS4 | 2019-01-01 08:00 | 2019-01-14 17:00 | 10d | Project Leader | 2400 | 0 | 0 | 0 | 2400
4 | 2. Type of cars | 1.1.1.2 | 3FS | FS5 | 2019-01-15 08:00 | 2019-01-22 17:00 | 6d | Engineer | 2400 | 0 | 0 | 0 | 2400
5 | 3. Determine amount of ars needed and parking place | 1.1.1.3 | 4FS | FS6;FS7;FS8 | 2019-01-23 08:00 | 2019-01-30 17:00 | 6d | Engineer | 2400 | 0 | 0 | 0 | 2400
6 | 4. Research for charging stations (suppliers) | 1.1.1.4 | 5FS | FS9 | 2019-01-31 08:00 | 2019-02-01 17:00 | 2d | Engineer | 800 | 0 | 0 | 0 | 800
7 | 5. Research use of exsisting charging stations | 1.1.1.5 | 5FS | FS9 | 2019-01-31 08:00 | 2019-01-31 17:00 | 1d | Engineer | 400 | 0 | 0 | 0 | 400
8 | 6. Research for traffic sign supplier (Trafiroad) | 1.1.1.6 | 5FS | FS9 | 2019-01-31 08:00 | 2019-01-31 17:00 | 1d | Engineer | 400 | 0 | 0 | 0 | 400
9 | 7. Research amount of staff needed (extra contractors) | 1.1.1.7 | 6FS;7FS;8FS | FS10 | 2019-02-04 08:00 | 2019-02-06 17:00 | 3d | Engineer | 1200 | 0 | 0 | 0 | 1200
10 | 8. Feasibility study | 1.1.1.8 | 9FS | FS11 | 2019-02-07 08:00 | 2019-02-15 17:00 | 7d | Engineer | 2800 | 0 | 0 | 0 | 2800
11 | 9. Search for funding (VC, Business angels, bankloan) | 1.1.1.9 | 10FS | FS13 | 2019-02-18 08:00 | 2019-03-05 17:00 | 12d | Project Leader | 2880 | 0 | 0 | 0 | 2880
12 | Meeting | 1.1.2 |  |  | 2019-03-06 08:00 | 2019-07-30 17:00 | 105d |  |  | 0 |  |  | 24000
13 | 10. Contact city to get the approval | 1.1.2.1 | 11FS | FS14;FS15;FS19 | 2019-03-06 08:00 | 2019-04-02 17:00 | 20d | Project Leader | 4800 | 0 | 0 | 0 | 4800
14 | 11. Asking city for blue prints power network | 1.1.2.2 | 13FS | FS16 | 2019-04-10 08:00 | 2019-05-07 17:00 | 20d | Project Leader | 4800 | 0 | 0 | 0 | 4800
15 | 12. Meeting with car leasers + quotation | 1.1.2.3 | 13FS | FS25;FS34 | 2019-06-26 08:00 | 2019-07-30 17:00 | 25d | Project Leader | 6000 | 0 | 0 | 0 | 6000
16 | 13. Meeting with docking station suppliers | 1.1.2.4 | 14FS | FS17 | 2019-05-08 08:00 | 2019-06-11 17:00 | 25d | Project Leader | 6000 | 0 | 0 | 0 | 6000
17 | 14. Meeting with possible contractors | 1.1.2.5 | 16FS | FS27 | 2019-06-12 08:00 | 2019-06-25 17:00 | 10d | Project Leader | 2400 | 0 | 0 | 0 | 2400
18 | IT | 1.1.3 |  |  | 2019-04-03 08:00 | 2019-10-22 17:00 | 145d |  |  | 116000 |  |  | 117200
19 | 15. Web/app developer search | 1.1.3.1 | 13FS | FS20 | 2019-04-03 08:00 | 2019-04-09 17:00 | 5d | Project Leader | 1200 | 0 | 0 | 0 | 1200
20 | 16. Developing website/app | 1.1.3.2 | 19FS | FS21 | 2019-04-10 08:00 | 2019-07-16 17:00 | 70d |  | 0 | 90000 | 0 | 0 | 90000
21 | 17. Developing payment system | 1.1.3.3 | 20FS | FS22;FS23 | 2019-07-17 08:00 | 2019-10-01 17:00 | 55d |  | 0 | 20000 | 0 | 0 | 20000
22 | 18. Testing &amp; approving app | 1.1.3.4 | 21FS | FS41 | 2019-10-02 08:00 | 2019-10-22 17:00 | 15d |  | 0 | 4500 | 0 | 0 | 4500
23 | 19. Testing &amp; approving payment system | 1.1.3.5 | 21FS | FS41 | 2019-10-02 08:00 | 2019-10-22 17:00 | 15d |  | 0 | 1500 | 0 | 0 | 1500
24 | Repair and maintenance | 1.1.4 |  |  | 2019-07-31 08:00 | 2019-08-27 17:00 | 20d |  |  | 0 |  |  | 4800
25 | 20. Negotiate maintenance contract with possible partners | 1.1.4.1 | 15FS |  | 2019-07-31 08:00 | 2019-08-27 17:00 | 20d | Project Leader | 4800 | 0 | 0 | 0 | 4800
26 | Construction | 1.1.5 |  |  | 2019-06-26 08:00 | 2019-08-22 17:00 | 42d |  |  | 119794 |  |  | 119794
27 | 21. Drilling the holes where the charging blocks will be put by Eandis and where the traffic signs will be put | 1.1.5.1 | 17FS | FS28;FS45 | 2019-06-26 08:00 | 2019-07-11 17:00 | 12d |  | 0 | 10599 | 0 | 0 | 10599
28 | 22. Delivery and placing of the charging blocks (UwLaadpunt) | 1.1.5.2 | 27FS | FS29;FS30;FS31;FS42 | 2019-07-12 08:00 | 2019-07-29 17:00 | 12d |  | 0 | 78715 | 0 | 0 | 78715
29 | 23. Access power network: connecting charging blocks to power grid (Eandis) | 1.1.5.3 | 28FS | FS32;FS43 | 2019-07-30 08:00 | 2019-08-14 17:00 | 12d |  | 0 | 19500 | 0 | 0 | 19500
30 | 24. Installation of visibility marks (Trafiroad) | 1.1.5.4 | 28FS | FS34;FS44 | 2019-07-30 08:00 | 2019-08-06 17:00 | 6d |  | 0 | 2480 | 0 | 0 | 2480
31 | 25. Installation of trafic signs (Trafiroad) | 1.1.5.5 | 28FS | FS34;FS44 | 2019-07-30 08:00 | 2019-08-06 17:00 | 6d |  | 0 | 8500 | 0 | 0 | 8500
32 | 26. Testing of the charging blocks | 1.1.5.6 | 29FS | FS34 | 2019-08-15 08:00 | 2019-08-22 17:00 | 6d |  | 0 | 0 | 0 | 0 | 0
33 | Delivery | 1.1.6 |  |  | 2019-08-23 08:00 | 2019-08-30 17:00 | 6d |  |  | 144000 |  |  | 144000
34 | 27. Delivery cars | 1.1.6.1 | 15FS;30FS;31FS;32FS | FS36;FS46 | 2019-08-23 08:00 | 2019-08-30 17:00 | 6d |  | 0 | 144000 | 0 | 0 | 144000
35 | Finalising actions | 1.1.7 |  |  | 2019-09-02 08:00 | 2019-10-04 17:00 | 25d |  |  | 0 |  |  | 8960
36 | 28. Placing cars | 1.1.7.1 | 34FS | FS37 | 2019-09-02 08:00 | 2019-09-06 17:00 | 5d | Worker | 960 | 0 | 0 | 0 | 960
37 | 29. Final testing of the finished system | 1.1.7.2 | 36FS | FS39 | 2019-09-09 08:00 | 2019-10-04 17:00 | 20d | Engineer | 8000 | 0 | 0 | 0 | 8000
38 | Marketing | 1.1.8 |  |  | 2019-10-07 08:00 | 2019-10-25 17:00 | 15d |  |  | 0 |  |  | 3360
39 | 30. Publicity campaign for our company | 1.1.8.1 | 37FS |  | 2019-10-07 08:00 | 2019-10-25 17:00 | 15d | Marketeer | 3360 | 0 | 0 | 0 | 3360
40 | Payments | 1.1.9 |  |  | 2019-07-12 08:00 | 2019-10-23 17:00 | 74d |  |  | 0 |  |  | 1440
41 | 31. Payment of Web/app developers | 1.1.9.1 | 22FS;23FS | FS48 | 2019-10-23 08:00 | 2019-10-23 17:00 | 1d | Administrator | 240 | 0 | 0 | 0 | 240
42 | 32. Payment 'UwLaadpunt' | 1.1.9.2 | 28FS | FS48 | 2019-07-30 08:00 | 2019-07-30 17:00 | 1d | Administrator | 240 | 0 | 0 | 0 | 240
43 | 33. Payment 'Eandis' | 1.1.9.3 | 29FS | FS48 | 2019-08-15 08:00 | 2019-08-15 17:00 | 1d | Administrator | 240 | 0 | 0 | 0 | 240
44 | 34. Payment 'Traffiroad' | 1.1.9.4 | 30FS;31FS | FS48 | 2019-08-07 08:00 | 2019-08-07 17:00 | 1d | Administrator | 240 | 0 | 0 | 0 | 240
45 | 35. Payment of the construction firm | 1.1.9.5 | 27FS | FS48 | 2019-07-12 08:00 | 2019-07-12 17:00 | 1d | Administrator | 240 | 0 | 0 | 0 | 240
46 | 36. Payment carleasing | 1.1.9.6 | 34FS | FS48 | 2019-09-02 08:00 | 2019-09-02 17:00 | 1d | Administrator | 240 | 0 | 0 | 0 | 240
47 | launch | 1.1.10 |  |  | 2019-10-23 17:00 | 2019-10-23 17:00 | 0 |  |  | 0 |  |  | 0
48 | 37. Launch | 1.1.10.1 | 41FS;42FS;43FS;44FS;45FS;46FS |  | 2019-10-23 17:00 | 2019-10-23 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Project Leader | Renewable | 1 | 0 | 30 | 3;11;13;14;15;16;17;19;25; | 35280
2 | Engineer | Renewable | 3 | 0 | 50 | 4;5;6;7;8;9;10;37; | 18400
3 | Worker | Renewable | 2 | 0 | 24 | 36; | 960
4 | Marketeer | Renewable | 1 | 0 | 28 | 39; | 3360
5 | Administrator | Renewable | 1 | 0 | 30 | 41;42;43;44;45;46; | 1440

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | Project | 1712h
1 | Total | 1712h
2 | Research for possible docking stations | 368h
3 | 1. Analysis of car usage in general, link to car sharing, environment, cost of parking | 80h | standard - symmetric | 80 | 100 | 120
4 | 2. Type of cars | 48h | standard - symmetric | 80 | 100 | 120
5 | 3. Determine amount of ars needed and parking place | 48h | standard - symmetric | 80 | 100 | 120
6 | 4. Research for charging stations (suppliers) | 16h | standard - symmetric | 80 | 100 | 120
7 | 5. Research use of exsisting charging stations | 8h | standard - symmetric | 80 | 100 | 120
8 | 6. Research for traffic sign supplier (Trafiroad) | 8h | standard - symmetric | 80 | 100 | 120
9 | 7. Research amount of staff needed (extra contractors) | 24h | standard - symmetric | 80 | 100 | 120
10 | 8. Feasibility study | 56h | standard - symmetric | 80 | 100 | 120
11 | 9. Search for funding (VC, Business angels, bankloan) | 96h | standard - symmetric | 80 | 100 | 120
12 | Meeting | 840h
13 | 10. Contact city to get the approval | 160h | standard - symmetric | 80 | 100 | 120
14 | 11. Asking city for blue prints power network | 160h | standard - symmetric | 80 | 100 | 120
15 | 12. Meeting with car leasers + quotation | 200h | standard - symmetric | 80 | 100 | 120
16 | 13. Meeting with docking station suppliers | 200h | standard - symmetric | 80 | 100 | 120
17 | 14. Meeting with possible contractors | 80h | standard - symmetric | 80 | 100 | 120
18 | IT | 1160h
19 | 15. Web/app developer search | 40h | standard - symmetric | 80 | 100 | 120
20 | 16. Developing website/app | 560h | standard - symmetric | 80 | 100 | 120
21 | 17. Developing payment system | 440h | standard - symmetric | 80 | 100 | 120
22 | 18. Testing &amp; approving app | 120h | standard - symmetric | 80 | 100 | 120
23 | 19. Testing &amp; approving payment system | 120h | standard - symmetric | 80 | 100 | 120
24 | Repair and maintenance | 160h
25 | 20. Negotiate maintenance contract with possible partners | 160h | standard - symmetric | 80 | 100 | 120
26 | Construction | 336h
27 | 21. Drilling the holes where the charging blocks will be put by Eandis and where the traffic signs will be put | 96h | standard - symmetric | 80 | 100 | 120
28 | 22. Delivery and placing of the charging blocks (UwLaadpunt) | 96h | standard - symmetric | 80 | 100 | 120
29 | 23. Access power network: connecting charging blocks to power grid (Eandis) | 96h | standard - symmetric | 80 | 100 | 120
30 | 24. Installation of visibility marks (Trafiroad) | 48h | standard - symmetric | 80 | 100 | 120
31 | 25. Installation of trafic signs (Trafiroad) | 48h | standard - symmetric | 80 | 100 | 120
32 | 26. Testing of the charging blocks | 48h | standard - symmetric | 80 | 100 | 120
33 | Delivery | 48h
34 | 27. Delivery cars | 48h | standard - symmetric | 80 | 100 | 120
35 | Finalising actions | 200h
36 | 28. Placing cars | 40h | standard - symmetric | 80 | 100 | 120
37 | 29. Final testing of the finished system | 160h | standard - symmetric | 80 | 100 | 120
38 | Marketing | 120h
39 | 30. Publicity campaign for our company | 120h | standard - symmetric | 80 | 100 | 120
40 | Payments | 592h
41 | 31. Payment of Web/app developers | 8h | standard - symmetric | 80 | 100 | 120
42 | 32. Payment 'UwLaadpunt' | 8h | standard - symmetric | 80 | 100 | 120
43 | 33. Payment 'Eandis' | 8h | standard - symmetric | 80 | 100 | 120
44 | 34. Payment 'Traffiroad' | 8h | standard - symmetric | 80 | 100 | 120
45 | 35. Payment of the construction firm | 8h | standard - symmetric | 80 | 100 | 120
46 | 36. Payment carleasing | 8h | standard - symmetric | 80 | 100 | 120
47 | launch | 0
48 | 37. Launch | 0 | standard - symmetric | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t))