## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | Cornflakes | 1 |  |  | 2018-11-28 08:00 | 2019-12-18 10:00 | 275d 2h |  |  | 30500 |  |  | 751410
31 | Meeting with company | 1.1 |  | FS5 | 2018-11-28 08:00 | 2018-11-28 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0
5 | Selection Raw Materials | 1.2 | 31FS | FS6;FS14;FS23 | 2018-11-29 08:00 | 2018-12-07 17:00 | 7d | Engineer[2.00 #4] | 22800 | 0 | 0 | 0 | 22800
6 | Order an receive raw materials | 1.3 | 5FS | FS7 | 2018-12-10 08:00 | 2018-12-28 17:00 | 15d |  | 0 | 1300 | 0 | 0 | 1300
7 | R&D test trail | 1.4 | 6FS | FS8 | 2018-12-31 08:00 | 2019-03-22 17:00 | 60d | Engineer[2.00 #4] | 192400 | 0 | 12 | 5760 | 198160
8 | R&D analysis texture | 1.5 | 7FS | FS9 | 2019-03-25 08:00 | 2019-04-22 17:00 | 21d | Engineer[2.00 #4] | 67600 | 0 | 0 | 0 | 67600
9 | R&D taste test | 1.6 | 8FS | FS12 | 2019-04-23 08:00 | 2019-08-12 17:00 | 80d |  | 0 | 0 | 0 | 0 | 0
12 | Feedback loop: taste | 1.7 | 9FS | FS13 | 2019-08-13 08:00 | 2019-08-14 17:00 | 2d | Engineer[2.00 #4] | 6800 | 0 | 0 | 0 | 6800
13 | Order and receive final raw materials | 1.8 | 12FS | FS24 | 2019-08-15 08:00 | 2019-09-04 17:00 | 15d |  | 0 | 10000 | 0 | 0 | 10000
14 | R&D designing extrusion head | 1.9 | 5FS | FS15 | 2018-12-10 08:00 | 2019-04-04 10:00 | 83d 2h | Engineer[2.00 #4] | 266800 | 2000 | 0 | 0 | 268800
15 | Feedback loop: extrusion head | 1.10 | 14FS | FS21 | 2019-04-23 08:00 | 2019-04-23 15:00 | 6h | Engineer[2.00 #4] | 2800 | 0 | 0 | 0 | 2800
21 | Production Final extrusion head | 1.11 | 15FS | FS22 | 2019-04-23 15:00 | 2019-06-06 15:00 | 32d |  | 0 | 15000 | 0 | 0 | 15000
22 | Final extrusion head installation | 1.12 | 21FS | FS24 | 2019-06-06 15:00 | 2019-06-20 15:00 | 10d | Operator | 12150 | 0 | 0 | 0 | 12150
23 | Packaging design | 1.13 | 5FS | FS24 | 2019-04-04 10:00 | 2019-05-09 10:00 | 25d | Engineer[2.00 #4] | 80400 | 1200 | 0 | 0 | 81600
24 | Industrial test | 1.14 | 13FS;22FS;23FS | FS25;FS29;FS30 | 2019-09-05 08:00 | 2019-09-18 17:00 | 10d | Operator[3.00 #3] | 36450 | 0 | 0 | 0 | 36450
25 | Extra quality check | 1.15 | 24FS | FS28 | 2019-09-19 08:00 | 2019-09-20 17:00 | 2d | Operator | 2550 | 0 | 0 | 0 | 2550
28 | Consumer test | 1.16 | 25FS |  | 2019-09-23 08:00 | 2019-12-18 10:00 | 62d 2h |  | 0 | 1000 | 0 | 0 | 1000
29 | Control claims | 1.17 | 24FS |  | 2019-09-19 08:00 | 2019-09-27 17:00 | 7d | Engineer | 11400 | 0 | 0 | 0 | 11400
30 | Adjust HACCP | 1.18 | 24FS |  | 2019-09-19 08:00 | 2019-09-30 17:00 | 8d | Engineer | 13000 | 0 | 0 | 0 | 13000

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Engineer | Renewable | 4 | 200 | 200 | 5[2.00 Engineer];7[2.00 Engineer];8[2.00 Engineer];12[2.00 Engineer];14[2.00 Engineer];15[2.00 Engineer];23[2.00 Engineer];29;30; | 665200
2 | Operator | Renewable | 3 | 150 | 150 | 22;24[3.00 Operator];25; | 51150

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | Cornflakes | 2202h
31 | Meeting with company | 8h | standard - symmetric | 80 | 100 | 120
5 | Selection Raw Materials | 56h | standard - symmetric | 80 | 100 | 120
6 | Order an receive raw materials | 120h | standard - symmetric | 80 | 100 | 120
7 | R&D test trail | 480h | standard - symmetric | 80 | 100 | 120
8 | R&D analysis texture | 168h | standard - symmetric | 80 | 100 | 120
9 | R&D taste test | 640h | standard - symmetric | 80 | 100 | 120
12 | Feedback loop: taste | 16h | standard - symmetric | 80 | 100 | 120
13 | Order and receive final raw materials | 120h | standard - symmetric | 80 | 100 | 120
14 | R&D designing extrusion head | 666h | standard - symmetric | 80 | 100 | 120
15 | Feedback loop: extrusion head | 6h | standard - symmetric | 80 | 100 | 120
21 | Production Final extrusion head | 256h | standard - symmetric | 80 | 100 | 120
22 | Final extrusion head installation | 80h | standard - symmetric | 80 | 100 | 120
23 | Packaging design | 200h | standard - symmetric | 80 | 100 | 120
24 | Industrial test | 80h | standard - symmetric | 80 | 100 | 120
25 | Extra quality check | 16h | standard - symmetric | 80 | 100 | 120
28 | Consumer test | 498h | standard - symmetric | 80 | 100 | 120
29 | Control claims | 56h | standard - symmetric | 80 | 100 | 120
30 | Adjust HACCP | 64h | standard - symmetric | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t))