## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Project | 1 |  |  | 2019-12-09 09:00 | 2020-01-09 12:00 | 27d 3h |  |  | 118411.3 |  |  | 126955.3 | 31.125
1 | Start | 1.1 |  | FS2 | 2019-12-09 09:00 | 2019-12-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | -1.6667
2 | Mowing and cleaning up cuttings | 1.2 | 1FS | FS3;FS6;FS7;FS11;FS17;FS25;FS27 | 2019-12-09 09:00 | 2019-12-09 12:00 | 3h | Volunteers[3.00 #15] | 36 | 931.5 | 0 | 0 | 967.5 | 0.125
3 | Drilling holes | 1.3 | 2FS | FS4 | 2019-12-09 13:00 | 2019-12-14 12:00 | 5d | Volunteers[6.00 #15] | 840 | 950.5 | 0 | 0 | 1790.5 | 4.9583
4 | Placing poles | 1.4 | 3FS | FS5 | 2019-12-14 13:00 | 2019-12-17 15:00 | 2d 2h | Volunteers[10.00 #15] | 640 | 8819 | 0 | 0 | 9459 | 3.0833
5 | Attaching ropes and nets to poles | 1.5 | 4FS | FS8;FS9;FS10;FS15;FS18;FS26 | 2019-12-17 15:00 | 2019-12-28 17:00 | 10d 2h | Volunteers[10.00 #15] | 2880 | 3166.5 | 0 | 0 | 6046.5 | 11.0833
6 | Building material post | 1.6 | 2FS | FS28 | 2019-12-31 14:00 | 2020-01-02 14:00 | 2d | Volunteers[8.00 #15] | 448 | 1802.5 | 0 | 0 | 2250.5 | 2
7 | Building bridges and exits | 1.7 | 2FS | FS30 | 2019-12-16 10:00 | 2019-12-23 10:00 | 6d | Volunteers[4.00 #15] | 672 | 1970.5 | 0 | 0 | 2642.5 | 7
8 | Building plateau and staircase audience | 1.8 | 5FS | FS30 | 2020-01-01 14:00 | 2020-01-02 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 1
9 | Building camera plateau | 1.9 | 5FS | FS30 | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 1
10 | Creating starting sections and finish line | 1.10 | 5FS | FS19 | 2019-12-30 09:00 | 2019-12-30 17:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 0.33333
11 | Installing bicycle storage | 1.11 | 2FS | FS30 | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2
13 | Placing poles for banners and flags | 1.12 | 17FS | FS14;FS16 | 2019-12-24 10:00 | 2019-12-24 14:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 0.16667
14 | Hanging banners | 1.13 | 13FS | FS30 | 2020-01-06 14:00 | 2020-01-08 14:00 | 2d | Volunteers[12.00 #15] | 672 | 602.5 | 0 | 0 | 1274.5 | 2
15 | Hanging track signs | 1.14 | 5FS | FS30 | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 1
16 | Placing flagpoles for homage | 1.15 | 13FS | FS30 | 2019-12-28 10:00 | 2019-12-28 14:00 | 3h | Volunteers[4.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 | 0.16667
17 | Building podium | 1.16 | 2FS | FS13 | 2019-12-23 10:00 | 2019-12-24 10:00 | 1d | Volunteers[5.00 #15] | 140 | 3302.5 | 0 | 0 | 3442.5 | 1
18 | Placing traffic signs | 1.17 | 5FS | FS30 | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 1
19 | Placing crush barriers and banners | 1.18 | 10FS | FS30 | 2020-01-03 14:00 | 2020-01-06 14:00 | 2d | Volunteers[12.00 #15] | 672 | 2252.5 | 0 | 0 | 2924.5 | 3
20 | Constructing VIP tents | 1.19 | 27FS | FS21;FS22;FS23 | 2019-12-25 10:00 | 2019-12-26 10:00 | 1d | Volunteers[2.00 #15] | 56 | 28602.5 | 0 | 0 | 28658.5 | 1
21 | Placing building fences for VIP tents | 1.20 | 20FS | FS30 | 2019-12-31 14:00 | 2020-01-01 14:00 | 1d | Volunteers[6.00 #15] | 168 | 3677.5 | 0 | 0 | 3845.5 | 1
22 | Installing drains for VIP tents | 1.21 | 20FS | FS24 | 2019-12-26 10:00 | 2019-12-27 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 1
23 | Decorating VIP tents | 1.22 | 20FS | FS30 | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[8.00 #15] | 224 | 43602.5 | 0 | 0 | 43826.5 | 1
24 | Placing toilets for VIP tents | 1.23 | 22FS | FS30 | 2019-12-27 10:00 | 2019-12-28 10:00 | 1d | Volunteers[2.00 #15] | 56 | 1577.5 | 0 | 0 | 1633.5 | 1
25 | Placing public toilets | 1.24 | 2FS | FS30 | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2524.5 | 0 | 0 | 2580.5 | 2
26 | Placing garbage bins | 1.25 | 5FS | FS30 | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 3442.3 | 0 | 0 | 3554.3 | 1
27 | Placing and testing generator | 1.26 | 2FS | FS20 | 2019-12-24 10:00 | 2019-12-25 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2972.5 | 0 | 0 | 3028.5 | 1
28 | Equipping material post | 1.27 | 6FS | FS29 | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[2.00 #15] | 56 | 1586.5 | 0 | 0 | 1642.5 | 1
29 | Testing high pressure cleaners | 1.28 | 28FS | FS30 | 2020-01-03 14:00 | 2020-01-03 17:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 0.125
30 | Final check up | 1.29 | 29FS;8FS;9FS;15FS;19FS;18FS;26FS;7FS;11FS;14FS;16FS;21FS;24FS;23FS;25FS | FS31 | 2020-01-08 14:00 | 2020-01-09 12:00 | 6h | Volunteers[2.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 | 0.91667
31 | Finish | 1.30 | 30FS |  | 2020-01-09 12:00 | 2020-01-09 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Volunteers | Renewable | 15 person | 0 | 4 | 2[3.00 Volunteers];3[6.00 Volunteers];4[10.00 Volunteers];5[10.00 Volunteers];6[8.00 Volunteers];7[4.00 Volunteers];8[4.00 Volunteers];9[4.00 Volunteers];10[2.00 Volunteers];11[2.00 Volunteers];13[2.00 Volunteers];14[12.00 Volunteers];15[4.00 Volunteers];16[4.00 Volunteers];17[5.00 Volunteers];18[4.00 Volunteers];19[12.00 Volunteers];20[2.00 Volunteers];21[6.00 Volunteers];22[2.00 Volunteers];23[8.00 Volunteers];24[2.00 Volunteers];25[2.00 Volunteers];26[4.00 Volunteers];27[2.00 Volunteers];28[2.00 Volunteers];29[2.00 Volunteers];30[2.00 Volunteers]; | 8544

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Project | 192h |  |  |  |  | 99 | 100 | 101
1 | Start | 0 | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
2 | Mowing and cleaning up cuttings | 3h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
3 | Drilling holes | 35h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
4 | Placing poles | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
5 | Attaching ropes and nets to poles | 72h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
6 | Building material post | 14h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
7 | Building bridges and exits | 42h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
8 | Building plateau and staircase audience | 7h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
9 | Building camera plateau | 7h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
10 | Creating starting sections and finish line | 7h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
11 | Installing bicycle storage | 7h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
13 | Placing poles for banners and flags | 3h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
14 | Hanging banners | 14h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
15 | Hanging track signs | 7h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
16 | Placing flagpoles for homage | 3h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
17 | Building podium | 7h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
18 | Placing traffic signs | 7h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
19 | Placing crush barriers and banners | 14h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
20 | Constructing VIP tents | 7h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
21 | Placing building fences for VIP tents | 7h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
22 | Installing drains for VIP tents | 7h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
23 | Decorating VIP tents | 7h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
24 | Placing toilets for VIP tents | 7h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
25 | Placing public toilets | 7h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
26 | Placing garbage bins | 7h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
27 | Placing and testing generator | 7h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
28 | Equipping material post | 7h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
29 | Testing high pressure cleaners | 3h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
30 | Final check up | 6h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
31 | Finish | 0 | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120

## Project Control - TP1
| TP Status Date | 2019-12-09 17:00 |  | TP Name | 9/12/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Project | 2019-12-09 09:00 | 2020-01-09 12:00 | 27d 3h |  |  | 118411.3 |  |  | 126955.3 |  | 1d | [5 empty] | 3944.5 |  | 3.125%
1 | Start | 2019-12-09 09:00 | 2019-12-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-12-09 09:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished
2 | Mowing and cleaning up cuttings | 2019-12-09 09:00 | 2019-12-09 12:00 | 3h | Volunteers[3.00 #15] | 36 | 931.5 | 0 | 0 | 967.5 | 2019-12-09 09:00 | 3h | 967.5 | 0 | 0 | 0 | 0 | 967.5 | 0 | 100% | Finished
3 | Drilling holes | 2019-12-09 13:00 | 2019-12-14 12:00 | 5d | Volunteers[6.00 #15] | 840 | 950.5 | 0 | 0 | 1790.5 | 2019-12-09 13:00 | 4h | 1046.5 | 504 | 3d | 0 | 0 | 1046.5 | 504 | 16% | Started
4 | Placing poles | 2019-12-14 13:00 | 2019-12-17 15:00 | 2d 2h | Volunteers[10.00 #15] | 640 | 8819 | 0 | 0 | 9459 |  | 0 | 0 | 9459 | 2d 2h | 0 | 0 | 0 | 9459 | 0% | Not Started
5 | Attaching ropes and nets to poles | 2019-12-17 15:00 | 2019-12-28 17:00 | 10d 2h | Volunteers[10.00 #15] | 2880 | 3166.5 | 0 | 0 | 6046.5 |  | 0 | 0 | 6046.5 | 10d 2h | 0 | 0 | 0 | 6046.5 | 0% | Not Started
6 | Building material post | 2019-12-31 14:00 | 2020-01-02 14:00 | 2d | Volunteers[8.00 #15] | 448 | 1802.5 | 0 | 0 | 2250.5 | 2019-12-09 13:00 | 4h | 1930.5 | 384 | 1d 5h | 0 | 0 | 1930.5 | 384 | 25% | Started
7 | Building bridges and exits | 2019-12-16 10:00 | 2019-12-23 10:00 | 6d | Volunteers[4.00 #15] | 672 | 1970.5 | 0 | 0 | 2642.5 |  | 0 | 0 | 2642.5 | 6d | 0 | 0 | 0 | 2642.5 | 0% | Not Started
8 | Building plateau and staircase audience | 2020-01-01 14:00 | 2020-01-02 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
9 | Building camera plateau | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
10 | Creating starting sections and finish line | 2019-12-30 09:00 | 2019-12-30 17:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
11 | Installing bicycle storage | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
13 | Placing poles for banners and flags | 2019-12-24 10:00 | 2019-12-24 14:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 |  | 0 | 0 | 626.5 | 3h | 0 | 0 | 0 | 626.5 | 0% | Not Started
14 | Hanging banners | 2020-01-06 14:00 | 2020-01-08 14:00 | 2d | Volunteers[12.00 #15] | 672 | 602.5 | 0 | 0 | 1274.5 |  | 0 | 0 | 1274.5 | 2d | 0 | 0 | 0 | 1274.5 | 0% | Not Started
15 | Hanging track signs | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
16 | Placing flagpoles for homage | 2019-12-28 10:00 | 2019-12-28 14:00 | 3h | Volunteers[4.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 |  | 0 | 0 | 650.5 | 3h | 0 | 0 | 0 | 650.5 | 0% | Not Started
17 | Building podium | 2019-12-23 10:00 | 2019-12-24 10:00 | 1d | Volunteers[5.00 #15] | 140 | 3302.5 | 0 | 0 | 3442.5 |  | 0 | 0 | 3442.5 | 1d | 0 | 0 | 0 | 3442.5 | 0% | Not Started
18 | Placing traffic signs | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
19 | Placing crush barriers and banners | 2020-01-03 14:00 | 2020-01-06 14:00 | 2d | Volunteers[12.00 #15] | 672 | 2252.5 | 0 | 0 | 2924.5 |  | 0 | 0 | 2924.5 | 2d | 0 | 0 | 0 | 2924.5 | 0% | Not Started
20 | Constructing VIP tents | 2019-12-25 10:00 | 2019-12-26 10:00 | 1d | Volunteers[2.00 #15] | 56 | 28602.5 | 0 | 0 | 28658.5 |  | 0 | 0 | 28658.5 | 1d | 0 | 0 | 0 | 28658.5 | 0% | Not Started
21 | Placing building fences for VIP tents | 2019-12-31 14:00 | 2020-01-01 14:00 | 1d | Volunteers[6.00 #15] | 168 | 3677.5 | 0 | 0 | 3845.5 |  | 0 | 0 | 3845.5 | 1d | 0 | 0 | 0 | 3845.5 | 0% | Not Started
22 | Installing drains for VIP tents | 2019-12-26 10:00 | 2019-12-27 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
23 | Decorating VIP tents | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[8.00 #15] | 224 | 43602.5 | 0 | 0 | 43826.5 |  | 0 | 0 | 43826.5 | 1d | 0 | 0 | 0 | 43826.5 | 0% | Not Started
24 | Placing toilets for VIP tents | 2019-12-27 10:00 | 2019-12-28 10:00 | 1d | Volunteers[2.00 #15] | 56 | 1577.5 | 0 | 0 | 1633.5 |  | 0 | 0 | 1633.5 | 1d | 0 | 0 | 0 | 1633.5 | 0% | Not Started
25 | Placing public toilets | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2524.5 | 0 | 0 | 2580.5 |  | 0 | 0 | 2580.5 | 1d | 0 | 0 | 0 | 2580.5 | 0% | Not Started
26 | Placing garbage bins | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 3442.3 | 0 | 0 | 3554.3 |  | 0 | 0 | 3554.3 | 1d | 0 | 0 | 0 | 3554.3 | 0% | Not Started
27 | Placing and testing generator | 2019-12-24 10:00 | 2019-12-25 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2972.5 | 0 | 0 | 3028.5 |  | 0 | 0 | 3028.5 | 1d | 0 | 0 | 0 | 3028.5 | 0% | Not Started
28 | Equipping material post | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[2.00 #15] | 56 | 1586.5 | 0 | 0 | 1642.5 |  | 0 | 0 | 1642.5 | 1d | 0 | 0 | 0 | 1642.5 | 0% | Not Started
29 | Testing high pressure cleaners | 2020-01-03 14:00 | 2020-01-03 17:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 |  | 0 | 0 | 626.5 | 3h | 0 | 0 | 0 | 626.5 | 0% | Not Started
30 | Final check up | 2020-01-08 14:00 | 2020-01-09 12:00 | 6h | Volunteers[2.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 |  | 0 | 0 | 650.5 | 6h | 0 | 0 | 0 | 650.5 | 0% | Not Started
31 | Finish | 2020-01-09 12:00 | 2020-01-09 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started

## TP2
| TP Status Date | 2019-12-10 17:00 |  | TP Name | 10/12/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Project | 2019-12-09 09:00 | 2020-01-09 12:00 | 27d 3h |  |  | 118411.3 |  |  | 126955.3 |  | 2d | [5 empty] | 4336.5 |  | 3.464%
1 | Start | 2019-12-09 09:00 | 2019-12-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-12-09 09:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished
2 | Mowing and cleaning up cuttings | 2019-12-09 09:00 | 2019-12-09 12:00 | 3h | Volunteers[3.00 #15] | 36 | 931.5 | 0 | 0 | 967.5 | 2019-12-09 09:00 | 3h | 967.5 | 0 | 0 | 0 | 0 | 967.5 | 0 | 100% | Finished
3 | Drilling holes | 2019-12-09 13:00 | 2019-12-14 12:00 | 5d | Volunteers[6.00 #15] | 840 | 950.5 | 0 | 0 | 1790.5 | 2019-12-09 13:00 | 1d 4h | 1214.5 | 336 | 2d | 0 | 0 | 1214.5 | 336 | 44% | Started
4 | Placing poles | 2019-12-14 13:00 | 2019-12-17 15:00 | 2d 2h | Volunteers[10.00 #15] | 640 | 8819 | 0 | 0 | 9459 |  | 0 | 0 | 9459 | 2d 2h | 0 | 0 | 0 | 9459 | 0% | Not Started
5 | Attaching ropes and nets to poles | 2019-12-17 15:00 | 2019-12-28 17:00 | 10d 2h | Volunteers[10.00 #15] | 2880 | 3166.5 | 0 | 0 | 6046.5 |  | 0 | 0 | 6046.5 | 10d 2h | 0 | 0 | 0 | 6046.5 | 0% | Not Started
6 | Building material post | 2019-12-31 14:00 | 2020-01-02 14:00 | 2d | Volunteers[8.00 #15] | 448 | 1802.5 | 0 | 0 | 2250.5 | 2019-12-09 13:00 | 1d 4h | 2154.5 | 160 | 5h | 0 | 0 | 2154.5 | 160 | 68.75% | Started
7 | Building bridges and exits | 2019-12-16 10:00 | 2019-12-23 10:00 | 6d | Volunteers[4.00 #15] | 672 | 1970.5 | 0 | 0 | 2642.5 |  | 0 | 0 | 2642.5 | 6d | 0 | 0 | 0 | 2642.5 | 0% | Not Started
8 | Building plateau and staircase audience | 2020-01-01 14:00 | 2020-01-02 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
9 | Building camera plateau | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
10 | Creating starting sections and finish line | 2019-12-30 09:00 | 2019-12-30 17:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
11 | Installing bicycle storage | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
13 | Placing poles for banners and flags | 2019-12-24 10:00 | 2019-12-24 14:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 |  | 0 | 0 | 626.5 | 3h | 0 | 0 | 0 | 626.5 | 0% | Not Started
14 | Hanging banners | 2020-01-06 14:00 | 2020-01-08 14:00 | 2d | Volunteers[12.00 #15] | 672 | 602.5 | 0 | 0 | 1274.5 |  | 0 | 0 | 1274.5 | 2d | 0 | 0 | 0 | 1274.5 | 0% | Not Started
15 | Hanging track signs | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
16 | Placing flagpoles for homage | 2019-12-28 10:00 | 2019-12-28 14:00 | 3h | Volunteers[4.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 |  | 0 | 0 | 650.5 | 3h | 0 | 0 | 0 | 650.5 | 0% | Not Started
17 | Building podium | 2019-12-23 10:00 | 2019-12-24 10:00 | 1d | Volunteers[5.00 #15] | 140 | 3302.5 | 0 | 0 | 3442.5 |  | 0 | 0 | 3442.5 | 1d | 0 | 0 | 0 | 3442.5 | 0% | Not Started
18 | Placing traffic signs | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
19 | Placing crush barriers and banners | 2020-01-03 14:00 | 2020-01-06 14:00 | 2d | Volunteers[12.00 #15] | 672 | 2252.5 | 0 | 0 | 2924.5 |  | 0 | 0 | 2924.5 | 2d | 0 | 0 | 0 | 2924.5 | 0% | Not Started
20 | Constructing VIP tents | 2019-12-25 10:00 | 2019-12-26 10:00 | 1d | Volunteers[2.00 #15] | 56 | 28602.5 | 0 | 0 | 28658.5 |  | 0 | 0 | 28658.5 | 1d | 0 | 0 | 0 | 28658.5 | 0% | Not Started
21 | Placing building fences for VIP tents | 2019-12-31 14:00 | 2020-01-01 14:00 | 1d | Volunteers[6.00 #15] | 168 | 3677.5 | 0 | 0 | 3845.5 |  | 0 | 0 | 3845.5 | 1d | 0 | 0 | 0 | 3845.5 | 0% | Not Started
22 | Installing drains for VIP tents | 2019-12-26 10:00 | 2019-12-27 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
23 | Decorating VIP tents | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[8.00 #15] | 224 | 43602.5 | 0 | 0 | 43826.5 |  | 0 | 0 | 43826.5 | 1d | 0 | 0 | 0 | 43826.5 | 0% | Not Started
24 | Placing toilets for VIP tents | 2019-12-27 10:00 | 2019-12-28 10:00 | 1d | Volunteers[2.00 #15] | 56 | 1577.5 | 0 | 0 | 1633.5 |  | 0 | 0 | 1633.5 | 1d | 0 | 0 | 0 | 1633.5 | 0% | Not Started
25 | Placing public toilets | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2524.5 | 0 | 0 | 2580.5 |  | 0 | 0 | 2580.5 | 1d | 0 | 0 | 0 | 2580.5 | 0% | Not Started
26 | Placing garbage bins | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 3442.3 | 0 | 0 | 3554.3 |  | 0 | 0 | 3554.3 | 1d | 0 | 0 | 0 | 3554.3 | 0% | Not Started
27 | Placing and testing generator | 2019-12-24 10:00 | 2019-12-25 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2972.5 | 0 | 0 | 3028.5 |  | 0 | 0 | 3028.5 | 1d | 0 | 0 | 0 | 3028.5 | 0% | Not Started
28 | Equipping material post | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[2.00 #15] | 56 | 1586.5 | 0 | 0 | 1642.5 |  | 0 | 0 | 1642.5 | 1d | 0 | 0 | 0 | 1642.5 | 0% | Not Started
29 | Testing high pressure cleaners | 2020-01-03 14:00 | 2020-01-03 17:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 |  | 0 | 0 | 626.5 | 3h | 0 | 0 | 0 | 626.5 | 0% | Not Started
30 | Final check up | 2020-01-08 14:00 | 2020-01-09 12:00 | 6h | Volunteers[2.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 |  | 0 | 0 | 650.5 | 6h | 0 | 0 | 0 | 650.5 | 0% | Not Started
31 | Finish | 2020-01-09 12:00 | 2020-01-09 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started

## TP3
| TP Status Date | 2019-12-11 17:00 |  | TP Name | 11/12/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Project | 2019-12-09 09:00 | 2020-01-09 12:00 | 27d 3h |  |  | 118411.3 |  |  | 126955.3 |  | 3d | [5 empty] | 12598 |  | 10.04%
1 | Start | 2019-12-09 09:00 | 2019-12-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-12-09 09:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished
2 | Mowing and cleaning up cuttings | 2019-12-09 09:00 | 2019-12-09 12:00 | 3h | Volunteers[3.00 #15] | 36 | 931.5 | 0 | 0 | 967.5 | 2019-12-09 09:00 | 3h | 967.5 | 0 | 0 | 0 | 0 | 967.5 | 0 | 100% | Finished
3 | Drilling holes | 2019-12-09 13:00 | 2019-12-14 12:00 | 5d | Volunteers[6.00 #15] | 840 | 950.5 | 0 | 0 | 1790.5 | 2019-12-09 13:00 | 2d 4h | 1382.5 | 168 | 1d | 0 | 0 | 1382.5 | 168 | 72% | Started
4 | Placing poles | 2019-12-14 13:00 | 2019-12-17 15:00 | 2d 2h | Volunteers[10.00 #15] | 640 | 8819 | 0 | 0 | 9459 |  | 0 | 0 | 9459 | 2d 2h | 0 | 0 | 0 | 9459 | 0% | Not Started
5 | Attaching ropes and nets to poles | 2019-12-17 15:00 | 2019-12-28 17:00 | 10d 2h | Volunteers[10.00 #15] | 2880 | 3166.5 | 0 | 0 | 6046.5 |  | 0 | 0 | 6046.5 | 10d 2h | 0 | 0 | 0 | 6046.5 | 0% | Not Started
6 | Building material post | 2019-12-31 14:00 | 2020-01-02 14:00 | 2d | Volunteers[8.00 #15] | 448 | 1802.5 | 0 | 0 | 2250.5 | 2019-12-09 13:00 | 2d 2h | 2314.5 | 0 | 0 | 0 | 0 | 2314.5 | 0 | 100% | Finished
7 | Building bridges and exits | 2019-12-16 10:00 | 2019-12-23 10:00 | 6d | Volunteers[4.00 #15] | 672 | 1970.5 | 0 | 0 | 2642.5 |  | 0 | 0 | 2642.5 | 6d | 0 | 0 | 0 | 2642.5 | 0% | Not Started
8 | Building plateau and staircase audience | 2020-01-01 14:00 | 2020-01-02 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
9 | Building camera plateau | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
10 | Creating starting sections and finish line | 2019-12-30 09:00 | 2019-12-30 17:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
11 | Installing bicycle storage | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
13 | Placing poles for banners and flags | 2019-12-24 10:00 | 2019-12-24 14:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 |  | 0 | 0 | 626.5 | 3h | 0 | 0 | 0 | 626.5 | 0% | Not Started
14 | Hanging banners | 2020-01-06 14:00 | 2020-01-08 14:00 | 2d | Volunteers[12.00 #15] | 672 | 602.5 | 0 | 0 | 1274.5 |  | 0 | 0 | 1274.5 | 2d | 0 | 0 | 0 | 1274.5 | 0% | Not Started
15 | Hanging track signs | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
16 | Placing flagpoles for homage | 2019-12-28 10:00 | 2019-12-28 14:00 | 3h | Volunteers[4.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 |  | 0 | 0 | 650.5 | 3h | 0 | 0 | 0 | 650.5 | 0% | Not Started
17 | Building podium | 2019-12-23 10:00 | 2019-12-24 10:00 | 1d | Volunteers[5.00 #15] | 140 | 3302.5 | 0 | 0 | 3442.5 | 2019-12-11 15:00 | 2h | 3342.5 | 40 | 2h | 0 | 0 | 3342.5 | 40 | 50% | Started
18 | Placing traffic signs | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
19 | Placing crush barriers and banners | 2020-01-03 14:00 | 2020-01-06 14:00 | 2d | Volunteers[12.00 #15] | 672 | 2252.5 | 0 | 0 | 2924.5 |  | 0 | 0 | 2924.5 | 2d | 0 | 0 | 0 | 2924.5 | 0% | Not Started
20 | Constructing VIP tents | 2019-12-25 10:00 | 2019-12-26 10:00 | 1d | Volunteers[2.00 #15] | 56 | 28602.5 | 0 | 0 | 28658.5 |  | 0 | 0 | 28658.5 | 1d | 0 | 0 | 0 | 28658.5 | 0% | Not Started
21 | Placing building fences for VIP tents | 2019-12-31 14:00 | 2020-01-01 14:00 | 1d | Volunteers[6.00 #15] | 168 | 3677.5 | 0 | 0 | 3845.5 |  | 0 | 0 | 3845.5 | 1d | 0 | 0 | 0 | 3845.5 | 0% | Not Started
22 | Installing drains for VIP tents | 2019-12-26 10:00 | 2019-12-27 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
23 | Decorating VIP tents | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[8.00 #15] | 224 | 43602.5 | 0 | 0 | 43826.5 |  | 0 | 0 | 43826.5 | 1d | 0 | 0 | 0 | 43826.5 | 0% | Not Started
24 | Placing toilets for VIP tents | 2019-12-27 10:00 | 2019-12-28 10:00 | 1d | Volunteers[2.00 #15] | 56 | 1577.5 | 0 | 0 | 1633.5 |  | 0 | 0 | 1633.5 | 1d | 0 | 0 | 0 | 1633.5 | 0% | Not Started
25 | Placing public toilets | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2524.5 | 0 | 0 | 2580.5 |  | 0 | 0 | 2580.5 | 1d | 0 | 0 | 0 | 2580.5 | 0% | Not Started
26 | Placing garbage bins | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 3442.3 | 0 | 0 | 3554.3 |  | 0 | 0 | 3554.3 | 1d | 0 | 0 | 0 | 3554.3 | 0% | Not Started
27 | Placing and testing generator | 2019-12-24 10:00 | 2019-12-25 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2972.5 | 0 | 0 | 3028.5 | 2019-12-11 15:00 | 2h | 2988.5 | 16 | 2h | 0 | 0 | 2988.5 | 16 | 50% | Started
28 | Equipping material post | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[2.00 #15] | 56 | 1586.5 | 0 | 0 | 1642.5 | 2019-12-11 15:00 | 2h | 1602.5 | 64 | 1d 1h | 0 | 0 | 1602.5 | 64 | 20% | Started
29 | Testing high pressure cleaners | 2020-01-03 14:00 | 2020-01-03 17:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 |  | 0 | 0 | 626.5 | 3h | 0 | 0 | 0 | 626.5 | 0% | Not Started
30 | Final check up | 2020-01-08 14:00 | 2020-01-09 12:00 | 6h | Volunteers[2.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 |  | 0 | 0 | 650.5 | 6h | 0 | 0 | 0 | 650.5 | 0% | Not Started
31 | Finish | 2020-01-09 12:00 | 2020-01-09 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started

## TP4
| TP Status Date | 2019-12-12 17:00 |  | TP Name | 12/12/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Project | 2019-12-09 09:00 | 2020-01-09 12:00 | 27d 3h |  |  | 118411.3 |  |  | 126955.3 |  | 4d | [5 empty] | 42147 |  | 33.4%
1 | Start | 2019-12-09 09:00 | 2019-12-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-12-09 09:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished
2 | Mowing and cleaning up cuttings | 2019-12-09 09:00 | 2019-12-09 12:00 | 3h | Volunteers[3.00 #15] | 36 | 931.5 | 0 | 0 | 967.5 | 2019-12-09 09:00 | 3h | 967.5 | 0 | 0 | 0 | 0 | 967.5 | 0 | 100% | Finished
3 | Drilling holes | 2019-12-09 13:00 | 2019-12-14 12:00 | 5d | Volunteers[6.00 #15] | 840 | 950.5 | 0 | 0 | 1790.5 | 2019-12-09 13:00 | 3d 4h | 1550.5 | 0 | 0 | 0 | 0 | 1550.5 | 0 | 100% | Finished
4 | Placing poles | 2019-12-14 13:00 | 2019-12-17 15:00 | 2d 2h | Volunteers[10.00 #15] | 640 | 8819 | 0 | 0 | 9459 |  | 0 | 0 | 9459 | 2d 2h | 0 | 0 | 0 | 9459 | 0% | Not Started
5 | Attaching ropes and nets to poles | 2019-12-17 15:00 | 2019-12-28 17:00 | 10d 2h | Volunteers[10.00 #15] | 2880 | 3166.5 | 0 | 0 | 6046.5 |  | 0 | 0 | 6046.5 | 10d 2h | 0 | 0 | 0 | 6046.5 | 0% | Not Started
6 | Building material post | 2019-12-31 14:00 | 2020-01-02 14:00 | 2d | Volunteers[8.00 #15] | 448 | 1802.5 | 0 | 0 | 2250.5 | 2019-12-09 13:00 | 2d 2h | 2314.5 | 0 | 0 | 0 | 0 | 2314.5 | 0 | 100% | Finished
7 | Building bridges and exits | 2019-12-16 10:00 | 2019-12-23 10:00 | 6d | Volunteers[4.00 #15] | 672 | 1970.5 | 0 | 0 | 2642.5 |  | 0 | 0 | 2642.5 | 6d | 0 | 0 | 0 | 2642.5 | 0% | Not Started
8 | Building plateau and staircase audience | 2020-01-01 14:00 | 2020-01-02 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
9 | Building camera plateau | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
10 | Creating starting sections and finish line | 2019-12-30 09:00 | 2019-12-30 17:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
11 | Installing bicycle storage | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
13 | Placing poles for banners and flags | 2019-12-24 10:00 | 2019-12-24 14:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-12 11:00 | 3h | 626.5 | 0 | 0 | 0 | 0 | 626.5 | 0 | 100% | Finished
14 | Hanging banners | 2020-01-06 14:00 | 2020-01-08 14:00 | 2d | Volunteers[12.00 #15] | 672 | 602.5 | 0 | 0 | 1274.5 |  | 0 | 0 | 1274.5 | 2d | 0 | 0 | 0 | 1274.5 | 0% | Not Started
15 | Hanging track signs | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
16 | Placing flagpoles for homage | 2019-12-28 10:00 | 2019-12-28 14:00 | 3h | Volunteers[4.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 |  | 0 | 0 | 650.5 | 3h | 0 | 0 | 0 | 650.5 | 0% | Not Started
17 | Building podium | 2019-12-23 10:00 | 2019-12-24 10:00 | 1d | Volunteers[5.00 #15] | 140 | 3302.5 | 0 | 0 | 3442.5 | 2019-12-11 15:00 | 4h | 3382.5 | 0 | 0 | 0 | 0 | 3382.5 | 0 | 100% | Finished
18 | Placing traffic signs | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
19 | Placing crush barriers and banners | 2020-01-03 14:00 | 2020-01-06 14:00 | 2d | Volunteers[12.00 #15] | 672 | 2252.5 | 0 | 0 | 2924.5 |  | 0 | 0 | 2924.5 | 2d | 0 | 0 | 0 | 2924.5 | 0% | Not Started
20 | Constructing VIP tents | 2019-12-25 10:00 | 2019-12-26 10:00 | 1d | Volunteers[2.00 #15] | 56 | 28602.5 | 0 | 0 | 28658.5 | 2019-12-12 11:00 | 5h | 28642.5 | 0 | 0 | 0 | 0 | 28642.5 | 0 | 100% | Finished
21 | Placing building fences for VIP tents | 2019-12-31 14:00 | 2020-01-01 14:00 | 1d | Volunteers[6.00 #15] | 168 | 3677.5 | 0 | 0 | 3845.5 |  | 0 | 0 | 3845.5 | 1d | 0 | 0 | 0 | 3845.5 | 0% | Not Started
22 | Installing drains for VIP tents | 2019-12-26 10:00 | 2019-12-27 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
23 | Decorating VIP tents | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[8.00 #15] | 224 | 43602.5 | 0 | 0 | 43826.5 |  | 0 | 0 | 43826.5 | 1d | 0 | 0 | 0 | 43826.5 | 0% | Not Started
24 | Placing toilets for VIP tents | 2019-12-27 10:00 | 2019-12-28 10:00 | 1d | Volunteers[2.00 #15] | 56 | 1577.5 | 0 | 0 | 1633.5 |  | 0 | 0 | 1633.5 | 1d | 0 | 0 | 0 | 1633.5 | 0% | Not Started
25 | Placing public toilets | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2524.5 | 0 | 0 | 2580.5 |  | 0 | 0 | 2580.5 | 1d | 0 | 0 | 0 | 2580.5 | 0% | Not Started
26 | Placing garbage bins | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 3442.3 | 0 | 0 | 3554.3 |  | 0 | 0 | 3554.3 | 1d | 0 | 0 | 0 | 3554.3 | 0% | Not Started
27 | Placing and testing generator | 2019-12-24 10:00 | 2019-12-25 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2972.5 | 0 | 0 | 3028.5 | 2019-12-11 15:00 | 4h | 3004.5 | 0 | 0 | 0 | 0 | 3004.5 | 0 | 100% | Finished
28 | Equipping material post | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[2.00 #15] | 56 | 1586.5 | 0 | 0 | 1642.5 | 2019-12-11 15:00 | 1d 2h | 1658.5 | 8 | 1h | 0 | 0 | 1658.5 | 8 | 90% | Started
29 | Testing high pressure cleaners | 2020-01-03 14:00 | 2020-01-03 17:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 |  | 0 | 0 | 626.5 | 3h | 0 | 0 | 0 | 626.5 | 0% | Not Started
30 | Final check up | 2020-01-08 14:00 | 2020-01-09 12:00 | 6h | Volunteers[2.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 |  | 0 | 0 | 650.5 | 6h | 0 | 0 | 0 | 650.5 | 0% | Not Started
31 | Finish | 2020-01-09 12:00 | 2020-01-09 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started

## TP5
| TP Status Date | 2019-12-13 17:00 |  | TP Name | 13/12/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Project | 2019-12-09 09:00 | 2020-01-09 12:00 | 27d 3h |  |  | 118411.3 |  |  | 126955.3 |  | 5d | [5 empty] | 56665 |  | 44.98%
1 | Start | 2019-12-09 09:00 | 2019-12-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-12-09 09:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished
2 | Mowing and cleaning up cuttings | 2019-12-09 09:00 | 2019-12-09 12:00 | 3h | Volunteers[3.00 #15] | 36 | 931.5 | 0 | 0 | 967.5 | 2019-12-09 09:00 | 3h | 967.5 | 0 | 0 | 0 | 0 | 967.5 | 0 | 100% | Finished
3 | Drilling holes | 2019-12-09 13:00 | 2019-12-14 12:00 | 5d | Volunteers[6.00 #15] | 840 | 950.5 | 0 | 0 | 1790.5 | 2019-12-09 13:00 | 3d 4h | 1550.5 | 0 | 0 | 0 | 0 | 1550.5 | 0 | 100% | Finished
4 | Placing poles | 2019-12-14 13:00 | 2019-12-17 15:00 | 2d 2h | Volunteers[10.00 #15] | 640 | 8819 | 0 | 0 | 9459 | 2019-12-13 09:00 | 1d | 9099 | 120 | 3h | 0 | 0 | 9099 | 120 | 70% | Started
5 | Attaching ropes and nets to poles | 2019-12-17 15:00 | 2019-12-28 17:00 | 10d 2h | Volunteers[10.00 #15] | 2880 | 3166.5 | 0 | 0 | 6046.5 |  | 0 | 0 | 6046.5 | 10d 2h | 0 | 0 | 0 | 6046.5 | 0% | Not Started
6 | Building material post | 2019-12-31 14:00 | 2020-01-02 14:00 | 2d | Volunteers[8.00 #15] | 448 | 1802.5 | 0 | 0 | 2250.5 | 2019-12-09 13:00 | 2d 2h | 2314.5 | 0 | 0 | 0 | 0 | 2314.5 | 0 | 100% | Finished
7 | Building bridges and exits | 2019-12-16 10:00 | 2019-12-23 10:00 | 6d | Volunteers[4.00 #15] | 672 | 1970.5 | 0 | 0 | 2642.5 |  | 0 | 0 | 2642.5 | 6d | 0 | 0 | 0 | 2642.5 | 0% | Not Started
8 | Building plateau and staircase audience | 2020-01-01 14:00 | 2020-01-02 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
9 | Building camera plateau | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
10 | Creating starting sections and finish line | 2019-12-30 09:00 | 2019-12-30 17:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
11 | Installing bicycle storage | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
13 | Placing poles for banners and flags | 2019-12-24 10:00 | 2019-12-24 14:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-12 11:00 | 3h | 626.5 | 0 | 0 | 0 | 0 | 626.5 | 0 | 100% | Finished
14 | Hanging banners | 2020-01-06 14:00 | 2020-01-08 14:00 | 2d | Volunteers[12.00 #15] | 672 | 602.5 | 0 | 0 | 1274.5 |  | 0 | 0 | 1274.5 | 2d | 0 | 0 | 0 | 1274.5 | 0% | Not Started
15 | Hanging track signs | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
16 | Placing flagpoles for homage | 2019-12-28 10:00 | 2019-12-28 14:00 | 3h | Volunteers[4.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 |  | 0 | 0 | 650.5 | 3h | 0 | 0 | 0 | 650.5 | 0% | Not Started
17 | Building podium | 2019-12-23 10:00 | 2019-12-24 10:00 | 1d | Volunteers[5.00 #15] | 140 | 3302.5 | 0 | 0 | 3442.5 | 2019-12-11 15:00 | 4h | 3382.5 | 0 | 0 | 0 | 0 | 3382.5 | 0 | 100% | Finished
18 | Placing traffic signs | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
19 | Placing crush barriers and banners | 2020-01-03 14:00 | 2020-01-06 14:00 | 2d | Volunteers[12.00 #15] | 672 | 2252.5 | 0 | 0 | 2924.5 |  | 0 | 0 | 2924.5 | 2d | 0 | 0 | 0 | 2924.5 | 0% | Not Started
20 | Constructing VIP tents | 2019-12-25 10:00 | 2019-12-26 10:00 | 1d | Volunteers[2.00 #15] | 56 | 28602.5 | 0 | 0 | 28658.5 | 2019-12-12 11:00 | 5h | 28642.5 | 0 | 0 | 0 | 0 | 28642.5 | 0 | 100% | Finished
21 | Placing building fences for VIP tents | 2019-12-31 14:00 | 2020-01-01 14:00 | 1d | Volunteers[6.00 #15] | 168 | 3677.5 | 0 | 0 | 3845.5 |  | 0 | 0 | 3845.5 | 1d | 0 | 0 | 0 | 3845.5 | 0% | Not Started
22 | Installing drains for VIP tents | 2019-12-26 10:00 | 2019-12-27 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-13 09:00 | 6h | 650.5 | 0 | 0 | 0 | 0 | 650.5 | 0 | 100% | Finished
23 | Decorating VIP tents | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[8.00 #15] | 224 | 43602.5 | 0 | 0 | 43826.5 |  | 0 | 0 | 43826.5 | 1d | 0 | 0 | 0 | 43826.5 | 0% | Not Started
24 | Placing toilets for VIP tents | 2019-12-27 10:00 | 2019-12-28 10:00 | 1d | Volunteers[2.00 #15] | 56 | 1577.5 | 0 | 0 | 1633.5 | 2019-12-13 16:00 | 1h | 1585.5 | 48 | 6h | 0 | 0 | 1585.5 | 48 | 14.29% | Started
25 | Placing public toilets | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2524.5 | 0 | 0 | 2580.5 | 2019-12-13 13:00 | 4h | 2556.5 | 24 | 3h | 0 | 0 | 2556.5 | 24 | 57.14% | Started
26 | Placing garbage bins | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 3442.3 | 0 | 0 | 3554.3 |  | 0 | 0 | 3554.3 | 1d | 0 | 0 | 0 | 3554.3 | 0% | Not Started
27 | Placing and testing generator | 2019-12-24 10:00 | 2019-12-25 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2972.5 | 0 | 0 | 3028.5 | 2019-12-11 15:00 | 4h | 3004.5 | 0 | 0 | 0 | 0 | 3004.5 | 0 | 100% | Finished
28 | Equipping material post | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[2.00 #15] | 56 | 1586.5 | 0 | 0 | 1642.5 | 2019-12-11 15:00 | 1d 3h | 1666.5 | 0 | 0 | 0 | 0 | 1666.5 | 0 | 100% | Finished
29 | Testing high pressure cleaners | 2020-01-03 14:00 | 2020-01-03 17:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-13 10:00 | 2h | 618.5 | 0 | 0 | 0 | 0 | 618.5 | 0 | 100% | Finished
30 | Final check up | 2020-01-08 14:00 | 2020-01-09 12:00 | 6h | Volunteers[2.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 |  | 0 | 0 | 650.5 | 6h | 0 | 0 | 0 | 650.5 | 0% | Not Started
31 | Finish | 2020-01-09 12:00 | 2020-01-09 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started

## TP6
| TP Status Date | 2019-12-14 17:00 |  | TP Name | 14/12/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Project | 2019-12-09 09:00 | 2020-01-09 12:00 | 27d 3h |  |  | 118411.3 |  |  | 126955.3 |  | 6d | [5 empty] | 60802 |  | 48.3%
1 | Start | 2019-12-09 09:00 | 2019-12-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-12-09 09:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished
2 | Mowing and cleaning up cuttings | 2019-12-09 09:00 | 2019-12-09 12:00 | 3h | Volunteers[3.00 #15] | 36 | 931.5 | 0 | 0 | 967.5 | 2019-12-09 09:00 | 3h | 967.5 | 0 | 0 | 0 | 0 | 967.5 | 0 | 100% | Finished
3 | Drilling holes | 2019-12-09 13:00 | 2019-12-14 12:00 | 5d | Volunteers[6.00 #15] | 840 | 950.5 | 0 | 0 | 1790.5 | 2019-12-09 13:00 | 3d 4h | 1550.5 | 0 | 0 | 0 | 0 | 1550.5 | 0 | 100% | Finished
4 | Placing poles | 2019-12-14 13:00 | 2019-12-17 15:00 | 2d 2h | Volunteers[10.00 #15] | 640 | 8819 | 0 | 0 | 9459 | 2019-12-13 09:00 | 1d 3h | 9219 | 0 | 0 | 0 | 0 | 9219 | 0 | 100% | Finished
5 | Attaching ropes and nets to poles | 2019-12-17 15:00 | 2019-12-28 17:00 | 10d 2h | Volunteers[10.00 #15] | 2880 | 3166.5 | 0 | 0 | 6046.5 | 2019-12-14 13:00 | 4h | 3326.5 | 2480 | 8d 6h | 0 | 0 | 3326.5 | 2480 | 6.061% | Started
6 | Building material post | 2019-12-31 14:00 | 2020-01-02 14:00 | 2d | Volunteers[8.00 #15] | 448 | 1802.5 | 0 | 0 | 2250.5 | 2019-12-09 13:00 | 2d 2h | 2314.5 | 0 | 0 | 0 | 0 | 2314.5 | 0 | 100% | Finished
7 | Building bridges and exits | 2019-12-16 10:00 | 2019-12-23 10:00 | 6d | Volunteers[4.00 #15] | 672 | 1970.5 | 0 | 0 | 2642.5 |  | 0 | 0 | 2642.5 | 6d | 0 | 0 | 0 | 2642.5 | 0% | Not Started
8 | Building plateau and staircase audience | 2020-01-01 14:00 | 2020-01-02 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
9 | Building camera plateau | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
10 | Creating starting sections and finish line | 2019-12-30 09:00 | 2019-12-30 17:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
11 | Installing bicycle storage | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
13 | Placing poles for banners and flags | 2019-12-24 10:00 | 2019-12-24 14:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-12 11:00 | 3h | 626.5 | 0 | 0 | 0 | 0 | 626.5 | 0 | 100% | Finished
14 | Hanging banners | 2020-01-06 14:00 | 2020-01-08 14:00 | 2d | Volunteers[12.00 #15] | 672 | 602.5 | 0 | 0 | 1274.5 |  | 0 | 0 | 1274.5 | 2d | 0 | 0 | 0 | 1274.5 | 0% | Not Started
15 | Hanging track signs | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
16 | Placing flagpoles for homage | 2019-12-28 10:00 | 2019-12-28 14:00 | 3h | Volunteers[4.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 | 2019-12-14 16:00 | 1h | 618.5 | 48 | 3h | 0 | 0 | 618.5 | 48 | 25% | Started
17 | Building podium | 2019-12-23 10:00 | 2019-12-24 10:00 | 1d | Volunteers[5.00 #15] | 140 | 3302.5 | 0 | 0 | 3442.5 | 2019-12-11 15:00 | 4h | 3382.5 | 0 | 0 | 0 | 0 | 3382.5 | 0 | 100% | Finished
18 | Placing traffic signs | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
19 | Placing crush barriers and banners | 2020-01-03 14:00 | 2020-01-06 14:00 | 2d | Volunteers[12.00 #15] | 672 | 2252.5 | 0 | 0 | 2924.5 |  | 0 | 0 | 2924.5 | 2d | 0 | 0 | 0 | 2924.5 | 0% | Not Started
20 | Constructing VIP tents | 2019-12-25 10:00 | 2019-12-26 10:00 | 1d | Volunteers[2.00 #15] | 56 | 28602.5 | 0 | 0 | 28658.5 | 2019-12-12 11:00 | 5h | 28642.5 | 0 | 0 | 0 | 0 | 28642.5 | 0 | 100% | Finished
21 | Placing building fences for VIP tents | 2019-12-31 14:00 | 2020-01-01 14:00 | 1d | Volunteers[6.00 #15] | 168 | 3677.5 | 0 | 0 | 3845.5 |  | 0 | 0 | 3845.5 | 1d | 0 | 0 | 0 | 3845.5 | 0% | Not Started
22 | Installing drains for VIP tents | 2019-12-26 10:00 | 2019-12-27 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-13 09:00 | 6h | 650.5 | 0 | 0 | 0 | 0 | 650.5 | 0 | 100% | Finished
23 | Decorating VIP tents | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[8.00 #15] | 224 | 43602.5 | 0 | 0 | 43826.5 |  | 0 | 0 | 43826.5 | 1d | 0 | 0 | 0 | 43826.5 | 0% | Not Started
24 | Placing toilets for VIP tents | 2019-12-27 10:00 | 2019-12-28 10:00 | 1d | Volunteers[2.00 #15] | 56 | 1577.5 | 0 | 0 | 1633.5 | 2019-12-13 16:00 | 1d | 1633.5 | 0 | 0 | 0 | 0 | 1633.5 | 0 | 100% | Finished
25 | Placing public toilets | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2524.5 | 0 | 0 | 2580.5 | 2019-12-13 13:00 | 1d | 2580.5 | 0 | 0 | 0 | 0 | 2580.5 | 0 | 100% | Finished
26 | Placing garbage bins | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 3442.3 | 0 | 0 | 3554.3 |  | 0 | 0 | 3554.3 | 1d | 0 | 0 | 0 | 3554.3 | 0% | Not Started
27 | Placing and testing generator | 2019-12-24 10:00 | 2019-12-25 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2972.5 | 0 | 0 | 3028.5 | 2019-12-11 15:00 | 4h | 3004.5 | 0 | 0 | 0 | 0 | 3004.5 | 0 | 100% | Finished
28 | Equipping material post | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[2.00 #15] | 56 | 1586.5 | 0 | 0 | 1642.5 | 2019-12-11 15:00 | 1d 3h | 1666.5 | 0 | 0 | 0 | 0 | 1666.5 | 0 | 100% | Finished
29 | Testing high pressure cleaners | 2020-01-03 14:00 | 2020-01-03 17:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-13 10:00 | 2h | 618.5 | 0 | 0 | 0 | 0 | 618.5 | 0 | 100% | Finished
30 | Final check up | 2020-01-08 14:00 | 2020-01-09 12:00 | 6h | Volunteers[2.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 |  | 0 | 0 | 650.5 | 6h | 0 | 0 | 0 | 650.5 | 0% | Not Started
31 | Finish | 2020-01-09 12:00 | 2020-01-09 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started

## TP7
| TP Status Date | 2019-12-16 17:00 |  | TP Name | 16/12/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Project | 2019-12-09 09:00 | 2020-01-09 12:00 | 27d 3h |  |  | 118411.3 |  |  | 126955.3 |  | 7d | [5 empty] | 63164.5 |  | 50.16%
1 | Start | 2019-12-09 09:00 | 2019-12-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-12-09 09:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished
2 | Mowing and cleaning up cuttings | 2019-12-09 09:00 | 2019-12-09 12:00 | 3h | Volunteers[3.00 #15] | 36 | 931.5 | 0 | 0 | 967.5 | 2019-12-09 09:00 | 3h | 967.5 | 0 | 0 | 0 | 0 | 967.5 | 0 | 100% | Finished
3 | Drilling holes | 2019-12-09 13:00 | 2019-12-14 12:00 | 5d | Volunteers[6.00 #15] | 840 | 950.5 | 0 | 0 | 1790.5 | 2019-12-09 13:00 | 3d 4h | 1550.5 | 0 | 0 | 0 | 0 | 1550.5 | 0 | 100% | Finished
4 | Placing poles | 2019-12-14 13:00 | 2019-12-17 15:00 | 2d 2h | Volunteers[10.00 #15] | 640 | 8819 | 0 | 0 | 9459 | 2019-12-13 09:00 | 1d 3h | 9219 | 0 | 0 | 0 | 0 | 9219 | 0 | 100% | Finished
5 | Attaching ropes and nets to poles | 2019-12-17 15:00 | 2019-12-28 17:00 | 10d 2h | Volunteers[10.00 #15] | 2880 | 3166.5 | 0 | 0 | 6046.5 | 2019-12-14 13:00 | 1d 4h | 3606.5 | 2200 | 7d 6h | 0 | 0 | 3606.5 | 2200 | 16.67% | Started
6 | Building material post | 2019-12-31 14:00 | 2020-01-02 14:00 | 2d | Volunteers[8.00 #15] | 448 | 1802.5 | 0 | 0 | 2250.5 | 2019-12-09 13:00 | 2d 2h | 2314.5 | 0 | 0 | 0 | 0 | 2314.5 | 0 | 100% | Finished
7 | Building bridges and exits | 2019-12-16 10:00 | 2019-12-23 10:00 | 6d | Volunteers[4.00 #15] | 672 | 1970.5 | 0 | 0 | 2642.5 | 2019-12-16 13:00 | 4h | 2034.5 | 832 | 7d 3h | 0 | 0 | 2034.5 | 832 | 7.143% | Started
8 | Building plateau and staircase audience | 2020-01-01 14:00 | 2020-01-02 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
9 | Building camera plateau | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
10 | Creating starting sections and finish line | 2019-12-30 09:00 | 2019-12-30 17:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
11 | Installing bicycle storage | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
13 | Placing poles for banners and flags | 2019-12-24 10:00 | 2019-12-24 14:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-12 11:00 | 3h | 626.5 | 0 | 0 | 0 | 0 | 626.5 | 0 | 100% | Finished
14 | Hanging banners | 2020-01-06 14:00 | 2020-01-08 14:00 | 2d | Volunteers[12.00 #15] | 672 | 602.5 | 0 | 0 | 1274.5 |  | 0 | 0 | 1274.5 | 2d | 0 | 0 | 0 | 1274.5 | 0% | Not Started
15 | Hanging track signs | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
16 | Placing flagpoles for homage | 2019-12-28 10:00 | 2019-12-28 14:00 | 3h | Volunteers[4.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 | 2019-12-14 16:00 | 4h | 666.5 | 0 | 0 | 0 | 0 | 666.5 | 0 | 100% | Finished
17 | Building podium | 2019-12-23 10:00 | 2019-12-24 10:00 | 1d | Volunteers[5.00 #15] | 140 | 3302.5 | 0 | 0 | 3442.5 | 2019-12-11 15:00 | 4h | 3382.5 | 0 | 0 | 0 | 0 | 3382.5 | 0 | 100% | Finished
18 | Placing traffic signs | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
19 | Placing crush barriers and banners | 2020-01-03 14:00 | 2020-01-06 14:00 | 2d | Volunteers[12.00 #15] | 672 | 2252.5 | 0 | 0 | 2924.5 |  | 0 | 0 | 2924.5 | 2d | 0 | 0 | 0 | 2924.5 | 0% | Not Started
20 | Constructing VIP tents | 2019-12-25 10:00 | 2019-12-26 10:00 | 1d | Volunteers[2.00 #15] | 56 | 28602.5 | 0 | 0 | 28658.5 | 2019-12-12 11:00 | 5h | 28642.5 | 0 | 0 | 0 | 0 | 28642.5 | 0 | 100% | Finished
21 | Placing building fences for VIP tents | 2019-12-31 14:00 | 2020-01-01 14:00 | 1d | Volunteers[6.00 #15] | 168 | 3677.5 | 0 | 0 | 3845.5 |  | 0 | 0 | 3845.5 | 1d | 0 | 0 | 0 | 3845.5 | 0% | Not Started
22 | Installing drains for VIP tents | 2019-12-26 10:00 | 2019-12-27 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-13 09:00 | 6h | 650.5 | 0 | 0 | 0 | 0 | 650.5 | 0 | 100% | Finished
23 | Decorating VIP tents | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[8.00 #15] | 224 | 43602.5 | 0 | 0 | 43826.5 |  | 0 | 0 | 43826.5 | 1d | 0 | 0 | 0 | 43826.5 | 0% | Not Started
24 | Placing toilets for VIP tents | 2019-12-27 10:00 | 2019-12-28 10:00 | 1d | Volunteers[2.00 #15] | 56 | 1577.5 | 0 | 0 | 1633.5 | 2019-12-13 16:00 | 1d | 1633.5 | 0 | 0 | 0 | 0 | 1633.5 | 0 | 100% | Finished
25 | Placing public toilets | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2524.5 | 0 | 0 | 2580.5 | 2019-12-13 13:00 | 1d | 2580.5 | 0 | 0 | 0 | 0 | 2580.5 | 0 | 100% | Finished
26 | Placing garbage bins | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 3442.3 | 0 | 0 | 3554.3 |  | 0 | 0 | 3554.3 | 1d | 0 | 0 | 0 | 3554.3 | 0% | Not Started
27 | Placing and testing generator | 2019-12-24 10:00 | 2019-12-25 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2972.5 | 0 | 0 | 3028.5 | 2019-12-11 15:00 | 4h | 3004.5 | 0 | 0 | 0 | 0 | 3004.5 | 0 | 100% | Finished
28 | Equipping material post | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[2.00 #15] | 56 | 1586.5 | 0 | 0 | 1642.5 | 2019-12-11 15:00 | 1d 3h | 1666.5 | 0 | 0 | 0 | 0 | 1666.5 | 0 | 100% | Finished
29 | Testing high pressure cleaners | 2020-01-03 14:00 | 2020-01-03 17:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-13 10:00 | 2h | 618.5 | 0 | 0 | 0 | 0 | 618.5 | 0 | 100% | Finished
30 | Final check up | 2020-01-08 14:00 | 2020-01-09 12:00 | 6h | Volunteers[2.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 |  | 0 | 0 | 650.5 | 6h | 0 | 0 | 0 | 650.5 | 0% | Not Started
31 | Finish | 2020-01-09 12:00 | 2020-01-09 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started

## TP8
| TP Status Date | 2019-12-17 17:00 |  | TP Name | 17/12/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Project | 2019-12-09 09:00 | 2020-01-09 12:00 | 27d 3h |  |  | 118411.3 |  |  | 126955.3 |  | 8d | [5 empty] | 63556.5 |  | 50.47%
1 | Start | 2019-12-09 09:00 | 2019-12-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-12-09 09:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished
2 | Mowing and cleaning up cuttings | 2019-12-09 09:00 | 2019-12-09 12:00 | 3h | Volunteers[3.00 #15] | 36 | 931.5 | 0 | 0 | 967.5 | 2019-12-09 09:00 | 3h | 967.5 | 0 | 0 | 0 | 0 | 967.5 | 0 | 100% | Finished
3 | Drilling holes | 2019-12-09 13:00 | 2019-12-14 12:00 | 5d | Volunteers[6.00 #15] | 840 | 950.5 | 0 | 0 | 1790.5 | 2019-12-09 13:00 | 3d 4h | 1550.5 | 0 | 0 | 0 | 0 | 1550.5 | 0 | 100% | Finished
4 | Placing poles | 2019-12-14 13:00 | 2019-12-17 15:00 | 2d 2h | Volunteers[10.00 #15] | 640 | 8819 | 0 | 0 | 9459 | 2019-12-13 09:00 | 1d 3h | 9219 | 0 | 0 | 0 | 0 | 9219 | 0 | 100% | Finished
5 | Attaching ropes and nets to poles | 2019-12-17 15:00 | 2019-12-28 17:00 | 10d 2h | Volunteers[10.00 #15] | 2880 | 3166.5 | 0 | 0 | 6046.5 | 2019-12-14 13:00 | 2d 4h | 3886.5 | 1920 | 6d 6h | 0 | 0 | 3886.5 | 1920 | 27.27% | Started
6 | Building material post | 2019-12-31 14:00 | 2020-01-02 14:00 | 2d | Volunteers[8.00 #15] | 448 | 1802.5 | 0 | 0 | 2250.5 | 2019-12-09 13:00 | 2d 2h | 2314.5 | 0 | 0 | 0 | 0 | 2314.5 | 0 | 100% | Finished
7 | Building bridges and exits | 2019-12-16 10:00 | 2019-12-23 10:00 | 6d | Volunteers[4.00 #15] | 672 | 1970.5 | 0 | 0 | 2642.5 | 2019-12-16 13:00 | 1d 4h | 2146.5 | 720 | 6d 3h | 0 | 0 | 2146.5 | 720 | 19.64% | Started
8 | Building plateau and staircase audience | 2020-01-01 14:00 | 2020-01-02 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
9 | Building camera plateau | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
10 | Creating starting sections and finish line | 2019-12-30 09:00 | 2019-12-30 17:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
11 | Installing bicycle storage | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
13 | Placing poles for banners and flags | 2019-12-24 10:00 | 2019-12-24 14:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-12 11:00 | 3h | 626.5 | 0 | 0 | 0 | 0 | 626.5 | 0 | 100% | Finished
14 | Hanging banners | 2020-01-06 14:00 | 2020-01-08 14:00 | 2d | Volunteers[12.00 #15] | 672 | 602.5 | 0 | 0 | 1274.5 |  | 0 | 0 | 1274.5 | 2d | 0 | 0 | 0 | 1274.5 | 0% | Not Started
15 | Hanging track signs | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
16 | Placing flagpoles for homage | 2019-12-28 10:00 | 2019-12-28 14:00 | 3h | Volunteers[4.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 | 2019-12-14 16:00 | 4h | 666.5 | 0 | 0 | 0 | 0 | 666.5 | 0 | 100% | Finished
17 | Building podium | 2019-12-23 10:00 | 2019-12-24 10:00 | 1d | Volunteers[5.00 #15] | 140 | 3302.5 | 0 | 0 | 3442.5 | 2019-12-11 15:00 | 4h | 3382.5 | 0 | 0 | 0 | 0 | 3382.5 | 0 | 100% | Finished
18 | Placing traffic signs | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
19 | Placing crush barriers and banners | 2020-01-03 14:00 | 2020-01-06 14:00 | 2d | Volunteers[12.00 #15] | 672 | 2252.5 | 0 | 0 | 2924.5 |  | 0 | 0 | 2924.5 | 2d | 0 | 0 | 0 | 2924.5 | 0% | Not Started
20 | Constructing VIP tents | 2019-12-25 10:00 | 2019-12-26 10:00 | 1d | Volunteers[2.00 #15] | 56 | 28602.5 | 0 | 0 | 28658.5 | 2019-12-12 11:00 | 5h | 28642.5 | 0 | 0 | 0 | 0 | 28642.5 | 0 | 100% | Finished
21 | Placing building fences for VIP tents | 2019-12-31 14:00 | 2020-01-01 14:00 | 1d | Volunteers[6.00 #15] | 168 | 3677.5 | 0 | 0 | 3845.5 |  | 0 | 0 | 3845.5 | 1d | 0 | 0 | 0 | 3845.5 | 0% | Not Started
22 | Installing drains for VIP tents | 2019-12-26 10:00 | 2019-12-27 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-13 09:00 | 6h | 650.5 | 0 | 0 | 0 | 0 | 650.5 | 0 | 100% | Finished
23 | Decorating VIP tents | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[8.00 #15] | 224 | 43602.5 | 0 | 0 | 43826.5 |  | 0 | 0 | 43826.5 | 1d | 0 | 0 | 0 | 43826.5 | 0% | Not Started
24 | Placing toilets for VIP tents | 2019-12-27 10:00 | 2019-12-28 10:00 | 1d | Volunteers[2.00 #15] | 56 | 1577.5 | 0 | 0 | 1633.5 | 2019-12-13 16:00 | 1d | 1633.5 | 0 | 0 | 0 | 0 | 1633.5 | 0 | 100% | Finished
25 | Placing public toilets | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2524.5 | 0 | 0 | 2580.5 | 2019-12-13 13:00 | 1d | 2580.5 | 0 | 0 | 0 | 0 | 2580.5 | 0 | 100% | Finished
26 | Placing garbage bins | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 3442.3 | 0 | 0 | 3554.3 |  | 0 | 0 | 3554.3 | 1d | 0 | 0 | 0 | 3554.3 | 0% | Not Started
27 | Placing and testing generator | 2019-12-24 10:00 | 2019-12-25 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2972.5 | 0 | 0 | 3028.5 | 2019-12-11 15:00 | 4h | 3004.5 | 0 | 0 | 0 | 0 | 3004.5 | 0 | 100% | Finished
28 | Equipping material post | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[2.00 #15] | 56 | 1586.5 | 0 | 0 | 1642.5 | 2019-12-11 15:00 | 1d 3h | 1666.5 | 0 | 0 | 0 | 0 | 1666.5 | 0 | 100% | Finished
29 | Testing high pressure cleaners | 2020-01-03 14:00 | 2020-01-03 17:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-13 10:00 | 2h | 618.5 | 0 | 0 | 0 | 0 | 618.5 | 0 | 100% | Finished
30 | Final check up | 2020-01-08 14:00 | 2020-01-09 12:00 | 6h | Volunteers[2.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 |  | 0 | 0 | 650.5 | 6h | 0 | 0 | 0 | 650.5 | 0% | Not Started
31 | Finish | 2020-01-09 12:00 | 2020-01-09 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started

## TP9
| TP Status Date | 2019-12-18 17:00 |  | TP Name | 18/12/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Project | 2019-12-09 09:00 | 2020-01-09 12:00 | 27d 3h |  |  | 118411.3 |  |  | 126955.3 |  | 9d | [5 empty] | 63948.5 |  | 50.77%
1 | Start | 2019-12-09 09:00 | 2019-12-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-12-09 09:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished
2 | Mowing and cleaning up cuttings | 2019-12-09 09:00 | 2019-12-09 12:00 | 3h | Volunteers[3.00 #15] | 36 | 931.5 | 0 | 0 | 967.5 | 2019-12-09 09:00 | 3h | 967.5 | 0 | 0 | 0 | 0 | 967.5 | 0 | 100% | Finished
3 | Drilling holes | 2019-12-09 13:00 | 2019-12-14 12:00 | 5d | Volunteers[6.00 #15] | 840 | 950.5 | 0 | 0 | 1790.5 | 2019-12-09 13:00 | 3d 4h | 1550.5 | 0 | 0 | 0 | 0 | 1550.5 | 0 | 100% | Finished
4 | Placing poles | 2019-12-14 13:00 | 2019-12-17 15:00 | 2d 2h | Volunteers[10.00 #15] | 640 | 8819 | 0 | 0 | 9459 | 2019-12-13 09:00 | 1d 3h | 9219 | 0 | 0 | 0 | 0 | 9219 | 0 | 100% | Finished
5 | Attaching ropes and nets to poles | 2019-12-17 15:00 | 2019-12-28 17:00 | 10d 2h | Volunteers[10.00 #15] | 2880 | 3166.5 | 0 | 0 | 6046.5 | 2019-12-14 13:00 | 3d 4h | 4166.5 | 1640 | 5d 6h | 0 | 0 | 4166.5 | 1640 | 37.88% | Started
6 | Building material post | 2019-12-31 14:00 | 2020-01-02 14:00 | 2d | Volunteers[8.00 #15] | 448 | 1802.5 | 0 | 0 | 2250.5 | 2019-12-09 13:00 | 2d 2h | 2314.5 | 0 | 0 | 0 | 0 | 2314.5 | 0 | 100% | Finished
7 | Building bridges and exits | 2019-12-16 10:00 | 2019-12-23 10:00 | 6d | Volunteers[4.00 #15] | 672 | 1970.5 | 0 | 0 | 2642.5 | 2019-12-16 13:00 | 2d 4h | 2258.5 | 608 | 5d 3h | 0 | 0 | 2258.5 | 608 | 32.14% | Started
8 | Building plateau and staircase audience | 2020-01-01 14:00 | 2020-01-02 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
9 | Building camera plateau | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
10 | Creating starting sections and finish line | 2019-12-30 09:00 | 2019-12-30 17:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
11 | Installing bicycle storage | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
13 | Placing poles for banners and flags | 2019-12-24 10:00 | 2019-12-24 14:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-12 11:00 | 3h | 626.5 | 0 | 0 | 0 | 0 | 626.5 | 0 | 100% | Finished
14 | Hanging banners | 2020-01-06 14:00 | 2020-01-08 14:00 | 2d | Volunteers[12.00 #15] | 672 | 602.5 | 0 | 0 | 1274.5 |  | 0 | 0 | 1274.5 | 2d | 0 | 0 | 0 | 1274.5 | 0% | Not Started
15 | Hanging track signs | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
16 | Placing flagpoles for homage | 2019-12-28 10:00 | 2019-12-28 14:00 | 3h | Volunteers[4.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 | 2019-12-14 16:00 | 4h | 666.5 | 0 | 0 | 0 | 0 | 666.5 | 0 | 100% | Finished
17 | Building podium | 2019-12-23 10:00 | 2019-12-24 10:00 | 1d | Volunteers[5.00 #15] | 140 | 3302.5 | 0 | 0 | 3442.5 | 2019-12-11 15:00 | 4h | 3382.5 | 0 | 0 | 0 | 0 | 3382.5 | 0 | 100% | Finished
18 | Placing traffic signs | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
19 | Placing crush barriers and banners | 2020-01-03 14:00 | 2020-01-06 14:00 | 2d | Volunteers[12.00 #15] | 672 | 2252.5 | 0 | 0 | 2924.5 |  | 0 | 0 | 2924.5 | 2d | 0 | 0 | 0 | 2924.5 | 0% | Not Started
20 | Constructing VIP tents | 2019-12-25 10:00 | 2019-12-26 10:00 | 1d | Volunteers[2.00 #15] | 56 | 28602.5 | 0 | 0 | 28658.5 | 2019-12-12 11:00 | 5h | 28642.5 | 0 | 0 | 0 | 0 | 28642.5 | 0 | 100% | Finished
21 | Placing building fences for VIP tents | 2019-12-31 14:00 | 2020-01-01 14:00 | 1d | Volunteers[6.00 #15] | 168 | 3677.5 | 0 | 0 | 3845.5 |  | 0 | 0 | 3845.5 | 1d | 0 | 0 | 0 | 3845.5 | 0% | Not Started
22 | Installing drains for VIP tents | 2019-12-26 10:00 | 2019-12-27 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-13 09:00 | 6h | 650.5 | 0 | 0 | 0 | 0 | 650.5 | 0 | 100% | Finished
23 | Decorating VIP tents | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[8.00 #15] | 224 | 43602.5 | 0 | 0 | 43826.5 |  | 0 | 0 | 43826.5 | 1d | 0 | 0 | 0 | 43826.5 | 0% | Not Started
24 | Placing toilets for VIP tents | 2019-12-27 10:00 | 2019-12-28 10:00 | 1d | Volunteers[2.00 #15] | 56 | 1577.5 | 0 | 0 | 1633.5 | 2019-12-13 16:00 | 1d | 1633.5 | 0 | 0 | 0 | 0 | 1633.5 | 0 | 100% | Finished
25 | Placing public toilets | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2524.5 | 0 | 0 | 2580.5 | 2019-12-13 13:00 | 1d | 2580.5 | 0 | 0 | 0 | 0 | 2580.5 | 0 | 100% | Finished
26 | Placing garbage bins | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 3442.3 | 0 | 0 | 3554.3 |  | 0 | 0 | 3554.3 | 1d | 0 | 0 | 0 | 3554.3 | 0% | Not Started
27 | Placing and testing generator | 2019-12-24 10:00 | 2019-12-25 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2972.5 | 0 | 0 | 3028.5 | 2019-12-11 15:00 | 4h | 3004.5 | 0 | 0 | 0 | 0 | 3004.5 | 0 | 100% | Finished
28 | Equipping material post | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[2.00 #15] | 56 | 1586.5 | 0 | 0 | 1642.5 | 2019-12-11 15:00 | 1d 3h | 1666.5 | 0 | 0 | 0 | 0 | 1666.5 | 0 | 100% | Finished
29 | Testing high pressure cleaners | 2020-01-03 14:00 | 2020-01-03 17:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-13 10:00 | 2h | 618.5 | 0 | 0 | 0 | 0 | 618.5 | 0 | 100% | Finished
30 | Final check up | 2020-01-08 14:00 | 2020-01-09 12:00 | 6h | Volunteers[2.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 |  | 0 | 0 | 650.5 | 6h | 0 | 0 | 0 | 650.5 | 0% | Not Started
31 | Finish | 2020-01-09 12:00 | 2020-01-09 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started

## TP10
| TP Status Date | 2019-12-19 17:00 |  | TP Name | 19/12/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Project | 2019-12-09 09:00 | 2020-01-09 12:00 | 27d 3h |  |  | 118411.3 |  |  | 126955.3 |  | 10d | [5 empty] | 64340.5 |  | 51.08%
1 | Start | 2019-12-09 09:00 | 2019-12-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-12-09 09:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished
2 | Mowing and cleaning up cuttings | 2019-12-09 09:00 | 2019-12-09 12:00 | 3h | Volunteers[3.00 #15] | 36 | 931.5 | 0 | 0 | 967.5 | 2019-12-09 09:00 | 3h | 967.5 | 0 | 0 | 0 | 0 | 967.5 | 0 | 100% | Finished
3 | Drilling holes | 2019-12-09 13:00 | 2019-12-14 12:00 | 5d | Volunteers[6.00 #15] | 840 | 950.5 | 0 | 0 | 1790.5 | 2019-12-09 13:00 | 3d 4h | 1550.5 | 0 | 0 | 0 | 0 | 1550.5 | 0 | 100% | Finished
4 | Placing poles | 2019-12-14 13:00 | 2019-12-17 15:00 | 2d 2h | Volunteers[10.00 #15] | 640 | 8819 | 0 | 0 | 9459 | 2019-12-13 09:00 | 1d 3h | 9219 | 0 | 0 | 0 | 0 | 9219 | 0 | 100% | Finished
5 | Attaching ropes and nets to poles | 2019-12-17 15:00 | 2019-12-28 17:00 | 10d 2h | Volunteers[10.00 #15] | 2880 | 3166.5 | 0 | 0 | 6046.5 | 2019-12-14 13:00 | 4d 4h | 4446.5 | 1360 | 4d 6h | 0 | 0 | 4446.5 | 1360 | 48.48% | Started
6 | Building material post | 2019-12-31 14:00 | 2020-01-02 14:00 | 2d | Volunteers[8.00 #15] | 448 | 1802.5 | 0 | 0 | 2250.5 | 2019-12-09 13:00 | 2d 2h | 2314.5 | 0 | 0 | 0 | 0 | 2314.5 | 0 | 100% | Finished
7 | Building bridges and exits | 2019-12-16 10:00 | 2019-12-23 10:00 | 6d | Volunteers[4.00 #15] | 672 | 1970.5 | 0 | 0 | 2642.5 | 2019-12-16 13:00 | 3d 4h | 2370.5 | 496 | 4d 3h | 0 | 0 | 2370.5 | 496 | 44.64% | Started
8 | Building plateau and staircase audience | 2020-01-01 14:00 | 2020-01-02 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
9 | Building camera plateau | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
10 | Creating starting sections and finish line | 2019-12-30 09:00 | 2019-12-30 17:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
11 | Installing bicycle storage | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
13 | Placing poles for banners and flags | 2019-12-24 10:00 | 2019-12-24 14:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-12 11:00 | 3h | 626.5 | 0 | 0 | 0 | 0 | 626.5 | 0 | 100% | Finished
14 | Hanging banners | 2020-01-06 14:00 | 2020-01-08 14:00 | 2d | Volunteers[12.00 #15] | 672 | 602.5 | 0 | 0 | 1274.5 |  | 0 | 0 | 1274.5 | 2d | 0 | 0 | 0 | 1274.5 | 0% | Not Started
15 | Hanging track signs | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
16 | Placing flagpoles for homage | 2019-12-28 10:00 | 2019-12-28 14:00 | 3h | Volunteers[4.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 | 2019-12-14 16:00 | 4h | 666.5 | 0 | 0 | 0 | 0 | 666.5 | 0 | 100% | Finished
17 | Building podium | 2019-12-23 10:00 | 2019-12-24 10:00 | 1d | Volunteers[5.00 #15] | 140 | 3302.5 | 0 | 0 | 3442.5 | 2019-12-11 15:00 | 4h | 3382.5 | 0 | 0 | 0 | 0 | 3382.5 | 0 | 100% | Finished
18 | Placing traffic signs | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
19 | Placing crush barriers and banners | 2020-01-03 14:00 | 2020-01-06 14:00 | 2d | Volunteers[12.00 #15] | 672 | 2252.5 | 0 | 0 | 2924.5 |  | 0 | 0 | 2924.5 | 2d | 0 | 0 | 0 | 2924.5 | 0% | Not Started
20 | Constructing VIP tents | 2019-12-25 10:00 | 2019-12-26 10:00 | 1d | Volunteers[2.00 #15] | 56 | 28602.5 | 0 | 0 | 28658.5 | 2019-12-12 11:00 | 5h | 28642.5 | 0 | 0 | 0 | 0 | 28642.5 | 0 | 100% | Finished
21 | Placing building fences for VIP tents | 2019-12-31 14:00 | 2020-01-01 14:00 | 1d | Volunteers[6.00 #15] | 168 | 3677.5 | 0 | 0 | 3845.5 |  | 0 | 0 | 3845.5 | 1d | 0 | 0 | 0 | 3845.5 | 0% | Not Started
22 | Installing drains for VIP tents | 2019-12-26 10:00 | 2019-12-27 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-13 09:00 | 6h | 650.5 | 0 | 0 | 0 | 0 | 650.5 | 0 | 100% | Finished
23 | Decorating VIP tents | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[8.00 #15] | 224 | 43602.5 | 0 | 0 | 43826.5 |  | 0 | 0 | 43826.5 | 1d | 0 | 0 | 0 | 43826.5 | 0% | Not Started
24 | Placing toilets for VIP tents | 2019-12-27 10:00 | 2019-12-28 10:00 | 1d | Volunteers[2.00 #15] | 56 | 1577.5 | 0 | 0 | 1633.5 | 2019-12-13 16:00 | 1d | 1633.5 | 0 | 0 | 0 | 0 | 1633.5 | 0 | 100% | Finished
25 | Placing public toilets | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2524.5 | 0 | 0 | 2580.5 | 2019-12-13 13:00 | 1d | 2580.5 | 0 | 0 | 0 | 0 | 2580.5 | 0 | 100% | Finished
26 | Placing garbage bins | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 3442.3 | 0 | 0 | 3554.3 |  | 0 | 0 | 3554.3 | 1d | 0 | 0 | 0 | 3554.3 | 0% | Not Started
27 | Placing and testing generator | 2019-12-24 10:00 | 2019-12-25 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2972.5 | 0 | 0 | 3028.5 | 2019-12-11 15:00 | 4h | 3004.5 | 0 | 0 | 0 | 0 | 3004.5 | 0 | 100% | Finished
28 | Equipping material post | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[2.00 #15] | 56 | 1586.5 | 0 | 0 | 1642.5 | 2019-12-11 15:00 | 1d 3h | 1666.5 | 0 | 0 | 0 | 0 | 1666.5 | 0 | 100% | Finished
29 | Testing high pressure cleaners | 2020-01-03 14:00 | 2020-01-03 17:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-13 10:00 | 2h | 618.5 | 0 | 0 | 0 | 0 | 618.5 | 0 | 100% | Finished
30 | Final check up | 2020-01-08 14:00 | 2020-01-09 12:00 | 6h | Volunteers[2.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 |  | 0 | 0 | 650.5 | 6h | 0 | 0 | 0 | 650.5 | 0% | Not Started
31 | Finish | 2020-01-09 12:00 | 2020-01-09 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started

## TP11
| TP Status Date | 2019-12-20 17:00 |  | TP Name | 20/12/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Project | 2019-12-09 09:00 | 2020-01-09 12:00 | 27d 3h |  |  | 118411.3 |  |  | 126955.3 |  | 11d | [5 empty] | 64732.5 |  | 51.39%
1 | Start | 2019-12-09 09:00 | 2019-12-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-12-09 09:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished
2 | Mowing and cleaning up cuttings | 2019-12-09 09:00 | 2019-12-09 12:00 | 3h | Volunteers[3.00 #15] | 36 | 931.5 | 0 | 0 | 967.5 | 2019-12-09 09:00 | 3h | 967.5 | 0 | 0 | 0 | 0 | 967.5 | 0 | 100% | Finished
3 | Drilling holes | 2019-12-09 13:00 | 2019-12-14 12:00 | 5d | Volunteers[6.00 #15] | 840 | 950.5 | 0 | 0 | 1790.5 | 2019-12-09 13:00 | 3d 4h | 1550.5 | 0 | 0 | 0 | 0 | 1550.5 | 0 | 100% | Finished
4 | Placing poles | 2019-12-14 13:00 | 2019-12-17 15:00 | 2d 2h | Volunteers[10.00 #15] | 640 | 8819 | 0 | 0 | 9459 | 2019-12-13 09:00 | 1d 3h | 9219 | 0 | 0 | 0 | 0 | 9219 | 0 | 100% | Finished
5 | Attaching ropes and nets to poles | 2019-12-17 15:00 | 2019-12-28 17:00 | 10d 2h | Volunteers[10.00 #15] | 2880 | 3166.5 | 0 | 0 | 6046.5 | 2019-12-14 13:00 | 5d 4h | 4726.5 | 1080 | 3d 6h | 0 | 0 | 4726.5 | 1080 | 59.09% | Started
6 | Building material post | 2019-12-31 14:00 | 2020-01-02 14:00 | 2d | Volunteers[8.00 #15] | 448 | 1802.5 | 0 | 0 | 2250.5 | 2019-12-09 13:00 | 2d 2h | 2314.5 | 0 | 0 | 0 | 0 | 2314.5 | 0 | 100% | Finished
7 | Building bridges and exits | 2019-12-16 10:00 | 2019-12-23 10:00 | 6d | Volunteers[4.00 #15] | 672 | 1970.5 | 0 | 0 | 2642.5 | 2019-12-16 13:00 | 4d 4h | 2482.5 | 384 | 3d 3h | 0 | 0 | 2482.5 | 384 | 57.14% | Started
8 | Building plateau and staircase audience | 2020-01-01 14:00 | 2020-01-02 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
9 | Building camera plateau | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
10 | Creating starting sections and finish line | 2019-12-30 09:00 | 2019-12-30 17:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
11 | Installing bicycle storage | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
13 | Placing poles for banners and flags | 2019-12-24 10:00 | 2019-12-24 14:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-12 11:00 | 3h | 626.5 | 0 | 0 | 0 | 0 | 626.5 | 0 | 100% | Finished
14 | Hanging banners | 2020-01-06 14:00 | 2020-01-08 14:00 | 2d | Volunteers[12.00 #15] | 672 | 602.5 | 0 | 0 | 1274.5 |  | 0 | 0 | 1274.5 | 2d | 0 | 0 | 0 | 1274.5 | 0% | Not Started
15 | Hanging track signs | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
16 | Placing flagpoles for homage | 2019-12-28 10:00 | 2019-12-28 14:00 | 3h | Volunteers[4.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 | 2019-12-14 16:00 | 4h | 666.5 | 0 | 0 | 0 | 0 | 666.5 | 0 | 100% | Finished
17 | Building podium | 2019-12-23 10:00 | 2019-12-24 10:00 | 1d | Volunteers[5.00 #15] | 140 | 3302.5 | 0 | 0 | 3442.5 | 2019-12-11 15:00 | 4h | 3382.5 | 0 | 0 | 0 | 0 | 3382.5 | 0 | 100% | Finished
18 | Placing traffic signs | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
19 | Placing crush barriers and banners | 2020-01-03 14:00 | 2020-01-06 14:00 | 2d | Volunteers[12.00 #15] | 672 | 2252.5 | 0 | 0 | 2924.5 |  | 0 | 0 | 2924.5 | 2d | 0 | 0 | 0 | 2924.5 | 0% | Not Started
20 | Constructing VIP tents | 2019-12-25 10:00 | 2019-12-26 10:00 | 1d | Volunteers[2.00 #15] | 56 | 28602.5 | 0 | 0 | 28658.5 | 2019-12-12 11:00 | 5h | 28642.5 | 0 | 0 | 0 | 0 | 28642.5 | 0 | 100% | Finished
21 | Placing building fences for VIP tents | 2019-12-31 14:00 | 2020-01-01 14:00 | 1d | Volunteers[6.00 #15] | 168 | 3677.5 | 0 | 0 | 3845.5 |  | 0 | 0 | 3845.5 | 1d | 0 | 0 | 0 | 3845.5 | 0% | Not Started
22 | Installing drains for VIP tents | 2019-12-26 10:00 | 2019-12-27 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-13 09:00 | 6h | 650.5 | 0 | 0 | 0 | 0 | 650.5 | 0 | 100% | Finished
23 | Decorating VIP tents | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[8.00 #15] | 224 | 43602.5 | 0 | 0 | 43826.5 |  | 0 | 0 | 43826.5 | 1d | 0 | 0 | 0 | 43826.5 | 0% | Not Started
24 | Placing toilets for VIP tents | 2019-12-27 10:00 | 2019-12-28 10:00 | 1d | Volunteers[2.00 #15] | 56 | 1577.5 | 0 | 0 | 1633.5 | 2019-12-13 16:00 | 1d | 1633.5 | 0 | 0 | 0 | 0 | 1633.5 | 0 | 100% | Finished
25 | Placing public toilets | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2524.5 | 0 | 0 | 2580.5 | 2019-12-13 13:00 | 1d | 2580.5 | 0 | 0 | 0 | 0 | 2580.5 | 0 | 100% | Finished
26 | Placing garbage bins | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 3442.3 | 0 | 0 | 3554.3 |  | 0 | 0 | 3554.3 | 1d | 0 | 0 | 0 | 3554.3 | 0% | Not Started
27 | Placing and testing generator | 2019-12-24 10:00 | 2019-12-25 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2972.5 | 0 | 0 | 3028.5 | 2019-12-11 15:00 | 4h | 3004.5 | 0 | 0 | 0 | 0 | 3004.5 | 0 | 100% | Finished
28 | Equipping material post | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[2.00 #15] | 56 | 1586.5 | 0 | 0 | 1642.5 | 2019-12-11 15:00 | 1d 3h | 1666.5 | 0 | 0 | 0 | 0 | 1666.5 | 0 | 100% | Finished
29 | Testing high pressure cleaners | 2020-01-03 14:00 | 2020-01-03 17:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-13 10:00 | 2h | 618.5 | 0 | 0 | 0 | 0 | 618.5 | 0 | 100% | Finished
30 | Final check up | 2020-01-08 14:00 | 2020-01-09 12:00 | 6h | Volunteers[2.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 |  | 0 | 0 | 650.5 | 6h | 0 | 0 | 0 | 650.5 | 0% | Not Started
31 | Finish | 2020-01-09 12:00 | 2020-01-09 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started

## TP12
| TP Status Date | 2019-12-21 17:00 |  | TP Name | 21/12/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Project | 2019-12-09 09:00 | 2020-01-09 12:00 | 27d 3h |  |  | 118411.3 |  |  | 126955.3 |  | 12d | [5 empty] | 65124.5 |  | 51.69%
1 | Start | 2019-12-09 09:00 | 2019-12-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-12-09 09:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished
2 | Mowing and cleaning up cuttings | 2019-12-09 09:00 | 2019-12-09 12:00 | 3h | Volunteers[3.00 #15] | 36 | 931.5 | 0 | 0 | 967.5 | 2019-12-09 09:00 | 3h | 967.5 | 0 | 0 | 0 | 0 | 967.5 | 0 | 100% | Finished
3 | Drilling holes | 2019-12-09 13:00 | 2019-12-14 12:00 | 5d | Volunteers[6.00 #15] | 840 | 950.5 | 0 | 0 | 1790.5 | 2019-12-09 13:00 | 3d 4h | 1550.5 | 0 | 0 | 0 | 0 | 1550.5 | 0 | 100% | Finished
4 | Placing poles | 2019-12-14 13:00 | 2019-12-17 15:00 | 2d 2h | Volunteers[10.00 #15] | 640 | 8819 | 0 | 0 | 9459 | 2019-12-13 09:00 | 1d 3h | 9219 | 0 | 0 | 0 | 0 | 9219 | 0 | 100% | Finished
5 | Attaching ropes and nets to poles | 2019-12-17 15:00 | 2019-12-28 17:00 | 10d 2h | Volunteers[10.00 #15] | 2880 | 3166.5 | 0 | 0 | 6046.5 | 2019-12-14 13:00 | 6d 4h | 5006.5 | 800 | 2d 6h | 0 | 0 | 5006.5 | 800 | 69.7% | Started
6 | Building material post | 2019-12-31 14:00 | 2020-01-02 14:00 | 2d | Volunteers[8.00 #15] | 448 | 1802.5 | 0 | 0 | 2250.5 | 2019-12-09 13:00 | 2d 2h | 2314.5 | 0 | 0 | 0 | 0 | 2314.5 | 0 | 100% | Finished
7 | Building bridges and exits | 2019-12-16 10:00 | 2019-12-23 10:00 | 6d | Volunteers[4.00 #15] | 672 | 1970.5 | 0 | 0 | 2642.5 | 2019-12-16 13:00 | 5d 4h | 2594.5 | 272 | 2d 3h | 0 | 0 | 2594.5 | 272 | 69.64% | Started
8 | Building plateau and staircase audience | 2020-01-01 14:00 | 2020-01-02 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
9 | Building camera plateau | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
10 | Creating starting sections and finish line | 2019-12-30 09:00 | 2019-12-30 17:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
11 | Installing bicycle storage | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
13 | Placing poles for banners and flags | 2019-12-24 10:00 | 2019-12-24 14:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-12 11:00 | 3h | 626.5 | 0 | 0 | 0 | 0 | 626.5 | 0 | 100% | Finished
14 | Hanging banners | 2020-01-06 14:00 | 2020-01-08 14:00 | 2d | Volunteers[12.00 #15] | 672 | 602.5 | 0 | 0 | 1274.5 |  | 0 | 0 | 1274.5 | 2d | 0 | 0 | 0 | 1274.5 | 0% | Not Started
15 | Hanging track signs | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
16 | Placing flagpoles for homage | 2019-12-28 10:00 | 2019-12-28 14:00 | 3h | Volunteers[4.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 | 2019-12-14 16:00 | 4h | 666.5 | 0 | 0 | 0 | 0 | 666.5 | 0 | 100% | Finished
17 | Building podium | 2019-12-23 10:00 | 2019-12-24 10:00 | 1d | Volunteers[5.00 #15] | 140 | 3302.5 | 0 | 0 | 3442.5 | 2019-12-11 15:00 | 4h | 3382.5 | 0 | 0 | 0 | 0 | 3382.5 | 0 | 100% | Finished
18 | Placing traffic signs | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
19 | Placing crush barriers and banners | 2020-01-03 14:00 | 2020-01-06 14:00 | 2d | Volunteers[12.00 #15] | 672 | 2252.5 | 0 | 0 | 2924.5 |  | 0 | 0 | 2924.5 | 2d | 0 | 0 | 0 | 2924.5 | 0% | Not Started
20 | Constructing VIP tents | 2019-12-25 10:00 | 2019-12-26 10:00 | 1d | Volunteers[2.00 #15] | 56 | 28602.5 | 0 | 0 | 28658.5 | 2019-12-12 11:00 | 5h | 28642.5 | 0 | 0 | 0 | 0 | 28642.5 | 0 | 100% | Finished
21 | Placing building fences for VIP tents | 2019-12-31 14:00 | 2020-01-01 14:00 | 1d | Volunteers[6.00 #15] | 168 | 3677.5 | 0 | 0 | 3845.5 |  | 0 | 0 | 3845.5 | 1d | 0 | 0 | 0 | 3845.5 | 0% | Not Started
22 | Installing drains for VIP tents | 2019-12-26 10:00 | 2019-12-27 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-13 09:00 | 6h | 650.5 | 0 | 0 | 0 | 0 | 650.5 | 0 | 100% | Finished
23 | Decorating VIP tents | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[8.00 #15] | 224 | 43602.5 | 0 | 0 | 43826.5 |  | 0 | 0 | 43826.5 | 1d | 0 | 0 | 0 | 43826.5 | 0% | Not Started
24 | Placing toilets for VIP tents | 2019-12-27 10:00 | 2019-12-28 10:00 | 1d | Volunteers[2.00 #15] | 56 | 1577.5 | 0 | 0 | 1633.5 | 2019-12-13 16:00 | 1d | 1633.5 | 0 | 0 | 0 | 0 | 1633.5 | 0 | 100% | Finished
25 | Placing public toilets | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2524.5 | 0 | 0 | 2580.5 | 2019-12-13 13:00 | 1d | 2580.5 | 0 | 0 | 0 | 0 | 2580.5 | 0 | 100% | Finished
26 | Placing garbage bins | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 3442.3 | 0 | 0 | 3554.3 |  | 0 | 0 | 3554.3 | 1d | 0 | 0 | 0 | 3554.3 | 0% | Not Started
27 | Placing and testing generator | 2019-12-24 10:00 | 2019-12-25 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2972.5 | 0 | 0 | 3028.5 | 2019-12-11 15:00 | 4h | 3004.5 | 0 | 0 | 0 | 0 | 3004.5 | 0 | 100% | Finished
28 | Equipping material post | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[2.00 #15] | 56 | 1586.5 | 0 | 0 | 1642.5 | 2019-12-11 15:00 | 1d 3h | 1666.5 | 0 | 0 | 0 | 0 | 1666.5 | 0 | 100% | Finished
29 | Testing high pressure cleaners | 2020-01-03 14:00 | 2020-01-03 17:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-13 10:00 | 2h | 618.5 | 0 | 0 | 0 | 0 | 618.5 | 0 | 100% | Finished
30 | Final check up | 2020-01-08 14:00 | 2020-01-09 12:00 | 6h | Volunteers[2.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 |  | 0 | 0 | 650.5 | 6h | 0 | 0 | 0 | 650.5 | 0% | Not Started
31 | Finish | 2020-01-09 12:00 | 2020-01-09 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started

## TP13
| TP Status Date | 2019-12-23 17:00 |  | TP Name | 23/12/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Project | 2019-12-09 09:00 | 2020-01-09 12:00 | 27d 3h |  |  | 118411.3 |  |  | 126955.3 |  | 13d | [5 empty] | 65516.5 |  | 52%
1 | Start | 2019-12-09 09:00 | 2019-12-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-12-09 09:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished
2 | Mowing and cleaning up cuttings | 2019-12-09 09:00 | 2019-12-09 12:00 | 3h | Volunteers[3.00 #15] | 36 | 931.5 | 0 | 0 | 967.5 | 2019-12-09 09:00 | 3h | 967.5 | 0 | 0 | 0 | 0 | 967.5 | 0 | 100% | Finished
3 | Drilling holes | 2019-12-09 13:00 | 2019-12-14 12:00 | 5d | Volunteers[6.00 #15] | 840 | 950.5 | 0 | 0 | 1790.5 | 2019-12-09 13:00 | 3d 4h | 1550.5 | 0 | 0 | 0 | 0 | 1550.5 | 0 | 100% | Finished
4 | Placing poles | 2019-12-14 13:00 | 2019-12-17 15:00 | 2d 2h | Volunteers[10.00 #15] | 640 | 8819 | 0 | 0 | 9459 | 2019-12-13 09:00 | 1d 3h | 9219 | 0 | 0 | 0 | 0 | 9219 | 0 | 100% | Finished
5 | Attaching ropes and nets to poles | 2019-12-17 15:00 | 2019-12-28 17:00 | 10d 2h | Volunteers[10.00 #15] | 2880 | 3166.5 | 0 | 0 | 6046.5 | 2019-12-14 13:00 | 7d 4h | 5286.5 | 520 | 1d 6h | 0 | 0 | 5286.5 | 520 | 80.3% | Started
6 | Building material post | 2019-12-31 14:00 | 2020-01-02 14:00 | 2d | Volunteers[8.00 #15] | 448 | 1802.5 | 0 | 0 | 2250.5 | 2019-12-09 13:00 | 2d 2h | 2314.5 | 0 | 0 | 0 | 0 | 2314.5 | 0 | 100% | Finished
7 | Building bridges and exits | 2019-12-16 10:00 | 2019-12-23 10:00 | 6d | Volunteers[4.00 #15] | 672 | 1970.5 | 0 | 0 | 2642.5 | 2019-12-16 13:00 | 6d 4h | 2706.5 | 160 | 1d 3h | 0 | 0 | 2706.5 | 160 | 82.14% | Started
8 | Building plateau and staircase audience | 2020-01-01 14:00 | 2020-01-02 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
9 | Building camera plateau | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
10 | Creating starting sections and finish line | 2019-12-30 09:00 | 2019-12-30 17:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
11 | Installing bicycle storage | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
13 | Placing poles for banners and flags | 2019-12-24 10:00 | 2019-12-24 14:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-12 11:00 | 3h | 626.5 | 0 | 0 | 0 | 0 | 626.5 | 0 | 100% | Finished
14 | Hanging banners | 2020-01-06 14:00 | 2020-01-08 14:00 | 2d | Volunteers[12.00 #15] | 672 | 602.5 | 0 | 0 | 1274.5 |  | 0 | 0 | 1274.5 | 2d | 0 | 0 | 0 | 1274.5 | 0% | Not Started
15 | Hanging track signs | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
16 | Placing flagpoles for homage | 2019-12-28 10:00 | 2019-12-28 14:00 | 3h | Volunteers[4.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 | 2019-12-14 16:00 | 4h | 666.5 | 0 | 0 | 0 | 0 | 666.5 | 0 | 100% | Finished
17 | Building podium | 2019-12-23 10:00 | 2019-12-24 10:00 | 1d | Volunteers[5.00 #15] | 140 | 3302.5 | 0 | 0 | 3442.5 | 2019-12-11 15:00 | 4h | 3382.5 | 0 | 0 | 0 | 0 | 3382.5 | 0 | 100% | Finished
18 | Placing traffic signs | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
19 | Placing crush barriers and banners | 2020-01-03 14:00 | 2020-01-06 14:00 | 2d | Volunteers[12.00 #15] | 672 | 2252.5 | 0 | 0 | 2924.5 |  | 0 | 0 | 2924.5 | 2d | 0 | 0 | 0 | 2924.5 | 0% | Not Started
20 | Constructing VIP tents | 2019-12-25 10:00 | 2019-12-26 10:00 | 1d | Volunteers[2.00 #15] | 56 | 28602.5 | 0 | 0 | 28658.5 | 2019-12-12 11:00 | 5h | 28642.5 | 0 | 0 | 0 | 0 | 28642.5 | 0 | 100% | Finished
21 | Placing building fences for VIP tents | 2019-12-31 14:00 | 2020-01-01 14:00 | 1d | Volunteers[6.00 #15] | 168 | 3677.5 | 0 | 0 | 3845.5 |  | 0 | 0 | 3845.5 | 1d | 0 | 0 | 0 | 3845.5 | 0% | Not Started
22 | Installing drains for VIP tents | 2019-12-26 10:00 | 2019-12-27 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-13 09:00 | 6h | 650.5 | 0 | 0 | 0 | 0 | 650.5 | 0 | 100% | Finished
23 | Decorating VIP tents | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[8.00 #15] | 224 | 43602.5 | 0 | 0 | 43826.5 |  | 0 | 0 | 43826.5 | 1d | 0 | 0 | 0 | 43826.5 | 0% | Not Started
24 | Placing toilets for VIP tents | 2019-12-27 10:00 | 2019-12-28 10:00 | 1d | Volunteers[2.00 #15] | 56 | 1577.5 | 0 | 0 | 1633.5 | 2019-12-13 16:00 | 1d | 1633.5 | 0 | 0 | 0 | 0 | 1633.5 | 0 | 100% | Finished
25 | Placing public toilets | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2524.5 | 0 | 0 | 2580.5 | 2019-12-13 13:00 | 1d | 2580.5 | 0 | 0 | 0 | 0 | 2580.5 | 0 | 100% | Finished
26 | Placing garbage bins | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 3442.3 | 0 | 0 | 3554.3 |  | 0 | 0 | 3554.3 | 1d | 0 | 0 | 0 | 3554.3 | 0% | Not Started
27 | Placing and testing generator | 2019-12-24 10:00 | 2019-12-25 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2972.5 | 0 | 0 | 3028.5 | 2019-12-11 15:00 | 4h | 3004.5 | 0 | 0 | 0 | 0 | 3004.5 | 0 | 100% | Finished
28 | Equipping material post | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[2.00 #15] | 56 | 1586.5 | 0 | 0 | 1642.5 | 2019-12-11 15:00 | 1d 3h | 1666.5 | 0 | 0 | 0 | 0 | 1666.5 | 0 | 100% | Finished
29 | Testing high pressure cleaners | 2020-01-03 14:00 | 2020-01-03 17:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-13 10:00 | 2h | 618.5 | 0 | 0 | 0 | 0 | 618.5 | 0 | 100% | Finished
30 | Final check up | 2020-01-08 14:00 | 2020-01-09 12:00 | 6h | Volunteers[2.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 |  | 0 | 0 | 650.5 | 6h | 0 | 0 | 0 | 650.5 | 0% | Not Started
31 | Finish | 2020-01-09 12:00 | 2020-01-09 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started

## TP14
| TP Status Date | 2019-12-24 17:00 |  | TP Name | 24/12/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Project | 2019-12-09 09:00 | 2020-01-09 12:00 | 27d 3h |  |  | 118411.3 |  |  | 126955.3 |  | 14d | [5 empty] | 65908.5 |  | 52.31%
1 | Start | 2019-12-09 09:00 | 2019-12-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-12-09 09:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished
2 | Mowing and cleaning up cuttings | 2019-12-09 09:00 | 2019-12-09 12:00 | 3h | Volunteers[3.00 #15] | 36 | 931.5 | 0 | 0 | 967.5 | 2019-12-09 09:00 | 3h | 967.5 | 0 | 0 | 0 | 0 | 967.5 | 0 | 100% | Finished
3 | Drilling holes | 2019-12-09 13:00 | 2019-12-14 12:00 | 5d | Volunteers[6.00 #15] | 840 | 950.5 | 0 | 0 | 1790.5 | 2019-12-09 13:00 | 3d 4h | 1550.5 | 0 | 0 | 0 | 0 | 1550.5 | 0 | 100% | Finished
4 | Placing poles | 2019-12-14 13:00 | 2019-12-17 15:00 | 2d 2h | Volunteers[10.00 #15] | 640 | 8819 | 0 | 0 | 9459 | 2019-12-13 09:00 | 1d 3h | 9219 | 0 | 0 | 0 | 0 | 9219 | 0 | 100% | Finished
5 | Attaching ropes and nets to poles | 2019-12-17 15:00 | 2019-12-28 17:00 | 10d 2h | Volunteers[10.00 #15] | 2880 | 3166.5 | 0 | 0 | 6046.5 | 2019-12-14 13:00 | 8d 4h | 5566.5 | 240 | 6h | 0 | 0 | 5566.5 | 240 | 90.91% | Started
6 | Building material post | 2019-12-31 14:00 | 2020-01-02 14:00 | 2d | Volunteers[8.00 #15] | 448 | 1802.5 | 0 | 0 | 2250.5 | 2019-12-09 13:00 | 2d 2h | 2314.5 | 0 | 0 | 0 | 0 | 2314.5 | 0 | 100% | Finished
7 | Building bridges and exits | 2019-12-16 10:00 | 2019-12-23 10:00 | 6d | Volunteers[4.00 #15] | 672 | 1970.5 | 0 | 0 | 2642.5 | 2019-12-16 13:00 | 7d 4h | 2818.5 | 48 | 3h | 0 | 0 | 2818.5 | 48 | 94.64% | Started
8 | Building plateau and staircase audience | 2020-01-01 14:00 | 2020-01-02 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
9 | Building camera plateau | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
10 | Creating starting sections and finish line | 2019-12-30 09:00 | 2019-12-30 17:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
11 | Installing bicycle storage | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
13 | Placing poles for banners and flags | 2019-12-24 10:00 | 2019-12-24 14:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-12 11:00 | 3h | 626.5 | 0 | 0 | 0 | 0 | 626.5 | 0 | 100% | Finished
14 | Hanging banners | 2020-01-06 14:00 | 2020-01-08 14:00 | 2d | Volunteers[12.00 #15] | 672 | 602.5 | 0 | 0 | 1274.5 |  | 0 | 0 | 1274.5 | 2d | 0 | 0 | 0 | 1274.5 | 0% | Not Started
15 | Hanging track signs | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
16 | Placing flagpoles for homage | 2019-12-28 10:00 | 2019-12-28 14:00 | 3h | Volunteers[4.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 | 2019-12-14 16:00 | 4h | 666.5 | 0 | 0 | 0 | 0 | 666.5 | 0 | 100% | Finished
17 | Building podium | 2019-12-23 10:00 | 2019-12-24 10:00 | 1d | Volunteers[5.00 #15] | 140 | 3302.5 | 0 | 0 | 3442.5 | 2019-12-11 15:00 | 4h | 3382.5 | 0 | 0 | 0 | 0 | 3382.5 | 0 | 100% | Finished
18 | Placing traffic signs | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
19 | Placing crush barriers and banners | 2020-01-03 14:00 | 2020-01-06 14:00 | 2d | Volunteers[12.00 #15] | 672 | 2252.5 | 0 | 0 | 2924.5 |  | 0 | 0 | 2924.5 | 2d | 0 | 0 | 0 | 2924.5 | 0% | Not Started
20 | Constructing VIP tents | 2019-12-25 10:00 | 2019-12-26 10:00 | 1d | Volunteers[2.00 #15] | 56 | 28602.5 | 0 | 0 | 28658.5 | 2019-12-12 11:00 | 5h | 28642.5 | 0 | 0 | 0 | 0 | 28642.5 | 0 | 100% | Finished
21 | Placing building fences for VIP tents | 2019-12-31 14:00 | 2020-01-01 14:00 | 1d | Volunteers[6.00 #15] | 168 | 3677.5 | 0 | 0 | 3845.5 |  | 0 | 0 | 3845.5 | 1d | 0 | 0 | 0 | 3845.5 | 0% | Not Started
22 | Installing drains for VIP tents | 2019-12-26 10:00 | 2019-12-27 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-13 09:00 | 6h | 650.5 | 0 | 0 | 0 | 0 | 650.5 | 0 | 100% | Finished
23 | Decorating VIP tents | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[8.00 #15] | 224 | 43602.5 | 0 | 0 | 43826.5 |  | 0 | 0 | 43826.5 | 1d | 0 | 0 | 0 | 43826.5 | 0% | Not Started
24 | Placing toilets for VIP tents | 2019-12-27 10:00 | 2019-12-28 10:00 | 1d | Volunteers[2.00 #15] | 56 | 1577.5 | 0 | 0 | 1633.5 | 2019-12-13 16:00 | 1d | 1633.5 | 0 | 0 | 0 | 0 | 1633.5 | 0 | 100% | Finished
25 | Placing public toilets | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2524.5 | 0 | 0 | 2580.5 | 2019-12-13 13:00 | 1d | 2580.5 | 0 | 0 | 0 | 0 | 2580.5 | 0 | 100% | Finished
26 | Placing garbage bins | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 3442.3 | 0 | 0 | 3554.3 |  | 0 | 0 | 3554.3 | 1d | 0 | 0 | 0 | 3554.3 | 0% | Not Started
27 | Placing and testing generator | 2019-12-24 10:00 | 2019-12-25 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2972.5 | 0 | 0 | 3028.5 | 2019-12-11 15:00 | 4h | 3004.5 | 0 | 0 | 0 | 0 | 3004.5 | 0 | 100% | Finished
28 | Equipping material post | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[2.00 #15] | 56 | 1586.5 | 0 | 0 | 1642.5 | 2019-12-11 15:00 | 1d 3h | 1666.5 | 0 | 0 | 0 | 0 | 1666.5 | 0 | 100% | Finished
29 | Testing high pressure cleaners | 2020-01-03 14:00 | 2020-01-03 17:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-13 10:00 | 2h | 618.5 | 0 | 0 | 0 | 0 | 618.5 | 0 | 100% | Finished
30 | Final check up | 2020-01-08 14:00 | 2020-01-09 12:00 | 6h | Volunteers[2.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 |  | 0 | 0 | 650.5 | 6h | 0 | 0 | 0 | 650.5 | 0% | Not Started
31 | Finish | 2020-01-09 12:00 | 2020-01-09 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started

## TP15
| TP Status Date | 2019-12-25 17:00 |  | TP Name | 25/12/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Project | 2019-12-09 09:00 | 2020-01-09 12:00 | 27d 3h |  |  | 118411.3 |  |  | 126955.3 |  | 15d | [5 empty] | 68662.5 |  | 54.48%
1 | Start | 2019-12-09 09:00 | 2019-12-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-12-09 09:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished
2 | Mowing and cleaning up cuttings | 2019-12-09 09:00 | 2019-12-09 12:00 | 3h | Volunteers[3.00 #15] | 36 | 931.5 | 0 | 0 | 967.5 | 2019-12-09 09:00 | 3h | 967.5 | 0 | 0 | 0 | 0 | 967.5 | 0 | 100% | Finished
3 | Drilling holes | 2019-12-09 13:00 | 2019-12-14 12:00 | 5d | Volunteers[6.00 #15] | 840 | 950.5 | 0 | 0 | 1790.5 | 2019-12-09 13:00 | 3d 4h | 1550.5 | 0 | 0 | 0 | 0 | 1550.5 | 0 | 100% | Finished
4 | Placing poles | 2019-12-14 13:00 | 2019-12-17 15:00 | 2d 2h | Volunteers[10.00 #15] | 640 | 8819 | 0 | 0 | 9459 | 2019-12-13 09:00 | 1d 3h | 9219 | 0 | 0 | 0 | 0 | 9219 | 0 | 100% | Finished
5 | Attaching ropes and nets to poles | 2019-12-17 15:00 | 2019-12-28 17:00 | 10d 2h | Volunteers[10.00 #15] | 2880 | 3166.5 | 0 | 0 | 6046.5 | 2019-12-14 13:00 | 9d 3h | 5806.5 | 0 | 0 | 0 | 0 | 5806.5 | 0 | 100% | Finished
6 | Building material post | 2019-12-31 14:00 | 2020-01-02 14:00 | 2d | Volunteers[8.00 #15] | 448 | 1802.5 | 0 | 0 | 2250.5 | 2019-12-09 13:00 | 2d 2h | 2314.5 | 0 | 0 | 0 | 0 | 2314.5 | 0 | 100% | Finished
7 | Building bridges and exits | 2019-12-16 10:00 | 2019-12-23 10:00 | 6d | Volunteers[4.00 #15] | 672 | 1970.5 | 0 | 0 | 2642.5 | 2019-12-16 13:00 | 8d | 2866.5 | 0 | 0 | 0 | 0 | 2866.5 | 0 | 100% | Finished
8 | Building plateau and staircase audience | 2020-01-01 14:00 | 2020-01-02 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1h | 618.5 | 112 | 1d | 0 | 0 | 618.5 | 112 | 12.5% | Started
9 | Building camera plateau | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
10 | Creating starting sections and finish line | 2019-12-30 09:00 | 2019-12-30 17:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-25 16:00 | 1h | 610.5 | 48 | 6h | 0 | 0 | 610.5 | 48 | 14.29% | Started
11 | Installing bicycle storage | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 |  | 0 | 0 | 658.5 | 1d | 0 | 0 | 0 | 658.5 | 0% | Not Started
13 | Placing poles for banners and flags | 2019-12-24 10:00 | 2019-12-24 14:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-12 11:00 | 3h | 626.5 | 0 | 0 | 0 | 0 | 626.5 | 0 | 100% | Finished
14 | Hanging banners | 2020-01-06 14:00 | 2020-01-08 14:00 | 2d | Volunteers[12.00 #15] | 672 | 602.5 | 0 | 0 | 1274.5 |  | 0 | 0 | 1274.5 | 2d | 0 | 0 | 0 | 1274.5 | 0% | Not Started
15 | Hanging track signs | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1h | 618.5 | 128 | 1d 1h | 0 | 0 | 618.5 | 128 | 11.11% | Started
16 | Placing flagpoles for homage | 2019-12-28 10:00 | 2019-12-28 14:00 | 3h | Volunteers[4.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 | 2019-12-14 16:00 | 4h | 666.5 | 0 | 0 | 0 | 0 | 666.5 | 0 | 100% | Finished
17 | Building podium | 2019-12-23 10:00 | 2019-12-24 10:00 | 1d | Volunteers[5.00 #15] | 140 | 3302.5 | 0 | 0 | 3442.5 | 2019-12-11 15:00 | 4h | 3382.5 | 0 | 0 | 0 | 0 | 3382.5 | 0 | 100% | Finished
18 | Placing traffic signs | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1h | 618.5 | 128 | 1d 1h | 0 | 0 | 618.5 | 128 | 11.11% | Started
19 | Placing crush barriers and banners | 2020-01-03 14:00 | 2020-01-06 14:00 | 2d | Volunteers[12.00 #15] | 672 | 2252.5 | 0 | 0 | 2924.5 |  | 0 | 0 | 2924.5 | 2d | 0 | 0 | 0 | 2924.5 | 0% | Not Started
20 | Constructing VIP tents | 2019-12-25 10:00 | 2019-12-26 10:00 | 1d | Volunteers[2.00 #15] | 56 | 28602.5 | 0 | 0 | 28658.5 | 2019-12-12 11:00 | 5h | 28642.5 | 0 | 0 | 0 | 0 | 28642.5 | 0 | 100% | Finished
21 | Placing building fences for VIP tents | 2019-12-31 14:00 | 2020-01-01 14:00 | 1d | Volunteers[6.00 #15] | 168 | 3677.5 | 0 | 0 | 3845.5 |  | 0 | 0 | 3845.5 | 1d | 0 | 0 | 0 | 3845.5 | 0% | Not Started
22 | Installing drains for VIP tents | 2019-12-26 10:00 | 2019-12-27 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-13 09:00 | 6h | 650.5 | 0 | 0 | 0 | 0 | 650.5 | 0 | 100% | Finished
23 | Decorating VIP tents | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[8.00 #15] | 224 | 43602.5 | 0 | 0 | 43826.5 |  | 0 | 0 | 43826.5 | 1d | 0 | 0 | 0 | 43826.5 | 0% | Not Started
24 | Placing toilets for VIP tents | 2019-12-27 10:00 | 2019-12-28 10:00 | 1d | Volunteers[2.00 #15] | 56 | 1577.5 | 0 | 0 | 1633.5 | 2019-12-13 16:00 | 1d | 1633.5 | 0 | 0 | 0 | 0 | 1633.5 | 0 | 100% | Finished
25 | Placing public toilets | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2524.5 | 0 | 0 | 2580.5 | 2019-12-13 13:00 | 1d | 2580.5 | 0 | 0 | 0 | 0 | 2580.5 | 0 | 100% | Finished
26 | Placing garbage bins | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 3442.3 | 0 | 0 | 3554.3 |  | 0 | 0 | 3554.3 | 1d | 0 | 0 | 0 | 3554.3 | 0% | Not Started
27 | Placing and testing generator | 2019-12-24 10:00 | 2019-12-25 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2972.5 | 0 | 0 | 3028.5 | 2019-12-11 15:00 | 4h | 3004.5 | 0 | 0 | 0 | 0 | 3004.5 | 0 | 100% | Finished
28 | Equipping material post | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[2.00 #15] | 56 | 1586.5 | 0 | 0 | 1642.5 | 2019-12-11 15:00 | 1d 3h | 1666.5 | 0 | 0 | 0 | 0 | 1666.5 | 0 | 100% | Finished
29 | Testing high pressure cleaners | 2020-01-03 14:00 | 2020-01-03 17:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-13 10:00 | 2h | 618.5 | 0 | 0 | 0 | 0 | 618.5 | 0 | 100% | Finished
30 | Final check up | 2020-01-08 14:00 | 2020-01-09 12:00 | 6h | Volunteers[2.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 |  | 0 | 0 | 650.5 | 6h | 0 | 0 | 0 | 650.5 | 0% | Not Started
31 | Finish | 2020-01-09 12:00 | 2020-01-09 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started

## TP16
| TP Status Date | 2019-12-26 17:00 |  | TP Name | 26/12/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Project | 2019-12-09 09:00 | 2020-01-09 12:00 | 27d 3h |  |  | 118411.3 |  |  | 126955.3 |  | 16d | [5 empty] | 69657 |  | 55.21%
1 | Start | 2019-12-09 09:00 | 2019-12-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-12-09 09:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished
2 | Mowing and cleaning up cuttings | 2019-12-09 09:00 | 2019-12-09 12:00 | 3h | Volunteers[3.00 #15] | 36 | 931.5 | 0 | 0 | 967.5 | 2019-12-09 09:00 | 3h | 967.5 | 0 | 0 | 0 | 0 | 967.5 | 0 | 100% | Finished
3 | Drilling holes | 2019-12-09 13:00 | 2019-12-14 12:00 | 5d | Volunteers[6.00 #15] | 840 | 950.5 | 0 | 0 | 1790.5 | 2019-12-09 13:00 | 3d 4h | 1550.5 | 0 | 0 | 0 | 0 | 1550.5 | 0 | 100% | Finished
4 | Placing poles | 2019-12-14 13:00 | 2019-12-17 15:00 | 2d 2h | Volunteers[10.00 #15] | 640 | 8819 | 0 | 0 | 9459 | 2019-12-13 09:00 | 1d 3h | 9219 | 0 | 0 | 0 | 0 | 9219 | 0 | 100% | Finished
5 | Attaching ropes and nets to poles | 2019-12-17 15:00 | 2019-12-28 17:00 | 10d 2h | Volunteers[10.00 #15] | 2880 | 3166.5 | 0 | 0 | 6046.5 | 2019-12-14 13:00 | 9d 3h | 5806.5 | 0 | 0 | 0 | 0 | 5806.5 | 0 | 100% | Finished
6 | Building material post | 2019-12-31 14:00 | 2020-01-02 14:00 | 2d | Volunteers[8.00 #15] | 448 | 1802.5 | 0 | 0 | 2250.5 | 2019-12-09 13:00 | 2d 2h | 2314.5 | 0 | 0 | 0 | 0 | 2314.5 | 0 | 100% | Finished
7 | Building bridges and exits | 2019-12-16 10:00 | 2019-12-23 10:00 | 6d | Volunteers[4.00 #15] | 672 | 1970.5 | 0 | 0 | 2642.5 | 2019-12-16 13:00 | 8d | 2866.5 | 0 | 0 | 0 | 0 | 2866.5 | 0 | 100% | Finished
8 | Building plateau and staircase audience | 2020-01-01 14:00 | 2020-01-02 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1d 1h | 730.5 | 0 | 0 | 0 | 0 | 730.5 | 0 | 100% | Finished
9 | Building camera plateau | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
10 | Creating starting sections and finish line | 2019-12-30 09:00 | 2019-12-30 17:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-25 16:00 | 1d | 658.5 | 0 | 0 | 0 | 0 | 658.5 | 0 | 100% | Finished
11 | Installing bicycle storage | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-26 16:00 | 1h | 610.5 | 64 | 1d 1h | 0 | 0 | 610.5 | 64 | 11.11% | Started
13 | Placing poles for banners and flags | 2019-12-24 10:00 | 2019-12-24 14:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-12 11:00 | 3h | 626.5 | 0 | 0 | 0 | 0 | 626.5 | 0 | 100% | Finished
14 | Hanging banners | 2020-01-06 14:00 | 2020-01-08 14:00 | 2d | Volunteers[12.00 #15] | 672 | 602.5 | 0 | 0 | 1274.5 |  | 0 | 0 | 1274.5 | 2d | 0 | 0 | 0 | 1274.5 | 0% | Not Started
15 | Hanging track signs | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1d 1h | 730.5 | 16 | 1h | 0 | 0 | 730.5 | 16 | 88.89% | Started
16 | Placing flagpoles for homage | 2019-12-28 10:00 | 2019-12-28 14:00 | 3h | Volunteers[4.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 | 2019-12-14 16:00 | 4h | 666.5 | 0 | 0 | 0 | 0 | 666.5 | 0 | 100% | Finished
17 | Building podium | 2019-12-23 10:00 | 2019-12-24 10:00 | 1d | Volunteers[5.00 #15] | 140 | 3302.5 | 0 | 0 | 3442.5 | 2019-12-11 15:00 | 4h | 3382.5 | 0 | 0 | 0 | 0 | 3382.5 | 0 | 100% | Finished
18 | Placing traffic signs | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1d 1h | 730.5 | 16 | 1h | 0 | 0 | 730.5 | 16 | 88.89% | Started
19 | Placing crush barriers and banners | 2020-01-03 14:00 | 2020-01-06 14:00 | 2d | Volunteers[12.00 #15] | 672 | 2252.5 | 0 | 0 | 2924.5 |  | 0 | 0 | 2924.5 | 2d | 0 | 0 | 0 | 2924.5 | 0% | Not Started
20 | Constructing VIP tents | 2019-12-25 10:00 | 2019-12-26 10:00 | 1d | Volunteers[2.00 #15] | 56 | 28602.5 | 0 | 0 | 28658.5 | 2019-12-12 11:00 | 5h | 28642.5 | 0 | 0 | 0 | 0 | 28642.5 | 0 | 100% | Finished
21 | Placing building fences for VIP tents | 2019-12-31 14:00 | 2020-01-01 14:00 | 1d | Volunteers[6.00 #15] | 168 | 3677.5 | 0 | 0 | 3845.5 |  | 0 | 0 | 3845.5 | 1d | 0 | 0 | 0 | 3845.5 | 0% | Not Started
22 | Installing drains for VIP tents | 2019-12-26 10:00 | 2019-12-27 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-13 09:00 | 6h | 650.5 | 0 | 0 | 0 | 0 | 650.5 | 0 | 100% | Finished
23 | Decorating VIP tents | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[8.00 #15] | 224 | 43602.5 | 0 | 0 | 43826.5 |  | 0 | 0 | 43826.5 | 1d | 0 | 0 | 0 | 43826.5 | 0% | Not Started
24 | Placing toilets for VIP tents | 2019-12-27 10:00 | 2019-12-28 10:00 | 1d | Volunteers[2.00 #15] | 56 | 1577.5 | 0 | 0 | 1633.5 | 2019-12-13 16:00 | 1d | 1633.5 | 0 | 0 | 0 | 0 | 1633.5 | 0 | 100% | Finished
25 | Placing public toilets | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2524.5 | 0 | 0 | 2580.5 | 2019-12-13 13:00 | 1d | 2580.5 | 0 | 0 | 0 | 0 | 2580.5 | 0 | 100% | Finished
26 | Placing garbage bins | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 3442.3 | 0 | 0 | 3554.3 |  | 0 | 0 | 3554.3 | 1d | 0 | 0 | 0 | 3554.3 | 0% | Not Started
27 | Placing and testing generator | 2019-12-24 10:00 | 2019-12-25 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2972.5 | 0 | 0 | 3028.5 | 2019-12-11 15:00 | 4h | 3004.5 | 0 | 0 | 0 | 0 | 3004.5 | 0 | 100% | Finished
28 | Equipping material post | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[2.00 #15] | 56 | 1586.5 | 0 | 0 | 1642.5 | 2019-12-11 15:00 | 1d 3h | 1666.5 | 0 | 0 | 0 | 0 | 1666.5 | 0 | 100% | Finished
29 | Testing high pressure cleaners | 2020-01-03 14:00 | 2020-01-03 17:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-13 10:00 | 2h | 618.5 | 0 | 0 | 0 | 0 | 618.5 | 0 | 100% | Finished
30 | Final check up | 2020-01-08 14:00 | 2020-01-09 12:00 | 6h | Volunteers[2.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 |  | 0 | 0 | 650.5 | 6h | 0 | 0 | 0 | 650.5 | 0% | Not Started
31 | Finish | 2020-01-09 12:00 | 2020-01-09 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started

## TP17
| TP Status Date | 2019-12-27 17:00 |  | TP Name | 27/12/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Project | 2019-12-09 09:00 | 2020-01-09 12:00 | 27d 3h |  |  | 118411.3 |  |  | 126955.3 |  | 17d | [5 empty] | 72285.5 |  | 57.43%
1 | Start | 2019-12-09 09:00 | 2019-12-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-12-09 09:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished
2 | Mowing and cleaning up cuttings | 2019-12-09 09:00 | 2019-12-09 12:00 | 3h | Volunteers[3.00 #15] | 36 | 931.5 | 0 | 0 | 967.5 | 2019-12-09 09:00 | 3h | 967.5 | 0 | 0 | 0 | 0 | 967.5 | 0 | 100% | Finished
3 | Drilling holes | 2019-12-09 13:00 | 2019-12-14 12:00 | 5d | Volunteers[6.00 #15] | 840 | 950.5 | 0 | 0 | 1790.5 | 2019-12-09 13:00 | 3d 4h | 1550.5 | 0 | 0 | 0 | 0 | 1550.5 | 0 | 100% | Finished
4 | Placing poles | 2019-12-14 13:00 | 2019-12-17 15:00 | 2d 2h | Volunteers[10.00 #15] | 640 | 8819 | 0 | 0 | 9459 | 2019-12-13 09:00 | 1d 3h | 9219 | 0 | 0 | 0 | 0 | 9219 | 0 | 100% | Finished
5 | Attaching ropes and nets to poles | 2019-12-17 15:00 | 2019-12-28 17:00 | 10d 2h | Volunteers[10.00 #15] | 2880 | 3166.5 | 0 | 0 | 6046.5 | 2019-12-14 13:00 | 9d 3h | 5806.5 | 0 | 0 | 0 | 0 | 5806.5 | 0 | 100% | Finished
6 | Building material post | 2019-12-31 14:00 | 2020-01-02 14:00 | 2d | Volunteers[8.00 #15] | 448 | 1802.5 | 0 | 0 | 2250.5 | 2019-12-09 13:00 | 2d 2h | 2314.5 | 0 | 0 | 0 | 0 | 2314.5 | 0 | 100% | Finished
7 | Building bridges and exits | 2019-12-16 10:00 | 2019-12-23 10:00 | 6d | Volunteers[4.00 #15] | 672 | 1970.5 | 0 | 0 | 2642.5 | 2019-12-16 13:00 | 8d | 2866.5 | 0 | 0 | 0 | 0 | 2866.5 | 0 | 100% | Finished
8 | Building plateau and staircase audience | 2020-01-01 14:00 | 2020-01-02 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1d 1h | 730.5 | 0 | 0 | 0 | 0 | 730.5 | 0 | 100% | Finished
9 | Building camera plateau | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 |  | 0 | 0 | 714.5 | 1d | 0 | 0 | 0 | 714.5 | 0% | Not Started
10 | Creating starting sections and finish line | 2019-12-30 09:00 | 2019-12-30 17:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-25 16:00 | 1d | 658.5 | 0 | 0 | 0 | 0 | 658.5 | 0 | 100% | Finished
11 | Installing bicycle storage | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-26 16:00 | 1d 1h | 666.5 | 8 | 1h | 0 | 0 | 666.5 | 8 | 88.89% | Started
13 | Placing poles for banners and flags | 2019-12-24 10:00 | 2019-12-24 14:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-12 11:00 | 3h | 626.5 | 0 | 0 | 0 | 0 | 626.5 | 0 | 100% | Finished
14 | Hanging banners | 2020-01-06 14:00 | 2020-01-08 14:00 | 2d | Volunteers[12.00 #15] | 672 | 602.5 | 0 | 0 | 1274.5 |  | 0 | 0 | 1274.5 | 2d | 0 | 0 | 0 | 1274.5 | 0% | Not Started
15 | Hanging track signs | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1d 2h | 746.5 | 0 | 0 | 0 | 0 | 746.5 | 0 | 100% | Finished
16 | Placing flagpoles for homage | 2019-12-28 10:00 | 2019-12-28 14:00 | 3h | Volunteers[4.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 | 2019-12-14 16:00 | 4h | 666.5 | 0 | 0 | 0 | 0 | 666.5 | 0 | 100% | Finished
17 | Building podium | 2019-12-23 10:00 | 2019-12-24 10:00 | 1d | Volunteers[5.00 #15] | 140 | 3302.5 | 0 | 0 | 3442.5 | 2019-12-11 15:00 | 4h | 3382.5 | 0 | 0 | 0 | 0 | 3382.5 | 0 | 100% | Finished
18 | Placing traffic signs | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1d 2h | 746.5 | 0 | 0 | 0 | 0 | 746.5 | 0 | 100% | Finished
19 | Placing crush barriers and banners | 2020-01-03 14:00 | 2020-01-06 14:00 | 2d | Volunteers[12.00 #15] | 672 | 2252.5 | 0 | 0 | 2924.5 | 2019-12-27 10:00 | 6h | 2540.5 | 96 | 2h | 0 | 0 | 2540.5 | 96 | 75% | Started
20 | Constructing VIP tents | 2019-12-25 10:00 | 2019-12-26 10:00 | 1d | Volunteers[2.00 #15] | 56 | 28602.5 | 0 | 0 | 28658.5 | 2019-12-12 11:00 | 5h | 28642.5 | 0 | 0 | 0 | 0 | 28642.5 | 0 | 100% | Finished
21 | Placing building fences for VIP tents | 2019-12-31 14:00 | 2020-01-01 14:00 | 1d | Volunteers[6.00 #15] | 168 | 3677.5 | 0 | 0 | 3845.5 |  | 0 | 0 | 3845.5 | 1d | 0 | 0 | 0 | 3845.5 | 0% | Not Started
22 | Installing drains for VIP tents | 2019-12-26 10:00 | 2019-12-27 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-13 09:00 | 6h | 650.5 | 0 | 0 | 0 | 0 | 650.5 | 0 | 100% | Finished
23 | Decorating VIP tents | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[8.00 #15] | 224 | 43602.5 | 0 | 0 | 43826.5 |  | 0 | 0 | 43826.5 | 1d | 0 | 0 | 0 | 43826.5 | 0% | Not Started
24 | Placing toilets for VIP tents | 2019-12-27 10:00 | 2019-12-28 10:00 | 1d | Volunteers[2.00 #15] | 56 | 1577.5 | 0 | 0 | 1633.5 | 2019-12-13 16:00 | 1d | 1633.5 | 0 | 0 | 0 | 0 | 1633.5 | 0 | 100% | Finished
25 | Placing public toilets | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2524.5 | 0 | 0 | 2580.5 | 2019-12-13 13:00 | 1d | 2580.5 | 0 | 0 | 0 | 0 | 2580.5 | 0 | 100% | Finished
26 | Placing garbage bins | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 3442.3 | 0 | 0 | 3554.3 |  | 0 | 0 | 3554.3 | 1d | 0 | 0 | 0 | 3554.3 | 0% | Not Started
27 | Placing and testing generator | 2019-12-24 10:00 | 2019-12-25 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2972.5 | 0 | 0 | 3028.5 | 2019-12-11 15:00 | 4h | 3004.5 | 0 | 0 | 0 | 0 | 3004.5 | 0 | 100% | Finished
28 | Equipping material post | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[2.00 #15] | 56 | 1586.5 | 0 | 0 | 1642.5 | 2019-12-11 15:00 | 1d 3h | 1666.5 | 0 | 0 | 0 | 0 | 1666.5 | 0 | 100% | Finished
29 | Testing high pressure cleaners | 2020-01-03 14:00 | 2020-01-03 17:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-13 10:00 | 2h | 618.5 | 0 | 0 | 0 | 0 | 618.5 | 0 | 100% | Finished
30 | Final check up | 2020-01-08 14:00 | 2020-01-09 12:00 | 6h | Volunteers[2.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 |  | 0 | 0 | 650.5 | 6h | 0 | 0 | 0 | 650.5 | 0% | Not Started
31 | Finish | 2020-01-09 12:00 | 2020-01-09 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started

## TP18
| TP Status Date | 2019-12-28 17:00 |  | TP Name | 28/12/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Project | 2019-12-09 09:00 | 2020-01-09 12:00 | 27d 3h |  |  | 118411.3 |  |  | 126955.3 |  | 18d | [5 empty] | 80391.8 |  | 63.9%
1 | Start | 2019-12-09 09:00 | 2019-12-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-12-09 09:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished
2 | Mowing and cleaning up cuttings | 2019-12-09 09:00 | 2019-12-09 12:00 | 3h | Volunteers[3.00 #15] | 36 | 931.5 | 0 | 0 | 967.5 | 2019-12-09 09:00 | 3h | 967.5 | 0 | 0 | 0 | 0 | 967.5 | 0 | 100% | Finished
3 | Drilling holes | 2019-12-09 13:00 | 2019-12-14 12:00 | 5d | Volunteers[6.00 #15] | 840 | 950.5 | 0 | 0 | 1790.5 | 2019-12-09 13:00 | 3d 4h | 1550.5 | 0 | 0 | 0 | 0 | 1550.5 | 0 | 100% | Finished
4 | Placing poles | 2019-12-14 13:00 | 2019-12-17 15:00 | 2d 2h | Volunteers[10.00 #15] | 640 | 8819 | 0 | 0 | 9459 | 2019-12-13 09:00 | 1d 3h | 9219 | 0 | 0 | 0 | 0 | 9219 | 0 | 100% | Finished
5 | Attaching ropes and nets to poles | 2019-12-17 15:00 | 2019-12-28 17:00 | 10d 2h | Volunteers[10.00 #15] | 2880 | 3166.5 | 0 | 0 | 6046.5 | 2019-12-14 13:00 | 9d 3h | 5806.5 | 0 | 0 | 0 | 0 | 5806.5 | 0 | 100% | Finished
6 | Building material post | 2019-12-31 14:00 | 2020-01-02 14:00 | 2d | Volunteers[8.00 #15] | 448 | 1802.5 | 0 | 0 | 2250.5 | 2019-12-09 13:00 | 2d 2h | 2314.5 | 0 | 0 | 0 | 0 | 2314.5 | 0 | 100% | Finished
7 | Building bridges and exits | 2019-12-16 10:00 | 2019-12-23 10:00 | 6d | Volunteers[4.00 #15] | 672 | 1970.5 | 0 | 0 | 2642.5 | 2019-12-16 13:00 | 8d | 2866.5 | 0 | 0 | 0 | 0 | 2866.5 | 0 | 100% | Finished
8 | Building plateau and staircase audience | 2020-01-01 14:00 | 2020-01-02 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1d 1h | 730.5 | 0 | 0 | 0 | 0 | 730.5 | 0 | 100% | Finished
9 | Building camera plateau | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-28 11:00 | 5h | 682.5 | 32 | 2h | 0 | 0 | 682.5 | 32 | 71.43% | Started
10 | Creating starting sections and finish line | 2019-12-30 09:00 | 2019-12-30 17:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-25 16:00 | 1d | 658.5 | 0 | 0 | 0 | 0 | 658.5 | 0 | 100% | Finished
11 | Installing bicycle storage | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-26 16:00 | 1d 2h | 674.5 | 0 | 0 | 0 | 0 | 674.5 | 0 | 100% | Finished
13 | Placing poles for banners and flags | 2019-12-24 10:00 | 2019-12-24 14:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-12 11:00 | 3h | 626.5 | 0 | 0 | 0 | 0 | 626.5 | 0 | 100% | Finished
14 | Hanging banners | 2020-01-06 14:00 | 2020-01-08 14:00 | 2d | Volunteers[12.00 #15] | 672 | 602.5 | 0 | 0 | 1274.5 |  | 0 | 0 | 1274.5 | 2d | 0 | 0 | 0 | 1274.5 | 0% | Not Started
15 | Hanging track signs | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1d 2h | 746.5 | 0 | 0 | 0 | 0 | 746.5 | 0 | 100% | Finished
16 | Placing flagpoles for homage | 2019-12-28 10:00 | 2019-12-28 14:00 | 3h | Volunteers[4.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 | 2019-12-14 16:00 | 4h | 666.5 | 0 | 0 | 0 | 0 | 666.5 | 0 | 100% | Finished
17 | Building podium | 2019-12-23 10:00 | 2019-12-24 10:00 | 1d | Volunteers[5.00 #15] | 140 | 3302.5 | 0 | 0 | 3442.5 | 2019-12-11 15:00 | 4h | 3382.5 | 0 | 0 | 0 | 0 | 3382.5 | 0 | 100% | Finished
18 | Placing traffic signs | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1d 2h | 746.5 | 0 | 0 | 0 | 0 | 746.5 | 0 | 100% | Finished
19 | Placing crush barriers and banners | 2020-01-03 14:00 | 2020-01-06 14:00 | 2d | Volunteers[12.00 #15] | 672 | 2252.5 | 0 | 0 | 2924.5 | 2019-12-27 10:00 | 1d 1h | 2636.5 | 0 | 0 | 0 | 0 | 2636.5 | 0 | 100% | Finished
20 | Constructing VIP tents | 2019-12-25 10:00 | 2019-12-26 10:00 | 1d | Volunteers[2.00 #15] | 56 | 28602.5 | 0 | 0 | 28658.5 | 2019-12-12 11:00 | 5h | 28642.5 | 0 | 0 | 0 | 0 | 28642.5 | 0 | 100% | Finished
21 | Placing building fences for VIP tents | 2019-12-31 14:00 | 2020-01-01 14:00 | 1d | Volunteers[6.00 #15] | 168 | 3677.5 | 0 | 0 | 3845.5 | 2019-12-28 11:00 | 5h | 3797.5 | 24 | 1h | 0 | 0 | 3797.5 | 24 | 83.33% | Started
22 | Installing drains for VIP tents | 2019-12-26 10:00 | 2019-12-27 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-13 09:00 | 6h | 650.5 | 0 | 0 | 0 | 0 | 650.5 | 0 | 100% | Finished
23 | Decorating VIP tents | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[8.00 #15] | 224 | 43602.5 | 0 | 0 | 43826.5 |  | 0 | 0 | 43826.5 | 1d | 0 | 0 | 0 | 43826.5 | 0% | Not Started
24 | Placing toilets for VIP tents | 2019-12-27 10:00 | 2019-12-28 10:00 | 1d | Volunteers[2.00 #15] | 56 | 1577.5 | 0 | 0 | 1633.5 | 2019-12-13 16:00 | 1d | 1633.5 | 0 | 0 | 0 | 0 | 1633.5 | 0 | 100% | Finished
25 | Placing public toilets | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2524.5 | 0 | 0 | 2580.5 | 2019-12-13 13:00 | 1d | 2580.5 | 0 | 0 | 0 | 0 | 2580.5 | 0 | 100% | Finished
26 | Placing garbage bins | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 3442.3 | 0 | 0 | 3554.3 | 2019-12-28 11:00 | 5h | 3522.3 | 16 | 1h | 0 | 0 | 3522.3 | 16 | 83.33% | Started
27 | Placing and testing generator | 2019-12-24 10:00 | 2019-12-25 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2972.5 | 0 | 0 | 3028.5 | 2019-12-11 15:00 | 4h | 3004.5 | 0 | 0 | 0 | 0 | 3004.5 | 0 | 100% | Finished
28 | Equipping material post | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[2.00 #15] | 56 | 1586.5 | 0 | 0 | 1642.5 | 2019-12-11 15:00 | 1d 3h | 1666.5 | 0 | 0 | 0 | 0 | 1666.5 | 0 | 100% | Finished
29 | Testing high pressure cleaners | 2020-01-03 14:00 | 2020-01-03 17:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-13 10:00 | 2h | 618.5 | 0 | 0 | 0 | 0 | 618.5 | 0 | 100% | Finished
30 | Final check up | 2020-01-08 14:00 | 2020-01-09 12:00 | 6h | Volunteers[2.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 |  | 0 | 0 | 650.5 | 6h | 0 | 0 | 0 | 650.5 | 0% | Not Started
31 | Finish | 2020-01-09 12:00 | 2020-01-09 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started

## TP19
| TP Status Date | 2019-12-30 17:00 |  | TP Name | 30/12/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Project | 2019-12-09 09:00 | 2020-01-09 12:00 | 27d 3h |  |  | 118411.3 |  |  | 126955.3 |  | 19d | [5 empty] | 124258.3 |  | 98.44%
1 | Start | 2019-12-09 09:00 | 2019-12-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-12-09 09:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished
2 | Mowing and cleaning up cuttings | 2019-12-09 09:00 | 2019-12-09 12:00 | 3h | Volunteers[3.00 #15] | 36 | 931.5 | 0 | 0 | 967.5 | 2019-12-09 09:00 | 3h | 967.5 | 0 | 0 | 0 | 0 | 967.5 | 0 | 100% | Finished
3 | Drilling holes | 2019-12-09 13:00 | 2019-12-14 12:00 | 5d | Volunteers[6.00 #15] | 840 | 950.5 | 0 | 0 | 1790.5 | 2019-12-09 13:00 | 3d 4h | 1550.5 | 0 | 0 | 0 | 0 | 1550.5 | 0 | 100% | Finished
4 | Placing poles | 2019-12-14 13:00 | 2019-12-17 15:00 | 2d 2h | Volunteers[10.00 #15] | 640 | 8819 | 0 | 0 | 9459 | 2019-12-13 09:00 | 1d 3h | 9219 | 0 | 0 | 0 | 0 | 9219 | 0 | 100% | Finished
5 | Attaching ropes and nets to poles | 2019-12-17 15:00 | 2019-12-28 17:00 | 10d 2h | Volunteers[10.00 #15] | 2880 | 3166.5 | 0 | 0 | 6046.5 | 2019-12-14 13:00 | 9d 3h | 5806.5 | 0 | 0 | 0 | 0 | 5806.5 | 0 | 100% | Finished
6 | Building material post | 2019-12-31 14:00 | 2020-01-02 14:00 | 2d | Volunteers[8.00 #15] | 448 | 1802.5 | 0 | 0 | 2250.5 | 2019-12-09 13:00 | 2d 2h | 2314.5 | 0 | 0 | 0 | 0 | 2314.5 | 0 | 100% | Finished
7 | Building bridges and exits | 2019-12-16 10:00 | 2019-12-23 10:00 | 6d | Volunteers[4.00 #15] | 672 | 1970.5 | 0 | 0 | 2642.5 | 2019-12-16 13:00 | 8d | 2866.5 | 0 | 0 | 0 | 0 | 2866.5 | 0 | 100% | Finished
8 | Building plateau and staircase audience | 2020-01-01 14:00 | 2020-01-02 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1d 1h | 730.5 | 0 | 0 | 0 | 0 | 730.5 | 0 | 100% | Finished
9 | Building camera plateau | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-28 11:00 | 1d | 714.5 | 0 | 0 | 0 | 0 | 714.5 | 0 | 100% | Finished
10 | Creating starting sections and finish line | 2019-12-30 09:00 | 2019-12-30 17:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-25 16:00 | 1d | 658.5 | 0 | 0 | 0 | 0 | 658.5 | 0 | 100% | Finished
11 | Installing bicycle storage | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-26 16:00 | 1d 2h | 674.5 | 0 | 0 | 0 | 0 | 674.5 | 0 | 100% | Finished
13 | Placing poles for banners and flags | 2019-12-24 10:00 | 2019-12-24 14:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-12 11:00 | 3h | 626.5 | 0 | 0 | 0 | 0 | 626.5 | 0 | 100% | Finished
14 | Hanging banners | 2020-01-06 14:00 | 2020-01-08 14:00 | 2d | Volunteers[12.00 #15] | 672 | 602.5 | 0 | 0 | 1274.5 |  | 0 | 0 | 1274.5 | 2d | 0 | 0 | 0 | 1274.5 | 0% | Not Started
15 | Hanging track signs | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1d 2h | 746.5 | 0 | 0 | 0 | 0 | 746.5 | 0 | 100% | Finished
16 | Placing flagpoles for homage | 2019-12-28 10:00 | 2019-12-28 14:00 | 3h | Volunteers[4.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 | 2019-12-14 16:00 | 4h | 666.5 | 0 | 0 | 0 | 0 | 666.5 | 0 | 100% | Finished
17 | Building podium | 2019-12-23 10:00 | 2019-12-24 10:00 | 1d | Volunteers[5.00 #15] | 140 | 3302.5 | 0 | 0 | 3442.5 | 2019-12-11 15:00 | 4h | 3382.5 | 0 | 0 | 0 | 0 | 3382.5 | 0 | 100% | Finished
18 | Placing traffic signs | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1d 2h | 746.5 | 0 | 0 | 0 | 0 | 746.5 | 0 | 100% | Finished
19 | Placing crush barriers and banners | 2020-01-03 14:00 | 2020-01-06 14:00 | 2d | Volunteers[12.00 #15] | 672 | 2252.5 | 0 | 0 | 2924.5 | 2019-12-27 10:00 | 1d 1h | 2636.5 | 0 | 0 | 0 | 0 | 2636.5 | 0 | 100% | Finished
20 | Constructing VIP tents | 2019-12-25 10:00 | 2019-12-26 10:00 | 1d | Volunteers[2.00 #15] | 56 | 28602.5 | 0 | 0 | 28658.5 | 2019-12-12 11:00 | 5h | 28642.5 | 0 | 0 | 0 | 0 | 28642.5 | 0 | 100% | Finished
21 | Placing building fences for VIP tents | 2019-12-31 14:00 | 2020-01-01 14:00 | 1d | Volunteers[6.00 #15] | 168 | 3677.5 | 0 | 0 | 3845.5 | 2019-12-28 11:00 | 6h | 3821.5 | 0 | 0 | 0 | 0 | 3821.5 | 0 | 100% | Finished
22 | Installing drains for VIP tents | 2019-12-26 10:00 | 2019-12-27 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-13 09:00 | 6h | 650.5 | 0 | 0 | 0 | 0 | 650.5 | 0 | 100% | Finished
23 | Decorating VIP tents | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[8.00 #15] | 224 | 43602.5 | 0 | 0 | 43826.5 | 2019-12-30 10:00 | 6h | 43794.5 | 64 | 2h | 0 | 0 | 43794.5 | 64 | 75% | Started
24 | Placing toilets for VIP tents | 2019-12-27 10:00 | 2019-12-28 10:00 | 1d | Volunteers[2.00 #15] | 56 | 1577.5 | 0 | 0 | 1633.5 | 2019-12-13 16:00 | 1d | 1633.5 | 0 | 0 | 0 | 0 | 1633.5 | 0 | 100% | Finished
25 | Placing public toilets | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2524.5 | 0 | 0 | 2580.5 | 2019-12-13 13:00 | 1d | 2580.5 | 0 | 0 | 0 | 0 | 2580.5 | 0 | 100% | Finished
26 | Placing garbage bins | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 3442.3 | 0 | 0 | 3554.3 | 2019-12-28 11:00 | 6h | 3538.3 | 0 | 0 | 0 | 0 | 3538.3 | 0 | 100% | Finished
27 | Placing and testing generator | 2019-12-24 10:00 | 2019-12-25 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2972.5 | 0 | 0 | 3028.5 | 2019-12-11 15:00 | 4h | 3004.5 | 0 | 0 | 0 | 0 | 3004.5 | 0 | 100% | Finished
28 | Equipping material post | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[2.00 #15] | 56 | 1586.5 | 0 | 0 | 1642.5 | 2019-12-11 15:00 | 1d 3h | 1666.5 | 0 | 0 | 0 | 0 | 1666.5 | 0 | 100% | Finished
29 | Testing high pressure cleaners | 2020-01-03 14:00 | 2020-01-03 17:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-13 10:00 | 2h | 618.5 | 0 | 0 | 0 | 0 | 618.5 | 0 | 100% | Finished
30 | Final check up | 2020-01-08 14:00 | 2020-01-09 12:00 | 6h | Volunteers[2.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 |  | 0 | 0 | 650.5 | 6h | 0 | 0 | 0 | 650.5 | 0% | Not Started
31 | Finish | 2020-01-09 12:00 | 2020-01-09 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started

## TP20
| TP Status Date | 2019-12-31 17:00 |  | TP Name | 31/12/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Project | 2019-12-09 09:00 | 2020-01-09 12:00 | 27d 3h |  |  | 118411.3 |  |  | 126955.3 |  | 20d | [5 empty] | 125164.8 |  | 99.12%
1 | Start | 2019-12-09 09:00 | 2019-12-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-12-09 09:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished
2 | Mowing and cleaning up cuttings | 2019-12-09 09:00 | 2019-12-09 12:00 | 3h | Volunteers[3.00 #15] | 36 | 931.5 | 0 | 0 | 967.5 | 2019-12-09 09:00 | 3h | 967.5 | 0 | 0 | 0 | 0 | 967.5 | 0 | 100% | Finished
3 | Drilling holes | 2019-12-09 13:00 | 2019-12-14 12:00 | 5d | Volunteers[6.00 #15] | 840 | 950.5 | 0 | 0 | 1790.5 | 2019-12-09 13:00 | 3d 4h | 1550.5 | 0 | 0 | 0 | 0 | 1550.5 | 0 | 100% | Finished
4 | Placing poles | 2019-12-14 13:00 | 2019-12-17 15:00 | 2d 2h | Volunteers[10.00 #15] | 640 | 8819 | 0 | 0 | 9459 | 2019-12-13 09:00 | 1d 3h | 9219 | 0 | 0 | 0 | 0 | 9219 | 0 | 100% | Finished
5 | Attaching ropes and nets to poles | 2019-12-17 15:00 | 2019-12-28 17:00 | 10d 2h | Volunteers[10.00 #15] | 2880 | 3166.5 | 0 | 0 | 6046.5 | 2019-12-14 13:00 | 9d 3h | 5806.5 | 0 | 0 | 0 | 0 | 5806.5 | 0 | 100% | Finished
6 | Building material post | 2019-12-31 14:00 | 2020-01-02 14:00 | 2d | Volunteers[8.00 #15] | 448 | 1802.5 | 0 | 0 | 2250.5 | 2019-12-09 13:00 | 2d 2h | 2314.5 | 0 | 0 | 0 | 0 | 2314.5 | 0 | 100% | Finished
7 | Building bridges and exits | 2019-12-16 10:00 | 2019-12-23 10:00 | 6d | Volunteers[4.00 #15] | 672 | 1970.5 | 0 | 0 | 2642.5 | 2019-12-16 13:00 | 8d | 2866.5 | 0 | 0 | 0 | 0 | 2866.5 | 0 | 100% | Finished
8 | Building plateau and staircase audience | 2020-01-01 14:00 | 2020-01-02 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1d 1h | 730.5 | 0 | 0 | 0 | 0 | 730.5 | 0 | 100% | Finished
9 | Building camera plateau | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-28 11:00 | 1d | 714.5 | 0 | 0 | 0 | 0 | 714.5 | 0 | 100% | Finished
10 | Creating starting sections and finish line | 2019-12-30 09:00 | 2019-12-30 17:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-25 16:00 | 1d | 658.5 | 0 | 0 | 0 | 0 | 658.5 | 0 | 100% | Finished
11 | Installing bicycle storage | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-26 16:00 | 1d 2h | 674.5 | 0 | 0 | 0 | 0 | 674.5 | 0 | 100% | Finished
13 | Placing poles for banners and flags | 2019-12-24 10:00 | 2019-12-24 14:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-12 11:00 | 3h | 626.5 | 0 | 0 | 0 | 0 | 626.5 | 0 | 100% | Finished
14 | Hanging banners | 2020-01-06 14:00 | 2020-01-08 14:00 | 2d | Volunteers[12.00 #15] | 672 | 602.5 | 0 | 0 | 1274.5 | 2019-12-31 11:00 | 5h | 842.5 | 528 | 1d 4h | 0 | 0 | 842.5 | 528 | 31.25% | Started
15 | Hanging track signs | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1d 2h | 746.5 | 0 | 0 | 0 | 0 | 746.5 | 0 | 100% | Finished
16 | Placing flagpoles for homage | 2019-12-28 10:00 | 2019-12-28 14:00 | 3h | Volunteers[4.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 | 2019-12-14 16:00 | 4h | 666.5 | 0 | 0 | 0 | 0 | 666.5 | 0 | 100% | Finished
17 | Building podium | 2019-12-23 10:00 | 2019-12-24 10:00 | 1d | Volunteers[5.00 #15] | 140 | 3302.5 | 0 | 0 | 3442.5 | 2019-12-11 15:00 | 4h | 3382.5 | 0 | 0 | 0 | 0 | 3382.5 | 0 | 100% | Finished
18 | Placing traffic signs | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1d 2h | 746.5 | 0 | 0 | 0 | 0 | 746.5 | 0 | 100% | Finished
19 | Placing crush barriers and banners | 2020-01-03 14:00 | 2020-01-06 14:00 | 2d | Volunteers[12.00 #15] | 672 | 2252.5 | 0 | 0 | 2924.5 | 2019-12-27 10:00 | 1d 1h | 2636.5 | 0 | 0 | 0 | 0 | 2636.5 | 0 | 100% | Finished
20 | Constructing VIP tents | 2019-12-25 10:00 | 2019-12-26 10:00 | 1d | Volunteers[2.00 #15] | 56 | 28602.5 | 0 | 0 | 28658.5 | 2019-12-12 11:00 | 5h | 28642.5 | 0 | 0 | 0 | 0 | 28642.5 | 0 | 100% | Finished
21 | Placing building fences for VIP tents | 2019-12-31 14:00 | 2020-01-01 14:00 | 1d | Volunteers[6.00 #15] | 168 | 3677.5 | 0 | 0 | 3845.5 | 2019-12-28 11:00 | 6h | 3821.5 | 0 | 0 | 0 | 0 | 3821.5 | 0 | 100% | Finished
22 | Installing drains for VIP tents | 2019-12-26 10:00 | 2019-12-27 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-13 09:00 | 6h | 650.5 | 0 | 0 | 0 | 0 | 650.5 | 0 | 100% | Finished
23 | Decorating VIP tents | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[8.00 #15] | 224 | 43602.5 | 0 | 0 | 43826.5 | 2019-12-30 10:00 | 1d 1h | 43858.5 | 0 | 0 | 0 | 0 | 43858.5 | 0 | 100% | Finished
24 | Placing toilets for VIP tents | 2019-12-27 10:00 | 2019-12-28 10:00 | 1d | Volunteers[2.00 #15] | 56 | 1577.5 | 0 | 0 | 1633.5 | 2019-12-13 16:00 | 1d | 1633.5 | 0 | 0 | 0 | 0 | 1633.5 | 0 | 100% | Finished
25 | Placing public toilets | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2524.5 | 0 | 0 | 2580.5 | 2019-12-13 13:00 | 1d | 2580.5 | 0 | 0 | 0 | 0 | 2580.5 | 0 | 100% | Finished
26 | Placing garbage bins | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 3442.3 | 0 | 0 | 3554.3 | 2019-12-28 11:00 | 6h | 3538.3 | 0 | 0 | 0 | 0 | 3538.3 | 0 | 100% | Finished
27 | Placing and testing generator | 2019-12-24 10:00 | 2019-12-25 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2972.5 | 0 | 0 | 3028.5 | 2019-12-11 15:00 | 4h | 3004.5 | 0 | 0 | 0 | 0 | 3004.5 | 0 | 100% | Finished
28 | Equipping material post | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[2.00 #15] | 56 | 1586.5 | 0 | 0 | 1642.5 | 2019-12-11 15:00 | 1d 3h | 1666.5 | 0 | 0 | 0 | 0 | 1666.5 | 0 | 100% | Finished
29 | Testing high pressure cleaners | 2020-01-03 14:00 | 2020-01-03 17:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-13 10:00 | 2h | 618.5 | 0 | 0 | 0 | 0 | 618.5 | 0 | 100% | Finished
30 | Final check up | 2020-01-08 14:00 | 2020-01-09 12:00 | 6h | Volunteers[2.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 |  | 0 | 0 | 650.5 | 6h | 0 | 0 | 0 | 650.5 | 0% | Not Started
31 | Finish | 2020-01-09 12:00 | 2020-01-09 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started

## TP21
| TP Status Date | 2020-01-01 17:00 |  | TP Name | 1/01/2020 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Project | 2019-12-09 09:00 | 2020-01-09 12:00 | 27d 3h |  |  | 118411.3 |  |  | 126955.3 |  | 21d | [5 empty] | 125500.8 |  | 99.36%
1 | Start | 2019-12-09 09:00 | 2019-12-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-12-09 09:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished
2 | Mowing and cleaning up cuttings | 2019-12-09 09:00 | 2019-12-09 12:00 | 3h | Volunteers[3.00 #15] | 36 | 931.5 | 0 | 0 | 967.5 | 2019-12-09 09:00 | 3h | 967.5 | 0 | 0 | 0 | 0 | 967.5 | 0 | 100% | Finished
3 | Drilling holes | 2019-12-09 13:00 | 2019-12-14 12:00 | 5d | Volunteers[6.00 #15] | 840 | 950.5 | 0 | 0 | 1790.5 | 2019-12-09 13:00 | 3d 4h | 1550.5 | 0 | 0 | 0 | 0 | 1550.5 | 0 | 100% | Finished
4 | Placing poles | 2019-12-14 13:00 | 2019-12-17 15:00 | 2d 2h | Volunteers[10.00 #15] | 640 | 8819 | 0 | 0 | 9459 | 2019-12-13 09:00 | 1d 3h | 9219 | 0 | 0 | 0 | 0 | 9219 | 0 | 100% | Finished
5 | Attaching ropes and nets to poles | 2019-12-17 15:00 | 2019-12-28 17:00 | 10d 2h | Volunteers[10.00 #15] | 2880 | 3166.5 | 0 | 0 | 6046.5 | 2019-12-14 13:00 | 9d 3h | 5806.5 | 0 | 0 | 0 | 0 | 5806.5 | 0 | 100% | Finished
6 | Building material post | 2019-12-31 14:00 | 2020-01-02 14:00 | 2d | Volunteers[8.00 #15] | 448 | 1802.5 | 0 | 0 | 2250.5 | 2019-12-09 13:00 | 2d 2h | 2314.5 | 0 | 0 | 0 | 0 | 2314.5 | 0 | 100% | Finished
7 | Building bridges and exits | 2019-12-16 10:00 | 2019-12-23 10:00 | 6d | Volunteers[4.00 #15] | 672 | 1970.5 | 0 | 0 | 2642.5 | 2019-12-16 13:00 | 8d | 2866.5 | 0 | 0 | 0 | 0 | 2866.5 | 0 | 100% | Finished
8 | Building plateau and staircase audience | 2020-01-01 14:00 | 2020-01-02 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1d 1h | 730.5 | 0 | 0 | 0 | 0 | 730.5 | 0 | 100% | Finished
9 | Building camera plateau | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-28 11:00 | 1d | 714.5 | 0 | 0 | 0 | 0 | 714.5 | 0 | 100% | Finished
10 | Creating starting sections and finish line | 2019-12-30 09:00 | 2019-12-30 17:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-25 16:00 | 1d | 658.5 | 0 | 0 | 0 | 0 | 658.5 | 0 | 100% | Finished
11 | Installing bicycle storage | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-26 16:00 | 1d 2h | 674.5 | 0 | 0 | 0 | 0 | 674.5 | 0 | 100% | Finished
13 | Placing poles for banners and flags | 2019-12-24 10:00 | 2019-12-24 14:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-12 11:00 | 3h | 626.5 | 0 | 0 | 0 | 0 | 626.5 | 0 | 100% | Finished
14 | Hanging banners | 2020-01-06 14:00 | 2020-01-08 14:00 | 2d | Volunteers[12.00 #15] | 672 | 602.5 | 0 | 0 | 1274.5 | 2019-12-31 11:00 | 1d 5h | 1178.5 | 192 | 4h | 0 | 0 | 1178.5 | 192 | 75% | Started
15 | Hanging track signs | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1d 2h | 746.5 | 0 | 0 | 0 | 0 | 746.5 | 0 | 100% | Finished
16 | Placing flagpoles for homage | 2019-12-28 10:00 | 2019-12-28 14:00 | 3h | Volunteers[4.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 | 2019-12-14 16:00 | 4h | 666.5 | 0 | 0 | 0 | 0 | 666.5 | 0 | 100% | Finished
17 | Building podium | 2019-12-23 10:00 | 2019-12-24 10:00 | 1d | Volunteers[5.00 #15] | 140 | 3302.5 | 0 | 0 | 3442.5 | 2019-12-11 15:00 | 4h | 3382.5 | 0 | 0 | 0 | 0 | 3382.5 | 0 | 100% | Finished
18 | Placing traffic signs | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1d 2h | 746.5 | 0 | 0 | 0 | 0 | 746.5 | 0 | 100% | Finished
19 | Placing crush barriers and banners | 2020-01-03 14:00 | 2020-01-06 14:00 | 2d | Volunteers[12.00 #15] | 672 | 2252.5 | 0 | 0 | 2924.5 | 2019-12-27 10:00 | 1d 1h | 2636.5 | 0 | 0 | 0 | 0 | 2636.5 | 0 | 100% | Finished
20 | Constructing VIP tents | 2019-12-25 10:00 | 2019-12-26 10:00 | 1d | Volunteers[2.00 #15] | 56 | 28602.5 | 0 | 0 | 28658.5 | 2019-12-12 11:00 | 5h | 28642.5 | 0 | 0 | 0 | 0 | 28642.5 | 0 | 100% | Finished
21 | Placing building fences for VIP tents | 2019-12-31 14:00 | 2020-01-01 14:00 | 1d | Volunteers[6.00 #15] | 168 | 3677.5 | 0 | 0 | 3845.5 | 2019-12-28 11:00 | 6h | 3821.5 | 0 | 0 | 0 | 0 | 3821.5 | 0 | 100% | Finished
22 | Installing drains for VIP tents | 2019-12-26 10:00 | 2019-12-27 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-13 09:00 | 6h | 650.5 | 0 | 0 | 0 | 0 | 650.5 | 0 | 100% | Finished
23 | Decorating VIP tents | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[8.00 #15] | 224 | 43602.5 | 0 | 0 | 43826.5 | 2019-12-30 10:00 | 1d 1h | 43858.5 | 0 | 0 | 0 | 0 | 43858.5 | 0 | 100% | Finished
24 | Placing toilets for VIP tents | 2019-12-27 10:00 | 2019-12-28 10:00 | 1d | Volunteers[2.00 #15] | 56 | 1577.5 | 0 | 0 | 1633.5 | 2019-12-13 16:00 | 1d | 1633.5 | 0 | 0 | 0 | 0 | 1633.5 | 0 | 100% | Finished
25 | Placing public toilets | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2524.5 | 0 | 0 | 2580.5 | 2019-12-13 13:00 | 1d | 2580.5 | 0 | 0 | 0 | 0 | 2580.5 | 0 | 100% | Finished
26 | Placing garbage bins | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 3442.3 | 0 | 0 | 3554.3 | 2019-12-28 11:00 | 6h | 3538.3 | 0 | 0 | 0 | 0 | 3538.3 | 0 | 100% | Finished
27 | Placing and testing generator | 2019-12-24 10:00 | 2019-12-25 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2972.5 | 0 | 0 | 3028.5 | 2019-12-11 15:00 | 4h | 3004.5 | 0 | 0 | 0 | 0 | 3004.5 | 0 | 100% | Finished
28 | Equipping material post | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[2.00 #15] | 56 | 1586.5 | 0 | 0 | 1642.5 | 2019-12-11 15:00 | 1d 3h | 1666.5 | 0 | 0 | 0 | 0 | 1666.5 | 0 | 100% | Finished
29 | Testing high pressure cleaners | 2020-01-03 14:00 | 2020-01-03 17:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-13 10:00 | 2h | 618.5 | 0 | 0 | 0 | 0 | 618.5 | 0 | 100% | Finished
30 | Final check up | 2020-01-08 14:00 | 2020-01-09 12:00 | 6h | Volunteers[2.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 |  | 0 | 0 | 650.5 | 6h | 0 | 0 | 0 | 650.5 | 0% | Not Started
31 | Finish | 2020-01-09 12:00 | 2020-01-09 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started

## TP22
| TP Status Date | 2020-01-02 17:00 |  | TP Name | 2/01/2020 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Project | 2019-12-09 09:00 | 2020-01-09 12:00 | 27d 3h |  |  | 118411.3 |  |  | 126955.3 |  | 22d | [5 empty] | 126319.3 |  | 99.98%
1 | Start | 2019-12-09 09:00 | 2019-12-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-12-09 09:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished
2 | Mowing and cleaning up cuttings | 2019-12-09 09:00 | 2019-12-09 12:00 | 3h | Volunteers[3.00 #15] | 36 | 931.5 | 0 | 0 | 967.5 | 2019-12-09 09:00 | 3h | 967.5 | 0 | 0 | 0 | 0 | 967.5 | 0 | 100% | Finished
3 | Drilling holes | 2019-12-09 13:00 | 2019-12-14 12:00 | 5d | Volunteers[6.00 #15] | 840 | 950.5 | 0 | 0 | 1790.5 | 2019-12-09 13:00 | 3d 4h | 1550.5 | 0 | 0 | 0 | 0 | 1550.5 | 0 | 100% | Finished
4 | Placing poles | 2019-12-14 13:00 | 2019-12-17 15:00 | 2d 2h | Volunteers[10.00 #15] | 640 | 8819 | 0 | 0 | 9459 | 2019-12-13 09:00 | 1d 3h | 9219 | 0 | 0 | 0 | 0 | 9219 | 0 | 100% | Finished
5 | Attaching ropes and nets to poles | 2019-12-17 15:00 | 2019-12-28 17:00 | 10d 2h | Volunteers[10.00 #15] | 2880 | 3166.5 | 0 | 0 | 6046.5 | 2019-12-14 13:00 | 9d 3h | 5806.5 | 0 | 0 | 0 | 0 | 5806.5 | 0 | 100% | Finished
6 | Building material post | 2019-12-31 14:00 | 2020-01-02 14:00 | 2d | Volunteers[8.00 #15] | 448 | 1802.5 | 0 | 0 | 2250.5 | 2019-12-09 13:00 | 2d 2h | 2314.5 | 0 | 0 | 0 | 0 | 2314.5 | 0 | 100% | Finished
7 | Building bridges and exits | 2019-12-16 10:00 | 2019-12-23 10:00 | 6d | Volunteers[4.00 #15] | 672 | 1970.5 | 0 | 0 | 2642.5 | 2019-12-16 13:00 | 8d | 2866.5 | 0 | 0 | 0 | 0 | 2866.5 | 0 | 100% | Finished
8 | Building plateau and staircase audience | 2020-01-01 14:00 | 2020-01-02 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1d 1h | 730.5 | 0 | 0 | 0 | 0 | 730.5 | 0 | 100% | Finished
9 | Building camera plateau | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-28 11:00 | 1d | 714.5 | 0 | 0 | 0 | 0 | 714.5 | 0 | 100% | Finished
10 | Creating starting sections and finish line | 2019-12-30 09:00 | 2019-12-30 17:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-25 16:00 | 1d | 658.5 | 0 | 0 | 0 | 0 | 658.5 | 0 | 100% | Finished
11 | Installing bicycle storage | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-26 16:00 | 1d 2h | 674.5 | 0 | 0 | 0 | 0 | 674.5 | 0 | 100% | Finished
13 | Placing poles for banners and flags | 2019-12-24 10:00 | 2019-12-24 14:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-12 11:00 | 3h | 626.5 | 0 | 0 | 0 | 0 | 626.5 | 0 | 100% | Finished
14 | Hanging banners | 2020-01-06 14:00 | 2020-01-08 14:00 | 2d | Volunteers[12.00 #15] | 672 | 602.5 | 0 | 0 | 1274.5 | 2019-12-31 11:00 | 2d 2h | 1370.5 | 0 | 0 | 0 | 0 | 1370.5 | 0 | 100% | Finished
15 | Hanging track signs | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1d 2h | 746.5 | 0 | 0 | 0 | 0 | 746.5 | 0 | 100% | Finished
16 | Placing flagpoles for homage | 2019-12-28 10:00 | 2019-12-28 14:00 | 3h | Volunteers[4.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 | 2019-12-14 16:00 | 4h | 666.5 | 0 | 0 | 0 | 0 | 666.5 | 0 | 100% | Finished
17 | Building podium | 2019-12-23 10:00 | 2019-12-24 10:00 | 1d | Volunteers[5.00 #15] | 140 | 3302.5 | 0 | 0 | 3442.5 | 2019-12-11 15:00 | 4h | 3382.5 | 0 | 0 | 0 | 0 | 3382.5 | 0 | 100% | Finished
18 | Placing traffic signs | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1d 2h | 746.5 | 0 | 0 | 0 | 0 | 746.5 | 0 | 100% | Finished
19 | Placing crush barriers and banners | 2020-01-03 14:00 | 2020-01-06 14:00 | 2d | Volunteers[12.00 #15] | 672 | 2252.5 | 0 | 0 | 2924.5 | 2019-12-27 10:00 | 1d 1h | 2636.5 | 0 | 0 | 0 | 0 | 2636.5 | 0 | 100% | Finished
20 | Constructing VIP tents | 2019-12-25 10:00 | 2019-12-26 10:00 | 1d | Volunteers[2.00 #15] | 56 | 28602.5 | 0 | 0 | 28658.5 | 2019-12-12 11:00 | 5h | 28642.5 | 0 | 0 | 0 | 0 | 28642.5 | 0 | 100% | Finished
21 | Placing building fences for VIP tents | 2019-12-31 14:00 | 2020-01-01 14:00 | 1d | Volunteers[6.00 #15] | 168 | 3677.5 | 0 | 0 | 3845.5 | 2019-12-28 11:00 | 6h | 3821.5 | 0 | 0 | 0 | 0 | 3821.5 | 0 | 100% | Finished
22 | Installing drains for VIP tents | 2019-12-26 10:00 | 2019-12-27 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-13 09:00 | 6h | 650.5 | 0 | 0 | 0 | 0 | 650.5 | 0 | 100% | Finished
23 | Decorating VIP tents | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[8.00 #15] | 224 | 43602.5 | 0 | 0 | 43826.5 | 2019-12-30 10:00 | 1d 1h | 43858.5 | 0 | 0 | 0 | 0 | 43858.5 | 0 | 100% | Finished
24 | Placing toilets for VIP tents | 2019-12-27 10:00 | 2019-12-28 10:00 | 1d | Volunteers[2.00 #15] | 56 | 1577.5 | 0 | 0 | 1633.5 | 2019-12-13 16:00 | 1d | 1633.5 | 0 | 0 | 0 | 0 | 1633.5 | 0 | 100% | Finished
25 | Placing public toilets | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2524.5 | 0 | 0 | 2580.5 | 2019-12-13 13:00 | 1d | 2580.5 | 0 | 0 | 0 | 0 | 2580.5 | 0 | 100% | Finished
26 | Placing garbage bins | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 3442.3 | 0 | 0 | 3554.3 | 2019-12-28 11:00 | 6h | 3538.3 | 0 | 0 | 0 | 0 | 3538.3 | 0 | 100% | Finished
27 | Placing and testing generator | 2019-12-24 10:00 | 2019-12-25 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2972.5 | 0 | 0 | 3028.5 | 2019-12-11 15:00 | 4h | 3004.5 | 0 | 0 | 0 | 0 | 3004.5 | 0 | 100% | Finished
28 | Equipping material post | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[2.00 #15] | 56 | 1586.5 | 0 | 0 | 1642.5 | 2019-12-11 15:00 | 1d 3h | 1666.5 | 0 | 0 | 0 | 0 | 1666.5 | 0 | 100% | Finished
29 | Testing high pressure cleaners | 2020-01-03 14:00 | 2020-01-03 17:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-13 10:00 | 2h | 618.5 | 0 | 0 | 0 | 0 | 618.5 | 0 | 100% | Finished
30 | Final check up | 2020-01-08 14:00 | 2020-01-09 12:00 | 6h | Volunteers[2.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 | 2020-01-02 14:00 | 3h | 626.5 | 32 | 4h | 0 | 0 | 626.5 | 32 | 42.86% | Started
31 | Finish | 2020-01-09 12:00 | 2020-01-09 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started

## TP23
| TP Status Date | 2020-01-03 17:00 |  | TP Name | 3/01/2020 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Project | 2019-12-09 09:00 | 2020-01-09 12:00 | 27d 3h |  |  | 118411.3 |  |  | 126955.3 |  | 22d 4h | [5 empty] | 126351.3 |  | 100%
1 | Start | 2019-12-09 09:00 | 2019-12-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-12-09 09:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished
2 | Mowing and cleaning up cuttings | 2019-12-09 09:00 | 2019-12-09 12:00 | 3h | Volunteers[3.00 #15] | 36 | 931.5 | 0 | 0 | 967.5 | 2019-12-09 09:00 | 3h | 967.5 | 0 | 0 | 0 | 0 | 967.5 | 0 | 100% | Finished
3 | Drilling holes | 2019-12-09 13:00 | 2019-12-14 12:00 | 5d | Volunteers[6.00 #15] | 840 | 950.5 | 0 | 0 | 1790.5 | 2019-12-09 13:00 | 3d 4h | 1550.5 | 0 | 0 | 0 | 0 | 1550.5 | 0 | 100% | Finished
4 | Placing poles | 2019-12-14 13:00 | 2019-12-17 15:00 | 2d 2h | Volunteers[10.00 #15] | 640 | 8819 | 0 | 0 | 9459 | 2019-12-13 09:00 | 1d 3h | 9219 | 0 | 0 | 0 | 0 | 9219 | 0 | 100% | Finished
5 | Attaching ropes and nets to poles | 2019-12-17 15:00 | 2019-12-28 17:00 | 10d 2h | Volunteers[10.00 #15] | 2880 | 3166.5 | 0 | 0 | 6046.5 | 2019-12-14 13:00 | 9d 3h | 5806.5 | 0 | 0 | 0 | 0 | 5806.5 | 0 | 100% | Finished
6 | Building material post | 2019-12-31 14:00 | 2020-01-02 14:00 | 2d | Volunteers[8.00 #15] | 448 | 1802.5 | 0 | 0 | 2250.5 | 2019-12-09 13:00 | 2d 2h | 2314.5 | 0 | 0 | 0 | 0 | 2314.5 | 0 | 100% | Finished
7 | Building bridges and exits | 2019-12-16 10:00 | 2019-12-23 10:00 | 6d | Volunteers[4.00 #15] | 672 | 1970.5 | 0 | 0 | 2642.5 | 2019-12-16 13:00 | 8d | 2866.5 | 0 | 0 | 0 | 0 | 2866.5 | 0 | 100% | Finished
8 | Building plateau and staircase audience | 2020-01-01 14:00 | 2020-01-02 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1d 1h | 730.5 | 0 | 0 | 0 | 0 | 730.5 | 0 | 100% | Finished
9 | Building camera plateau | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-28 11:00 | 1d | 714.5 | 0 | 0 | 0 | 0 | 714.5 | 0 | 100% | Finished
10 | Creating starting sections and finish line | 2019-12-30 09:00 | 2019-12-30 17:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-25 16:00 | 1d | 658.5 | 0 | 0 | 0 | 0 | 658.5 | 0 | 100% | Finished
11 | Installing bicycle storage | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-26 16:00 | 1d 2h | 674.5 | 0 | 0 | 0 | 0 | 674.5 | 0 | 100% | Finished
13 | Placing poles for banners and flags | 2019-12-24 10:00 | 2019-12-24 14:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-12 11:00 | 3h | 626.5 | 0 | 0 | 0 | 0 | 626.5 | 0 | 100% | Finished
14 | Hanging banners | 2020-01-06 14:00 | 2020-01-08 14:00 | 2d | Volunteers[12.00 #15] | 672 | 602.5 | 0 | 0 | 1274.5 | 2019-12-31 11:00 | 2d 2h | 1370.5 | 0 | 0 | 0 | 0 | 1370.5 | 0 | 100% | Finished
15 | Hanging track signs | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1d 2h | 746.5 | 0 | 0 | 0 | 0 | 746.5 | 0 | 100% | Finished
16 | Placing flagpoles for homage | 2019-12-28 10:00 | 2019-12-28 14:00 | 3h | Volunteers[4.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 | 2019-12-14 16:00 | 4h | 666.5 | 0 | 0 | 0 | 0 | 666.5 | 0 | 100% | Finished
17 | Building podium | 2019-12-23 10:00 | 2019-12-24 10:00 | 1d | Volunteers[5.00 #15] | 140 | 3302.5 | 0 | 0 | 3442.5 | 2019-12-11 15:00 | 4h | 3382.5 | 0 | 0 | 0 | 0 | 3382.5 | 0 | 100% | Finished
18 | Placing traffic signs | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[4.00 #15] | 112 | 602.5 | 0 | 0 | 714.5 | 2019-12-25 16:00 | 1d 2h | 746.5 | 0 | 0 | 0 | 0 | 746.5 | 0 | 100% | Finished
19 | Placing crush barriers and banners | 2020-01-03 14:00 | 2020-01-06 14:00 | 2d | Volunteers[12.00 #15] | 672 | 2252.5 | 0 | 0 | 2924.5 | 2019-12-27 10:00 | 1d 1h | 2636.5 | 0 | 0 | 0 | 0 | 2636.5 | 0 | 100% | Finished
20 | Constructing VIP tents | 2019-12-25 10:00 | 2019-12-26 10:00 | 1d | Volunteers[2.00 #15] | 56 | 28602.5 | 0 | 0 | 28658.5 | 2019-12-12 11:00 | 5h | 28642.5 | 0 | 0 | 0 | 0 | 28642.5 | 0 | 100% | Finished
21 | Placing building fences for VIP tents | 2019-12-31 14:00 | 2020-01-01 14:00 | 1d | Volunteers[6.00 #15] | 168 | 3677.5 | 0 | 0 | 3845.5 | 2019-12-28 11:00 | 6h | 3821.5 | 0 | 0 | 0 | 0 | 3821.5 | 0 | 100% | Finished
22 | Installing drains for VIP tents | 2019-12-26 10:00 | 2019-12-27 10:00 | 1d | Volunteers[2.00 #15] | 56 | 602.5 | 0 | 0 | 658.5 | 2019-12-13 09:00 | 6h | 650.5 | 0 | 0 | 0 | 0 | 650.5 | 0 | 100% | Finished
23 | Decorating VIP tents | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[8.00 #15] | 224 | 43602.5 | 0 | 0 | 43826.5 | 2019-12-30 10:00 | 1d 1h | 43858.5 | 0 | 0 | 0 | 0 | 43858.5 | 0 | 100% | Finished
24 | Placing toilets for VIP tents | 2019-12-27 10:00 | 2019-12-28 10:00 | 1d | Volunteers[2.00 #15] | 56 | 1577.5 | 0 | 0 | 1633.5 | 2019-12-13 16:00 | 1d | 1633.5 | 0 | 0 | 0 | 0 | 1633.5 | 0 | 100% | Finished
25 | Placing public toilets | 2019-12-14 10:00 | 2019-12-16 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2524.5 | 0 | 0 | 2580.5 | 2019-12-13 13:00 | 1d | 2580.5 | 0 | 0 | 0 | 0 | 2580.5 | 0 | 100% | Finished
26 | Placing garbage bins | 2019-12-30 14:00 | 2019-12-31 14:00 | 1d | Volunteers[4.00 #15] | 112 | 3442.3 | 0 | 0 | 3554.3 | 2019-12-28 11:00 | 6h | 3538.3 | 0 | 0 | 0 | 0 | 3538.3 | 0 | 100% | Finished
27 | Placing and testing generator | 2019-12-24 10:00 | 2019-12-25 10:00 | 1d | Volunteers[2.00 #15] | 56 | 2972.5 | 0 | 0 | 3028.5 | 2019-12-11 15:00 | 4h | 3004.5 | 0 | 0 | 0 | 0 | 3004.5 | 0 | 100% | Finished
28 | Equipping material post | 2020-01-02 14:00 | 2020-01-03 14:00 | 1d | Volunteers[2.00 #15] | 56 | 1586.5 | 0 | 0 | 1642.5 | 2019-12-11 15:00 | 1d 3h | 1666.5 | 0 | 0 | 0 | 0 | 1666.5 | 0 | 100% | Finished
29 | Testing high pressure cleaners | 2020-01-03 14:00 | 2020-01-03 17:00 | 3h | Volunteers[2.00 #15] | 24 | 602.5 | 0 | 0 | 626.5 | 2019-12-13 10:00 | 2h | 618.5 | 0 | 0 | 0 | 0 | 618.5 | 0 | 100% | Finished
30 | Final check up | 2020-01-08 14:00 | 2020-01-09 12:00 | 6h | Volunteers[2.00 #15] | 48 | 602.5 | 0 | 0 | 650.5 | 2020-01-02 14:00 | 1d | 658.5 | 0 | 0 | 0 | 0 | 658.5 | 0 | 100% | Finished
31 | Finish | 2020-01-09 12:00 | 2020-01-09 12:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2020-01-03 14:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | Yes
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | No
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
9/12/2019 17:00 | 2019-12-09 09:00 | 2019-12-09 17:00 | 2014 | 3966.9 | 3944.5 | 2019-12-14 11:00 | 1952.9 | 197% | 22.4 | 100.6% | 4d 2h | 528.6% | 34.92% | 2020-01-08 17:00 | 2019-12-24 16:00 | 2019-12-24 16:00 | 2020-01-08 12:00 | 2019-12-24 16:00 | 2019-12-24 16:00 | 2020-01-04 10:00 | 2019-12-14 10:00 | 2019-12-14 10:00 | 126932.9001 | 126238.4183 | 66385.8617 | 27212.5757 | 66033.2725 | 27081.1872 | 106565.2039 | 70007.4168 | 5.2857 | 1.0057 | 1.9697 | 0.34923 | 4.25 | 1.0057 | 1 | 5.2857 | 1
10/12/2019 17:00 | 2019-12-09 17:00 | 2019-12-10 17:00 | 2182 | 4398.1 | 4336.5 | 2019-12-14 11:00 | 2216.1 | 201.6% | 61.6 | 101.4% | 3d 2h | 264.3% | 38.92% | 2020-01-08 17:00 | 2019-12-24 14:00 | 2019-12-24 12:00 | 2020-01-07 12:00 | 2019-12-24 14:00 | 2019-12-24 12:00 | 2020-01-06 10:00 | 2019-12-20 12:00 | 2019-12-20 11:00 | 126893.7001 | 125177.1581 | 65139.9857 | 50709.4946 | 64288.3692 | 50059.9922 | 105249.0171 | 95801.5043 | 2.6429 | 1.0142 | 2.0156 | 0.38925 | 3.25 | 1.0142 | 1 | 2.6429 | 1
11/12/2019 17:00 | 2019-12-10 17:00 | 2019-12-11 17:00 | 2350 | 12744 | 12598 | 2019-12-14 14:00 | 10394 | 542.3% | 146 | 101.2% | 2d 4h | 185.7% | 17.06% | 2020-01-07 10:00 | 2019-12-13 17:00 | 2019-12-13 17:00 | 2019-12-25 10:00 | 2019-12-13 17:00 | 2019-12-13 17:00 | 2020-01-06 16:00 | 2019-12-25 15:00 | 2019-12-25 14:00 | 126809.3 | 125500.8527 | 33658.621 | 74096.3923 | 33417.3427 | 73391.8438 | 72903.8696 | 109329.8634 | 1.8571 | 1.0116 | 5.423 | 0.17055 | 2.5 | 1.0116 | 1 | 1.8571 | 1
12/12/2019 17:00 | 2019-12-11 17:00 | 2019-12-12 17:00 | 2518 | 42401.4 | 42147 | 2019-12-25 11:00 | 39883.4 | 1684% | 254.4 | 100.6% | 10d 2h | 357.1% | 65.4% | 2019-12-30 16:00 | 2019-12-10 14:00 | 2019-12-10 14:00 | 2019-12-07 17:00 | 2019-12-10 14:00 | 2019-12-10 15:00 | 2019-12-28 10:00 | 2019-12-17 15:00 | 2019-12-17 15:00 | 126700.9001 | 126193.5934 | 47168.2191 | 65822.092 | 47138.0928 | 65680.0462 | 62410.6322 | 97806.9904 | 3.5714 | 1.006 | 16.8393 | 0.65404 | 10.25 | 1.006 | 1 | 3.5714 | 1
13/12/2019 17:00 | 2019-12-12 17:00 | 2019-12-13 17:00 | 2686 | 57101 | 56665 | 2019-12-25 11:00 | 54415 | 2126% | 436 | 100.8% | 9d 2h | 285.7% | 85.51% | 2019-12-26 15:00 | 2019-12-10 11:00 | 2019-12-10 11:00 | 2019-12-07 17:00 | 2019-12-10 11:00 | 2019-12-10 11:00 | 2019-12-30 10:00 | 2019-12-19 14:00 | 2019-12-19 14:00 | 126519.3001 | 125985.9211 | 59950.9083 | 81114.005 | 59925.8184 | 80927.3224 | 70475.915 | 107372.8318 | 2.8571 | 1.0077 | 21.2587 | 0.85507 | 9.25 | 1.0077 | 1 | 2.8571 | 1
14/12/2019 17:00 | 2019-12-13 17:00 | 2019-12-14 17:00 | 14960 | 61320.5455 | 60802 | 2019-12-27 11:00 | 46360.5455 | 409.9% | 518.5455 | 100.9% | 10d 2h | 271.4% | 91.04% | 2019-12-28 12:00 | 2019-12-16 15:00 | 2019-12-16 14:00 | 2019-12-18 16:00 | 2019-12-16 15:00 | 2019-12-16 15:00 | 2019-12-28 10:00 | 2019-12-20 10:00 | 2019-12-19 17:00 | 126436.7546 | 125881.7268 | 76814.5113 | 84983.2254 | 76679.1046 | 84778.7415 | 101152.488 | 109431.868 | 2.7143 | 1.0085 | 4.099 | 0.91038 | 10.25 | 1.0085 | 1 | 2.7143 | 1
16/12/2019 17:00 | 2019-12-14 17:00 | 2019-12-16 17:00 | 17322.5 | 63680.5 | 63164.5 | 2019-12-30 15:00 | 46358 | 367.6% | 516 | 100.8% | 11d 5h | 267.3% | 86.77% | 2019-12-28 12:00 | 2019-12-17 12:00 | 2019-12-17 12:00 | 2019-12-18 15:00 | 2019-12-17 12:00 | 2019-12-17 12:00 | 2019-12-26 15:00 | 2019-12-20 11:00 | 2019-12-20 11:00 | 126439.3 | 125926.5874 | 80376.6407 | 86832.1733 | 80237.1715 | 86640.3953 | 104204.867 | 110341.2244 | 2.6735 | 1.0082 | 3.6762 | 0.8677 | 11.625 | 1.0082 | 1 | 2.6735 | 1
17/12/2019 17:00 | 2019-12-16 17:00 | 2019-12-17 17:00 | 20881 | 64069.9546 | 63556.5 | 2019-12-30 15:00 | 43188.9546 | 306.8% | 513.4546 | 100.8% | 10d 5h | 233.9% | 87.34% | 2019-12-30 10:00 | 2019-12-18 17:00 | 2019-12-18 16:00 | 2019-12-20 16:00 | 2019-12-18 17:00 | 2019-12-18 17:00 | 2019-12-27 15:00 | 2019-12-21 15:00 | 2019-12-21 15:00 | 126441.8455 | 125937.8843 | 84051.4248 | 90438.7851 | 83887.1791 | 90223.3513 | 107837.8863 | 112904.6543 | 2.3393 | 1.0081 | 3.0683 | 0.87341 | 10.625 | 1.0081 | 1 | 2.3393 | 1
18/12/2019 17:00 | 2019-12-17 17:00 | 2019-12-18 17:00 | 21273 | 64459.4091 | 63948.5 | 2019-12-30 15:00 | 43186.4091 | 303% | 510.9091 | 100.8% | 9d 5h | 207.9% | 87.91% | 2019-12-30 10:00 | 2019-12-18 17:00 | 2019-12-18 17:00 | 2019-12-19 10:00 | 2019-12-18 17:00 | 2019-12-18 17:00 | 2019-12-28 15:00 | 2019-12-24 10:00 | 2019-12-24 10:00 | 126444.391 | 125949.0449 | 84573.4965 | 94003.7758 | 84410.0216 | 93765.5559 | 108196.1237 | 115079.7321 | 2.0794 | 1.008 | 3.0301 | 0.87913 | 9.625 | 1.008 | 1 | 2.0794 | 1
19/12/2019 17:00 | 2019-12-18 17:00 | 2019-12-19 17:00 | 21665 | 64848.8637 | 64340.5 | 2019-12-30 15:00 | 43183.8637 | 299.3% | 508.3637 | 100.8% | 8d 5h | 187.1% | 88.48% | 2019-12-30 10:00 | 2019-12-19 10:00 | 2019-12-19 10:00 | 2019-12-17 12:00 | 2019-12-19 10:00 | 2019-12-19 10:00 | 2019-12-30 15:00 | 2019-12-25 15:00 | 2019-12-25 14:00 | 126446.9364 | 125960.0712 | 85089.2976 | 97527.1454 | 84926.6434 | 97266.9884 | 108545.2546 | 116946.029 | 1.8714 | 1.0079 | 2.9933 | 0.88484 | 8.625 | 1.0079 | 1 | 1.8714 | 1
20/12/2019 17:00 | 2019-12-19 17:00 | 2019-12-20 17:00 | 22057 | 65238.3181 | 64732.5 | 2019-12-30 15:00 | 43181.3181 | 295.8% | 505.8181 | 100.8% | 7d 5h | 170.1% | 89.05% | 2019-12-30 10:00 | 2019-12-19 11:00 | 2019-12-19 10:00 | 2019-12-14 16:00 | 2019-12-19 11:00 | 2019-12-19 11:00 | 2019-12-31 15:00 | 2019-12-27 10:00 | 2019-12-27 10:00 | 126449.4819 | 125970.9661 | 85598.9403 | 101008.894 | 85437.1547 | 100727.6289 | 108885.626 | 118562.7609 | 1.7013 | 1.0078 | 2.9577 | 0.89055 | 7.625 | 1.0078 | 1 | 1.7013 | 1
21/12/2019 17:00 | 2019-12-20 17:00 | 2019-12-21 17:00 | 22449 | 65627.7727 | 65124.5 | 2019-12-30 15:00 | 43178.7727 | 292.3% | 503.2727 | 100.8% | 6d 5h | 156% | 89.63% | 2019-12-30 10:00 | 2019-12-19 12:00 | 2019-12-19 11:00 | 2019-12-13 11:00 | 2019-12-19 12:00 | 2019-12-19 12:00 | 2020-01-01 15:00 | 2019-12-28 14:00 | 2019-12-28 14:00 | 126452.0273 | 125981.7314 | 86102.5342 | 104449.0213 | 85941.6622 | 104147.4576 | 109217.5667 | 119974.905 | 1.5595 | 1.0077 | 2.9234 | 0.89626 | 6.625 | 1.0077 | 1 | 1.5595 | 1
23/12/2019 17:00 | 2019-12-21 17:00 | 2019-12-23 17:00 | 26167.5 | 66017.2273 | 65516.5 | 2019-12-30 15:00 | 39849.7273 | 252.3% | 500.7273 | 100.8% | 5d 5h | 144% | 90.2% | 2019-12-30 16:00 | 2019-12-20 16:00 | 2019-12-20 16:00 | 2019-12-17 14:00 | 2019-12-20 16:00 | 2019-12-20 16:00 | 2020-01-02 15:00 | 2019-12-30 17:00 | 2019-12-30 17:00 | 126454.5727 | 125992.3698 | 89670.7561 | 107847.5276 | 89487.551 | 107526.4553 | 112009.6802 | 121217.2383 | 1.4396 | 1.0076 | 2.5229 | 0.90197 | 5.625 | 1.0076 | 1 | 1.4396 | 1
24/12/2019 17:00 | 2019-12-23 17:00 | 2019-12-24 17:00 | 30114.5 | 66406.6819 | 65908.5 | 2019-12-30 15:00 | 36292.1819 | 220.5% | 498.1819 | 100.8% | 4d 5h | 133.7% | 90.77% | 2019-12-31 14:00 | 2019-12-23 12:00 | 2019-12-23 11:00 | 2019-12-20 14:00 | 2019-12-23 12:00 | 2019-12-23 12:00 | 2020-01-03 15:00 | 2020-01-01 14:00 | 2020-01-01 12:00 | 126457.1181 | 126002.8833 | 93366.4501 | 111204.4128 | 93160.461 | 110864.6036 | 114461.011 | 122317.0735 | 1.3367 | 1.0076 | 2.2051 | 0.90769 | 4.625 | 1.0076 | 1 | 1.3367 | 1
25/12/2019 17:00 | 2019-12-24 17:00 | 2019-12-25 17:00 | 59053 | 69161.3889 | 68662.5 | 2019-12-31 15:00 | 10108.3889 | 117.1% | 498.8889 | 100.7% | 4d 5h | 131.4% | 88.14% | 2020-01-07 11:00 | 2020-01-04 12:00 | 2020-01-04 11:00 | 2020-01-06 16:00 | 2020-01-04 12:00 | 2020-01-04 12:00 | 2020-01-03 15:00 | 2020-01-01 16:00 | 2020-01-01 16:00 | 126456.4112 | 126039.5205 | 118009.4534 | 112636.1281 | 117653.494 | 112318.9286 | 124231.0239 | 122742.7328 | 1.3143 | 1.0073 | 1.1712 | 0.88143 | 4.625 | 1.0073 | 1 | 1.3143 | 1
26/12/2019 17:00 | 2019-12-25 17:00 | 2019-12-26 17:00 | 59991.5 | 70090.3333 | 69657 | 2019-12-31 15:00 | 10098.8333 | 116.8% | 433.3333 | 100.6% | 3d 5h | 123.2% | 89.15% | 2020-01-07 11:00 | 2020-01-04 12:00 | 2020-01-04 11:00 | 2020-01-06 15:00 | 2020-01-04 12:00 | 2020-01-04 12:00 | 2020-01-04 15:00 | 2020-01-03 11:00 | 2020-01-03 11:00 | 126521.9667 | 126170.3992 | 118328.6854 | 115808.2773 | 118027.7728 | 115522.9472 | 124406.2206 | 123741.7232 | 1.2321 | 1.0062 | 1.1683 | 0.89148 | 3.625 | 1.0062 | 1 | 1.2321 | 1
27/12/2019 17:00 | 2019-12-26 17:00 | 2019-12-27 17:00 | 61905 | 72915.2778 | 72285.5 | 2019-12-31 15:00 | 11010.2778 | 117.8% | 629.7778 | 100.9% | 2d 5h | 116% | 89.22% | 2020-01-06 17:00 | 2020-01-04 11:00 | 2020-01-04 10:00 | 2020-01-06 12:00 | 2020-01-04 11:00 | 2020-01-04 11:00 | 2020-01-06 15:00 | 2020-01-04 15:00 | 2020-01-04 14:00 | 126325.5223 | 125858.7723 | 118165.4264 | 118885.2293 | 117769.1561 | 118482.742 | 124120.3922 | 124301.9439 | 1.1597 | 1.0087 | 1.1779 | 0.89224 | 2.625 | 1.0087 | 1 | 1.1597 | 1
28/12/2019 17:00 | 2019-12-27 17:00 | 2019-12-28 17:00 | 62843.5 | 81125.1334 | 80391.8 | 2020-01-02 15:00 | 18281.6334 | 129.1% | 733.3333 | 100.9% | 3d 5h | 120.6% | 63.92% | 2020-01-04 12:00 | 2020-01-02 11:00 | 2020-01-01 17:00 | 2020-01-03 10:00 | 2020-01-02 11:00 | 2020-01-02 11:00 | 2020-01-04 15:00 | 2020-01-03 15:00 | 2020-01-03 15:00 | 126221.9667 | 125807.6834 | 115894.0909 | 118382.5961 | 115573.1667 | 118039.177 | 123405.4721 | 124099.2099 | 1.2063 | 1.0091 | 1.2909 | 0.63916 | 3.625 | 1.0091 | 1 | 1.2063 | 1
30/12/2019 17:00 | 2019-12-28 17:00 | 2019-12-30 17:00 | 68293.3 | 124974.3 | 124258.3 | 2020-01-06 12:00 | 56681 | 183% | 716 | 100.6% | 5d 3h | 128.6% | 99.96% | 2019-12-26 10:00 | 2019-12-25 17:00 | 2019-12-25 16:00 | 2019-12-21 15:00 | 2019-12-25 17:00 | 2019-12-25 17:00 | 2020-01-02 17:00 | 2020-01-02 11:00 | 2020-01-02 11:00 | 126239.3 | 126227.9505 | 125340.8348 | 125799.0778 | 125334.6328 | 125790.2504 | 125950.5908 | 126124.0831 | 1.2857 | 1.0058 | 1.83 | 0.99955 | 5.375 | 1.0058 | 1 | 1.2857 | 1
31/12/2019 17:00 | 2019-12-30 17:00 | 2019-12-31 17:00 | 74133.3 | 125842.8 | 125164.8 | 2020-01-07 11:00 | 51709.5 | 169.8% | 678 | 100.5% | 5d 2h | 126.4% | 99.98% | 2019-12-27 11:00 | 2019-12-27 10:00 | 2019-12-26 17:00 | 2019-12-24 12:00 | 2019-12-27 10:00 | 2019-12-27 10:00 | 2020-01-03 10:00 | 2020-01-02 15:00 | 2020-01-02 15:00 | 126277.3 | 126271.3063 | 125820.1677 | 126044.7436 | 125816.6368 | 126040.0027 | 126137.4032 | 126217.1174 | 1.2643 | 1.0054 | 1.6975 | 0.99976 | 5.25 | 1.0054 | 1 | 1.2643 | 1
1/01/2020 17:00 | 2019-12-31 17:00 | 2020-01-01 17:00 | 75103.8 | 126136.8 | 125500.8 | 2020-01-08 10:00 | 51033 | 167.9% | 636 | 100.5% | 5d 1h | 124.5% | 99.98% | 2019-12-27 12:00 | 2019-12-27 11:00 | 2019-12-27 11:00 | 2019-12-24 10:00 | 2019-12-27 11:00 | 2019-12-27 11:00 | 2020-01-03 11:00 | 2020-01-02 17:00 | 2020-01-02 17:00 | 126319.3 | 126315.1731 | 125988.1476 | 126158.2837 | 125985.6903 | 126154.9685 | 126218.8114 | 126278.0781 | 1.2449 | 1.0051 | 1.6795 | 0.99981 | 5.125 | 1.0051 | 1 | 1.2449 | 1
2/01/2020 17:00 | 2020-01-01 17:00 | 2020-01-02 17:00 | 121255.3 | 126927.8715 | 126319.3 | 2020-01-08 17:00 | 5672.5714 | 104.7% | 608.5714 | 100.5% | 5d | 122.7% | 100% | 2020-01-08 10:00 | 2020-01-08 10:00 | 2020-01-08 10:00 | 2020-01-08 12:00 | 2020-01-08 10:00 | 2020-01-08 10:00 | 2020-01-03 12:00 | 2020-01-03 11:00 | 2020-01-03 11:00 | 126346.7286 | 126346.5971 | 126345.5028 | 126341.6493 | 126345.3772 | 126341.5421 | 126346.371 | 126345.4397 | 1.2273 | 1.0048 | 1.0468 | 0.99997 | 5 | 1.0048 | 1 | 1.2273 | 1
3/01/2020 17:00 | 2020-01-02 17:00 | 2020-01-03 17:00 | 124502.3 | 126955.3 | 126351.3 | 2020-01-09 12:00 | 2453 | 102% | 604 | 100.5% | 4d 3h | 119.3% | 100% | 2020-01-08 16:00 | 2020-01-08 16:00 | 2020-01-08 15:00 | 2020-01-08 17:00 | 2020-01-08 16:00 | 2020-01-08 16:00 | 2020-01-03 17:00 | 2020-01-03 17:00 | 2020-01-03 17:00 | 126351.3 | 126351.3 | 126351.3 | 126351.3 | 126351.3 | 126351.3 | 126351.3 | 126351.3 | 1.1925 | 1.0048 | 1.0197 | 1 | 4.375 | 1.0048 | 1 | 1.1925 | 1