## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | Lock Ganzepoot Ypres | 1 |  |  | 2019-05-20 08:00 | 2019-07-03 17:00 | 33d |  |  | 144080 |  |  | 170000
1 | Installation of power generators, lighting, toilets, fencing, supply of concrete and wooden partition | 1.1 |  | FS2;FS3;FS4 | 2019-05-20 08:00 | 2019-05-21 17:00 | 2d | Employees[3.00 #3] | 1920 | 2000 | 0 | 0 | 3920
2 | Remove railing and platforms | 1.2 | 1FS | FS30 | 2019-05-24 08:00 | 2019-05-27 17:00 | 2d | Employees[2.00 #3] | 1280 | 3500 | 0 | 0 | 4780
3 | preliminary works at gates (loosing hinges, disconnect hinges, hydraulics, anchorage points) | 1.3 | 1FS | FS30 | 2019-05-22 08:00 | 2019-05-22 17:00 | 1d | Employees[3.00 #3] | 960 | 4500 | 0 | 0 | 5460
4 | Sealing canal lock gates at other side and overflow sewers | 1.4 | 1FS | FS5;FS6 | 2019-05-23 08:00 | 2019-05-23 17:00 | 1d | Employees[2.00 #3] | 640 | 2000 | 0 | 0 | 2640
5 | Placing of concrete partition + Placing of wooden partition | 1.5 | 4FS | FS7;FS6 | 2019-05-28 08:00 | 2019-05-28 17:00 | 1d | Employees[3.00 #3] | 960 | 4800 | 0 | 0 | 5760
6 | Installing pumps | 1.6 | 5FS;4FS | FS7 | 2019-05-29 08:00 | 2019-05-29 17:00 | 1d | Employees[2.00 #3] | 640 | 2500 | 0 | 0 | 3140
7 | Check safety wooden partition + Check safety concrete partition | 1.7 | 6FS;5FS | FS30 | 2019-05-30 08:00 | 2019-05-30 17:00 | 1d | Employees[3.00 #3] | 960 | 1100 | 0 | 0 | 2060
30 | End Of Preparation/Start Restoration of lock head | 1.8 | 7FS;2FS;3FS | FS8 | 2019-05-30 17:00 | 2019-05-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
8 | Remove gates | 1.9 | 30FS | FS9;FS10 | 2019-05-31 08:00 | 2019-05-31 17:00 | 1d | Employees[2.00 #3] | 640 | 19300 | 0 | 0 | 19940
9 | Remove hinges | 1.10 | 8FS | FS14 | 2019-06-03 08:00 | 2019-06-03 17:00 | 1d | Employees[3.00 #3] | 960 | 2000 | 0 | 0 | 2960
10 | Pumping lock chamber completely dry | 1.11 | 8FS | FS11;FS12;FS14 | 2019-06-04 08:00 | 2019-06-04 17:00 | 1d | Employees[2.00 #3] | 640 | 1500 | 0 | 0 | 2140
11 | Cleaning lock floor | 1.12 | 10FS | FS13 | 2019-06-05 08:00 | 2019-06-05 17:00 | 1d | Employees | 320 | 2300 | 0 | 0 | 2620
12 | supply concrete blocks (to prevent the floor comes up) | 1.13 | 10FS | FS13 | 2019-06-05 08:00 | 2019-06-05 17:00 | 1d | Employees | 320 | 9400 | 0 | 0 | 9720
13 | placing concrete blocks | 1.14 | 11FS;12FS | FS15 | 2019-06-06 08:00 | 2019-06-06 17:00 | 1d | Employees[2.00 #3] | 640 | 2500 | 0 | 0 | 3140
14 | Cleaning walls and threshold | 1.15 | 9FS;10FS | FS15 | 2019-06-05 08:00 | 2019-06-05 17:00 | 1d | Employees | 320 | 3530 | 0 | 0 | 3850
15 | Installing stairs in lock chamber | 1.16 | 13FS;14FS | FS16;FS18;FS17 | 2019-06-07 08:00 | 2019-06-07 17:00 | 1d | Employees[3.00 #3] | 960 | 3200 | 0 | 0 | 4160
16 | Replacing hinges, pivot shoes and pivots | 1.17 | 15FS | FS31 | 2019-06-13 08:00 | 2019-06-13 17:00 | 1d | Employees[3.00 #3] | 960 | 9400 | 0 | 0 | 10360
17 | Cleaning lock head | 1.18 | 15FS | FS31 | 2019-06-10 08:00 | 2019-06-12 17:00 | 3d | Employees | 960 | 3000 | 0 | 0 | 3960
18 | Reparing walls | 1.19 | 15FS | FS31 | 2019-06-10 08:00 | 2019-06-11 17:00 | 2d | Employees[2.00 #3] | 1280 | 2900 | 0 | 0 | 4180
31 | End Restoration of lock head/Start Installing new gates | 1.20 | 16FS;17FS;18FS | FS19 | 2019-06-13 17:00 | 2019-06-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
19 | Transport of gates to the site | 1.21 | 31FS | FS20 | 2019-06-14 08:00 | 2019-06-14 17:00 | 1d | Employees | 320 | 5550 | 0 | 0 | 5870
20 | Put gates in place | 1.22 | 19FS | FS21 | 2019-06-17 08:00 | 2019-06-17 17:00 | 1d | Employees[3.00 #3] | 960 | 24000 | 0 | 0 | 24960
21 | Adjusting gates (Tightening hinges , front beams, sealing, anchorage points) | 1.23 | 20FS | FS22;FS23;FS25;FS26 | 2019-06-18 08:00 | 2019-06-18 17:00 | 1d | Employees[2.00 #3] | 640 | 8000 | 0 | 0 | 8640
22 | Installing railing | 1.24 | 21FS | FS32 | 2019-06-28 08:00 | 2019-06-28 17:00 | 1d | Employees[2.00 #3] | 640 | 2200 | 0 | 0 | 2840
23 | preliminary works at threshold | 1.25 | 21FS | FS24 | 2019-06-19 08:00 | 2019-06-19 17:00 | 1d | Employees[2.00 #3] | 640 | 2500 | 0 | 0 | 3140
24 | Repairing threshold | 1.26 | 23FS | FS32 | 2019-06-20 08:00 | 2019-06-21 17:00 | 2d | Employees[3.00 #3] | 1920 | 3300 | 0 | 0 | 5220
25 | Install platforms | 1.27 | 21FS | FS32 | 2019-06-24 08:00 | 2019-06-25 17:00 | 2d | Employees[2.00 #3] | 1280 | 4200 | 0 | 0 | 5480
26 | Installing ladder | 1.28 | 21FS | FS32 | 2019-06-26 08:00 | 2019-06-27 17:00 | 2d | Employees[2.00 #3] | 1280 | 5200 | 0 | 0 | 6480
32 | End Installing new gates/ Start Termination | 1.29 | 22FS;24FS;25FS;26FS | FS27 | 2019-06-28 17:00 | 2019-06-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
27 | Remove concrete blocks | 1.30 | 32FS | FS28 | 2019-07-01 08:00 | 2019-07-01 17:00 | 1d | Employees[3.00 #3] | 960 | 2500 | 0 | 0 | 3460
28 | Remove concrete and wooden partition | 1.31 | 27FS | FS29 | 2019-07-02 08:00 | 2019-07-02 17:00 | 1d | Employees[3.00 #3] | 960 | 3600 | 0 | 0 | 4560
29 | Cleaning site | 1.32 | 28FS |  | 2019-07-03 08:00 | 2019-07-03 17:00 | 1d | Employees[3.00 #3] | 960 | 3600 | 0 | 0 | 4560

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Employees | Renewable | 3 men | 0 | 40 | 1[3.00 Employees];2[2.00 Employees];3[3.00 Employees];4[2.00 Employees];5[3.00 Employees];6[2.00 Employees];7[3.00 Employees];8[2.00 Employees];9[3.00 Employees];10[2.00 Employees];11;12;13[2.00 Employees];14;15[3.00 Employees];16[3.00 Employees];17;18[2.00 Employees];19;20[3.00 Employees];21[2.00 Employees];22[2.00 Employees];23[2.00 Employees];24[3.00 Employees];25[2.00 Employees];26[2.00 Employees];27[3.00 Employees];28[3.00 Employees];29[3.00 Employees]; | 25920

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | Lock Ganzepoot Ypres | 264h
1 | Installation of power generators, lighting, toilets, fencing, supply of concrete and wooden partition | 16h | standard - symmetric | 80 | 100 | 120
2 | Remove railing and platforms | 16h | standard - symmetric | 80 | 100 | 120
3 | preliminary works at gates (loosing hinges, disconnect hinges, hydraulics, anchorage points) | 8h | standard - skewed right | 80 | 90 | 120
4 | Sealing canal lock gates at other side and overflow sewers | 8h | standard - symmetric | 80 | 100 | 120
5 | Placing of concrete partition + Placing of wooden partition | 8h | standard - skewed right | 80 | 90 | 120
6 | Installing pumps | 8h | standard - symmetric | 80 | 100 | 120
7 | Check safety wooden partition + Check safety concrete partition | 8h | standard - symmetric | 80 | 100 | 120
30 | End Of Preparation/Start Restoration of lock head | 0 | standard - symmetric | 80 | 100 | 120
8 | Remove gates | 8h | standard - skewed right | 80 | 90 | 120
9 | Remove hinges | 8h | standard - skewed right | 80 | 90 | 120
10 | Pumping lock chamber completely dry | 8h | standard - symmetric | 80 | 100 | 120
11 | Cleaning lock floor | 8h | standard - symmetric | 80 | 100 | 120
12 | supply concrete blocks (to prevent the floor comes up) | 8h | standard - symmetric | 80 | 100 | 120
13 | placing concrete blocks | 8h | standard - skewed right | 80 | 90 | 120
14 | Cleaning walls and threshold | 8h | standard - symmetric | 80 | 100 | 120
15 | Installing stairs in lock chamber | 8h | standard - symmetric | 80 | 100 | 120
16 | Replacing hinges, pivot shoes and pivots | 8h | standard - skewed right | 80 | 90 | 120
17 | Cleaning lock head | 24h | standard - symmetric | 80 | 100 | 120
18 | Reparing walls | 16h | standard - symmetric | 80 | 100 | 120
31 | End Restoration of lock head/Start Installing new gates | 0 | standard - symmetric | 80 | 100 | 120
19 | Transport of gates to the site | 8h | standard - skewed right | 80 | 90 | 120
20 | Put gates in place | 8h | standard - skewed right | 80 | 90 | 120
21 | Adjusting gates (Tightening hinges , front beams, sealing, anchorage points) | 8h | standard - skewed right | 80 | 90 | 120
22 | Installing railing | 8h | standard - symmetric | 80 | 100 | 120
23 | preliminary works at threshold | 8h | standard - symmetric | 80 | 100 | 120
24 | Repairing threshold | 16h | standard - symmetric | 80 | 100 | 120
25 | Install platforms | 16h | standard - symmetric | 80 | 100 | 120
26 | Installing ladder | 16h | standard - symmetric | 80 | 100 | 120
32 | End Installing new gates/ Start Termination | 0 | standard - symmetric | 80 | 100 | 120
27 | Remove concrete blocks | 8h | standard - symmetric | 80 | 100 | 120
28 | Remove concrete and wooden partition | 8h | standard - symmetric | 80 | 100 | 120
29 | Cleaning site | 8h | standard - symmetric | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t))