## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | Renovation Project
2 | Stellingen |  |  | FS31 | 2022-01-17 08:00 |  | 270d | worker[3,00 #8] |  | 12045 |  | 0
3 | Werfinrichting |  |  | FS31 | 2022-01-17 08:00 |  | 270d | worker[2,00 #8] |  | 22879.65 |  | 0
4 | Asbestverwijdering |  |  | FS5 | 2022-01-17 08:00 |  | 5d | worker[5,00 #8] |  | 9661.05 |  | 0
5 | Afbraakwerken |  | 4FS | FS7;FS6 | 2022-01-24 08:00 |  | 20d | worker[8,00 #8] |  | 48731.115 |  | 0
6 | Vochtinjecties |  | 5FS | FS8 | 2022-02-14 08:00 |  | 5d | worker[4,00 #8] |  | 2857.95 |  | 0
7 | Houtbehandeling |  | 5FS | FS31 | 2022-02-14 08:00 |  | 10d | worker[4,00 #8] |  | 4590 |  | 0
8 | Grondwerken |  | 6FS | FS9 | 2022-02-21 08:00 |  | 20d | worker[6,00 #8] |  | 32449.445 |  | 0
9 | Ruwbouwwerken |  | 8FS | FS10 | 2022-03-14 08:00 |  | 20d | worker[8,00 #8] |  | 30877.4685 |  | 0
10 | Brandwerend schilderwerk |  | 9FS | FS11 | 2022-04-04 08:00 |  | 5d | worker[2,00 #8] |  | 1250 |  | 0
11 | Timmer- & binnenschrijnwerk (dakconstructie + roostering): platte balken onder dak + vakantie?? |  | 10FS | FS12;FS13 | 2022-04-19 08:00 |  | 14d | worker[8,00 #8] |  | 56704.4762 |  | 0
12 | Buitenschrijnwerk-ALU |  | 11FS | FS14;FS15 | 2022-05-02 08:00 |  | 10d | worker[6,00 #8] |  | 68695.09 |  | 0
13 | Platte & hellende daken (incl. isolatiewerken) |  | 11FS | FS14;FS15 | 2022-05-02 08:00 |  | 10d | worker[5,00 #8] |  | 28603.7 |  | 0
14 | Elektriciteit - leidingwerk |  | 12FS;13FS | FS16;FS17;FS18;FS19;FS20 | 2022-05-16 08:00 |  | 30d | worker[6,00 #8] |  | 55879.65 |  | 0
15 | Sanitair - leidingwerk |  | 12FS;13FS | FS16;FS17;FS18;FS19;FS20 | 2022-05-16 08:00 |  | 30d | worker[6,00 #8] |  | 68798.23 |  | 0
16 | Dekvloeren |  | 14FS;15FS | FS31 | 2022-06-27 08:00 |  | 5d | worker[4,00 #8] |  | 7199.518 |  | 0
17 | Isolatiewerken |  | 14FS;15FS | FS31 | 2022-06-27 08:00 |  | 5d | worker[2,00 #8] |  | 5323.7912 |  | 0
18 | Metaalconstructies (leuning + ladder) |  | 14FS;15FS | FS31 | 2022-06-27 08:00 |  | 5d | worker[2,00 #8] |  | 21153.2281 |  | 0
19 | Buitenbepleistering |  | 14FS;15FS | FS21;FS22 | 2022-06-27 08:00 |  | 15d | worker[4,00 #8] |  | 15556.3908 |  | 0
20 | Pleisterwerken |  | 14FS;15FS | FS21;FS22 | 2022-06-27 08:00 |  | 15d | worker[5,00 #8] |  | 11539.62 |  | 0
21 | Lift |  | 19FS;20FS | FS23 | 2022-08-08 08:00 |  | 15d | worker[3,00 #8] |  | 48975.32 |  | 0
22 | Sanitair & Elektriciteit in lichte wanden |  | 19FS;20FS | FS23 | 2022-08-08 08:00 |  | 15d | worker[2,00 #8] |  | 20578.45 |  | 0
23 | Timmer- & binnenschrijnwerk (lichte wanden) |  | 21FS;22FS | FS24;FS25 | 2022-08-29 08:00 |  | 15d | worker[4,00 #8] |  | 37814.05 |  | 0
24 | Tegelvloeren |  | 23FS | FS26;FS27 | 2022-09-12 08:00 |  | 10d | worker[4,00 #8] |  | 9052.69 |  | 0
25 | Soepele Vloerbekledingen |  | 23FS | FS26;FS27 | 2022-09-12 08:00 |  | 10d | worker[2,00 #8] |  | 9421.0875 |  | 0
26 | Timmer- & binnenschrijnwerk (deuren + trap) |  | 24FS;25FS | FS28;FS29;FS30 | 2022-09-26 08:00 |  | 7d | worker[3,00 #8] |  | 41114.6904 |  | 0
27 | Sanitaire wanden |  | 24FS;25FS | FS28;FS29;FS30 | 2022-09-26 08:00 |  | 7d | worker[3,00 #8] |  | 3534 |  | 0
28 | Afwerking lift |  | 26FS;27FS | FS31 | 2022-10-04 08:00 |  | 10d | worker[8,00 #8] |  | 29385.192 |  | 0
29 | Afwerking elektriciteit |  | 26FS;27FS | FS31 | 2022-10-04 08:00 |  | 10d | worker[6,00 #8] |  | 33527.79 |  | 0
30 | Afwerking sanitair |  | 26FS;27FS | FS31 | 2022-10-04 08:00 |  | 10d | worker[6,00 #8] |  | 41278.938 |  | 0
31 | oplevering |  | 2FS;3FS;7FS;16FS;17FS;18FS;28FS;29FS;30FS |  | 2022-10-17 08:00 |  | 1d |  |  | 50 |  | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availibility | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | worker | Renewable | 8 | 0 | 0

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | Renovation Project
2 | Stellingen
3 | Werfinrichting |  | standard - symmetric | 80 | 100 | 120
4 | Asbestverwijdering |  | standard - symmetric | 80 | 100 | 120
5 | Afbraakwerken |  | standard - symmetric | 80 | 100 | 120
6 | Vochtinjecties |  | standard - symmetric | 80 | 100 | 120
7 | Houtbehandeling |  | standard - symmetric | 80 | 100 | 120
8 | Grondwerken |  | standard - symmetric | 80 | 100 | 120
9 | Ruwbouwwerken |  | standard - symmetric | 80 | 100 | 120
10 | Brandwerend schilderwerk |  | standard - symmetric | 80 | 100 | 120
11 | Timmer- & binnenschrijnwerk (dakconstructie + roostering): platte balken onder dak + vakantie?? |  | standard - symmetric | 80 | 100 | 120
12 | Buitenschrijnwerk-ALU |  | standard - symmetric | 80 | 100 | 120
13 | Platte & hellende daken (incl. isolatiewerken) |  | standard - symmetric | 80 | 100 | 120
14 | Elektriciteit - leidingwerk |  | standard - symmetric | 80 | 100 | 120
15 | Sanitair - leidingwerk |  | standard - symmetric | 80 | 100 | 120
16 | Dekvloeren |  | standard - symmetric | 80 | 100 | 120
17 | Isolatiewerken |  | standard - symmetric | 80 | 100 | 120
18 | Metaalconstructies (leuning + ladder) |  | standard - symmetric | 80 | 100 | 120
19 | Buitenbepleistering |  | standard - symmetric | 80 | 100 | 120
20 | Pleisterwerken |  | standard - symmetric | 80 | 100 | 120
21 | Lift |  | standard - symmetric | 80 | 100 | 120
22 | Sanitair & Elektriciteit in lichte wanden |  | standard - symmetric | 80 | 100 | 120
23 | Timmer- & binnenschrijnwerk (lichte wanden) |  | standard - symmetric | 80 | 100 | 120
24 | Tegelvloeren |  | standard - symmetric | 80 | 100 | 120
25 | Soepele Vloerbekledingen |  | standard - symmetric | 80 | 100 | 120
26 | Timmer- & binnenschrijnwerk (deuren + trap) |  | standard - symmetric | 80 | 100 | 120
27 | Sanitaire wanden |  | standard - symmetric | 80 | 100 | 120
28 | Afwerking lift |  | standard - symmetric | 80 | 100 | 120
29 | Afwerking elektriciteit |  | standard - symmetric | 80 | 100 | 120
30 | Afwerking sanitair |  | standard - symmetric | 80 | 100 | 120
31 | oplevering |  | standard - symmetric | 80 | 100 | 120
100 | oplevering |  | standard - symmetric | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2022-01-17 17:00 |  | TP Name | opvolging 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Renovation Project
2 | Stellingen | [9 empty] | 2022-01-17 08:00 | 1d | [5 empty] | 550 |  | 5%
3 | Werfinrichting | [9 empty] | 2022-01-17 08:00 | 1d | [5 empty] | 1100 |  | 5%
4 | Asbestverwijdering | [9 empty] | 2022-01-17 08:00 | 1d | [5 empty] | 1900 |  | 20%
5 | Afbraakwerken | [10 empty] | 0 | [5 empty] | 0 |  | 0%
6 | Vochtinjecties | [10 empty] | 0 | [5 empty] | 0 |  | 0%
7 | Houtbehandeling | [10 empty] | 0 | [5 empty] | 0 |  | 0%
8 | Grondwerken | [10 empty] | 0 | [5 empty] | 0 |  | 0%
9 | Ruwbouwwerken | [10 empty] | 0 | [5 empty] | 0 |  | 0%
10 | Brandwerend schilderwerk | [10 empty] | 0 | [5 empty] | 0 |  | 0%
11 | Timmer- & binnenschrijnwerk (dakconstructie + roostering): platte balken onder dak + vakantie?? | [10 empty] | 0 | [5 empty] | 0 |  | 0%
12 | Buitenschrijnwerk-ALU | [10 empty] | 0 | [5 empty] | 0 |  | 0%
13 | Platte & hellende daken (incl. isolatiewerken) | [10 empty] | 0 | [5 empty] | 0 |  | 0%
14 | Elektriciteit - leidingwerk | [10 empty] | 0 | [5 empty] | 0 |  | 0%
15 | Sanitair - leidingwerk | [10 empty] | 0 | [5 empty] | 0 |  | 0%
16 | Dekvloeren | [10 empty] | 0 | [5 empty] | 0 |  | 0%
17 | Isolatiewerken | [10 empty] | 0 | [5 empty] | 0 |  | 0%
18 | Metaalconstructies (leuning + ladder) | [10 empty] | 0 | [5 empty] | 0 |  | 0%
19 | Buitenbepleistering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
20 | Pleisterwerken | [10 empty] | 0 | [5 empty] | 0 |  | 0%
21 | Lift | [10 empty] | 0 | [5 empty] | 0 |  | 0%
22 | Sanitair & Elektriciteit in lichte wanden | [10 empty] | 0 | [5 empty] | 0 |  | 0%
23 | Timmer- & binnenschrijnwerk (lichte wanden) | [10 empty] | 0 | [5 empty] | 0 |  | 0%
24 | Tegelvloeren | [10 empty] | 0 | [5 empty] | 0 |  | 0%
25 | Soepele Vloerbekledingen | [10 empty] | 0 | [5 empty] | 0 |  | 0%
26 | Timmer- & binnenschrijnwerk (deuren + trap) | [10 empty] | 0 | [5 empty] | 0 |  | 0%
27 | Sanitaire wanden | [10 empty] | 0 | [5 empty] | 0 |  | 0%
28 | Afwerking lift | [10 empty] | 0 | [5 empty] | 0 |  | 0%
29 | Afwerking elektriciteit | [10 empty] | 0 | [5 empty] | 0 |  | 0%
30 | Afwerking sanitair | [10 empty] | 0 | [5 empty] | 0 |  | 0%
31 | oplevering | [10 empty] | 0 | [5 empty] | 0 |  | 0%

## TP2
| TP Status Date | 2022-01-24 17:00 |  | TP Name | opvolging 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Renovation Project
2 | Stellingen | [9 empty] | 2022-01-17 08:00 | 7d | [5 empty] | 3011 |  | 25%
3 | Werfinrichting | [9 empty] | 2022-01-17 08:00 | 7d | [5 empty] | 5719.91 |  | 25%
4 | Asbestverwijdering | [9 empty] | 2022-01-17 08:00 | 5d | [5 empty] | 9661.05 |  | 100%
5 | Afbraakwerken | [9 empty] | 2022-01-24 08:00 | 1d | [5 empty] | 2436.556 |  | 5%
6 | Vochtinjecties | [10 empty] | 0 | [5 empty] | 0 |  | 0%
7 | Houtbehandeling | [10 empty] | 0 | [5 empty] | 0 |  | 0%
8 | Grondwerken | [10 empty] | 0 | [5 empty] | 0 |  | 0%
9 | Ruwbouwwerken | [10 empty] | 0 | [5 empty] | 0 |  | 0%
10 | Brandwerend schilderwerk | [10 empty] | 0 | [5 empty] | 0 |  | 0%
11 | Timmer- & binnenschrijnwerk (dakconstructie + roostering): platte balken onder dak + vakantie?? | [10 empty] | 0 | [5 empty] | 0 |  | 0%
12 | Buitenschrijnwerk-ALU | [10 empty] | 0 | [5 empty] | 0 |  | 0%
13 | Platte & hellende daken (incl. isolatiewerken) | [10 empty] | 0 | [5 empty] | 0 |  | 0%
14 | Elektriciteit - leidingwerk | [10 empty] | 0 | [5 empty] | 0 |  | 0%
15 | Sanitair - leidingwerk | [10 empty] | 0 | [5 empty] | 0 |  | 0%
16 | Dekvloeren | [10 empty] | 0 | [5 empty] | 0 |  | 0%
17 | Isolatiewerken | [10 empty] | 0 | [5 empty] | 0 |  | 0%
18 | Metaalconstructies (leuning + ladder) | [10 empty] | 0 | [5 empty] | 0 |  | 0%
19 | Buitenbepleistering | [10 empty] | 0 | [5 empty] | 0 |  | 0%
20 | Pleisterwerken | [10 empty] | 0 | [5 empty] | 0 |  | 0%
21 | Lift | [10 empty] | 0 | [5 empty] | 0 |  | 0%
22 | Sanitair & Elektriciteit in lichte wanden | [10 empty] | 0 | [5 empty] | 0 |  | 0%
23 | Timmer- & binnenschrijnwerk (lichte wanden) | [10 empty] | 0 | [5 empty] | 0 |  | 0%
24 | Tegelvloeren | [10 empty] | 0 | [5 empty] | 0 |  | 0%
25 | Soepele Vloerbekledingen | [10 empty] | 0 | [5 empty] | 0 |  | 0%
26 | Timmer- & binnenschrijnwerk (deuren + trap) | [10 empty] | 0 | [5 empty] | 0 |  | 0%
27 | Sanitaire wanden | [10 empty] | 0 | [5 empty] | 0 |  | 0%
28 | Afwerking lift | [10 empty] | 0 | [5 empty] | 0 |  | 0%
29 | Afwerking elektriciteit | [10 empty] | 0 | [5 empty] | 0 |  | 0%
30 | Afwerking sanitair | [10 empty] | 0 | [5 empty] | 0 |  | 0%
31 | oplevering | [10 empty] | 0 | [5 empty] | 0 |  | 0%

## TP3
| TP Status Date | 2022-07-14 08:00 |  | TP Name | opvolging 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Renovation Project
2 | Stellingen | [9 empty] | 2022-01-17 08:00 | 270d | [5 empty] | 10238 |  | 85%
3 | Werfinrichting | [9 empty] | 2022-01-17 08:00 | 270d | [5 empty] | 19447 |  | 85%
4 | Asbestverwijdering | [9 empty] | 2022-01-17 08:00 | 5d | [5 empty] | 9661.05 |  | 100%
5 | Afbraakwerken | [9 empty] | 2022-01-24 08:00 | 20d | [5 empty] | 48731.115 |  | 100%
6 | Vochtinjecties | [9 empty] | 2022-02-14 08:00 | 5d | [5 empty] | 2857.95 |  | 100%
7 | Houtbehandeling | [9 empty] | 2022-02-14 08:00 | 10d | [5 empty] | 4590 |  | 100%
8 | Grondwerken | [9 empty] | 2022-02-21 08:00 | 20d | [5 empty] | 32449.445 |  | 100%
9 | Ruwbouwwerken | [9 empty] | 2022-03-14 08:00 | 20d | [5 empty] | 30877.4685 |  | 100%
10 | Brandwerend schilderwerk | [9 empty] | 2022-04-04 08:00 | 5d | [5 empty] | 1250 |  | 100%
11 | Timmer- & binnenschrijnwerk (dakconstructie + roostering): platte balken onder dak + vakantie?? | [9 empty] | 2022-04-19 08:00 | 14d | [5 empty] | 56704.4762 |  | 100%
12 | Buitenschrijnwerk-ALU | [9 empty] | 2022-05-02 08:00 | 10d | [5 empty] | 68695.09 |  | 100%
13 | Platte & hellende daken (incl. isolatiewerken) | [9 empty] | 2022-05-02 08:00 | 10d | [5 empty] | 28603.7 |  | 100%
14 | Elektriciteit - leidingwerk | [9 empty] | 2022-05-16 08:00 | 30d | [5 empty] | 55879.65 |  | 100%
15 | Sanitair - leidingwerk | [9 empty] | 2022-05-16 08:00 | 30d | [5 empty] | 68798.23 |  | 100%
16 | Dekvloeren | [9 empty] | 2022-06-27 08:00 | 5d | [5 empty] | 7199.518 |  | 100%
17 | Isolatiewerken | [9 empty] | 2022-06-27 08:00 | 5d | [5 empty] | 5323.7912 |  | 100%
18 | Metaalconstructies (leuning + ladder) | [9 empty] | 2022-06-27 08:00 | 5d | [5 empty] | 21153.2281 |  | 100%
19 | Buitenbepleistering | [9 empty] | 2022-06-27 08:00 | 15d | [5 empty] | 15556.3908 |  | 100%
20 | Pleisterwerken | [9 empty] | 2022-06-27 08:00 | 15d | [5 empty] | 11539.62 |  | 100%
21 | Lift | [9 empty] | 2022-06-29 08:00 | 15d | [5 empty] | 48975.32 |  | 100%
22 | Sanitair & Elektriciteit in lichte wanden | [18 empty] | 0%
23 | Timmer- & binnenschrijnwerk (lichte wanden) | [9 empty] | 2022-07-06 08:00 | 8d | [5 empty] | 18907.025 |  | 50%
24 | Tegelvloeren | [18 empty] | 0%
25 | Soepele Vloerbekledingen | [18 empty] | 0%
26 | Timmer- & binnenschrijnwerk (deuren + trap) | [18 empty] | 0%
27 | Sanitaire wanden | [18 empty] | 0%
28 | Afwerking lift | [18 empty] | 0%
29 | Afwerking elektriciteit | [18 empty] | 0%
30 | Afwerking sanitair | [18 empty] | 0%
31 | oplevering | [18 empty] | 0%

## TP4
| TP Status Date | 2022-10-25 08:08 |  | TP Name | opvolging 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Renovation Project
2 | Stellingen | [9 empty] | 2022-01-17 08:00 | 270d | [5 empty] | 10238 |  | 85%
3 | Werfinrichting | [9 empty] | 2022-01-17 08:00 | 270d | [5 empty] | 19447 |  | 85%
4 | Asbestverwijdering | [9 empty] | 2022-01-17 08:00 | 5d | [5 empty] | 9661.05 |  | 100%
5 | Afbraakwerken | [9 empty] | 2022-01-24 08:00 | 20d | [5 empty] | 48731.115 |  | 100%
6 | Vochtinjecties | [9 empty] | 2022-02-14 08:00 | 5d | [5 empty] | 2857.95 |  | 100%
7 | Houtbehandeling | [9 empty] | 2022-02-14 08:00 | 10d | [5 empty] | 4590 |  | 100%
8 | Grondwerken | [9 empty] | 2022-02-21 08:00 | 20d | [5 empty] | 32449.445 |  | 100%
9 | Ruwbouwwerken | [9 empty] | 2022-03-14 08:00 | 20d | [5 empty] | 30877.4685 |  | 100%
10 | Brandwerend schilderwerk | [9 empty] | 2022-04-04 08:00 | 5d | [5 empty] | 1250 |  | 100%
11 | Timmer- & binnenschrijnwerk (dakconstructie + roostering): platte balken onder dak + vakantie?? | [9 empty] | 2022-04-19 08:00 | 14d | [5 empty] | 56704.4762 |  | 100%
12 | Buitenschrijnwerk-ALU | [9 empty] | 2022-05-02 08:00 | 10d | [5 empty] | 68695.09 |  | 100%
13 | Platte & hellende daken (incl. isolatiewerken) | [9 empty] | 2022-05-02 08:00 | 10d | [5 empty] | 28603.7 |  | 100%
14 | Elektriciteit - leidingwerk | [9 empty] | 2022-05-16 08:00 | 30d | [5 empty] | 55879.65 |  | 100%
15 | Sanitair - leidingwerk | [9 empty] | 2022-05-16 08:00 | 30d | [5 empty] | 68798.23 |  | 100%
16 | Dekvloeren | [9 empty] | 2022-06-27 08:00 | 5d | [5 empty] | 7199.518 |  | 100%
17 | Isolatiewerken | [9 empty] | 2022-06-27 08:00 | 5d | [5 empty] | 5323.7912 |  | 100%
18 | Metaalconstructies (leuning + ladder) | [9 empty] | 2022-06-27 08:00 | 5d | [5 empty] | 21153.2281 |  | 100%
19 | Buitenbepleistering | [9 empty] | 2022-06-27 08:00 | 15d | [5 empty] | 15556.3908 |  | 100%
20 | Pleisterwerken | [9 empty] | 2022-06-27 08:00 | 15d | [5 empty] | 11539.62 |  | 100%
21 | Lift | [9 empty] | 2022-10-10 08:08 | 15d | [5 empty] | 48975.32 |  | 100%
22 | Sanitair & Elektriciteit in lichte wanden | [9 empty] | 2022-08-08 08:00 | 15d | [5 empty] | 20578.45 |  | 100%
23 | Timmer- & binnenschrijnwerk (lichte wanden) | [9 empty] | 2022-07-06 08:00 | 15d | [5 empty] | 37814.05 |  | 100%
24 | Tegelvloeren | [9 empty] | 2022-09-12 08:00 | 10d | [5 empty] | 9052.69 |  | 100%
25 | Soepele Vloerbekledingen | [9 empty] | 2022-09-12 08:00 | 10d | [5 empty] | 9421.0875 |  | 100%
26 | Timmer- & binnenschrijnwerk (deuren + trap) | [9 empty] | 2022-09-26 08:00 | 7d | [5 empty] | 41114.6904 |  | 100%
27 | Sanitaire wanden | [9 empty] | 2022-09-26 08:00 | 7d | [5 empty] | 3534 |  | 100%
28 | Afwerking lift | [9 empty] | 2022-10-04 08:00 | 10d | [5 empty] | 29385.192 |  | 100%
29 | Afwerking elektriciteit | [9 empty] | 2022-10-04 08:00 | 10d | [5 empty] | 16763.895 |  | 50%
30 | Afwerking sanitair | [9 empty] | 2022-10-04 08:00 | 10d | [5 empty] | 20639.469 |  | 50%
31 | oplevering | [10 empty] | 0 | [7 empty] | 0%

## TP5
| TP Status Date | 2022-10-29 08:00 |  | TP Name | einde
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Renovation Project
2 | Stellingen | [9 empty] | 2022-01-17 08:00 | 290d | [5 empty] | 12045 |  | 100%
3 | Werfinrichting | [9 empty] | 2022-01-17 08:00 | 290d | [5 empty] | 22879.65 |  | 100%
4 | Asbestverwijdering | [9 empty] | 2022-01-17 08:00 | 5d | [5 empty] | 9661.05 |  | 100%
5 | Afbraakwerken | [9 empty] | 2022-01-24 08:00 | 20d | [5 empty] | 48731.115 |  | 100%
6 | Vochtinjecties | [9 empty] | 2022-02-14 08:00 | 5d | [5 empty] | 2857.95 |  | 100%
7 | Houtbehandeling | [9 empty] | 2022-02-14 08:00 | 10d | [5 empty] | 4590 |  | 100%
8 | Grondwerken | [9 empty] | 2022-02-21 08:00 | 20d | [5 empty] | 32449.445 |  | 100%
9 | Ruwbouwwerken | [9 empty] | 2022-03-14 08:00 | 20d | [5 empty] | 30877.4685 |  | 100%
10 | Brandwerend schilderwerk | [9 empty] | 2022-04-04 08:00 | 5d | [5 empty] | 1250 |  | 100%
11 | Timmer- & binnenschrijnwerk (dakconstructie + roostering): platte balken onder dak + vakantie?? | [9 empty] | 2022-04-19 08:00 | 14d | [5 empty] | 56704.4762 |  | 100%
12 | Buitenschrijnwerk-ALU | [9 empty] | 2022-05-02 08:00 | 10d | [5 empty] | 68695.09 |  | 100%
13 | Platte & hellende daken (incl. isolatiewerken) | [9 empty] | 2022-05-02 08:00 | 10d | [5 empty] | 28603.7 |  | 100%
14 | Elektriciteit - leidingwerk | [9 empty] | 2022-05-16 08:00 | 30d | [5 empty] | 55879.65 |  | 100%
15 | Sanitair - leidingwerk | [9 empty] | 2022-05-16 08:00 | 30d | [5 empty] | 68798.23 |  | 100%
16 | Dekvloeren | [9 empty] | 2022-06-27 08:00 | 5d | [5 empty] | 7199.518 |  | 100%
17 | Isolatiewerken | [9 empty] | 2022-06-27 08:00 | 5d | [5 empty] | 5323.7912 |  | 100%
18 | Metaalconstructies (leuning + ladder) | [9 empty] | 2022-06-27 08:00 | 5d | [5 empty] | 21153.2281 |  | 100%
19 | Buitenbepleistering | [9 empty] | 2022-06-27 08:00 | 15d | [5 empty] | 15556.3908 |  | 100%
20 | Pleisterwerken | [9 empty] | 2022-06-27 08:00 | 15d | [5 empty] | 11539.62 |  | 100%
21 | Lift | [9 empty] | 2022-08-08 08:00 | 15d | [5 empty] | 48975.32 |  | 100%
22 | Sanitair & Elektriciteit in lichte wanden | [9 empty] | 2022-08-08 08:00 | 15d | [5 empty] | 20578.45 |  | 100%
23 | Timmer- & binnenschrijnwerk (lichte wanden) | [9 empty] | 2022-08-29 08:00 | 15d | [5 empty] | 37814.05 |  | 100%
24 | Tegelvloeren | [9 empty] | 2022-09-12 08:00 | 10d | [5 empty] | 9052.69 |  | 100%
25 | Soepele Vloerbekledingen | [9 empty] | 2022-09-12 08:00 | 10d | [5 empty] | 9421.0875 |  | 100%
26 | Timmer- & binnenschrijnwerk (deuren + trap) | [9 empty] | 2022-09-26 08:00 | 7d | [5 empty] | 41114.6904 |  | 100%
27 | Sanitaire wanden | [9 empty] | 2022-09-26 08:00 | 7d | [5 empty] | 3534 |  | 100%
28 | Afwerking lift | [9 empty] | 2022-10-04 08:00 | 10d | [5 empty] | 29385.192 |  | 100%
29 | Afwerking elektriciteit | [9 empty] | 2022-10-04 08:00 | 20d | [5 empty] | 33527.79 |  | 100%
30 | Afwerking sanitair | [9 empty] | 2022-10-04 08:00 | 20d | [5 empty] | 41278.938 |  | 100%
31 | oplevering | [9 empty] | 2022-10-28 08:00 | 1d | [5 empty] | 50 |  | 100%

## Agenda
Working Hours |  | Working Days |  | Holidays
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No