## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | Project | 1 |  |  | 2015-11-02 08:00 | 2016-11-15 17:00 | 272d |  |  | 90226 |  |  | 228090
1 | Review Business Strategy Landscape | 1.1 |  |  | 2015-11-02 08:00 | 2015-12-11 17:00 | 30d |  |  | 1936 |  |  | 16664
2 | Identify product gaps and opportunities | 1.1.1 |  | FS3 | 2015-11-02 08:00 | 2015-11-06 17:00 | 5d | Marketing Manager | 2400 | 300 | 0 | 0 | 2700
3 | Complete SWOT analysis | 1.1.2 | 2FS | FS4 | 2015-11-09 08:00 | 2015-11-13 17:00 | 5d | Marketing Manager | 2400 | 450 | 0 | 0 | 2850
4 | Review business model | 1.1.3 | 3FS | FS5 | 2015-11-17 08:00 | 2015-11-17 17:00 | 1d | Marketing Manager | 480 | 100 | 0 | 0 | 580
5 | Review organizational marketing strategy | 1.1.4 | 4FS | FS6 | 2015-11-18 08:00 | 2015-11-20 17:00 | 3d | Marketing Manager | 1440 | 100 | 0 | 0 | 1540
6 | Review local marketing strategy | 1.1.5 | 5FS | FS7 | 2015-11-23 08:00 | 2015-11-23 17:00 | 1d | Marketing Manager | 480 | 100 | 0 | 0 | 580
7 | Review global marketing strategy | 1.1.6 | 6FS | FS8 | 2015-11-24 08:00 | 2015-11-24 17:00 | 1d | Marketing Rep | 360 | 120 | 0 | 0 | 480
8 | Review marketing plan for campaign budget | 1.1.7 | 7FS | FS9 | 2015-11-25 08:00 | 2015-11-25 17:00 | 1d | Marketing Rep | 360 | 120 | 0 | 0 | 480
9 | Establish go-to-markets for organization | 1.1.8 | 8FS | FS10 | 2015-11-30 08:00 | 2015-11-30 17:00 | 1d | Marketing Manager | 480 | 250 | 0 | 0 | 730
10 | Evaluate alignment to corporate strategy goals | 1.1.9 | 9FS | FS11 | 2015-12-01 08:00 | 2015-12-02 17:00 | 2d | Marketing Manager;Sponsor | 1888 | 70 | 0 | 0 | 1958
11 | Evaluate competitive advantages | 1.1.10 | 10FS | FS12 | 2015-12-03 08:00 | 2015-12-07 17:00 | 3d | Marketing Manager;Marketing Research | 2520 | 86 | 0 | 0 | 2606
12 | Review product margins | 1.1.11 | 11FS | FS13 | 2015-12-08 08:00 | 2015-12-10 17:00 | 3d | Marketing Manager | 1440 | 120 | 0 | 0 | 1560
13 | Review previous campaign performance | 1.1.12 | 12FS | FS14 | 2015-12-11 08:00 | 2015-12-11 17:00 | 1d | Marketing Manager | 480 | 120 | 0 | 0 | 600
14 | Business Strategy Landscape Review Complete | 1.1.13 | 13FS | FS16 | 2015-12-11 17:00 | 2015-12-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
15 | Develop Campaign Concepts | 1.2 |  |  | 2015-12-14 08:00 | 2016-03-07 17:00 | 61d |  |  | 8730 |  |  | 33570
16 | Create process for qualifying ideas | 1.2.1 | 14FS | FS17 | 2015-12-14 08:00 | 2015-12-18 17:00 | 5d | Marketing Staff | 1800 | 50 | 0 | 0 | 1850
17 | Establish process for idea sharing | 1.2.2 | 16FS | FS18 | 2015-12-21 08:00 | 2015-12-25 17:00 | 5d | Marketing Staff | 1800 | 100 | 0 | 0 | 1900
18 | Gather ideas | 1.2.3 | 17FS | FS19 | 2015-12-28 08:00 | 2015-12-28 17:00 | 1d |  | 0 | 100 | 0 | 0 | 100
19 | Final shaping and development of ideas | 1.2.4 | 18FS | FS20 | 2015-12-29 08:00 | 2016-01-04 17:00 | 5d | Marketing Manager | 2400 | 100 | 0 | 0 | 2500
20 | Research market environment | 1.2.5 | 19FS | FS21 | 2016-01-06 08:00 | 2016-01-12 17:00 | 5d | Marketing Research | 1800 | 1500 | 0 | 0 | 3300
21 | Develop preliminary campaign concepts | 1.2.6 | 20FS | FS22 | 2016-01-13 08:00 | 2016-01-19 17:00 | 5d | Marketing Manager | 2400 | 200 | 0 | 0 | 2600
22 | Identify campaign targets | 1.2.7 | 21FS | FS23 | 2016-01-21 08:00 | 2016-01-22 17:00 | 2d | Marketing Manager | 960 | 300 | 0 | 0 | 1260
23 | Develop campaign success metrics | 1.2.8 | 22FS | FS24 | 2016-01-25 08:00 | 2016-01-26 17:00 | 2d | Marketing Rep | 720 | 350 | 0 | 0 | 1070
24 | Develop campaign tracking and analysis process | 1.2.9 | 23FS | FS25 | 2016-01-27 08:00 | 2016-01-29 17:00 | 3d | Marketing Staff | 1080 | 360 | 0 | 0 | 1440
25 | Validate concepts through test groups and market research | 1.2.10 | 24FS | FS26 | 2016-02-01 08:00 | 2016-02-05 17:00 | 5d | Marketing Rep | 1800 | 2000 | 0 | 0 | 3800
26 | Establish campaign focus list | 1.2.11 | 25FS | FS27;FS30;FS31;FS32 | 2016-02-08 08:00 | 2016-02-08 17:00 | 1d | Marketing Rep | 360 | 500 | 0 | 0 | 860
27 | Establish campaign categories | 1.2.12 | 26FS | FS28 | 2016-02-09 08:00 | 2016-02-09 17:00 | 1d | Marketing Rep | 360 | 500 | 0 | 0 | 860
28 | Develop public relations strategy | 1.2.13 | 27FS | FS29 | 2016-02-10 08:00 | 2016-02-12 17:00 | 3d |  | 0 | 450 | 0 | 0 | 450
29 | Establish preliminary ideal campaign timing for promotion | 1.2.14 | 28FS | FS34 | 2016-02-16 08:00 | 2016-02-16 17:00 | 1d | Marketing Rep | 360 | 670 | 0 | 0 | 1030
30 | Determine organization regional campaigns | 1.2.15 | 26FS | FS33 | 2016-02-16 08:00 | 2016-02-22 17:00 | 5d | Marketing Manager | 2400 | 400 | 0 | 0 | 2800
31 | Determine organization global campaigns | 1.2.16 | 26FS | FS33 | 2016-02-09 08:00 | 2016-02-15 17:00 | 5d | Marketing Manager | 2400 | 450 | 0 | 0 | 2850
32 | Determine organization country campaigns | 1.2.17 | 26FS | FS33 | 2016-02-23 08:00 | 2016-02-29 17:00 | 5d | Marketing Manager | 2400 | 450 | 0 | 0 | 2850
33 | Identify localization requirements | 1.2.18 | 30FS;31FS;32FS | FS34 | 2016-03-01 08:00 | 2016-03-07 17:00 | 5d | Marketing Staff | 1800 | 250 | 0 | 0 | 2050
34 | Campaign Concepts Complete | 1.2.19 | 33FS;29FS | FS36;FS37;FS38;FS39;FS40 | 2016-03-07 17:00 | 2016-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
35 | Create Localization Strategy | 1.3 |  |  | 2016-03-08 08:00 | 2016-04-05 17:00 | 21d |  |  | 4430 |  |  | 16070
36 | Review corporate sales objectives | 1.3.1 | 34FS | FS41 | 2016-03-08 08:00 | 2016-03-08 17:00 | 1d | Marketing Staff | 360 | 500 | 0 | 0 | 860
37 | Review regional business models | 1.3.2 | 34FS | FS41 | 2016-03-10 08:00 | 2016-03-10 17:00 | 1d | Marketing Rep | 360 | 400 | 0 | 0 | 760
38 | Review global/country business models | 1.3.3 | 34FS | FS41 | 2016-03-09 08:00 | 2016-03-09 17:00 | 1d | Marketing Rep | 360 | 450 | 0 | 0 | 810
39 | Review marketing objectives | 1.3.4 | 34FS | FS41 | 2016-03-11 08:00 | 2016-03-11 17:00 | 1d | Marketing Rep | 360 | 300 | 0 | 0 | 660
40 | Review marketing plan | 1.3.5 | 34FS | FS41 | 2016-03-08 08:00 | 2016-03-08 17:00 | 1d | Marketing Rep | 360 | 360 | 0 | 0 | 720
41 | Establish campaign opportunities | 1.3.6 | 36FS;37FS;38FS;39FS;40FS | FS42 | 2016-03-14 08:00 | 2016-03-16 17:00 | 3d | Marketing Rep | 1080 | 600 | 0 | 0 | 1680
42 | Review product mix and forecast | 1.3.7 | 41FS | FS43;FS44 | 2016-03-17 08:00 | 2016-03-21 17:00 | 3d | Marketing Rep | 1080 | 300 | 0 | 0 | 1380
43 | Review product release cycles | 1.3.8 | 42FS | FS47 | 2016-03-22 08:00 | 2016-03-24 17:00 | 3d | Marketing Rep | 1080 | 250 | 0 | 0 | 1330
44 | Determine campaign mix for each region | 1.3.9 | 42FS | FS45;FS47 | 2016-03-22 08:00 | 2016-03-24 17:00 | 3d | Marketing Manager | 1440 | 150 | 0 | 0 | 1590
45 | Determine campaign success measures for each region | 1.3.10 | 44FS | FS46 | 2016-03-25 08:00 | 2016-03-29 17:00 | 3d | Marketing Manager;Regional General Manager | 3360 | 150 | 0 | 0 | 3510
46 | Determine tracking mechanism | 1.3.11 | 45FS | FS47 | 2016-03-30 08:00 | 2016-04-01 17:00 | 3d | Marketing Staff | 1080 | 170 | 0 | 0 | 1250
47 | Create localization strategy | 1.3.12 | 46FS;44FS;43FS | FS48 | 2016-04-04 08:00 | 2016-04-05 17:00 | 2d | Marketing Staff | 720 | 800 | 0 | 0 | 1520
48 | Localization Strategy Complete | 1.3.13 | 47FS | FS50;FS56;FS60;FS61;FS67 | 2016-04-05 17:00 | 2016-04-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
49 | Communicate and Train Internal Organization | 1.4 |  |  | 2016-04-06 08:00 | 2016-05-26 17:00 | 37d |  |  | 6700 |  |  | 17180
50 | Establish corporate internal communications process | 1.4.1 | 48FS | FS51 | 2016-04-06 08:00 | 2016-04-08 17:00 | 3d | Marketing Staff | 1080 | 1500 | 0 | 0 | 2580
51 | Determine regional and country division communications process | 1.4.2 | 50FS | FS52 | 2016-04-19 08:00 | 2016-04-25 17:00 | 5d | Marketing Staff | 1800 | 850 | 0 | 0 | 2650
52 | Plan communications methods, logistics, and timing | 1.4.3 | 51FS | FS53 | 2016-04-26 08:00 | 2016-04-29 17:00 | 4d | Marketing Staff;Logistics Lead | 2560 | 450 | 0 | 0 | 3010
53 | Regional and country communications to sales, marketing, and management | 1.4.4 | 52FS | FS54 | 2016-05-02 08:00 | 2016-05-06 17:00 | 5d | Marketing Rep | 1800 | 650 | 0 | 0 | 2450
54 | Determine internal systems to respond to campaign | 1.4.5 | 53FS | FS55 | 2016-05-18 08:00 | 2016-05-24 17:00 | 5d | Marketing Staff | 1800 | 1200 | 0 | 0 | 3000
55 | Create communications plan | 1.4.6 | 54FS | FS58 | 2016-05-25 08:00 | 2016-05-26 17:00 | 2d |  | 0 | 100 | 0 | 0 | 100
56 | Identify internal training requirements | 1.4.7 | 48FS | FS57 | 2016-05-09 08:00 | 2016-05-09 17:00 | 1d | Marketing Staff | 360 | 350 | 0 | 0 | 710
57 | Develop internal training | 1.4.8 | 56FS | FS58 | 2016-05-10 08:00 | 2016-05-12 17:00 | 3d | Marketing Staff | 1080 | 1600 | 0 | 0 | 2680
58 | Organization Internal Communications and Training Complete | 1.4.9 | 55FS;57FS | FS74 | 2016-05-26 17:00 | 2016-05-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
59 | Customer Relationship Management | 1.5 |  |  | 2016-04-11 08:00 | 2016-05-31 17:00 | 37d |  |  | 4550 |  |  | 11390
60 | Review customer data and feedback | 1.5.1 | 48FS | FS62 | 2016-04-11 08:00 | 2016-04-13 17:00 | 3d | Marketing Staff | 1080 | 1400 | 0 | 0 | 2480
61 | Review company segments and channels | 1.5.2 | 48FS | FS62 | 2016-04-14 08:00 | 2016-04-18 17:00 | 3d | Marketing Staff | 1080 | 1200 | 0 | 0 | 2280
62 | Identify targets for each campaign | 1.5.3 | 60FS;61FS | FS63 | 2016-04-19 08:00 | 2016-04-21 17:00 | 3d | Marketing Research | 1080 | 600 | 0 | 0 | 1680
63 | Segment data for each campaign | 1.5.4 | 62FS | FS64 | 2016-05-02 08:00 | 2016-05-06 17:00 | 5d | Marketing Staff | 1800 | 750 | 0 | 0 | 2550
64 | Prepare/procure lists for each campaign | 1.5.5 | 63FS | FS65 | 2016-05-25 08:00 | 2016-05-31 17:00 | 5d | Marketing Staff | 1800 | 600 | 0 | 0 | 2400
65 | Customer Relationship Management Complete | 1.5.6 | 64FS | FS74 | 2016-05-31 17:00 | 2016-05-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
66 | Analyze Regional/Global/Country Business Models | 1.6 |  |  | 2016-05-13 08:00 | 2016-05-25 17:00 | 9d |  |  | 4050 |  |  | 8290
67 | Establish target regions | 1.6.1 | 48FS | FS68 | 2016-05-13 08:00 | 2016-05-13 17:00 | 1d | Marketing Staff | 360 | 900 | 0 | 0 | 1260
68 | Determine local gaps | 1.6.2 | 67FS | FS69 | 2016-05-16 08:00 | 2016-05-17 17:00 | 2d | Marketing Staff | 720 | 500 | 0 | 0 | 1220
69 | Review local competition | 1.6.3 | 68FS | FS70 | 2016-05-18 08:00 | 2016-05-20 17:00 | 3d | Marketing Research | 1080 | 350 | 0 | 0 | 1430
70 | Develop competitive advantage | 1.6.4 | 69FS | FS71 | 2016-05-23 08:00 | 2016-05-24 17:00 | 2d | Marketing Research;Marketing Manager | 1680 | 1800 | 0 | 0 | 3480
71 | Identify go-to partners | 1.6.5 | 70FS | FS72 | 2016-05-25 08:00 | 2016-05-25 17:00 | 1d | Strategic Alliance Lead | 400 | 500 | 0 | 0 | 900
72 | Regional/Global/Country Business Models Complete | 1.6.6 | 71FS | FS74 | 2016-05-25 17:00 | 2016-05-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
73 | Develop Campaign | 1.7 |  |  | 2016-06-01 08:00 | 2016-06-20 17:00 | 14d |  |  | 7440 |  |  | 14576
74 | Review campaign concepts | 1.7.1 | 58FS;65FS;72FS | FS75 | 2016-06-01 08:00 | 2016-06-02 17:00 | 2d | Marketing Manager | 960 | 1000 | 0 | 0 | 1960
75 | Create campaign list | 1.7.2 | 74FS | FS76 | 2016-06-03 08:00 | 2016-06-03 17:00 | 1d | Marketing Rep | 360 | 500 | 0 | 0 | 860
76 | Identify campaign leads | 1.7.3 | 75FS | FS77 | 2016-06-06 08:00 | 2016-06-06 17:00 | 1d | Marketing Rep | 360 | 640 | 172 | 1376 | 2376
77 | Develop Individual campaigns | 1.7.4 | 76FS | FS78 | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 1400 | 0 | 0 | 1400
78 | Develop campaign schedules | 1.7.5 | 77FS | FS79 | 2016-06-08 08:00 | 2016-06-09 17:00 | 2d | Marketing Rep | 720 | 1200 | 0 | 0 | 1920
79 | Determine calls to action | 1.7.6 | 78FS | FS80 | 2016-06-10 08:00 | 2016-06-13 17:00 | 2d | Marketing Manager | 960 | 800 | 0 | 0 | 1760
80 | Determine advertising/promotion methods and mix | 1.7.7 | 79FS | FS81 | 2016-06-14 08:00 | 2016-06-20 17:00 | 5d | Marketing Manager | 2400 | 1900 | 0 | 0 | 4300
81 | Campaign Development Complete | 1.7.8 | 80FS | FS83 | 2016-06-20 17:00 | 2016-06-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
82 | Develop Campaign Creative and Testing | 1.8 |  |  | 2016-06-21 08:00 | 2016-08-01 17:00 | 30d |  |  | 14600 |  |  | 30320
83 | Select vendor for creative | 1.8.1 | 81FS | FS84 | 2016-06-21 08:00 | 2016-06-21 17:00 | 1d | Marketing Manager;Marketing Rep | 840 | 700 | 0 | 0 | 1540
84 | Determine campaign voice/messaging style | 1.8.2 | 83FS | FS85 | 2016-06-22 08:00 | 2016-06-24 17:00 | 3d | Marketing Manager;Creative | 2520 | 2200 | 0 | 0 | 4720
85 | Develop concepts and comps | 1.8.3 | 84FS | FS86 | 2016-06-27 08:00 | 2016-07-01 17:00 | 5d | Creative | 1800 | 2000 | 0 | 0 | 3800
86 | Select creative for campaign | 1.8.4 | 85FS | FS87 | 2016-07-04 08:00 | 2016-07-08 17:00 | 5d | Marketing Manager;Corporate Sponsor | 4800 | 3200 | 0 | 0 | 8000
87 | Prepare pretest materials | 1.8.5 | 86FS | FS88 | 2016-07-11 08:00 | 2016-07-15 17:00 | 5d | Marketing Rep | 1800 | 2400 | 0 | 0 | 4200
88 | Pretest campaign | 1.8.6 | 87FS | FS89 | 2016-07-18 08:00 | 2016-07-22 17:00 | 5d | Marketing Rep | 1800 | 1500 | 0 | 0 | 3300
89 | Determine if pretest creative achieves objectives | 1.8.7 | 88FS | FS90 | 2016-07-25 08:00 | 2016-07-25 17:00 | 1d | Marketing Rep | 360 | 500 | 0 | 0 | 860
90 | Improve creative based on pretest results | 1.8.8 | 89FS | FS91 | 2016-07-26 08:00 | 2016-08-01 17:00 | 5d | Creative | 1800 | 2100 | 0 | 0 | 3900
91 | Campaign Creative and Testing Complete | 1.8.9 | 90FS | FS93;FS98 | 2016-08-01 17:00 | 2016-08-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
92 | Develop Strategy for External Promotions | 1.9 |  |  | 2016-08-02 08:00 | 2016-09-28 17:00 | 42d |  |  | 14450 |  |  | 33170
93 | Develop promotion strategy | 1.9.1 | 91FS | FS94;FS95;FS97 | 2016-08-02 08:00 | 2016-08-05 17:00 | 4d | Marketing Manager | 1920 | 2000 | 0 | 0 | 3920
94 | Develop press releases | 1.9.2 | 93FS | FS96 | 2016-08-16 08:00 | 2016-08-25 17:00 | 8d | PR Company | 3200 | 1950 | 0 | 0 | 5150
95 | Develop announcements | 1.9.3 | 93FS | FS96 | 2016-08-26 08:00 | 2016-09-06 17:00 | 8d | PR Company | 3200 | 2400 | 0 | 0 | 5600
96 | Provide pre-release information to analysts | 1.9.4 | 94FS;95FS | FS99 | 2016-09-07 08:00 | 2016-09-14 17:00 | 6d | PR Company | 2400 | 1750 | 0 | 0 | 4150
97 | Generate 'buzz' | 1.9.5 | 93FS | FS99 | 2016-09-15 08:00 | 2016-09-28 17:00 | 10d | PR Company | 4000 | 2850 | 0 | 0 | 6850
98 | Execute publicity strategy | 1.9.6 | 91FS | FS99 | 2016-08-02 08:00 | 2016-08-15 17:00 | 10d | PR Company | 4000 | 3500 | 0 | 0 | 7500
99 | Promotion - External Complete | 1.9.7 | 98FS;96FS;97FS | FS101 | 2016-09-28 17:00 | 2016-09-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
100 | Production | 1.10 |  |  | 2016-09-29 08:00 | 2016-10-18 17:00 | 14d |  |  | 7550 |  |  | 12590
101 | Submit campaign material for broadcast publications | 1.10.1 | 99FS | FS102;FS107 | 2016-09-29 08:00 | 2016-10-03 17:00 | 3d | Marketing Rep | 1080 | 2350 | 0 | 0 | 3430
102 | Select vendor for appropriate production methods | 1.10.2 | 101FS | FS103 | 2016-10-04 08:00 | 2016-10-04 17:00 | 1d | Marketing Staff | 360 | 750 | 0 | 0 | 1110
103 | Production of materials | 1.10.3 | 102FS | FS104 | 2016-10-05 08:00 | 2016-10-11 17:00 | 5d | Vendor | 1800 | 2450 | 0 | 0 | 4250
104 | Dissemination of materials | 1.10.4 | 103FS | FS105 | 2016-10-12 08:00 | 2016-10-18 17:00 | 5d | Vendor | 1800 | 2000 | 0 | 0 | 3800
105 | Production Complete | 1.10.5 | 104FS |  | 2016-10-18 17:00 | 2016-10-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
106 | Campaign Release | 1.11 |  |  | 2016-10-04 08:00 | 2016-10-20 17:00 | 13d |  |  | 8610 |  |  | 16410
107 | Develop campaign release schedules | 1.11.1 | 101FS | FS108 | 2016-10-04 08:00 | 2016-10-05 17:00 | 2d | Marketing Rep | 720 | 960 | 0 | 0 | 1680
108 | Determine release teams | 1.11.2 | 107FS | FS109 | 2016-10-06 08:00 | 2016-10-06 17:00 | 1d | Marketing Manager | 480 | 1200 | 0 | 0 | 1680
109 | Perform Inside sales calls | 1.11.3 | 108FS | FS110 | 2016-10-07 08:00 | 2016-10-13 17:00 | 5d | Marketing Manager;Inside Sales | 4200 | 3300 | 0 | 0 | 7500
110 | Execute campaign | 1.11.4 | 109FS | FS111 | 2016-10-14 08:00 | 2016-10-20 17:00 | 5d | Marketing Manager | 2400 | 3150 | 0 | 0 | 5550
111 | Campaign Release Complete | 1.11.5 | 110FS | FS113;FS114 | 2016-10-20 17:00 | 2016-10-20 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
112 | Campaign Effectiveness | 1.12 |  |  | 2016-10-21 08:00 | 2016-11-15 17:00 | 18d |  |  | 7180 |  |  | 17860
113 | Evaluate campaign effectiveness | 1.12.1 | 111FS | FS118 | 2016-10-25 08:00 | 2016-10-27 17:00 | 3d | Marketing Manager | 1440 | 300 | 0 | 0 | 1740
114 | Review regional sales | 1.12.2 | 111FS | FS115;FS118 | 2016-10-21 08:00 | 2016-10-21 17:00 | 1d | Marketing Manager;Sales | 840 | 550 | 0 | 0 | 1390
115 | Review global sales | 1.12.3 | 114FS | FS116;FS118 | 2016-10-24 08:00 | 2016-10-24 17:00 | 1d | Marketing Manager;Sales | 840 | 850 | 0 | 0 | 1690
116 | Review customer data and feedback | 1.12.4 | 115FS | FS117;FS118 | 2016-10-25 08:00 | 2016-10-25 17:00 | 1d | Marketing Rep;Marketing Staff | 720 | 950 | 0 | 0 | 1670
117 | Perform market analysis | 1.12.5 | 116FS | FS118 | 2016-10-26 08:00 | 2016-10-28 17:00 | 3d | Marketing Research | 1080 | 1200 | 0 | 0 | 2280
118 | Review success measures | 1.12.6 | 113FS;114FS;115FS;116FS;117FS | FS119 | 2016-10-31 08:00 | 2016-11-02 17:00 | 3d | Marketing Manager | 1440 | 1200 | 0 | 0 | 2640
119 | Measure campaign effectiveness | 1.12.7 | 118FS | FS120 | 2016-11-03 08:00 | 2016-11-07 17:00 | 3d | Marketing Manager | 1440 | 500 | 0 | 0 | 1940
120 | Identify any gaps | 1.12.8 | 119FS | FS121 | 2016-11-08 08:00 | 2016-11-08 17:00 | 1d | Marketing Manager | 480 | 330 | 0 | 0 | 810
121 | Develop future campaign ideas | 1.12.9 | 120FS | FS122 | 2016-11-09 08:00 | 2016-11-15 17:00 | 5d | Marketing Manager | 2400 | 1300 | 0 | 0 | 3700
122 | Campaign Effectiveness | 1.12.10 | 121FS | FS123 | 2016-11-15 17:00 | 2016-11-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
123 | Marketing Campaign Planning Complete | 1.13 | 122FS |  | 2016-11-15 17:00 | 2016-11-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Logistics Lead | Renewable | 1 | 0 | 35 | 52; | 1120
2 | Marketing Manager | Renewable | 1 | 0 | 60 | 2;3;4;5;6;9;10;11;12;13;19;21;22;30;31;32;44;45;70;74;79;80;83;84;86;93;108;109;110;113;114;115;118;119;120;121; | 52800
3 | Sponsor | Renewable | 1 | 0 | 58 | 10; | 928
4 | Sales | Renewable | 1 | 0 | 45 | 114;115; | 720
5 | Creative | Renewable | 1 | 0 | 45 | 84;85;90; | 4680
6 | Content Consultant | Renewable | 1 | 0 | 60 |  | 0
7 | Marketing | Renewable | 1 | 0 | 45 |  | 0
8 | Marketing Research | Renewable | 1 | 0 | 45 | 11;20;62;69;70;117; | 6840
9 | Corporate Sponsor | Renewable | 1 | 0 | 60 | 86; | 2400
10 | Subject Matter Expert | Renewable | 1 | 0 | 60 |  | 0
11 | Inside Sales | Renewable | 1 | 0 | 45 | 109; | 1800
12 | Marketing Staff | Renewable | 1 | 0 | 45 | 16;17;24;33;36;46;47;50;51;52;54;56;57;60;61;63;64;67;68;102;116; | 23760
13 | Product Marketing | Renewable | 1 | 0 | 45 |  | 0
14 | Regional General Manager | Renewable | 1 | 0 | 80 | 45; | 1920
15 | Country Manager | Renewable | 1 | 0 | 80 |  | 0
16 | Strategic Alliance Lead | Renewable | 1 | 0 | 50 | 71; | 400
17 | Marketing Rep | Renewable | 1 | 0 | 45 | 7;8;23;25;26;27;29;37;38;39;40;41;42;43;53;75;76;78;83;87;88;89;101;107;116; | 18720
18 | Marketing Research | Renewable | 1 | 0 | 45 |  | 0
19 | PR Company | Renewable | 1 | 0 | 50 | 94;95;96;97;98; | 16800
20 | Vendor | Renewable | 1 | 0 | 45 | 103;104; | 3600

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | Project | 2176h
1 | Review Business Strategy Landscape | 240h
2 | Identify product gaps and opportunities | 40h | standard - symmetric | 80 | 100 | 120
3 | Complete SWOT analysis | 40h | standard - symmetric | 80 | 100 | 120
4 | Review business model | 8h | standard - symmetric | 80 | 100 | 120
5 | Review organizational marketing strategy | 24h | standard - symmetric | 80 | 100 | 120
6 | Review local marketing strategy | 8h | standard - symmetric | 80 | 100 | 120
7 | Review global marketing strategy | 8h | standard - symmetric | 80 | 100 | 120
8 | Review marketing plan for campaign budget | 8h | standard - symmetric | 80 | 100 | 120
9 | Establish go-to-markets for organization | 8h | standard - symmetric | 80 | 100 | 120
10 | Evaluate alignment to corporate strategy goals | 16h | standard - symmetric | 80 | 100 | 120
11 | Evaluate competitive advantages | 24h | standard - symmetric | 80 | 100 | 120
12 | Review product margins | 24h | standard - symmetric | 80 | 100 | 120
13 | Review previous campaign performance | 8h | standard - symmetric | 80 | 100 | 120
14 | Business Strategy Landscape Review Complete | 0 | standard - symmetric | 80 | 100 | 120
15 | Develop Campaign Concepts | 488h
16 | Create process for qualifying ideas | 40h | standard - symmetric | 80 | 100 | 120
17 | Establish process for idea sharing | 40h | standard - symmetric | 80 | 100 | 120
18 | Gather ideas | 8h | standard - symmetric | 80 | 100 | 120
19 | Final shaping and development of ideas | 40h | standard - symmetric | 80 | 100 | 120
20 | Research market environment | 40h | standard - symmetric | 80 | 100 | 120
21 | Develop preliminary campaign concepts | 40h | standard - symmetric | 80 | 100 | 120
22 | Identify campaign targets | 16h | standard - symmetric | 80 | 100 | 120
23 | Develop campaign success metrics | 16h | standard - symmetric | 80 | 100 | 120
24 | Develop campaign tracking and analysis process | 24h | standard - symmetric | 80 | 100 | 120
25 | Validate concepts through test groups and market research | 40h | standard - symmetric | 80 | 100 | 120
26 | Establish campaign focus list | 8h | standard - symmetric | 80 | 100 | 120
27 | Establish campaign categories | 8h | standard - symmetric | 80 | 100 | 120
28 | Develop public relations strategy | 24h | standard - symmetric | 80 | 100 | 120
29 | Establish preliminary ideal campaign timing for promotion | 8h | standard - symmetric | 80 | 100 | 120
30 | Determine organization regional campaigns | 40h | standard - symmetric | 80 | 100 | 120
31 | Determine organization global campaigns | 40h | standard - symmetric | 80 | 100 | 120
32 | Determine organization country campaigns | 40h | standard - symmetric | 80 | 100 | 120
33 | Identify localization requirements | 40h | standard - symmetric | 80 | 100 | 120
34 | Campaign Concepts Complete | 0 | standard - symmetric | 80 | 100 | 120
35 | Create Localization Strategy | 168h
36 | Review corporate sales objectives | 8h | standard - symmetric | 80 | 100 | 120
37 | Review regional business models | 8h | standard - symmetric | 80 | 100 | 120
38 | Review global/country business models | 8h | standard - symmetric | 80 | 100 | 120
39 | Review marketing objectives | 8h | standard - symmetric | 80 | 100 | 120
40 | Review marketing plan | 8h | standard - symmetric | 80 | 100 | 120
41 | Establish campaign opportunities | 24h | standard - symmetric | 80 | 100 | 120
42 | Review product mix and forecast | 24h | standard - symmetric | 80 | 100 | 120
43 | Review product release cycles | 24h | standard - symmetric | 80 | 100 | 120
44 | Determine campaign mix for each region | 24h | standard - symmetric | 80 | 100 | 120
45 | Determine campaign success measures for each region | 24h | standard - symmetric | 80 | 100 | 120
46 | Determine tracking mechanism | 24h | standard - symmetric | 80 | 100 | 120
47 | Create localization strategy | 16h | standard - symmetric | 80 | 100 | 120
48 | Localization Strategy Complete | 0 | standard - symmetric | 80 | 100 | 120
49 | Communicate and Train Internal Organization | 296h
50 | Establish corporate internal communications process | 24h | standard - symmetric | 80 | 100 | 120
51 | Determine regional and country division communications process | 40h | standard - symmetric | 80 | 100 | 120
52 | Plan communications methods, logistics, and timing | 32h | standard - symmetric | 80 | 100 | 120
53 | Regional and country communications to sales, marketing, and management | 40h | standard - symmetric | 80 | 100 | 120
54 | Determine internal systems to respond to campaign | 40h | standard - symmetric | 80 | 100 | 120
55 | Create communications plan | 16h | standard - symmetric | 80 | 100 | 120
56 | Identify internal training requirements | 8h | standard - symmetric | 80 | 100 | 120
57 | Develop internal training | 24h | standard - symmetric | 80 | 100 | 120
58 | Organization Internal Communications and Training Complete | 0 | standard - symmetric | 80 | 100 | 120
59 | Customer Relationship Management | 296h
60 | Review customer data and feedback | 24h | standard - symmetric | 80 | 100 | 120
61 | Review company segments and channels | 24h | standard - symmetric | 80 | 100 | 120
62 | Identify targets for each campaign | 24h | standard - symmetric | 80 | 100 | 120
63 | Segment data for each campaign | 40h | standard - symmetric | 80 | 100 | 120
64 | Prepare/procure lists for each campaign | 40h | standard - symmetric | 80 | 100 | 120
65 | Customer Relationship Management Complete | 0 | standard - symmetric | 80 | 100 | 120
66 | Analyze Regional/Global/Country Business Models | 72h
67 | Establish target regions | 8h | standard - symmetric | 80 | 100 | 120
68 | Determine local gaps | 16h | standard - symmetric | 80 | 100 | 120
69 | Review local competition | 24h | standard - symmetric | 80 | 100 | 120
70 | Develop competitive advantage | 16h | standard - symmetric | 80 | 100 | 120
71 | Identify go-to partners | 8h | standard - symmetric | 80 | 100 | 120
72 | Regional/Global/Country Business Models Complete | 0 | standard - symmetric | 80 | 100 | 120
73 | Develop Campaign | 112h
74 | Review campaign concepts | 16h | standard - symmetric | 80 | 100 | 120
75 | Create campaign list | 8h | standard - symmetric | 80 | 100 | 120
76 | Identify campaign leads | 8h | standard - symmetric | 80 | 100 | 120
77 | Develop Individual campaigns | 8h | standard - symmetric | 80 | 100 | 120
78 | Develop campaign schedules | 16h | standard - symmetric | 80 | 100 | 120
79 | Determine calls to action | 16h | standard - symmetric | 80 | 100 | 120
80 | Determine advertising/promotion methods and mix | 40h | standard - symmetric | 80 | 100 | 120
81 | Campaign Development Complete | 0 | standard - symmetric | 80 | 100 | 120
82 | Develop Campaign Creative and Testing | 240h
83 | Select vendor for creative | 8h | standard - symmetric | 80 | 100 | 120
84 | Determine campaign voice/messaging style | 24h | standard - symmetric | 80 | 100 | 120
85 | Develop concepts and comps | 40h | standard - symmetric | 80 | 100 | 120
86 | Select creative for campaign | 40h | standard - symmetric | 80 | 100 | 120
87 | Prepare pretest materials | 40h | standard - symmetric | 80 | 100 | 120
88 | Pretest campaign | 40h | standard - symmetric | 80 | 100 | 120
89 | Determine if pretest creative achieves objectives | 8h | standard - symmetric | 80 | 100 | 120
90 | Improve creative based on pretest results | 40h | standard - symmetric | 80 | 100 | 120
91 | Campaign Creative and Testing Complete | 0 | standard - symmetric | 80 | 100 | 120
92 | Develop Strategy for External Promotions | 336h
93 | Develop promotion strategy | 32h | standard - symmetric | 80 | 100 | 120
94 | Develop press releases | 64h | standard - symmetric | 80 | 100 | 120
95 | Develop announcements | 64h | standard - symmetric | 80 | 100 | 120
96 | Provide pre-release information to analysts | 48h | standard - symmetric | 80 | 100 | 120
97 | Generate 'buzz' | 80h | standard - symmetric | 80 | 100 | 120
98 | Execute publicity strategy | 80h | standard - symmetric | 80 | 100 | 120
99 | Promotion - External Complete | 0 | standard - symmetric | 80 | 100 | 120
100 | Production | 112h
101 | Submit campaign material for broadcast publications | 24h | standard - symmetric | 80 | 100 | 120
102 | Select vendor for appropriate production methods | 8h | standard - symmetric | 80 | 100 | 120
103 | Production of materials | 40h | standard - symmetric | 80 | 100 | 120
104 | Dissemination of materials | 40h | standard - symmetric | 80 | 100 | 120
105 | Production Complete | 0 | standard - symmetric | 80 | 100 | 120
106 | Campaign Release | 104h
107 | Develop campaign release schedules | 16h | standard - symmetric | 80 | 100 | 120
108 | Determine release teams | 8h | standard - symmetric | 80 | 100 | 120
109 | Perform Inside sales calls | 40h | standard - symmetric | 80 | 100 | 120
110 | Execute campaign | 40h | standard - symmetric | 80 | 100 | 120
111 | Campaign Release Complete | 0 | standard - symmetric | 80 | 100 | 120
112 | Campaign Effectiveness | 144h
113 | Evaluate campaign effectiveness | 24h | standard - symmetric | 80 | 100 | 120
114 | Review regional sales | 8h | standard - symmetric | 80 | 100 | 120
115 | Review global sales | 8h | standard - symmetric | 80 | 100 | 120
116 | Review customer data and feedback | 8h | standard - symmetric | 80 | 100 | 120
117 | Perform market analysis | 24h | standard - symmetric | 80 | 100 | 120
118 | Review success measures | 24h | standard - symmetric | 80 | 100 | 120
119 | Measure campaign effectiveness | 24h | standard - symmetric | 80 | 100 | 120
120 | Identify any gaps | 8h | standard - symmetric | 80 | 100 | 120
121 | Develop future campaign ideas | 40h | standard - symmetric | 80 | 100 | 120
122 | Campaign Effectiveness | 0 | standard - symmetric | 80 | 100 | 120
123 | Marketing Campaign Planning Complete | 0 | standard - symmetric | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t))